## Sheet1
Project name | Date of formal closure | Lessons Learnt
Single Force Gazetteer | 2017-03-16 | The importance of a new single force gazetteer for the provision of Niche and ControlWorks was not recognised by the business as a prerequisite for both systems and would have led to the inclusion of this project within the scope of the ISP Programme.
The contract resources detailed in the original business case weren’t all recruited (only the Gazetteer Solutions Architect and the ETL Developer) and the shortfall was made up by using the GIS team and staff on temporary duty restrictions as project resources. This masked the true cost of the project but had a major impact on the BAU work of the GIS team which was effectively put on hold for in excess of 9 months. The lack of BTP standards that could be used to guide the build of databases and hardware to the required level led to some confusion over what was required and delays in the process.
24/7 Access Control Project | 2016-12-16 | Delivery of an extended and technically complex project like the 24/7 Access Control Project has proven to be very challenging for the team and the handover documentation from the outgoing project manager has revealed a lack of understanding of how to produce core project documentation, meet procurement regulations or identify project dependencies, resource requirements and phased deliverables. Corporate Services will ensure that all project managers tasked with managing a project have project management skills/training or, if no Departmental resource is suitable, ensure that the business case includes additional costs for this resource.
The recruitment of skilled project management resources into estates has proven extremely difficult and the Corporate Services Department carries vacancies extending over 12 months or more due to buoyant property industry employment demand. The Department therefore resorts to adding projects to the day jobs of existing staff. In the instance of 24/7 Access Control, the Force Technical and Compliance Manager - who is responsible for managing the statutory maintenance programme conducting legionella testing, asbestos, PAT testing, etc. - was asked to undertake the project. Corporate Services has escalated these resourcing issues to the Director of Capability of Resources and come to the following approach: - A review of Departmental roles and responsibilities will be undertaken to ensure the required resources occupy market valorised positions, including application of market supplements for roles where recruitment is difficult. - The medium-term Estates Strategy (for agreement by FEB) will assist in establishing a clear workload for the Department against which resourcing can be properly planned.
The management of access control is currently devolved to Divisions, where individual sites manage their access groups and nominated points of contact order access cards from a third party supplier. One outcome of this approach has been that there has been no central repository recording the details of the infrastructure installed, and no corporate specification for what that install ought to be. Part of this has been a lack of a perspective on the ‘assets’ of the estate, for which there must be a central approach to their lifecycle maintenance as physical components in BTP buildings. Corporate Services will: - Ensure that the EVOLUTION property asset management system is populated with the audit data arising from the project re-set. - Ensure that the ongoing practice of the Maintenance Team will be to record all the necessary asset information from any install and instruct suppliers to supply that data accordingly.
The selection and tasking of multiple suppliers undertaking various elements of the installation of access control systems has created a series of challenges for the project, compounded by the installs happening gradually over a number of years. The approach to the project has reflected the day-to-day practices of the Maintenance Team, which has been to commission different suppliers according to their specialities in conducting any single install, split surveying from installation, allow hand-written surveys, etc. The Team views these practices as cost-saving mechanisms which optimise use of the limited maintenance budget. However, what it does is displace work from the supplier onto the internal team and creates a dispersed responsibility for any individual install. Corporate Services will: - Work with the Maintenance Team to establish a single supplier responsible for the surveying, installation and maintenance of premises access control.
Court Video Link | 2016-12-16 | Time - The project was adversely affected due to delays to the PNSP Project. The project had a key dependency on the migration works being completed before any of the associate work streams could be implemented by the project. In terms of learning outcome, the dependency management could’ve been better managed via regular stakeholder management with meeting to fully understanding the impact.
Quality - There was reluctance from custody staff in being part of the testing schedule activities due to lack of training. In terms of lesson learnt, going forward block training for all custody staff/sergeants within their training block days would’ve helped bridge some training awareness in using the video conferencing.
Interim Reporting Solution | 2016-12-16 | Key personnel in the IRS (Analysts and BOXI Developers) needed information/training to appreciate how the new Niche system related to their specific areas of work. This was not available readily and accessing the right people with the knowledge was difficult as it was dispersed amongst several external contractors who did not understand the BTP business model initially. Therefore, setting up a technical working group between IRS and ISP helped in sharing information in the early stages of the project.
A finalised mapping diagram was needed for the new system to understand how the data fields/tables from the legacy system were being migrated into the new system. This would have helped in the design of the new Universe and communication with Analysts regarding how queries in business objects could be reproduced to develop reports.
The legacy crime data migration activity undertaken by ISP was crucial before Analysts were able to compare BOXI crime reports from the old system versus BOXI reports from Niche. The crime data migration activity went through several phases of refinement until a couple of weeks before the go-live date. Data migration plan should have taken into consideration the key data fields needed by Analysts and prioritised these areas first for transfer.
Op Trafalgar | 2016-12-16 | Planning - Giving the project an operational name gave the impression that the patrol strategy was a temporary operation and created confusion amongst officers in relation to the priority afforded to each operation. Consider not using operational names for future projects.
Implementation - Low crime thresholds were not introduced when the analysis for each hotspot location was produced. This resulted in dosage (patrolling minutes in hotspots) being diluted as low volume crime locations were treated equally to high volume locations. The new project will see a Threat, Risk and Harm Matrix applied to all crime types, weighting crimes and allowing higher harm and more threatening locations to be prioritised. Low crime thresholds will be introduced, releasing resources to patrol higher harm hotspots.
Implementation - Patrol returns were being completed by officers in the absence of a technical tracking solution, but due to volume, were not being recorded or monitored by the project or the business until a year into the project. The lesson learned would be to establish local governance and monitoring processes or to establish resource needed to cope with the volume during project planning.
Planning - Locations went live and resources were required to begin patrolling locations with very limited understanding and knowledge of Evidence Based Policing. A training programme was designed to be delivered to all uniformed resource but a strategic decision was made to deliver training alongside the roll out of patrols. This impacted on compliance levels and the coordination of patrol plans on divisions. This also significantly impacted on cultural acceptance of new ways of patrolling.
Planning - The scope of the project did not account for duplicative operational activity which would impact on the new patrol strategy being introduced. As a result of this, small, localised operations were kept in place which duplicated patrolling effort. A new project will seek to consolidate varying operations, where appropriate, to remove duplication and simplify priorities for patrolling resource.
Contact Management | 2016-12-16 | Recruitment activity was delayed due to an extended consultation period. To mitigate this in future projects more contingency should be added to the recruitment plan.
Recruitment milestones were missed due to the number of failures in vetting and subsequently the number of recruits who failed their training. The solution to recruitment delays in contact management is to retain a talent pool of people awaiting recruitment.
The FCC Manager role was a new post necessitating a recruitment process. The candidate chosen had a serious accident on the day before they were due to commence employment and her offer of employment was subsequently withdrawn. This delayed the appointment of a manger by a further 6 weeks and the post-holder did not commence their role until August 2016 four months after the transition from CRC to FCC commenced. Future similar roles should be appointed earlier to allow the manager to be involved in and have ownership of the implementation phase.
Origin / Oracle Upgrade Phase 2 | 2016 | Lesson 2: The FHQ Resilience Planning Unit should review the Business Continuity Management SOP ensuring the procedure is relevant to all BTP business areas.
Lesson 3: Staff working policy and relevant SOP should be reviewed with regards to the clarity of instances when police staff are requested to work hours outside their regular hours.
Lesson 4: Team leaders should make themselves familiar with the staff working policy and relevant SOP, when the work falls outside of BAU.
Lesson 5: Clarity should be sought with TSSA well in advance of the task taking place and before relaying any decisions made to the staff involved in the task.
Lesson 1: Specialist Operational planning should be involved from the offset for all operational projects in the future to increase efficiency of the operation and ensure all necessary parties are involved in communications.
Lesson 2: Departments should identify and publish their schedules of work for the coming year that would require a plan from the Specialist Operational planning team.
Lesson 3: Resource plans should form part of the overall planning and funding for those resources shall be approved by the project sponsor prior to work commencing.
Lesson 4: All heads of departments of the affected business areas should be represented during the planning meetings.
Lesson 5: Daily conference calls between project leads in relevant business areas should be held during the running the key dates of the Operation.
Justice Transformation | 2016-05-01 | Lessons learned include the opinion that the nominated Project Manager (PM) must, where possible, be included in the project process from inception to include initial scoping and production of the Business Case. In this project, the PM was not brought in to the project until the Business Case had been written in full. This meant much time being spent by the PM closely reviewing the complex Business Case to ensure full comprehension and to avoid duplicate work being carried out.
EDRMS | 2016-03-30 | The Force Records Manager was seconded to project manage this project which assisted greatly as this project relied heavily on scoping requirements for moving to better Information Management best practices.
During Phase 1 it was identified that the scope was too ambitions resulting in de-scoping and gaining approval for separating the scope and moving forward with two project phases.
CCTV Phase IV | 2016-06-10 | Recognise within planning the timelines for BTP and NR governance and approval processes. Network Rail required project commencement by September 2014 to secure funds, which put significant pressure on all parties to deliver the pre-programme approval stages
The key risk to the programme was the capacity and willingness for TOC’s to engage on implementation. On further investigation both the technology available and appetite of TOC’s was sometime lacking necessitating a significant number of changes to expected integrations
The programme has relatively devolved decision enabling it to be flexible and to meet BTP obligations. This was critical given the fixed price nature of the programme, and the expectation of rapid move to delivery.
Insufficient programme resources were allocated to business change and implementation, with the focus too much on the technical aspects of the work.
Programme staff were required to pick up gaps in general support resourcing (e.g. administrative processing, day-to-day running). Whilst this worked well for BTP, it meant a reliance was developed which re-created the gap once the FTC’s were terminated.
The programme office lost two of its four staff half way through the programme. As these were fixed term contracts there was insufficient time to recruit, leaving the PMO under resourced. Consideration should be given to centralisation of PMO resources to enable Force allocation against portfolio priorities.
G: and H: drive | 2015-12-14 | The Force Records Manager was seconded to project manage this project which assisted greatly as this project relied heavily on implementing new rules and guidance in relation to Information Management best practices.
It would have been advantageous to have had a full BTP organisational chart showing the teams that sit under each function / division. It was extremely time consuming establishing which departments / teams make up BTP and the contacts for the individual areas.
Additionally, the project found that a joint VDI / G: and H: drive communications plan was a good way to integrate these two projects and ensure a joined up approach.
There were some additional areas of work which touched on the G: and H: drive project which posed the possibility of ‘scope creep’; namely, the leavers process and clearance of the scanned folders. Both are now being progressed outside of the project, which helped the project to focus on, and achieve, the critical VDI dependency.
Enterprise Data Warehouse (EDW) - Phase 1 | 2015-10-13 | The inherent assumption of EDW Phase 1 business case was that it will have approval for Phase 2 works. Going forward projects should be cognisant of the complexity involved in getting approval for large programmes especially when BTPA/DfT/Cabinet Office approval is required.
Early engagement with internal BTP Procurement team to assist in navigating the Crown Commercial Services (CCS) procurement frameworks.
The focus of the project delivery was narrowed to meeting the ISP dependency whilst transferring the wider needs of the organisation to an undefined and unapproved Phase 2 programme of work. The Phase 2 project has now stalled and a review of the scope of EDW work is being performed. Consequently this has delayed improvements in the technical infrastructure requirements for BOXI which are not related to EDW.
ICCS Relocation Project | 2016-10-13 | Apply thorough product planning, project task, resource planning at the project onset that reflects the stages of the framework, where all resources including Third parties, BTP IT and BTP Business were tasked to deliver at key dates in the plan. Ensuring that key personnel become active at appropriate time in the lifecycle according to the project plan to deliver the project efficiently and effectively.
Drive the project through formal stage gates to ensure that project products are delivered to timescale.
The use of predefined stage payment criteria based on the project framework defined above ensured there was no ambiguity on when a payment can be made. This also served to focus suppliers on delivery to meet the schedule, rather than calendar dates and allowed the Project Manager to meet expected business deliver dates.
Register of unused but available equipment could be useful on other projects, rather than buying new equipment however this must be offset against the cost of re commissioning equipment and re licencing.
One team approach (BTP Business, IT and third parties). This particularly added great value throughout testing by having business users embedded in IT as part of the test team. Senior business staff played a significant role in the lead up to implementation by attending twice daily 15 minute conference calls which allowed quick communications and informed decisions to be taken which enabled a positive implementation.
EDW | 2015 | The inherent assumption of EDW Phase 1 business case was that it will have approval for Phase 2 works. Going forward projects should be cognisant of the complexity involved in getting approval for large programmes especially when BTPA/DfT/Cabinet Office approval is required. Early engagement with internal BTP Procurement team to assist in navigating the Crown Commercial Services (CCS) procurement frameworks. The focus of the project delivery was narrowed to meeting the ISP dependency whilst transferring the wider needs of the organisation to an undefined and unapproved Phase 2 programme of work. The Phase 2 project has now stalled and a review of the scope of EDW work is being performed. Consequently this has delayed improvements in the technical infrastructure requirements for BOXI which are not related to EDW.
Intranet Replacement and Governance | 2015 | The project had already overrun a couple of times and because no one was sure of the business expectations around time and scope, it was at risk of drifting on indefinitely. The project was therefore re-scoped and a definitive deadline (agreed by all parties) was cast in stone with no option to move unless a Critical/Major incident impacted the go live date.
What was evident from taking the project on midway was that there was a requirement for a Technical Project Manager (TPM) to assist in scoping and delivering the technical aspect of the project.
One lesson learnt is that; if feasible there should be two project managers working on the project, one working on business processes and business delivery and a second TPM working on technical delivery from the onset.
Agile Project Management is ideal in three main situations: Projects which are exploratory in nature, Projects which need to have a high degree of customer collaboration, Projects which have teams which are highly innovative.
The Intranet Replacement project clearly fitted these criteria. Once the scope was defined and definitive list of tasks ascertained, the decision was made to run it as such, with “daily scrums” to ensure that actions were carried out to short deadlines to meet the overall go-live deadline.
Leading on from the above point, because of the “creative” nature of the project it was important that that the scope was fixed and that any changes are managed via a stringent change control process to stop scope creep and delay. To this end we devised a screenshot of the final look and feel of the Homepage and made all parties of the Project Board “wet ink” sign it to ensure that there was no variance from that one key deliverable.
EBURY BRIDGE CCTV PROJECT PHASE 3 | 2015 | The Programme has delivered on the scopes outlined, within acceptable timeframes and to budget. However there are key lessons to be learned from Phase 3 to be worked into future phases.
Lessons learnt continue to be built into the Programme both through inclusion within issues documentation and more holistically through close-out activities. Through earlier phases, outcome of these lessons learnt have supported the scope identification, planning and management of subsequent phases of the programme including improving the identification and mitigation of project risk.
Where scopes are repeatable – for example extension of the current footprint - experience from the first integrations has enabled more accurate identification of costs and timelines. However it also highlighted the need for more detailed discovery phases to ensure the full extent of the works required was established.
Programme management and governance has also been reviewed, with Phase 3 introducing a distinct BTP governance team to provide additional scrutiny and assurance. However authorisation for Fixed Term contracts and BTP standard recruitment timelines meant that the Programme Manager was only in post for the latter half of the programme, and the support role at the end of the programme. Use of agency staff will therefore need to be considered for the future.
As a process of continuing improvement, Phase 4 will include better provision of business change and benefits realisation activities to ensure operations maximise use of new capabilities, and that there is more detailed measurement and reporting of impact, including financial and non-financial benefits. These processes will align with the overall benefits realisation processes being implemented at portfolio level.
Operationally the model and approach used for B Division (London/SE) has provided the learning and experience, which will support the roll-out to C Division (England & Wales).
Issues arising during previous phases have also fed into the primary risks for Phase 4. For example the impact and additional costs of unexpected changes to current NR/TOC systems has been identified as a key risk within Phase 4 as a direct result of experience. This is now therefore being mitigated through Network Rail, enabling communication, which should provide clarity for BTP of future works, so the schedule and impact can reflect this. This more integrated approach to enterprise planning both reduces project risk in the short-term, and cost to the industry in the long-run as subsequent funding to re-integrate is no longer required