## Sheet1
Theme | DisplayName | Cause | Impact | Details | Indicators | Severity | __PowerAppsId__
Governance | Governance and Accountability | Unclear organizational structure and responsibilities | Lack of clarity in project controls and cost management | Establish a project controls architecture and define responsibilities for cost management. | Indicators: Governance structure documentation, role and responsibility matrices, and decision-making records. Evidence: Governance documents, role definitions, and decision logs. Metrics: Number of governance meetings, clarity of roles and responsibilities, and decision turnaround time. | 5 | e2b98189-9267-451d-9ff1-e0aa91a5ddf4
CommercialStrategy | Commercial Strategy | Projects need to understand the strengths and challenges of specific markets, such as IT, construction, and education, and ensure that tender evaluation is appropriate for the relevant supplier market. There were also concerns about the volatile construction market. | Increased Project Costs: Without a clear commercial strategy, projects may face unexpected costs due to poor tender evaluations and supplier performance issues. Delays in Project Timelines: Ineffective commercial strategies can lead to delays in project timelines as issues with suppliers and market conditions are not anticipated or managed effectively. Reduced Quality of Deliverables: A lack of strategic direction can result in lower quality deliverables, as suppliers may not be adequately vetted or managed. Strained Supplier Relationships: Poor commercial strategies can lead to misunderstandings and conflicts with suppliers, damaging long-term relationships. Negative Stakeholder Perception: Stakeholders may lose confidence in the project's success and the organization's ability to manage commercial aspects effectively. | Recommendations focus on setting out a clear high-level strategy for the business case as well as the more detailed approaches to evaluating tenders. | Market Analysis Reports: Regularly review market analysis reports to identify trends and potential risks in specific markets. Tender Evaluation Scores: Monitor the scores and feedback from tender evaluations to ensure they align with the strategic goals. Supplier Performance Metrics: Track supplier performance metrics to identify any issues early on. Project Outcome Reviews: Conduct post-project reviews to assess the effectiveness of the commercial strategy and identify areas for improvement. Stakeholder Feedback: Gather feedback from stakeholders to understand their perspectives on the commercial strategy and its implementation. | 5 | 5c9ea03d-f920-4e91-8eb3-af85833a3641
ResourceManagement | Capacity and Resource Management | Lack of resources and capacity planning | Insufficient resources to support delivery, leading to delays and increased risks | Develop a capacity planning strategy, ensure sufficient resources, and manage resource constraints effectively. Recommendations emphasize the need for adequate resourcing and capacity planning. Risks include lack of specialist resources and insufficient capacity to support delivery | Indicators: Resource allocation plans, capacity planning documents, and resource utilization reports. Evidence: Resource plans, capacity assessments, and utilization logs. Metrics: Resource utilization rate, capacity planning accuracy, and frequency of resource reviews. | 4 | c2353d30-3a2b-4d73-8abf-b6effc3069e5
RiskManagement | Risk Management and Mitigation | Poor risk management can stem from several factors, including: Lack of a structured risk management framework. Inadequate risk identification and assessment processes. Insufficient communication and reporting of risks. Failure to monitor and review risks regularly. Lack of training and awareness among team members. | Increased Project Costs: Unmanaged risks can lead to unexpected costs, as issues arise that were not anticipated or mitigated. Project Delays: Poor risk management can result in delays as unforeseen problems disrupt the project timeline. Reduced Quality of Deliverables: Without proper risk management, the quality of project deliverables may suffer due to unaddressed issues. Loss of Stakeholder Confidence: Stakeholders may lose confidence in the project's success and the organization's ability to manage risks effectively. Regulatory and Compliance Issues: Failure to manage risks can lead to non-compliance with regulatory requirements, resulting in legal and financial repercussions. | Effective risk management involves identifying, assessing, and prioritizing risks, followed by the implementation of strategies to mitigate or manage these risks. | Risk Registers: Regularly review and update risk registers to ensure all potential risks are identified and assessed. Risk Assessment Reports: Monitor the frequency and quality of risk assessment reports to ensure they are comprehensive and up-to-date. Incident Reports: Track incident reports to identify any recurring issues that may indicate poor risk management. Stakeholder Feedback: Gather feedback from stakeholders to understand their perceptions of risk management effectiveness. Audit Reports: Conduct regular audits to assess the effectiveness of risk management processes and identify areas for improvement. Training Records: Review training records to ensure team members have received adequate training on risk management practices. | 4 | 2851ac23-e095-4018-91f1-6a1be2a6113f
FinancialPlanning | Financial Planning and Management | Inconsistencies in the business case and environmental standards | Cost and time overruns, benefits erosion, and non-approval of the business case | Recommendations focus on ensuring financial controls and reviewing cost models. Risks include financial controls and cost monitoring | Indicators: Budget variance reports, financial forecasts, and cost-benefit analyses. Evidence: Financial reports, budget documents, and cost-benefit analysis reports. Metrics: Budget variance percentage, accuracy of financial forecasts, and return on investment (ROI) | 3 | 5b84f3b6-09af-4c21-aca9-c686e2b84ddc
BenefitsRealisation | Benefits Management and Realization | Unclear benefits management strategy and lack of alignment with project objectives | Poor benefits management and realization, leading to missed opportunities and reduced project value | Develop a clear benefits management strategy, align benefits with project objectives, and ensure effective management and realization of benefits. Recommendations suggest developing a benefits realization plan and ensuring alignment with strategic objectives. Risks include benefits not being effectively managed or realized | Indicators: Benefits realization plans, alignment with project objectives, and benefits tracking reports. Evidence: Benefits management documents, alignment reports, and tracking logs. Metrics: Percentage of benefits realized, alignment score with project objectives, and frequency of benefits reviews. | 2 | f6283f42-5e32-4ac9-a070-e6272553a1bb
KnowledgeManagement | Lessons Learned and Knowledge Management | Missed opportunities to capture and apply lessons learned | Repetition of past mistakes, leading to cost, schedule, and benefit issues | Conduct lessons learned reviews, capture and apply lessons to future projects, and ensure effective knowledge management. Recommendations focus on capturing and applying lessons learned from the project. Risks include lessons not being applied to future projects and missed opportunities for improvement | Indicators: Lessons learned reviews, knowledge sharing sessions, and documentation of lessons. Evidence: Lessons learned reports, knowledge sharing session minutes, and documentation logs. Metrics: Number of lessons learned, frequency of knowledge sharing sessions, and application of lessons to future projects. | 1 | 46bce227-7bee-4d59-b76d-c0b225c470fa