## Risks (2)
Report_Date | Organisation | Business_Area | Portfolio_ID | Project_ID | Risk_ID | Risk_Unique_ID | Risk_Type | Contingency_Type | Status | Criticality | Criticality_Clean | Risk_Category | Risk_Title | Owner | Start | End | PreMit_Probability | PreMit_Cost | PreMit_Factored_Cost | Mitigation Strategy | PostMit _Probability | PostMit_Cost | PostMit_Factored_Cost | PostMit_Criticality | PostMit_Criticality_Clean | Trend | Criticality | Duration |  | Cost_Success | Probability_Success | Criticality_Success
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 487 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 10% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 718 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 455.0417 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Survey costs | Person_567 | 2016-04-22 | 2016-08-20 01:00 | 100% | 13.2573 | 13.2573 | Avoid | 0% | 13.2573 | 0 | 0 | 4 | -- | FALSE | 120.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-076 | Project_008_Risk-076 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Design Authority Support to Tech Pubs Review | Person_565 | 2016-05-23 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK017 | Project_012_RISK017 | Threat | Project Contingency | Closed | H3 | 3 |  | COVID impacts production | Person_359 | 2015-04-04 | 2016-04-12 | 21% | 0 | 0 | Avoid | 10% | 0 | 0 | 0 | 4 | -- | FALSE | 374 | Gap in data | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R001 | Project_016_Risk--R001 | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Programme Schedule | Person_574 | 2016-02-20 01:00 | 2019-05-23 | 25% | 21.6366 | 5.4092 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1187.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R012 | Project_021_Risk-R012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Additional profiles required - in addition to those planned | Person_174 | 2016-02-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 502 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R016 | Project_021_Risk-R016 | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Resource Avaliability for Tech Pubs and Courseware Updates | Person_279 | 2017-01-21 | 2018-01-21 | 30% | 0.49663 | 0.14899 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 365 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R015 | Project_021_Risk-R015 | Threat | Project Contingency | Closed | H3 | 3 |  | Recovery | Person_522 | 2016-08-21 | 2017-08-20 | 30% | 245.0028 | 73.5008 | Avoid | 0% | 245.0028 | 0 | 0 | 4 | -- | FALSE | 364 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R014 | Project_021_Risk-R014 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Marching Customer Cost Recovery | Person_522 | 2001-05-23 | 2018-02-19 | 20% | 39.7302 | 7.946 | Avoid | 0% | 39.7302 | 0 | 0 | 4 | -- | FALSE | 6116 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R026 | Project_021_Risk-R026 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay in readiness of System Equipment to commence Acceptance | Person_470 | 2016-02-28 | 2016-07-20 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | Stable | TRUE | 143 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Purchase of Development Licenses required | Person_470 | 2016-02-13 | 2017-05-21 | 10% | 9.8222 | 0.98222 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 463 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R023 | Project_021_Risk-R023 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer place a claim | Person_522 | 2016-02-13 | 2016-05-21 | 10% | 347.639 | 34.7639 | Avoid | 0% | 347.639 | 0 | 0 | 4 | Stable | FALSE | 98 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R013 | Project_021_Risk-R013 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials take longer to complete and delay the schedule | Person_470 | 2016-02-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 502 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 25% | 5.9904 | 1.4976 | Accept | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 612.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 1 | Customers | Succession Planning | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 61% | 0 | 0 | Accept | 61% | 0 | 0 | H1 | 1 | Stable | TRUE | 2542.1667 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS016 | Project_025_RS016 | Threat | Project Contingency | Open | H3 | 3 | Customers | Short Term Cover | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 21% | 0 | 0 | Accept | 21% | 0 | 0 | H3 | 3 | -- | TRUE | 2542.1667 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--121 | Project_026_Risk--121 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance of Service | Person_396 | 2016-01-22 01:00 | 2018-12-27 01:00 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1070 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer request earlier delivery of equipment | Person_396 | 2014-05-09 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--923 | Project_026_Risk--923 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Availability of SW / Changes to SW Version | Person_396 | 2016-01-22 01:00 | 2018-08-04 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 924.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1372 | Project_026_Risk--1372 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer equipment is damaged / lost / stolen prior to Setting to Work | Person_396 | 2018-05-12 | 2018-08-04 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 84 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-185 | Project_026_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of Installations data (System and Installation Guidance) to Customer | Person_396 | 2014-10-22 01:00 | 2016-08-20 01:00 | 40% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 668 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_396 | 2016-01-22 01:00 | 2018-02-07 01:00 | 35% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | -- | TRUE | 747 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-067 | Project_026_Risk-067 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Severe Shortages in supply of the electronic components within the world wide market place | Person_396 | 2016-01-22 01:00 | 2020-11-25 01:00 | 60% | 0 | 0 | Reduce | 25% | 0 | 0 | H1 | 1 | -- | TRUE | 1769 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--114 | Project_026_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Evidence not accepted | Person_396 | 2017-10-26 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-067 | Project_028_Risk-067 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Component Due to Obsolesence of hardware | Person_070 | 2014-01-21 | 2017-08-20 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1307 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Closed | H3 | 3 |  | Agreement on Interface | Person_371 | 2014-01-21 | 2017-08-20 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 | 2016-09-19 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 972 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Availability of the platforms for modification | Person_371 | 2014-01-21 | 2017-08-20 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-017 | Project_028_Risk-017 | Threat | Project Contingency | Closed | H3 | 3 |  | IPR owner for the solution | Person_371 | 2014-12-20 | 2017-08-20 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 974 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-052 | Project_028_Risk-052 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Resourcing | Person_371 | 2015-04-08 | 2016-09-18 23:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 529.9583 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | Stable | TRUE | 845 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-025 | Project_028_Risk-025 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Project Management WP for extended accreditation | Person_371 | 2014-01-21 | 2016-09-19 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 972 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-026 | Project_028_Risk-026 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | On Board Trainer | Person_371 | 2014-01-21 | 2017-08-20 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 41% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-104 | Project_029_Risk-104 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Assumed Synergies between Plan and Prospect | Person_692 | 2014-10-22 01:00 | 2021-05-22 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | H2 | 2 | Improving | TRUE | 2403.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_692 | 2017-09-02 01:00 | 2017-09-23 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 21 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 41% | 6.4168 | 2.6309 | Transfer | 41% | 0 | 0 | H1 | 1 | Stable | TRUE | 42 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-117 | Project_030_Risk-117 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Manage current System support contract | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-116 | Project_030_Risk-116 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Remove Uniteruptable Power Supply from Solution | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-154 | Project_030_Risk-154 | Threat | Project Contingency | Closed | H3 | 3 |  | Platform Availability | Person_518 | 2014-08-22 01:00 | 2017-01-19 01:00 | 40% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 881 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK045 | Project_031_RISK045 | Threat | Project Contingency | Closed | H3 | 3 |  | Acts of God | Person_506 | 2013-08-20 19:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2083 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK034 | Project_031_RISK034 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of interference due to the infrastructure | Person_029 | 2013-08-20 19:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2083 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK040 | Project_031_RISK040 | Threat | Project Contingency | Closed | H3 | 3 |  | Technology changes affecting ability to maintain security accreditation. | Person_506 | 2013-08-20 19:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2083 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R015 | Project_021_Risk-R015 | Threat | Project Contingency | Closed | H3 | 3 |  | Recovery | Person_522 | 2016-08-20 23:00 | 2017-08-19 23:00 | 30% | 245.0028 | 73.5008 | Avoid | 0% | 245.0028 | 0 | 0 | 4 | -- | FALSE | 364 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R014 | Project_021_Risk-R014 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Marching Customer Cost Recovery | Person_522 | 2001-05-23 | 2018-02-18 23:00 | 20% | 39.7302 | 7.946 | Avoid | 0% | 39.7302 | 0 | 0 | 4 | -- | FALSE | 6115.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK093 | Project_035_RISK093 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Sensitivity & Dynamic Range | Person_699 | 2015-01-22 01:00 | 2016-08-13 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | H2 | 2 | Stable | TRUE | 568.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_036 | RISK001 | Project_036_RISK001 | Threat | Project Contingency | Closed | H3 | 3 | Other Risks and Contingencies | Generic Risk Provision | Person_662 | 2011-05-24 | 2016-05-22 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1825 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-110 | Project_039_Risk-110 | Threat | Project Contingency | Closed | H3 | 3 | Contractual/Legal | Component Impact to Integrated System | Person_297 | 2014-12-22 01:00 | 2016-11-19 01:00 | 70% | 0 | 0 | Reduce | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 698 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-101 | Project_039_Risk-101 | Threat | Project Contingency | Closed | H3 | 3 | Contractual/Legal | Receiver architecture/performance baseline is late | Person_176 | 2015-11-21 01:00 | 2016-05-22 | 20% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 182.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Survey costs | Person_567 | 2016-04-22 | 2016-08-20 01:00 | 100% | 13.2573 | 13.2573 | Avoid | 0% | 13.2573 | 0 | 0 | 4 | -- | FALSE | 120.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-076 | Project_008_Risk-076 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Design Authority Support to Tech Pubs Review | Person_565 | 2016-05-23 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--121 | Project_026_Risk--121 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance of Service | Person_396 | 2016-01-22 01:00 | 2018-12-27 01:00 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1070 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer request earlier delivery of equipment | Person_396 | 2014-05-09 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--923 | Project_026_Risk--923 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Availability of SW / Changes to SW Version | Person_396 | 2016-01-22 01:00 | 2018-08-04 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 924.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1372 | Project_026_Risk--1372 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer equipment is damaged / lost / stolen prior to Setting to Work | Person_396 | 2018-05-12 | 2018-08-04 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 84 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_692 | 2017-09-02 01:00 | 2017-09-23 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 21 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-185 | Project_026_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of Installations data (System and Installation Guidance) to Customer | Person_396 | 2014-10-22 01:00 | 2016-08-20 01:00 | 40% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 668 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_396 | 2016-01-22 01:00 | 2018-02-07 01:00 | 35% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | -- | TRUE | 747 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-067 | Project_026_Risk-067 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Severe Shortages in supply of the electronic components within the world wide market place | Person_396 | 2016-01-22 01:00 | 2020-11-25 01:00 | 60% | 0 | 0 | Reduce | 25% | 0 | 0 | H1 | 1 | -- | TRUE | 1769 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--114 | Project_026_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Evidence not accepted | Person_396 | 2017-10-26 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R012 | Project_021_Risk-R012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Additional profiles required - in addition to those planned | Person_174 | 2016-02-05 23:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 502.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R016 | Project_021_Risk-R016 | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Resource Avaliability for Tech Pubs and Courseware Updates | Person_279 | 2017-01-20 23:00 | 2018-01-20 23:00 | 30% | 0.49663 | 0.14899 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 365 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Closed | H3 | 3 |  | Agreement on Interface | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-017 | Project_028_Risk-017 | Threat | Project Contingency | Closed | H3 | 3 |  | IPR owner for the solution | Person_371 | 2014-12-20 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 974 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R026 | Project_021_Risk-R026 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay in readiness of System Equipment to commence Acceptance | Person_470 | 2016-02-27 23:00 | 2016-07-20 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | Stable | TRUE | 143.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Purchase of Development Licenses required | Person_470 | 2016-02-12 23:00 | 2017-05-21 | 10% | 9.8222 | 0.98222 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 463.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R023 | Project_021_Risk-R023 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer place a claim | Person_522 | 2016-02-12 23:00 | 2016-05-21 | 10% | 347.639 | 34.7639 | Avoid | 0% | 347.639 | 0 | 0 | 4 | Stable | FALSE | 98.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R013 | Project_021_Risk-R013 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials take longer to complete and delay the schedule | Person_470 | 2016-02-05 23:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 502.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 41% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-104 | Project_029_Risk-104 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Assumed Synergies between Plan and Prospect | Person_692 | 2014-10-22 01:00 | 2021-05-22 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | H2 | 2 | Improving | TRUE | 2403.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-025 | Project_028_Risk-025 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Project Management WP for extended accreditation | Person_371 | 2014-01-21 01:00 | 2016-09-19 01:00 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 972 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 41% | 6.4168 | 2.6309 | Transfer | 41% | 0 | 0 | H1 | 1 | Stable | TRUE | 42 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-067 | Project_028_Risk-067 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Component Due to Obsolesence of hardware | Person_070 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1307 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-026 | Project_028_Risk-026 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | On Board Trainer | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-09-19 01:00 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 972 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Availability of the platforms for modification | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-117 | Project_030_Risk-117 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Manage current System support contract | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | Stable | TRUE | 845.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-116 | Project_030_Risk-116 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Remove Uniteruptable Power Supply from Solution | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-154 | Project_030_Risk-154 | Threat | Project Contingency | Closed | H3 | 3 |  | Platform Availability | Person_518 | 2014-08-22 01:00 | 2017-01-19 01:00 | 40% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 881 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK045 | Project_031_RISK045 | Threat | Project Contingency | Closed | H3 | 3 |  | Acts of God | Person_506 | 2013-08-20 18:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.25 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK034 | Project_031_RISK034 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of interference due to the infrastructure | Person_029 | 2013-08-20 18:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.25 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK040 | Project_031_RISK040 | Threat | Project Contingency | Closed | H3 | 3 |  | Technology changes affecting ability to maintain security accreditation. | Person_506 | 2013-08-20 18:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.25 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 25% | 5.9904 | 1.4976 | Accept | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 612.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R014 | Project_021_Risk-R014 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Marching Customer Cost Recovery | Person_174 | 2001-05-23 | 2018-02-19 01:00 | 20% | 39.7302 | 7.946 | Avoid | 0% | 39.7302 | 0 | 0 | 4 | -- | FALSE | 6116.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_692 | 2017-09-02 01:00 | 2017-09-23 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 21 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-117 | Project_030_Risk-117 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Manage current System support contract | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-116 | Project_030_Risk-116 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Remove Uniteruptable Power Supply from Solution | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 10% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 718 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 487 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 455.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-154 | Project_030_Risk-154 | Threat | Project Contingency | Closed | H3 | 3 |  | Platform Availability | Person_518 | 2014-08-22 01:00 | 2017-01-19 01:00 | 40% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 881 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 1 | Customers | Succession Planning | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 61% | 0 | 0 | Accept | 61% | 0 | 0 | H1 | 1 | Stable | TRUE | 2542.1667 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS016 | Project_025_RS016 | Threat | Project Contingency | Open | H3 | 3 | Customers | Short Term Cover | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 21% | 0 | 0 | Accept | 21% | 0 | 0 | H3 | 3 | -- | TRUE | 2542.1667 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2016-10-20 01:00 | 50% | 26.9674 | 13.4837 | Avoid | 10% | 0 | 0 | H2 | 2 | Worsening | TRUE | 119.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Survey costs | Person_567 | 2016-04-22 | 2016-08-20 01:00 | 100% | 13.2573 | 13.2573 | Avoid | 0% | 13.2573 | 0 | 0 | 4 | -- | FALSE | 120.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-076 | Project_008_Risk-076 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Design Authority Support to Tech Pubs Review | Person_565 | 2016-05-23 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R016 | Project_021_Risk-R016 | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Resource Avaliability for Tech Pubs and Courseware Updates | Person_174 | 2017-01-21 01:00 | 2018-01-21 01:00 | 30% | 0.49663 | 0.14899 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 365 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Closed | H3 | 3 |  | Agreement on Interface | Person_371 | 2014-01-21 01:00 | 2019-04-10 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1904.9583 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Purchase of Development Licenses required | Person_207 | 2016-02-13 01:00 | 2017-05-21 | 10% | 9.8222 | 0.98222 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 462.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R023 | Project_021_Risk-R023 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer place a claim | Person_522 | 2016-02-13 01:00 | 2016-05-21 | 10% | 347.639 | 34.7639 | Avoid | 0% | 347.639 | 0 | 0 | 4 | Stable | FALSE | 97.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-017 | Project_028_Risk-017 | Threat | Project Contingency | Closed | H3 | 3 |  | IPR owner for the solution | Person_371 | 2014-12-20 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 974 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 25% | 5.9904 | 1.4976 | Accept | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 612.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--121 | Project_026_Risk--121 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance of Service | Person_396 | 2016-01-22 01:00 | 2018-12-27 01:00 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1070 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer request earlier delivery of equipment | Person_396 | 2014-05-09 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--923 | Project_026_Risk--923 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Availability of SW / Changes to SW Version | Person_396 | 2016-01-22 01:00 | 2018-08-04 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 924.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1372 | Project_026_Risk--1372 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer equipment is damaged / lost / stolen prior to Setting to Work | Person_396 | 2018-05-12 | 2018-08-04 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 84 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-185 | Project_026_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of Installations data (System and Installation Guidance) to Customer | Person_396 | 2014-10-22 01:00 | 2016-08-20 01:00 | 40% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 668 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_396 | 2016-01-22 01:00 | 2018-02-07 01:00 | 35% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | -- | TRUE | 747 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-067 | Project_026_Risk-067 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Severe Shortages in supply of the electronic components within the world wide market place | Person_396 | 2016-01-22 01:00 | 2020-11-25 01:00 | 60% | 0 | 0 | Reduce | 25% | 0 | 0 | H1 | 1 | -- | TRUE | 1769 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--114 | Project_026_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Evidence not accepted | Person_396 | 2017-10-26 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 41% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-025 | Project_028_Risk-025 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Project Management WP for extended accreditation | Person_371 | 2014-01-21 01:00 | 2016-10-20 01:00 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1003 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 41% | 6.4168 | 2.6309 | Transfer | 41% | 0 | 0 | H1 | 1 | Stable | TRUE | 42 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-026 | Project_028_Risk-026 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | On Board Trainer | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK045 | Project_031_RISK045 | Threat | Project Contingency | Closed | H3 | 3 |  | Acts of God | Person_506 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK034 | Project_031_RISK034 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of interference due to the infrastructure | Person_029 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK040 | Project_031_RISK040 | Threat | Project Contingency | Closed | H3 | 3 |  | Technology changes affecting ability to maintain security accreditation. | Person_506 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-10-20 01:00 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1003 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Availability of the platforms for modification | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_692 | 2017-09-02 01:00 | 2017-09-23 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 21 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | Stable | TRUE | 845.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Closed | H3 | 3 |  | Agreement on Interface | Person_371 | 2014-01-21 01:00 | 2019-04-10 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1904.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-017 | Project_028_Risk-017 | Threat | Project Contingency | Closed | H3 | 3 |  | IPR owner for the solution | Person_371 | 2014-12-20 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 974 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-025 | Project_028_Risk-025 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Project Management WP for extended accreditation | Person_371 | 2014-01-21 01:00 | 2016-10-20 01:00 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1003 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-026 | Project_028_Risk-026 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | On Board Trainer | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-117 | Project_030_Risk-117 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Manage current System support contract | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 25% | 0 | 0 | -- | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 10% | 0 | 0 | Avoid | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 35% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 761 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 10% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 718 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 487 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 455.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-116 | Project_030_Risk-116 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Remove Uniteruptable Power Supply from Solution | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 1 | Customers | Succession Planning | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 61% | 0 | 0 | Accept | 61% | 0 | 0 | H1 | 1 | Stable | TRUE | 2542.1667 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS016 | Project_025_RS016 | Threat | Project Contingency | Open | H3 | 3 | Customers | Short Term Cover | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 21% | 0 | 0 | Accept | 21% | 0 | 0 | H3 | 3 | -- | TRUE | 2542.1667 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 311.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Improving | FALSE | 221.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-19 01:00 | 70% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 162.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-154 | Project_030_Risk-154 | Threat | Project Contingency | Closed | H3 | 3 |  | Platform Availability | Person_518 | 2014-08-22 | 2017-01-19 | 40% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 881 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 30% | 3.973 | 1.1919 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 99 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 221.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R036 | Project_021_Risk-R036 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-08-10 | 2016-09-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 40.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-153 | Project_020_Risk-153 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Liquidated Damages maybe reduced | Person_575 | 2003-12-22 01:00 | 2018-05-21 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5263.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK045 | Project_031_RISK045 | Threat | Project Contingency | Closed | H3 | 3 |  | Acts of God | Person_506 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 105.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R029 | Project_021_Risk-R029 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-08-03 | 2016-10-19 01:00 | 30% | 3.973 | 1.1919 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 77.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK034 | Project_031_RISK034 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of interference due to the infrastructure | Person_029 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 311.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 01:00 | 2017-06-29 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 290.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 99 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK040 | Project_031_RISK040 | Threat | Project Contingency | Closed | H3 | 3 |  | Technology changes affecting ability to maintain security accreditation. | Person_506 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R014 | Project_021_Risk-R014 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Marching Customer Cost Recovery | Person_174 | 2001-05-23 | 2018-02-19 | 20% | 39.7302 | 7.946 | Avoid | 0% | 39.7302 | 0 | 0 | 4 | -- | FALSE | 6116 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Closed | H3 | 3 |  | Agreement on Interface | Person_371 | 2014-01-21 01:00 | 2016-12-18 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1062 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-017 | Project_028_Risk-017 | Threat | Project Contingency | Closed | H3 | 3 |  | IPR owner for the solution | Person_371 | 2014-12-20 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 974 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 63 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 311.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R045 | Project_021_Risk-R045 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2016-12-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 121 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 311.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 2% | 0 | 0 | Reduce | 1% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 152 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R057 | Project_021_Risk-R057 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R058 | Project_021_Risk-R058 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R056 | Project_021_Risk-R056 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 152 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 63 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-026 | Project_028_Risk-026 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | On Board Trainer | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R014 | Project_021_Risk-R014 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Marching Customer Cost Recovery | Person_174 | 2001-05-23 | 2018-02-19 01:00 | 20% | 39.7302 | 7.946 | Avoid | 0% | 39.7302 | 0 | 0 | 4 | -- | FALSE | 6116.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 10% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 718 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-11-18 01:00 | 25% | 3.9852 | 0.9963 | Accept | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1834 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Survey costs | Person_567 | 2016-04-22 | 2016-08-20 01:00 | 100% | 13.2573 | 13.2573 | Avoid | 0% | 13.2573 | 0 | 0 | 4 | -- | FALSE | 120.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-076 | Project_008_Risk-076 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Design Authority Support to Tech Pubs Review | Person_565 | 2016-05-23 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-117 | Project_030_Risk-117 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Manage current System support contract | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 25% | 0 | 0 | -- | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer change environment | Person_187 | 2013-08-21 | 2018-08-21 | 10% | 0 | 0 | Avoid | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1826 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 35% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 761 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 41% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-116 | Project_030_Risk-116 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Remove Uniteruptable Power Supply from Solution | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 41% | 6.4168 | 2.6309 | Transfer | 41% | 0 | 0 | H1 | 1 | Stable | TRUE | 42 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-154 | Project_030_Risk-154 | Threat | Project Contingency | Closed | H3 | 3 |  | Platform Availability | Person_518 | 2014-08-22 01:00 | 2017-01-19 01:00 | 40% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 881 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-11-19 01:00 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1033 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Availability of the platforms for modification | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_692 | 2017-09-02 01:00 | 2017-09-23 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 21 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | Stable | TRUE | 845.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-153 | Project_020_Risk-153 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Liquidated Damages maybe reduced | Person_575 | 2003-12-22 01:00 | 2018-05-21 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5263.9583 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK045 | Project_031_RISK045 | Threat | Project Contingency | Closed | H3 | 3 |  | Acts of God | Person_506 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--121 | Project_026_Risk--121 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance of Service | Person_396 | 2016-01-22 01:00 | 2018-12-27 01:00 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1070 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer request earlier delivery of equipment | Person_396 | 2014-05-09 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--923 | Project_026_Risk--923 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Availability of SW / Changes to SW Version | Person_396 | 2016-01-22 01:00 | 2018-08-04 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 924.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1372 | Project_026_Risk--1372 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer equipment is damaged / lost / stolen prior to Setting to Work | Person_396 | 2018-05-12 | 2018-08-04 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 84 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-185 | Project_026_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of Installations data (System and Installation Guidance) to Customer | Person_396 | 2014-10-22 01:00 | 2016-11-19 01:00 | 40% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 759 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_396 | 2016-01-22 01:00 | 2018-02-07 01:00 | 35% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | -- | TRUE | 747 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-067 | Project_026_Risk-067 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Severe Shortages in supply of the electronic components within the world wide market place | Person_396 | 2016-01-22 01:00 | 2020-11-25 01:00 | 60% | 0 | 0 | Reduce | 25% | 0 | 0 | H1 | 1 | -- | TRUE | 1769 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--114 | Project_026_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Evidence not accepted | Person_396 | 2017-10-26 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 25% | 5.9904 | 1.4976 | Accept | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 612.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK034 | Project_031_RISK034 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of interference due to the infrastructure | Person_029 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK040 | Project_031_RISK040 | Threat | Project Contingency | Closed | H3 | 3 |  | Technology changes affecting ability to maintain security accreditation. | Person_506 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-153 | Project_020_Risk-153 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Liquidated Damages maybe reduced | Person_575 | 2003-12-22 01:00 | 2018-05-21 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5263.9583 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_692 | 2017-09-02 01:00 | 2017-09-23 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 21 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 487 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 455.0417 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-117 | Project_030_Risk-117 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Manage current System support contract | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-116 | Project_030_Risk-116 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Remove Uniteruptable Power Supply from Solution | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-154 | Project_030_Risk-154 | Threat | Project Contingency | Closed | H3 | 3 |  | Platform Availability | Person_518 | 2014-08-22 01:00 | 2017-01-19 01:00 | 40% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 881 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-026 | Project_028_Risk-026 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | On Board Trainer | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 1 | Customers | Succession Planning | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 61% | 0 | 0 | Accept | 61% | 0 | 0 | H1 | 1 | Stable | TRUE | 2542.1667 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS016 | Project_025_RS016 | Threat | Project Contingency | Open | H3 | 3 | Customers | Short Term Cover | Person_403 | 2012-08-20 20:00 | 2019-08-07 | 21% | 0 | 0 | Accept | 21% | 0 | 0 | H3 | 3 | -- | TRUE | 2542.1667 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R016 | Project_021_Risk-R016 | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Resource Avaliability for Tech Pubs and Courseware Updates | Person_174 | 2017-01-21 | 2018-01-21 | 30% | 0.49663 | 0.14899 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 365 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Closed | H3 | 3 |  | Agreement on Interface | Person_371 | 2014-01-21 01:00 | 2016-12-18 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1062 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Purchase of Development Licenses required | Person_207 | 2016-02-13 | 2017-05-21 | 10% | 9.8222 | 0.98222 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 463 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R023 | Project_021_Risk-R023 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer place a claim | Person_522 | 2016-02-13 | 2016-05-21 | 10% | 347.639 | 34.7639 | Avoid | 0% | 347.639 | 0 | 0 | 4 | Stable | FALSE | 98 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 312 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 | 2017-04-21 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Improving | FALSE | 222 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-19 | 70% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 162 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-017 | Project_028_Risk-017 | Threat | Project Contingency | Closed | H3 | 3 |  | IPR owner for the solution | Person_371 | 2014-12-20 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 974 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 | 2017-04-21 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 222 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R036 | Project_021_Risk-R036 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-08-10 | 2016-10-08 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 59 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK045 | Project_031_RISK045 | Threat | Project Contingency | Closed | H3 | 3 |  | Acts of God | Person_506 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK034 | Project_031_RISK034 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of interference due to the infrastructure | Person_029 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2016-11-19 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 105 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK040 | Project_031_RISK040 | Threat | Project Contingency | Closed | H3 | 3 |  | Technology changes affecting ability to maintain security accreditation. | Person_506 | 2013-08-20 17:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.2917 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-09-11 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 312 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 | 2017-06-29 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 291 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 | 2016-12-19 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 99 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Closed | H3 | 3 |  | Agreement on Interface | Person_499 | 2014-01-21 01:00 | 2017-01-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1095 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-017 | Project_028_Risk-017 | Threat | Project Contingency | Closed | H3 | 3 |  | IPR owner for the solution | Person_371 | 2014-12-20 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 974 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-153 | Project_020_Risk-153 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Liquidated Damages maybe reduced | Person_575 | 2003-12-22 01:00 | 2018-05-21 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5263.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_692 | 2017-09-02 01:00 | 2017-09-23 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 21 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 | 2017-01-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 63 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 | 2017-01-20 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 312 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R045 | Project_021_Risk-R045 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 | 2016-12-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 121 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 | 2017-07-20 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 312 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 | 2017-01-20 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 | 2017-01-20 | 2% | 0 | 0 | Reduce | 1% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 | 2017-01-20 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 152 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-20 | 2017-01-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R057 | Project_021_Risk-R057 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-20 | 2017-01-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R058 | Project_021_Risk-R058 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-11-20 | 2017-01-20 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 | 2017-01-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R056 | Project_021_Risk-R056 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 | 2017-01-20 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 152 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 | 2017-01-20 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 63 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 | 2017-01-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-117 | Project_030_Risk-117 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Manage current System support contract | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-116 | Project_030_Risk-116 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Remove Uniteruptable Power Supply from Solution | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Survey costs | Person_567 | 2016-04-22 | 2016-08-20 01:00 | 100% | 13.2573 | 13.2573 | Avoid | 0% | 13.2573 | 0 | 0 | 4 | -- | FALSE | 120.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-076 | Project_008_Risk-076 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Design Authority Support to Tech Pubs Review | Person_565 | 2016-05-23 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 25% | 0 | 0 | -- | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer change environment | Person_187 | 2013-08-21 | 2018-08-21 | 10% | 0 | 0 | Avoid | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1826 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 35% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 761 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-154 | Project_030_Risk-154 | Threat | Project Contingency | Closed | H3 | 3 |  | Platform Availability | Person_518 | 2014-08-22 01:00 | 2017-01-19 01:00 | 40% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 881 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-12-20 01:00 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1064 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Availability of the platforms for modification | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK045 | Project_031_RISK045 | Threat | Project Contingency | Closed | H3 | 3 |  | Acts of God | Person_506 | 2013-08-20 16:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.3333 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Purchase of Development Licenses required | Person_207 | 2016-02-13 01:00 | 2017-05-21 | 10% | 9.8222 | 0.98222 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 462.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R023 | Project_021_Risk-R023 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer place a claim | Person_522 | 2016-02-13 01:00 | 2016-05-21 | 10% | 347.639 | 34.7639 | Avoid | 0% | 347.639 | 0 | 0 | 4 | Stable | FALSE | 97.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | Stable | TRUE | 845.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 311.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Improving | FALSE | 221.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK034 | Project_031_RISK034 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of interference due to the infrastructure | Person_029 | 2013-08-20 16:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.3333 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-19 01:00 | 70% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 162.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK040 | Project_031_RISK040 | Threat | Project Contingency | Closed | H3 | 3 |  | Technology changes affecting ability to maintain security accreditation. | Person_506 | 2013-08-20 16:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.3333 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 221.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_692 | 2017-09-02 01:00 | 2017-09-23 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 21 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-153 | Project_020_Risk-153 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Liquidated Damages maybe reduced | Person_575 | 2003-12-22 01:00 | 2018-05-21 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5263.9583 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 105.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-117 | Project_030_Risk-117 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Manage current System support contract | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 311.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 01:00 | 2017-06-29 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 290.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 99 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 63 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 311.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R045 | Project_021_Risk-R045 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2016-12-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 121 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 311.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 2% | 0 | 0 | Reduce | 1% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 152 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R057 | Project_021_Risk-R057 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R058 | Project_021_Risk-R058 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R056 | Project_021_Risk-R056 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 152 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 63 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 91 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-116 | Project_030_Risk-116 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Remove Uniteruptable Power Supply from Solution | Person_639 | 2013-07-21 | 2014-05-06 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 289 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-154 | Project_030_Risk-154 | Threat | Project Contingency | Closed | H3 | 3 |  | Platform Availability | Person_518 | 2014-08-22 | 2017-01-19 | 40% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 881 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R016 | Project_021_Risk-R016 | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Resource Avaliability for Tech Pubs and Courseware Updates | Person_174 | 2017-01-21 01:00 | 2018-01-21 01:00 | 30% | 0.49663 | 0.14899 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 365 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-027 | Project_028_Risk-027 | Threat | Project Contingency | Closed | H3 | 3 |  | Agreement on Interface | Person_499 | 2014-01-21 01:00 | 2017-01-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1095 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-017 | Project_028_Risk-017 | Threat | Project Contingency | Closed | H3 | 3 |  | IPR owner for the solution | Person_371 | 2014-12-20 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 974 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-028 | Project_043_Risk-028 | Threat | Project Contingency | Closed | H3 | 3 |  | Subcontractor compliance to the Quality Requirements | Person_131 | 2014-09-13 01:00 | 2018-03-21 | 10% | 0.47906 | 0.047906 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1284.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK012 | Project_043_RISK012 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | System Interfaces | Person_136 | 2014-09-13 | 2018-03-21 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1285 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 41% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-008 | Project_043_Risk-008 | Threat | Project Contingency | Closed | H3 | 3 |  | Delivery of prime equipment - Customer | Person_657 | 2014-09-13 | 2018-03-21 | 50% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1285 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 41% | 6.4168 | 2.6309 | Transfer | 41% | 0 | 0 | H1 | 1 | Stable | TRUE | 42 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK068 | Project_043_RISK068 | Threat | Project Contingency | Closed | H3 | 3 |  | Service Delivery Manager | Person_084 | 2014-09-13 | 2018-03-21 | 30% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1285 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Closed | H3 | 3 | Acquisition and offsets | Minimum Order Quantities | Person_466 | 2011-05-24 | 2027-08-21 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5933.0417 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-185 | Project_026_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of Installations data (System and Installation Guidance) to Customer | Person_396 | 2014-10-22 01:00 | 2016-11-19 01:00 | 40% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 759 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_396 | 2016-01-22 01:00 | 2018-02-07 01:00 | 35% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | -- | TRUE | 747 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-067 | Project_026_Risk-067 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Severe Shortages in supply of the electronic components within the world wide market place | Person_396 | 2016-01-22 01:00 | 2020-11-25 01:00 | 60% | 0 | 0 | Reduce | 25% | 0 | 0 | H1 | 1 | -- | TRUE | 1769 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--114 | Project_026_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Evidence not accepted | Person_396 | 2017-10-26 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--121 | Project_026_Risk--121 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance of Service | Person_396 | 2016-01-22 01:00 | 2018-12-27 01:00 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1070 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer request earlier delivery of equipment | Person_396 | 2014-05-09 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--923 | Project_026_Risk--923 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Availability of SW / Changes to SW Version | Person_396 | 2016-01-22 01:00 | 2018-08-04 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 924.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1372 | Project_026_Risk--1372 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer equipment is damaged / lost / stolen prior to Setting to Work | Person_396 | 2018-05-12 | 2018-08-04 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 84 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 25% | 5.9904 | 1.4976 | Accept | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 612.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK067 | Project_043_RISK067 | Threat | Project Contingency | Closed | H3 | 3 |  | Service Desk | Person_204 | 2014-09-13 | 2018-03-21 | 30% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1285 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 10% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 718 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-11-18 01:00 | 25% | 3.9852 | 0.9963 | Accept | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1834 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK071 | Project_043_RISK071 | Threat | Project Contingency | Closed | H3 | 3 |  | Lack of Engine Data | Person_656 | 2014-09-13 | 2018-03-21 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1285 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK035 | Project_043_RISK035 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk we can't take Sub-system from Trials | Person_084 | 2014-09-13 | 2018-03-21 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1285 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-028 | Project_043_Risk-028 | Threat | Project Contingency | Closed | H3 | 3 |  | Subcontractor compliance to the Quality Requirements | Person_131 | 2014-09-13 | 2018-03-21 | 10% | 0.47906 | 0.047906 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1285 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 455 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 | 2016-03-21 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 487 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 1 | Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 61% | 0 | 0 | Accept | 61% | 0 | 0 | H1 | 1 | Stable | TRUE | 2542.2083 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS016 | Project_025_RS016 | Threat | Project Contingency | Open | H3 | 3 | Customers | Short Term Cover | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 21% | 0 | 0 | Accept | 21% | 0 | 0 | H3 | 3 | -- | TRUE | 2542.2083 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-11-20 | 2016-03-21 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 487 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-08-19 23:00 | 2016-08-07 | 10% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 718.0417 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Survey costs | Person_567 | 2016-04-22 | 2016-08-20 01:00 | 100% | 13.2573 | 13.2573 | Avoid | 0% | 13.2573 | 0 | 0 | 4 | -- | FALSE | 120.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-076 | Project_008_Risk-076 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Design Authority Support to Tech Pubs Review | Person_565 | 2016-05-23 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 25% | 0 | 0 | -- | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 10% | 0 | 0 | Avoid | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 35% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 761 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-185 | Project_026_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of Installations data (System and Installation Guidance) to Customer | Person_396 | 2014-10-22 01:00 | 2016-11-19 01:00 | 40% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 759 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_396 | 2016-01-22 01:00 | 2018-02-07 01:00 | 35% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | -- | TRUE | 747 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-067 | Project_026_Risk-067 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Severe Shortages in supply of the electronic components within the world wide market place | Person_396 | 2016-01-22 01:00 | 2020-11-25 01:00 | 60% | 0 | 0 | Reduce | 25% | 0 | 0 | H1 | 1 | -- | TRUE | 1769 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--114 | Project_026_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Evidence not accepted | Person_396 | 2017-10-26 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--121 | Project_026_Risk--121 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance of Service | Person_396 | 2016-01-22 01:00 | 2018-12-27 01:00 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1070 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer request earlier delivery of equipment | Person_396 | 2014-05-09 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--923 | Project_026_Risk--923 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Availability of SW / Changes to SW Version | Person_396 | 2016-01-22 01:00 | 2018-08-04 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 924.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1372 | Project_026_Risk--1372 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer equipment is damaged / lost / stolen prior to Setting to Work | Person_396 | 2018-05-12 | 2018-08-04 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 84 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Purchase of Development Licenses required | Person_207 | 2016-02-13 01:00 | 2017-05-21 | 10% | 9.8222 | 0.98222 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 462.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 221.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 70% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 172.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 221.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK045 | Project_031_RISK045 | Threat | Project Contingency | Closed | H3 | 3 |  | Acts of God | Person_506 | 2013-08-20 16:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.3333 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK034 | Project_031_RISK034 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of interference due to the infrastructure | Person_029 | 2013-08-20 16:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.3333 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 151.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 01:00 | 2017-06-29 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 290.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 40% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Improving | FALSE | 133 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 63 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R045 | Project_021_Risk-R045 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2016-12-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 121 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-02-19 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 2% | 0 | 0 | Reduce | 1% | 0 | 0 | H3 | 3 | Stable | FALSE | 61 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Worsening | FALSE | 152 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 61 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-02-19 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 63 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Worsening | FALSE | 91 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK040 | Project_031_RISK040 | Threat | Project Contingency | Closed | H3 | 3 |  | Technology changes affecting ability to maintain security accreditation. | Person_506 | 2013-08-20 16:00 | 2020-05-15 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2459.3333 |  | 1 | 1 | 1
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK070 | Project_058_RISK070 | Threat | Project Contingency | Closed | H3 | 3 |  | Subsystem Fails EMC Testing | Person_108 | 2017-06-23 | 2018-01-19 01:00 | 10% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 210.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 41% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK070 | Project_058_RISK070 | Threat | Project Contingency | Closed | H3 | 3 |  | Subsystem Fails EMC Testing | Person_108 | 2017-06-23 | 2018-01-19 01:00 | 10% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 210.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 41% | 6.4168 | 2.6309 | Transfer | 41% | 0 | 0 | H1 | 1 | Stable | TRUE | 42 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Closed | H3 | 3 | Acquisition and offsets | Minimum Order Quantities | Person_466 | 2011-05-24 | 2027-08-21 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 5933.0417 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_594 | 2016-09-08 01:00 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 590.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-015 | Project_023_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Illness | Person_371 | 2015-04-09 | 2016-12-11 01:00 | 25% | 5.9904 | 1.4976 | Accept | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 612.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Closed | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2013-02-20 01:00 | 2023-02-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_078 | 2016-09-03 01:00 | 2018-09-02 01:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_078 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 20% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | Stable | TRUE | 546.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 40% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 304.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 10% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 718 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-11-18 01:00 | 25% | 3.9852 | 0.9963 | Accept | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1834 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | Stable | TRUE | 845.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_559 | 2016-08-20 01:00 | 2019-08-21 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_078 | 2017-05-23 | 2019-10-22 01:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 882.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Accrediation Scope | Person_371 | 2014-01-21 01:00 | 2016-12-20 01:00 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1064 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Availability of the platforms for modification | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Closed | H3 | 3 |  | PTFE cables | Person_594 | 2017-05-23 | 2018-11-14 01:00 | 50% | 4.3229 | 2.1615 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 540.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-06 01:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1507.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_078 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 1 | Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 61% | 0 | 0 | Accept | 61% | 0 | 0 | H1 | 1 | Stable | TRUE | 2542.2083 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS016 | Project_025_RS016 | Threat | Project Contingency | Open | H3 | 3 | Customers | Short Term Cover | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 21% | 0 | 0 | Accept | 21% | 0 | 0 | H3 | 3 | -- | TRUE | 2542.2083 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 455 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Accrediation Scope | Person_253 | 2014-01-21 01:00 | 2017-03-22 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1155.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Availability of the platforms for modification | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--41 | Project_021_Risk--41 | Threat | Project Contingency | Closed | H3 | 3 |  | Routine Tech Pubs release does not align with Schedule | Person_126 | 2018-01-21 01:00 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 486.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | Stable | TRUE | 845.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Survey costs | Person_567 | 2016-04-22 | 2016-08-20 01:00 | 100% | 13.2573 | 13.2573 | Avoid | 0% | 13.2573 | 0 | 0 | 4 | -- | FALSE | 120.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-076 | Project_008_Risk-076 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Design Authority Support to Tech Pubs Review | Person_565 | 2016-05-23 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 20% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | Stable | TRUE | 546.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 40% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 304.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 25% | 0 | 0 | -- | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 10% | 0 | 0 | Avoid | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 35% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 761 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_078 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_078 | 2016-09-03 01:00 | 2018-09-02 01:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 41% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_594 | 2016-09-08 01:00 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 590.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 41% | 6.4168 | 2.6309 | Transfer | 41% | 0 | 0 | H1 | 1 | Stable | TRUE | 42 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Closed | H3 | 3 | Acquisition and offsets | Minimum Order Quantities | Person_466 | 2011-05-24 | 2027-08-21 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 5933.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-185 | Project_026_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of Installations data (System and Installation Guidance) to Customer | Person_396 | 2014-10-22 01:00 | 2017-02-19 01:00 | 40% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 851 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_396 | 2016-01-22 01:00 | 2018-02-07 01:00 | 35% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | -- | TRUE | 747 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-067 | Project_026_Risk-067 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Severe Shortages in supply of the electronic components within the world wide market place | Person_396 | 2016-01-22 01:00 | 2020-11-25 01:00 | 60% | 0 | 0 | Reduce | 25% | 0 | 0 | H1 | 1 | -- | TRUE | 1769 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--114 | Project_026_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Evidence not accepted | Person_396 | 2017-10-26 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--121 | Project_026_Risk--121 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance of Service | Person_396 | 2016-01-22 01:00 | 2018-12-27 01:00 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1070 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer request earlier delivery of equipment | Person_396 | 2014-05-09 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--923 | Project_026_Risk--923 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Availability of SW / Changes to SW Version | Person_396 | 2016-01-22 01:00 | 2018-08-04 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 924.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1372 | Project_026_Risk--1372 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer equipment is damaged / lost / stolen prior to Setting to Work | Person_396 | 2018-05-12 | 2018-08-04 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 84 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-075 | Project_026_Risk-075 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Late Assembly due to supply chain issues | Person_396 | 2018-02-07 01:00 | 2018-05-31 | 25% | 0 | 0 | Accept | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 112.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-072 | Project_026_Risk-072 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Late Delivery of Customer Furnished Equipmnet | Person_773 | 2016-12-08 01:00 | 2018-12-27 01:00 | 10% | 0 | 0 | -- | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 749 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Late Delivery of Product | Person_506 | 2016-12-11 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | -- | 50% | 0 | 0 | H1 | 1 | -- | TRUE | 746 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-078 | Project_026_Risk-078 | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Reduced Onboard Period | Person_630 | 2018-02-17 01:00 | 2018-08-04 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 167.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-074 | Project_026_Risk-074 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Integration of the subsystem | Person_127 | 2016-12-15 01:00 | 2023-11-20 01:00 | 85% | 0 | 0 | -- | 85% | 0 | 0 | H1 | 1 | -- | TRUE | 2531 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_559 | 2016-08-20 01:00 | 2019-08-21 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-06 01:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1507.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk008 | Project_002_Risk008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-08-20 | 2016-08-07 | 10% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 718 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Purchase of Development Licenses required | Person_207 | 2016-02-13 01:00 | 2017-05-21 | 10% | 9.8222 | 0.98222 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 462.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 221.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 70% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 172.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 221.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_078 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 151.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 01:00 | 2017-06-29 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 290.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 40% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Improving | FALSE | 133 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 63 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R045 | Project_021_Risk-R045 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2016-12-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 121 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-02-19 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 2% | 0 | 0 | Reduce | 1% | 0 | 0 | H3 | 3 | Stable | FALSE | 61 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Worsening | FALSE | 152 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 61 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-02-19 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 63 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Worsening | FALSE | 91 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_078 | 2017-05-23 | 2019-10-22 01:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 882.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 1 | Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 61% | 0 | 0 | Accept | 61% | 0 | 0 | H1 | 1 | Stable | TRUE | 2542.2083 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS016 | Project_025_RS016 | Threat | Project Contingency | Open | H3 | 3 | Customers | Short Term Cover | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 21% | 0 | 0 | Accept | 21% | 0 | 0 | H3 | 3 | -- | TRUE | 2542.2083 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 455 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Closed | H3 | 3 |  | PTFE cables | Person_594 | 2017-05-23 | 2018-11-14 01:00 | 50% | 4.3229 | 2.1615 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 540.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_078 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_078 | 2016-09-03 | 2018-09-02 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK005 | Project_004_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2014-11-19 23:00 | 2016-03-20 23:00 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 487 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 221.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 70% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Worsening | TRUE | 172.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 221.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_594 | 2016-09-08 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 591 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_559 | 2016-08-20 | 2019-08-21 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 151.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-09-11 01:00 | 2017-06-29 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 290.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to rig unavailability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 40% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Improving | FALSE | 133 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 100% | 0 | 0 | H1 | 1 | Stable | TRUE | 63 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-016 | Project_021_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R045 | Project_021_Risk-R045 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2016-12-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 121 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-02-19 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 2% | 0 | 0 | Reduce | 1% | 0 | 0 | H3 | 3 | Stable | FALSE | 61 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R051 | Project_021_Risk-R051 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2016-08-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Worsening | FALSE | 152 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 50% | 0 | 0 | Reduce | 60% | 0 | 0 | H1 | 1 | Stable | TRUE | 61 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-02-19 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 63 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Worsening | FALSE | 91 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_078 | 2013-02-20 | 2023-02-20 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-075 | Project_008_Risk-075 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Survey costs | Person_618 | 2016-04-22 | 2017-08-20 01:00 | 100% | 13.2573 | 13.2573 | Avoid | 0% | 13.2573 | 0 | 0 | 4 | -- | FALSE | 485.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-104 | Project_011_Risk-104 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Customer delayed in providing Custeomr Furnished Equipment | Person_147 | 2016-06-23 | 2017-04-21 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-121 | Project_011_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Impact of Enterprise System changes | Person_147 | 2017-02-20 01:00 | 2018-08-21 | 20% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | Stable | TRUE | 546.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-120 | Project_011_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Pick up and Drop off of Software Resource | Person_230 | 2017-04-21 | 2018-02-19 01:00 | 40% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 304.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-112 | Project_011_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Bid Management | Impact of Project Bid/Delivery | Person_147 | 2016-07-21 | 2018-05-21 | 25% | 0 | 0 | -- | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-118 | Project_011_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer change environment | Person_187 | 2013-08-21 01:00 | 2018-08-21 | 10% | 0 | 0 | Avoid | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-117 | Project_011_Risk-117 | Threat | Project Contingency | Closed | H3 | 3 | Customers | Customer Avaliability for testing/reviews | Person_147 | 2016-07-21 | 2018-08-21 | 35% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 761 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-06 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1507 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) on platform - performed by Customer | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 41% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_078 | 2013-02-20 | 2023-02-20 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_692 | 2017-09-02 01:00 | 2017-10-14 01:00 | 41% | 6.4168 | 2.6309 | Transfer | 41% | 0 | 0 | H1 | 1 | Stable | TRUE | 42 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Closed | H3 | 3 | Acquisition and offsets | Minimum Order Quantities | Person_466 | 2017-05-23 | 2019-05-16 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 723 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK037 | Project_029_Risk-RISK037 | Opportunitity | Project Contingency | Closed | H3 | 3 | System Integration, Verification & Validation | Reduction of tests and demonstrations for platform | Person_654 | 2019-12-22 01:00 | 2021-07-20 | 70% | 1.2834 | 0.89835 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 575.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_078 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--121 | Project_026_Risk--121 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance of Service | Person_690 | 2016-01-22 01:00 | 2018-12-27 01:00 | 25% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 1070 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--923 | Project_026_Risk--923 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Availability of SW / Changes to SW Version | Person_690 | 2016-01-22 01:00 | 2018-08-04 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 924.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1372 | Project_026_Risk--1372 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer equipment is damaged / lost / stolen prior to Setting to Work | Person_690 | 2018-05-12 | 2018-08-04 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 84 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-075 | Project_026_Risk-075 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Late Assembly due to supply chain issues | Person_690 | 2018-02-07 01:00 | 2018-05-31 | 25% | 0 | 0 | Accept | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 112.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-072 | Project_026_Risk-072 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Late Delivery of Customer Furnished Equipmnet | Person_773 | 2016-12-08 01:00 | 2018-12-27 01:00 | 10% | 0 | 0 | -- | 10% | 0 | 0 | H2 | 2 | -- | TRUE | 749 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Late Delivery of Product | Person_506 | 2016-12-11 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H1 | 1 | -- | TRUE | 746 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-078 | Project_026_Risk-078 | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Reduced Onboard Period | Person_630 | 2018-02-17 01:00 | 2018-08-04 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 167.9583 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-074 | Project_026_Risk-074 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Integration of the subsystem | Person_127 | 2016-12-15 01:00 | 2023-11-20 01:00 | 85% | 0 | 0 | -- | 85% | 0 | 0 | H1 | 1 | -- | TRUE | 2531 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-185 | Project_026_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of Installations data (System and Installation Guidance) to Customer | Person_690 | 2014-10-22 01:00 | 2017-02-19 01:00 | 40% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 851 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--1360 | Project_026_Risk--1360 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ability to deliver 3rd Party H/W in line with contract requirement | Person_690 | 2016-01-22 01:00 | 2018-02-07 01:00 | 35% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | -- | TRUE | 747 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-067 | Project_026_Risk-067 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Severe Shortages in supply of the electronic components within the world wide market place | Person_690 | 2016-01-22 01:00 | 2020-11-25 01:00 | 60% | 0 | 0 | Reduce | 25% | 0 | 0 | H1 | 1 | -- | TRUE | 1769 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk--114 | Project_026_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Evidence not accepted | Person_690 | 2017-10-26 01:00 | 2018-12-27 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_078 | 2017-05-23 | 2019-10-22 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 882 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Closed | H3 | 3 |  | PTFE cables | Person_594 | 2017-05-23 | 2018-11-14 | 50% | 4.3229 | 2.1615 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 540 |  | 1 | 0 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--41 | Project_021_Risk--41 | Threat | Project Contingency | Closed | H3 | 3 |  | Routine Tech Pubs release does not align with Schedule | Person_126 | 2018-01-21 01:00 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 486.9583 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_078 | 2016-09-03 01:00 | 2018-09-02 01:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-022 | Project_028_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Accrediation Scope | Person_253 | 2014-01-21 01:00 | 2017-03-22 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1155.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-021 | Project_028_Risk-021 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Availability of the platforms for modification | Person_371 | 2014-01-21 01:00 | 2017-08-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1307 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_559 | 2016-08-20 01:00 | 2019-08-21 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-008 | Project_028_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer Furnished Equipmnet Condition | Person_371 | 2015-04-27 | 2017-08-19 01:00 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H2 | 2 | Stable | TRUE | 845.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-06 01:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1507.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK018 | Project_043_RISK018 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance | Person_367 | 2014-09-13 | 2018-03-21 | 20% | 0 | 0 | -- | 5% | 0 | 0 | H3 | 3 | -- | FALSE | 1285 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_078 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_078 | 2017-05-23 | 2019-10-22 01:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 882.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Closed | H3 | 3 |  | PTFE cables | Person_594 | 2017-05-23 | 2018-11-14 01:00 | 50% | 4.3229 | 2.1615 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 540.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--41 | Project_021_Risk--41 | Threat | Project Contingency | Closed | H3 | 3 |  | Routine Tech Pubs release does not align with Schedule | Person_126 | 2018-01-21 01:00 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 486.9583 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_078 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_078 | 2016-09-02 23:00 | 2018-09-01 23:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_594 | 2016-09-07 23:00 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 591.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_559 | 2016-08-19 23:00 | 2019-08-20 23:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-05 23:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1506.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_078 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS015 | Project_025_RS015 | Threat | Project Contingency | Open | H1 | 1 | Customers | Succession Planning | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 61% | 0 | 0 | Accept | 61% | 0 | 0 | H1 | 1 | Stable | TRUE | 2542.2083 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS016 | Project_025_RS016 | Threat | Project Contingency | Open | H3 | 3 | Customers | Short Term Cover | Person_403 | 2012-08-20 19:00 | 2019-08-07 | 21% | 0 | 0 | Accept | 21% | 0 | 0 | H3 | 3 | -- | TRUE | 2542.2083 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK005 | Project_003_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Tank Room Availablity | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0 | 0 | Avoid | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 455 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_078 | 2017-05-23 | 2019-10-21 23:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 881.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Closed | H3 | 3 |  | PTFE cables | Person_594 | 2017-05-23 | 2018-11-13 23:00 | 50% | 4.3229 | 2.1615 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 539.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--41 | Project_021_Risk--41 | Threat | Project Contingency | Closed | H3 | 3 |  | Routine Tech Pubs release does not align with Schedule | Person_126 | 2018-01-21 01:00 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 486.9583 |  | 1 | 1 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-05-21 | 80% | 0 | 0 | Reduce | 60% | 0 | 0 | H1 | 1 | Worsening | TRUE | 284 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-06-22 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 320 |  | 1 | 0 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 100% | 0 | 0 | H1 | 1 | Stable | TRUE | 215.9583 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 2% | 0 | 0 | Reduce | 1% | 0 | 0 | H3 | 3 | Stable | FALSE | 213.9583 |  | 1 | 0 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 60% | 0 | 0 | H1 | 1 | Stable | TRUE | 213.9583 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 213.9583 |  | 1 | 0 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_078 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-05-21 | 80% | 0 | 0 | Reduce | 60% | 0 | 0 | H1 | 1 | Worsening | TRUE | 284 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-06-22 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 320 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_078 | 2016-09-02 22:00 | 2018-09-01 22:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 01:00 | 2017-08-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 213.9583 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_594 | 2016-09-07 22:00 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 591.0833 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-05-21 | 80% | 0 | 0 | Reduce | 60% | 0 | 0 | H1 | 1 | Worsening | TRUE | 284 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-06-22 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 320 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Trials delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 100% | 0 | 0 | H1 | 1 | Stable | TRUE | 215.9583 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R053 | Project_021_Risk-R053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trials delay due to equipment availability | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 2% | 0 | 0 | Reduce | 1% | 0 | 0 | H3 | 3 | Stable | FALSE | 213.9583 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R052 | Project_021_Risk-R052 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 60% | 0 | 0 | H1 | 1 | Stable | TRUE | 213.9583 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R055 | Project_021_Risk-R055 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 213.9583 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_559 | 2016-08-19 22:00 | 2019-08-20 22:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-05-21 | 80% | 0 | 0 | Reduce | 60% | 0 | 0 | H1 | 1 | Worsening | TRUE | 284 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_721 | 2016-08-06 | 2017-06-22 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 320 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 | 2017-08-20 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 | 2017-06-22 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 214 |  | 1 | 0 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 | 2017-06-22 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 216 |  | 1 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 244 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-05 22:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1506.9167 |  | 1 | 0 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_482 | 2016-08-06 | 2017-06-22 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 320 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 01:00 | 2017-08-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 20% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | Stable | FALSE | 213.9583 |  | 1 | 0 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_078 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_482 | 2016-08-06 | 2017-06-22 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 320 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_078 | 2017-05-23 | 2019-10-21 22:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 881.9167 |  | 1 | 0 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 01:00 | 2017-08-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 20% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | Stable | FALSE | 213.9583 |  | 1 | 0 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Closed | H3 | 3 |  | PTFE cables | Person_594 | 2017-05-23 | 2018-11-13 22:00 | 50% | 4.3229 | 2.1615 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 539.9167 |  | 1 | 0 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the aerosonic modification | Person_174 | 2016-11-20 01:00 | 2017-06-22 | 20% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | Stable | FALSE | 213.9583 |  | 1 | 0 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R028 | Project_021_Risk-R028 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_482 | 2016-08-06 | 2017-06-22 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 320 |  | 1 | 0 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R048 | Project_021_Risk-R048 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to performance | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R049 | Project_021_Risk-R049 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-05 23:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1506.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R047 | Project_021_Risk-R047 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Trial delay due to equip[ment availability | Person_174 | 2016-10-21 01:00 | 2017-08-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R054 | Project_021_Risk-R054 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to build standard issue relating to the modification of product | Person_174 | 2016-11-20 01:00 | 2017-10-19 01:00 | 20% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK028 | Project_021_RISK028 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK029 | Project_021_RISK029 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 60 |  | 1 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 60 |  | 1 | 1 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-022 | Project_021_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-021 | Project_021_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 60 |  | 1 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-022 | Project_021_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-021 | Project_021_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_078 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 60 |  | 1 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-022 | Project_021_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-021 | Project_021_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_078 | 2017-05-23 | 2019-10-21 23:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 881.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-002 | Project_021_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials Delay due to lack of personnel resource | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-001 | Project_021_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification Report delays due to insufficient resource in supply chain | Person_207 | 2017-09-20 01:00 | 2017-12-20 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 91 |  | 1 | 0 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_061 | 2017-12-21 01:00 | 2018-03-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-014 | Project_021_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to weather | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 311.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-013 | Project_021_Risk-013 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_174 | 2018-02-20 01:00 | 2018-05-21 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 89.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-010 | Project_021_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_207 | 2017-09-20 01:00 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 60 |  | 1 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-018 | Project_021_Risk-018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-015 | Project_021_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_174 | 2016-09-11 01:00 | 2017-07-20 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 311.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK021 | Project_021_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_174 | 2017-06-23 | 2017-09-19 01:00 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 88.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK024 | Project_021_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_482 | 2017-05-23 | 2017-11-19 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-022 | Project_021_Risk-022 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of supporting resources | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-021 | Project_021_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | trials delay due to lack of equipment | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-23 01:00 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1156.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Closed | H3 | 3 |  | PTFE cables | Person_594 | 2017-05-23 | 2018-11-13 23:00 | 50% | 4.3229 | 2.1615 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 539.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-16 01:00 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1180.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_078 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--41 | Project_021_Risk--41 | Threat | Project Contingency | Closed | H3 | 3 |  | Routine Tech Pubs release does not align with Schedule | Person_126 | 2018-01-21 01:00 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 486.9583 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 550.9583 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_661 | 2018-03-27 | 2018-03-28 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK015 | Project_079_RISK015 | Threat | Project Contingency | Closed | H3 | 3 |  | UK - Joint team | Person_580 | 2017-09-29 01:00 | 2018-04-22 | 10% | 17.8561 | 1.7856 | Transfer | 10% | 0 | 0 | 0 | 4 | Worsening | FALSE | 204.9583 | Gap in data | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2018-05-23 | 2023-02-20 01:00 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1734.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_550 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-05-21 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK028 | Project_079_RISK028 | Threat | Project Contingency | Closed | H3 | 3 |  | Export Applications | Person_002 | 2018-06-08 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 349 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_078 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_563 | 2016-09-03 01:00 | 2018-09-02 01:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_661 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_563 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_078 | 2016-02-21 01:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1915.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK470-X | Project_065_RISK470-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The increase in NRE will not be accepted by the customer as there is no supporting quote. | Person_594 | 2018-01-27 01:00 | 2018-11-16 01:00 | 70% | 12.6771 | 8.874 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 293 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_661 | 2017-09-20 01:00 | 2017-10-20 01:00 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 30 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-14 01:00 | 2024-05-23 | 50% | 25.3543 | 12.6771 | Avoid | 0% | 25.3543 | 0 | 0 | 4 | -- | FALSE | 2685.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_418 | 2016-09-08 01:00 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 590.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-20 01:00 | 2018-02-11 01:00 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 144 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_563 | 2016-08-20 01:00 | 2019-08-21 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_022 | 2015-07-22 | 2018-10-22 01:00 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1188.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Closed | H3 | 3 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2019-02-20 01:00 | 30% | 53.244 | 15.9732 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 950.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-20 01:00 | 2023-02-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_661 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3652 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_594 | 2016-09-08 01:00 | 2020-11-20 01:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-02-23 01:00 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 95 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_563 | 2017-05-23 | 2019-10-22 01:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 882.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 90.9583 |  | 1 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK556 | Project_065_RISK556 | Threat | Project Contingency | Closed | H3 | 3 |  | Post Transfer modifications are required | Person_418 | 2013-02-20 01:00 | 2023-03-22 | 40% | 13.9871 | 5.5948 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--22 | Project_021_Risk--22 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_061 | 2018-02-20 01:00 | 2019-02-10 01:00 | 50% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 355 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 149.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 149.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 179.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK551 | Project_065_RISK551 | Threat | Project Contingency | Closed | H3 | 3 |  | The previously agreed scope from HMI Workshops expands | Person_418 | 2018-07-22 | 2018-12-22 01:00 | 40% | 10.4375 | 4.175 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 153.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--40 | Project_021_Risk--40 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Delay due to late receipt of CoD | Person_470 | 2018-02-20 01:00 | 2018-02-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 0 |  | 1 | 1 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--38 | Project_021_Risk--38 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Delay to completion due to late supplier dependencies | Person_470 | 2018-05-23 | 2018-11-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 181.0417 |  | 1 | 1 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--36 | Project_021_Risk--36 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Schedule update due to Lessons Learned | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 90.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system releases due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 59.9583 |  | 1 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--33 | Project_021_Risk--33 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Trials interrupted by Production Tests/ Embodiment support | Person_174 | 2018-01-21 01:00 | 2018-12-21 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Customer resource to provide timely to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 80% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--30 | Project_021_Risk--30 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Emergent safety requirements for Client Server update | Person_061 | 2018-02-20 01:00 | 2018-06-22 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 121.9583 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_661 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_661 | 2017-09-20 01:00 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 212.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_022 | 2015-07-22 | 2018-10-22 01:00 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1188.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3652 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK564 | Project_065_RISK564 | Threat | Project Contingency | Closed | H3 | 3 |  | Unexpected design changes | Person_418 | 2018-04-20 | 2019-04-23 | 80% | 27.1882 | 21.7506 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 368 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-23 01:00 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1156.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Closed | H3 | 3 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-08-20 | 50% | 11.1812 | 5.5906 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 819 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-16 01:00 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1180.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_550 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-05-21 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Closed | H3 | 3 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Avoid | 0% | 1.2677 | 0 | 0 | 4 | -- | FALSE | 346 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_078 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-06 01:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1507.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_078 | 2016-02-21 01:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1915.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK470-X | Project_065_RISK470-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The increase in NRE will not be accepted by the customer as there is no supporting quote. | Person_594 | 2018-01-27 01:00 | 2018-11-16 01:00 | 70% | 12.6771 | 8.874 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 293 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-20 01:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 242.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_563 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-20 01:00 | 2023-02-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_661 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_594 | 2016-09-08 01:00 | 2020-11-20 01:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Closed | H3 | 3 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2022-05-23 | 2023-11-20 01:00 | 10% | 1.2677 | 0.12677 | Avoid | 0% | 1.2677 | 0 | 0 | 4 | Improving | FALSE | 546.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 160.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 550.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_661 | 2018-03-27 | 2018-03-28 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2018-05-23 | 2023-02-20 01:00 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1734.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_078 | 2016-09-02 22:00 | 2018-09-01 22:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-14 01:00 | 2024-05-23 | 50% | 25.3543 | 12.6771 | Avoid | 0% | 25.3543 | 0 | 0 | 4 | -- | FALSE | 2685.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_594 | 2016-09-07 22:00 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 591.0833 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_661 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_661 | 2017-09-20 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 213 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_022 | 2015-07-22 | 2018-10-22 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1188 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_559 | 2016-08-19 22:00 | 2019-08-20 22:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_078 | 2013-02-20 | 2023-02-20 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2013-02-20 | 2023-02-20 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_078 | 2013-02-20 | 2023-02-20 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-23 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1156 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-05 22:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1506.9167 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-16 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1180 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_550 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_661 | 2017-11-20 | 2018-05-21 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 182 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_078 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_078 | 2013-02-20 | 2023-02-20 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_078 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_078 | 2016-02-21 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1916 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK470-X | Project_065_RISK470-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The increase in NRE will not be accepted by the customer as there is no supporting quote. | Person_594 | 2018-01-27 | 2018-11-16 | 70% | 12.6771 | 8.874 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 293 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-20 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 243 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_078 | 2017-05-23 | 2019-10-21 22:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 881.9167 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-20 | 2023-02-20 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_661 | 2013-02-20 | 2023-02-20 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_594 | 2016-09-08 | 2020-11-20 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Closed | H3 | 3 |  | PTFE cables | Person_594 | 2017-05-23 | 2018-11-13 22:00 | 50% | 4.3229 | 2.1615 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 539.9167 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_661 | 2017-11-20 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 161 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 551 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_661 | 2018-03-27 | 2018-03-28 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_563 | 2016-09-03 | 2018-09-02 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2018-05-23 | 2023-02-20 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1734 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_563 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_078 | 2013-02-20 | 2023-02-20 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-14 | 2024-05-23 | 50% | 25.3543 | 12.6771 | Avoid | 0% | 25.3543 | 0 | 0 | 4 | -- | FALSE | 2686 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_418 | 2016-09-08 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 591 |  | 1 | 0 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--36 | Project_021_Risk--36 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Schedule update due to Lessons Learned | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 90.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system releases due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 59.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--33 | Project_021_Risk--33 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Trials interrupted by Production Tests/ Embodiment support | Person_174 | 2018-01-21 01:00 | 2018-12-21 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Customer resource to provide timely to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 80% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 90.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_563 | 2016-08-20 | 2019-08-21 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--22 | Project_021_Risk--22 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_061 | 2018-02-20 01:00 | 2019-02-10 01:00 | 50% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 355 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 149.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 149.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 179.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Closed | H3 | 3 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2019-02-20 | 30% | 53.244 | 15.9732 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 950 |  | 1 | 0 | 1
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--40 | Project_021_Risk--40 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Delay due to late receipt of CoD | Person_470 | 2018-02-20 01:00 | 2018-02-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 0 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_563 | 2017-05-23 | 2019-10-22 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 882 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_550 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-05-21 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK556 | Project_065_RISK556 | Threat | Project Contingency | Closed | H3 | 3 |  | Post Transfer modifications are required | Person_418 | 2013-02-20 | 2023-03-22 | 40% | 13.9871 | 5.5948 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_078 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK551 | Project_065_RISK551 | Threat | Project Contingency | Closed | H3 | 3 |  | The previously agreed scope from HMI Workshops expands | Person_418 | 2018-07-22 | 2018-12-22 | 40% | 10.4375 | 4.175 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 153 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_078 | 2016-02-21 01:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1915.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK470-X | Project_065_RISK470-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The increase in NRE will not be accepted by the customer as there is no supporting quote. | Person_594 | 2018-01-27 01:00 | 2018-11-16 01:00 | 70% | 12.6771 | 8.874 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 293 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-20 01:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 242.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_563 | 2013-02-20 | 2023-03-22 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-20 01:00 | 2023-02-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_661 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_594 | 2016-09-08 01:00 | 2020-11-20 01:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK564 | Project_065_RISK564 | Threat | Project Contingency | Closed | H3 | 3 |  | Unexpected design changes | Person_418 | 2018-04-20 | 2019-04-23 | 80% | 27.1882 | 21.7506 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 368 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 160.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 550.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_661 | 2018-03-27 | 2018-03-28 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Closed | H3 | 3 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-08-20 | 50% | 11.1812 | 5.5906 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 819 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2018-05-23 | 2023-02-20 01:00 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1734.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Closed | H3 | 3 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Avoid | 0% | 1.2677 | 0 | 0 | 4 | -- | FALSE | 346 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_078 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-14 01:00 | 2024-05-23 | 50% | 25.3543 | 12.6771 | Avoid | 0% | 25.3543 | 0 | 0 | 4 | -- | FALSE | 2685.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-06 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1507 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--36 | Project_021_Risk--36 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Schedule update due to Lessons Learned | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 90.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system releases due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 59.9583 |  | 1 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--33 | Project_021_Risk--33 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Trials interrupted by Production Tests/ Embodiment support | Person_174 | 2018-01-21 01:00 | 2018-12-21 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Customer resource to provide timely to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 80% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 90.9583 |  | 1 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_563 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--22 | Project_021_Risk--22 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_061 | 2018-02-20 01:00 | 2019-02-10 01:00 | 50% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 355 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 149.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 149.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 179.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Closed | H3 | 3 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2022-05-23 | 2023-11-20 | 10% | 1.2677 | 0.12677 | Avoid | 0% | 1.2677 | 0 | 0 | 4 | Improving | FALSE | 546 |  | 1 | 0 | 1
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--40 | Project_021_Risk--40 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Delay due to late receipt of CoD | Person_470 | 2018-02-20 01:00 | 2018-02-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 0 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_661 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_661 | 2017-09-19 23:00 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 213.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_022 | 2015-07-22 | 2018-10-21 23:00 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1187.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_563 | 2013-02-20 | 2023-03-22 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3652 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK028 | Project_079_RISK028 | Threat | Project Contingency | Closed | H3 | 3 |  | Export Applications | Person_002 | 2018-06-08 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 349 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-22 23:00 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1155.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK004 | Project_087_RISK004 | Threat | Project Contingency | Closed | H3 | 3 |  | We do not receive the relevant paperwork in order for us to process platformment of production unit... | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-15 23:00 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1179.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_550 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_661 | 2017-11-19 23:00 | 2018-05-21 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 182.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK003 | Project_087_RISK003 | Threat | Project Contingency | Closed | H3 | 3 |  | If any unit requires opened then there is a risk the connector fails. | Person_399 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_078 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK005 | Project_087_RISK005 | Threat | Project Contingency | Closed | H3 | 3 |  | Battery design not fit for purpose. | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_078 | 2016-02-20 23:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1916.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK470-X | Project_065_RISK470-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The increase in NRE will not be accepted by the customer as there is no supporting quote. | Person_594 | 2018-01-26 23:00 | 2018-11-15 23:00 | 70% | 12.6771 | 8.874 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 293 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-19 23:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 243.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK011 | Project_087_RISK011 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Will customer purchase rechargeable battery and charger | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-19 23:00 | 2023-02-19 23:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_661 | 2013-02-19 23:00 | 2023-02-19 23:00 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_594 | 2016-09-07 23:00 | 2020-11-19 23:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK002 | Project_087_RISK002 | Threat | Project Contingency | Closed | H3 | 3 |  | Fails pressure test. Not due to the addition of the filter. | Person_399 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_661 | 2017-11-19 23:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 161.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 23:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 551.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_661 | 2018-03-27 | 2018-03-28 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK012 | Project_087_RISK012 | Threat | Project Contingency | Closed | H3 | 3 |  | Material tear on removal of Protective Insert in the cover | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2018-05-23 | 2023-02-19 23:00 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1733.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK008 | Project_087_RISK008 | Threat | Project Contingency | Closed | H3 | 3 |  | Opening units can cause concequential damage | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-13 23:00 | 2024-05-23 | 50% | 25.3543 | 12.6771 | Avoid | 0% | 25.3543 | 0 | 0 | 4 | -- | FALSE | 2686.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK007 | Project_087_RISK007 | Threat | Project Contingency | Closed | H3 | 3 |  | Updated Filter Design | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to technical performance | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--36 | Project_021_Risk--36 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Schedule update due to Lessons Learned | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 90.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system releases due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 59.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--33 | Project_021_Risk--33 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Trials interrupted by Production Tests/ Embodiment support | Person_174 | 2018-01-21 01:00 | 2018-12-21 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Customer resource to provide timely to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 80% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 90.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_087 | RISK009 | Project_087_RISK009 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer may return/reject units due to workmanplatform issues | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--22 | Project_021_Risk--22 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_061 | 2018-02-20 01:00 | 2019-02-10 01:00 | 50% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 355 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 149.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 40% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | Stable | FALSE | 149.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 179.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK004 | Project_088_RISK004 | Threat | Project Contingency | Closed | H3 | 3 |  | We do not receive the relevant paperwork in order for us to process platformment of production unit... | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--40 | Project_021_Risk--40 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Delay due to late receipt of CoD | Person_470 | 2018-02-20 01:00 | 2018-02-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 0 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_661 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_661 | 2017-09-19 22:00 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 213.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_022 | 2015-07-22 | 2018-10-21 22:00 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1187.9167 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK003 | Project_088_RISK003 | Threat | Project Contingency | Closed | H3 | 3 |  | If any unit requires opened then there is a risk the connector fails. | Person_399 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3652 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK005 | Project_088_RISK005 | Threat | Project Contingency | Closed | H3 | 3 |  | Battery design not fit for purpose. | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-22 22:00 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1155.9167 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK011 | Project_088_RISK011 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Will customer purchase rechargeable battery and charger | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-15 22:00 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1179.9167 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_550 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_661 | 2017-11-19 22:00 | 2018-05-21 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 182.0833 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK002 | Project_088_RISK002 | Threat | Project Contingency | Closed | H3 | 3 |  | Fails pressure test. Not due to the addition of the filter. | Person_399 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_078 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK012 | Project_088_RISK012 | Threat | Project Contingency | Closed | H3 | 3 |  | Material tear on removal of Protective Insert in the cover | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_078 | 2016-02-20 22:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1916.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK470-X | Project_065_RISK470-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The increase in NRE will not be accepted by the customer as there is no supporting quote. | Person_594 | 2018-01-26 22:00 | 2018-11-15 22:00 | 70% | 12.6771 | 8.874 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 293 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-19 22:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 243.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK008 | Project_088_RISK008 | Threat | Project Contingency | Closed | H3 | 3 |  | Opening units can cause concequential damage | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-19 22:00 | 2023-02-19 22:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_661 | 2013-02-19 22:00 | 2023-02-19 22:00 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_594 | 2016-09-07 22:00 | 2020-11-19 22:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK007 | Project_088_RISK007 | Threat | Project Contingency | Closed | H3 | 3 |  | Updated Filter Design | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_661 | 2017-11-19 22:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 161.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 22:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 551.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_661 | 2018-03-27 | 2018-03-28 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK009 | Project_088_RISK009 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer may return/reject units due to workmanplatform issues | Person_002 | 2015-05-27 | 2019-03-16 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1389.0417 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2018-05-23 | 2023-02-19 22:00 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1733.9167 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK028 | Project_079_RISK028 | Threat | Project Contingency | Closed | H3 | 3 |  | Export Applications | Person_002 | 2018-06-08 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 349 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-13 22:00 | 2024-05-23 | 50% | 25.3543 | 12.6771 | Avoid | 0% | 25.3543 | 0 | 0 | 4 | -- | FALSE | 2686.0833 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_563 | 2016-09-03 01:00 | 2018-09-02 01:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_563 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_418 | 2016-09-08 01:00 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 590.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-19 23:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 243.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_563 | 2016-08-20 01:00 | 2019-08-21 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-19 23:00 | 2023-02-19 23:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_661 | 2013-02-19 23:00 | 2023-02-19 23:00 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_594 | 2016-09-07 23:00 | 2020-11-19 23:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Closed | H3 | 3 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2019-02-20 01:00 | 30% | 53.244 | 15.9732 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 950.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_661 | 2017-11-19 23:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 161.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 23:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 551.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_661 | 2018-03-27 | 2018-03-28 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_563 | 2017-05-23 | 2019-10-22 01:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 882.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2018-05-23 | 2023-02-19 23:00 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1733.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK556 | Project_065_RISK556 | Threat | Project Contingency | Closed | H3 | 3 |  | Post Transfer modifications are required | Person_418 | 2013-02-20 01:00 | 2023-03-22 | 40% | 13.9871 | 5.5948 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-13 23:00 | 2024-05-23 | 50% | 25.3543 | 12.6771 | Avoid | 0% | 25.3543 | 0 | 0 | 4 | -- | FALSE | 2686.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK551 | Project_065_RISK551 | Threat | Project Contingency | Closed | H3 | 3 |  | The previously agreed scope from HMI Workshops expands | Person_418 | 2018-07-22 | 2018-12-22 01:00 | 40% | 10.4375 | 4.175 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 153.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_661 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_661 | 2017-09-19 23:00 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 213.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_022 | 2015-07-22 | 2018-10-21 23:00 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1187.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3652 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_078 | 2013-02-19 23:00 | 2023-02-19 23:00 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--36 | Project_021_Risk--36 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Schedule update due to Lessons | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 90.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system ATRs and other Component dependencies due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 59.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-06-22 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--33 | Project_021_Risk--33 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Trials interrupted by Production Tests/ Embodiment support | Person_174 | 2018-01-21 01:00 | 2018-12-21 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Customer resource to provide timely input to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 80% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Worsening | FALSE | 90.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 90.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK564 | Project_065_RISK564 | Threat | Project Contingency | Closed | H3 | 3 |  | Unexpected design changes | Person_418 | 2018-04-20 | 2019-04-23 | 80% | 27.1882 | 21.7506 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 368 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--22 | Project_021_Risk--22 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_061 | 2018-02-20 01:00 | 2019-02-10 01:00 | 50% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 355 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 149.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 149.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--20 | Project_021_Risk--20 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | ERP implementation | Person_061 | 2018-01-21 01:00 | 2018-07-20 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | Stable | TRUE | 179.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Closed | H3 | 3 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-08-20 | 50% | 11.1812 | 5.5906 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 819 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--40 | Project_021_Risk--40 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Delay due to late receipt of CoD | Person_470 | 2018-02-20 01:00 | 2018-02-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 0 |  | 1 | 1 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delays due to technical performacne | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Closed | H3 | 3 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Avoid | 0% | 1.2677 | 0 | 0 | 4 | -- | FALSE | 346 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-06 01:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1507.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_563 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Closed | H3 | 3 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2022-05-23 | 2023-11-20 01:00 | 10% | 1.2677 | 0.12677 | Avoid | 0% | 1.2677 | 0 | 0 | 4 | Improving | FALSE | 546.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK028 | Project_079_RISK028 | Threat | Project Contingency | Closed | H3 | 3 |  | Export Applications | Person_683 | 2018-06-08 | 2019-05-23 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 349 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK511 | Project_065_RISK511 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Software modifications identified during integration | Person_550 | 2017-12-21 01:00 | 2018-07-22 | 20% | 0.66766 | 0.13353 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 212.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-08-20 | 50% | 9.2746 | 4.6373 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1125 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK016-X | Project_065_RISK016-X | Threat | Project Contingency | Closed | H3 | 3 |  | Engineering change drives material rework for System items | Person_563 | 2016-09-02 23:00 | 2018-09-01 23:00 | 50% | 11.8912 | 5.9456 | Transfer | 0% | 11.8912 | 0 | 0 | 4 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 550.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_563 | 2018-03-27 | 2018-06-23 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 88 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK313-X | Project_065_RISK313-X | Threat | Project Contingency | Closed | H3 | 3 |  | Global supply chain issues (sillicon and passive electronic components) drive schedule delays. | Person_563 | 2017-05-23 | 2019-05-24 | 70% | 8.7117 | 6.0982 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 731 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-23 01:00 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1156.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK096 | Project_065_RISK096 | Threat | Management Contingency | Closed | H3 | 3 |  | Requirement/Scope Creep | Person_418 | 2016-09-07 23:00 | 2018-04-22 | 20% | 15.0249 | 3.005 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 591.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-16 01:00 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1180.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_563 | 2018-05-23 | 2023-03-22 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1764 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_563 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_563 | 2017-11-20 01:00 | 2018-08-05 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 257.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK542 | Project_065_RISK542 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Patch updates causes issues with hardening | Person_550 | 2017-10-15 01:00 | 2019-07-28 | 10% | 0.51216 | 0.051216 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 650.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK545 | Project_065_RISK545 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Joystick materials are not acceptable | Person_418 | 2018-04-17 | 2019-02-20 01:00 | 20% | 4.7345 | 0.9469 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 309.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK124-X | Project_065_RISK124-X | Threat | Project Contingency | Closed | H3 | 3 |  | Risk of scrappage to Advance Procured Electronic Components | Person_563 | 2016-08-19 23:00 | 2019-08-20 23:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Closed | H3 | 3 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2019-02-19 23:00 | 30% | 53.244 | 15.9732 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 949.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK540 | Project_065_RISK540 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Sourcing log forwarder takes longer than expected | Person_550 | 2018-07-22 | 2019-07-28 | 50% | 0.1403 | 0.070148 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 371 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK547 | Project_065_RISK547 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Functionality to test dynamic scenarios is not provided by Customer | Person_418 | 2018-05-06 | 2020-03-21 | 90% | 5.632 | 5.0688 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 685 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_563 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK312-X | Project_065_RISK312-X | Threat | Project Contingency | Closed | H3 | 3 |  | Delta risk due to acceleration of procurement and parallel procurement caused by new schedule | Person_563 | 2017-05-23 | 2019-10-21 23:00 | 40% | 4.9796 | 1.9918 | Transfer | 0% | 0.62372 | 0 | 0 | 4 | -- | FALSE | 881.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK556 | Project_065_RISK556 | Threat | Project Contingency | Closed | H3 | 3 |  | Post Transfer modifications are required | Person_418 | 2013-02-19 23:00 | 2023-03-22 | 40% | 13.9871 | 5.5948 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK551 | Project_065_RISK551 | Threat | Project Contingency | Closed | H3 | 3 |  | The previously agreed scope from HMI Workshops expands | Person_418 | 2018-07-22 | 2018-12-21 23:00 | 40% | 10.4375 | 4.175 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 152.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_563 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK305-X | Project_065_RISK305-X | Threat | Project Contingency | Closed | H3 | 3 |  | Equipment being delivered prior to full EMC at System level | Person_563 | 2013-02-19 23:00 | 2023-03-22 | 30% | 1.8762 | 0.56286 | Transfer | 0% | 1.8762 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK564 | Project_065_RISK564 | Threat | Project Contingency | Closed | H3 | 3 |  | Unexpected design changes | Person_418 | 2018-04-20 | 2019-04-23 | 80% | 27.1882 | 21.7506 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 368 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_563 | 2016-02-21 01:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1915.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_563 | 2017-09-20 01:00 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 212.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-14 01:00 | 2024-05-23 | 50% | 34.6086 | 17.3043 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2685.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Closed | H3 | 3 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-08-20 | 50% | 11.1812 | 5.5906 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 819 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2018-04-08 | 2018-12-16 01:00 | 60% | 20.4355 | 12.2613 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 252.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-20 01:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 242.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Closed | H3 | 3 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Avoid | 0% | 1.2677 | 0 | 0 | 4 | -- | FALSE | 346 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK109 | Project_065_RISK109 | Threat | Project Contingency | Closed | H3 | 3 |  | Product line generic components do not satisfy System qualification standards | Person_550 | 2015-07-22 | 2019-09-05 23:00 | 40% | 5.3751 | 2.15 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1506.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_563 | 2015-07-22 | 2018-10-22 01:00 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1188.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK314-X | Project_065_RISK314-X | Threat | Project Contingency | Closed | H3 | 3 |  | Design Changes After Release of Material Orders causes scrap or material rework cost and delays. | Person_563 | 2017-05-23 | 2020-05-23 | 40% | 6.0326 | 2.4131 | Transfer | 0% | 6.0326 | 0 | 0 | 4 | -- | FALSE | 1096 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-20 01:00 | 2023-03-22 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_563 | 2016-09-08 01:00 | 2020-11-20 01:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Closed | H3 | 3 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2022-05-23 | 2023-11-19 23:00 | 10% | 1.2677 | 0.12677 | Avoid | 0% | 1.2677 | 0 | 0 | 4 | Improving | FALSE | 545.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_563 | 2017-11-20 01:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 160.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK307-X | Project_065_RISK307-X | Threat | Project Contingency | Closed | H3 | 3 |  | System does not achieve performance | Person_563 | 2013-02-19 23:00 | 2023-03-22 | 20% | 6.3234 | 1.2647 | Transfer | 0% | 6.3234 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3652 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-036 | Project_077_T-036 | Threat | Project Contingency | Closed | H3 | 3 |  | Risk when not working on SW | Person_092 | 2018-01-21 01:00 | 2020-01-21 01:00 | 50% | 6.7392 | 3.3696 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 730 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-22 22:00 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1155.9167 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK030 | Project_068_RISK030 | Threat | Project Contingency | Closed | H3 | 3 |  | EMC Waiver | Person_086 | 2017-02-20 01:00 | 2018-11-04 01:00 | 20% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 622 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-15 22:00 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1179.9167 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_550 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_661 | 2017-11-19 22:00 | 2018-05-21 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 182.0833 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK036 | Project_068_RISK036 | Threat | Project Contingency | Closed | H3 | 3 |  | Modifications to contributing systems not costed. | Person_394 | 2017-02-20 01:00 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 622 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_078 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK035 | Project_068_RISK035 | Threat | Project Contingency | Closed | H3 | 3 |  | End of tasking | Person_394 | 2018-08-20 | 2018-11-04 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Worsening | FALSE | 76.0417 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_078 | 2016-02-20 22:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1916.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK470-X | Project_065_RISK470-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The increase in NRE will not be accepted by the customer as there is no supporting quote. | Person_594 | 2018-01-26 22:00 | 2018-11-15 22:00 | 70% | 12.6771 | 8.874 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 293 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-19 22:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 243.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-153 | Project_020_Risk-153 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Liquidated Damages maybe reduced | Person_575 | 2003-12-22 01:00 | 2019-05-22 | 0% | 0 | 0 | Exploit | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5629.9583 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-19 22:00 | 2023-02-19 22:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_661 | 2013-02-19 22:00 | 2023-02-19 22:00 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_594 | 2016-09-07 22:00 | 2020-11-19 22:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK003 | Project_099_RISK003 | Threat | Project Contingency | Closed | H3 | 3 |  | New component fails Qualification on Shock/Vibration | Person_002 | 2018-10-21 01:00 | 2020-03-22 | 10% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 517.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_661 | 2017-11-19 22:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 161.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 22:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 551.0833 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_661 | 2018-03-27 | 2018-03-28 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK005 | Project_099_RISK005 | Threat | Project Contingency | Closed | H3 | 3 |  | Functional Test set up - missing equipment | Person_002 | 2018-08-21 | 2020-03-22 | 5% | 2.1523 | 0.10762 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 579 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_078 | 2018-05-23 | 2023-02-19 22:00 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1733.9167 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK013 | Project_099_RISK013 | Threat | Project Contingency | Closed | H3 | 3 |  | PO Issued to non-approved supplier | Person_243 | 2018-06-16 | 2018-09-20 01:00 | 30% | 2.7157 | 0.81471 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 96.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_078 | 2013-02-19 22:00 | 2023-02-19 22:00 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3652 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-13 22:00 | 2024-05-23 | 50% | 25.3543 | 12.6771 | Avoid | 0% | 25.3543 | 0 | 0 | 4 | -- | FALSE | 2686.0833 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_078 | RISK009 | Project_078_RISK009 | Threat | Project Contingency | Closed | H3 | 3 |  | External cable delivered late | Person_627 | 2017-11-20 01:00 | 2021-07-21 | 100% | 0 | 0 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1338.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK037 | Project_068_RISK037 | Threat | Project Contingency | Closed | H3 | 3 |  | Dependency on Supplier input/collaboration. | Person_002 | 2017-02-20 01:00 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Worsening | FALSE | 622 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK038 | Project_068_RISK038 | Threat | Project Contingency | Closed | H3 | 3 |  | Data Analysis | Person_086 | 2017-02-20 01:00 | 2018-11-04 01:00 | 50% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 622 |  | 1 | 0 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--36 | Project_021_Risk--36 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Schedule update due to Lessons | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 90.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system and other Components - dependencies due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 59.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-10-21 01:00 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 212.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--33 | Project_021_Risk--33 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Trials interrupted by Production Tests/ Embodiment support | Person_174 | 2018-01-21 01:00 | 2018-12-21 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Customer resource to provide timely input to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 80% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_207 | 2018-02-20 01:00 | 2018-10-05 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 227 |  | 1 | 0 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-09-20 01:00 | 2018-10-21 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 31 |  | 1 | 0 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK031 | Project_068_RISK031 | Threat | Project Contingency | Closed | H3 | 3 |  | SAP | Person_082 | 2017-02-20 01:00 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Worsening | FALSE | 622 |  | 1 | 1 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--22 | Project_021_Risk--22 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_061 | 2018-02-20 01:00 | 2019-02-10 01:00 | 50% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 355 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 181.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-10-05 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 227 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--40 | Project_021_Risk--40 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Delay due to late receipt of CoD | Person_470 | 2018-02-20 01:00 | 2018-08-22 01:00 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 183 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delays due to technical performacne | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK511 | Project_065_RISK511 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Software modifications identified during integration | Person_550 | 2017-12-21 | 2018-07-22 | 20% | 0.66766 | 0.13353 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 213 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Closed | H3 | 3 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-08-20 | 50% | 9.2746 | 4.6373 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1125 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-002 | Project_029_Risk-002 | Threat | Project Contingency | Closed | H3 | 3 |  | Customer Furnished Equipmnet Acceptance Assets - Availability | Person_585 | 2017-09-02 01:00 | 2020-09-05 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1099 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 551 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_563 | 2018-03-27 | 2018-06-23 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 88 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK114 | Project_066_RISK114 | Threat | Project Contingency | Closed | H3 | 3 |  | Acceptance Documentation | Person_068 | 2019-03-24 | 2019-11-21 01:00 | 50% | 4.4524 | 2.2262 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 242.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-23 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1156 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE002 | Project_067_SE002 | Threat | Project Contingency | Closed | H3 | 3 |  | Resource creating a single point of failure | Person_327 | 2018-06-23 | 2018-08-19 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 57 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Closed | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-16 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1180 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_563 | 2018-05-23 | 2023-03-22 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1764 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_563 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_563 | 2017-11-20 | 2018-08-05 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 258 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK542 | Project_065_RISK542 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Patch updates causes issues with hardening | Person_550 | 2017-10-15 | 2019-07-28 | 10% | 0.51216 | 0.051216 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 651 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK545 | Project_065_RISK545 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Joystick materials are not acceptable | Person_418 | 2018-04-17 | 2019-02-20 | 20% | 4.7345 | 0.9469 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 309 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | P001 | Project_067_P001 | Threat | Project Contingency | Closed | H3 | 3 |  | Export to customer will not be achieved in Project Timescales | Person_328 | 2018-06-13 | 2018-07-20 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | 0 | 4 | Improving | FALSE | 37 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK149 | Project_092_RISK149 | Threat | Project Contingency | Closed | H3 | 3 |  | Timing Change | Person_661 | 2018-02-20 01:00 | 2019-12-12 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 660 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK540 | Project_065_RISK540 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Sourcing log forwarder takes longer than expected | Person_550 | 2018-07-22 | 2019-07-28 | 50% | 0.1403 | 0.070148 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 371 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK547 | Project_065_RISK547 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Functionality to test dynamic scenarios is not provided by Customer | Person_418 | 2018-05-06 | 2020-03-21 | 90% | 5.632 | 5.0688 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 685 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Design stability drives change | Person_563 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_563 | 2013-02-20 | 2023-03-22 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK164 | Project_092_RISK164 | Threat | Project Contingency | Closed | H3 | 3 |  | Technical Debt: Information for internal ICD is unavailable | Person_533 | 2018-09-22 01:00 | 2019-11-25 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 429 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK161 | Project_092_RISK161 | Threat | Project Contingency | Closed | H3 | 3 |  | Technical debt - Absence of low level/ functional requirements | Person_533 | 2018-08-30 01:00 | 2018-09-30 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 31 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK163 | Project_092_RISK163 | Threat | Project Contingency | Closed | H3 | 3 |  | Technical Debt: Scope of obsolescence is bigger than bid estimates | Person_533 | 2019-04-25 | 2019-09-06 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 134.0417 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_563 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK162 | Project_092_RISK162 | Threat | Project Contingency | Closed | H3 | 3 |  | Long lead time for important components and buy parts | Person_533 | 2019-01-17 01:00 | 2020-09-29 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 621 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK008 | Project_095_RISK008 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Extra contract payment | Person_229 | 2018-08-22 01:00 | 2023-08-22 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1826 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Closed | H3 | 3 | Project Management | Material budget is insufficient | Person_563 | 2016-02-21 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1916 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_563 | 2017-09-20 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 213 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Closed | H3 | 3 | System Engineering | Production start before design proving complete | Person_563 | 2013-02-20 | 2023-03-22 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-14 | 2024-05-23 | 50% | 34.6086 | 17.3043 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2686 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK009 | Project_095_RISK009 | Opportunitity | Project Contingency | Closed | H3 | 3 |  | Early payment milestone payment. | Person_229 | 2018-10-22 01:00 | 2019-10-22 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 365 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2018-04-08 | 2018-12-16 | 60% | 20.4355 | 12.2613 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 252 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Closed | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-20 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 243 |  | 1 | 0 | 1
[30 empty] | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
[30 empty] | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_563 | 2015-07-22 | 2018-10-22 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1188 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK024 | Project_079_RISK024 | Threat | Project Contingency | Open | H1 | 1 |  | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 80% | 14.4992 | 11.5993 | -- | 80% | 0 | 0 | H1 | 1 | Worsening | TRUE | 809.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-20 | 2023-03-22 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_563 | 2013-02-20 | 2023-03-22 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_563 | 2013-02-20 | 2023-03-22 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_563 | 2013-02-20 | 2023-03-22 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3682 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_563 | 2016-09-08 | 2020-11-20 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK024 | Project_079_RISK024 | Threat | Project Contingency | Open | H1 | 1 |  | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 50% | 14.4992 | 7.2496 | -- | 80% | 0 | 0 | H1 | 1 | Stable | TRUE | 809.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_563 | 2017-11-20 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 161 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK040 | Project_068_RISK040 | Threat | Project Contingency | Open | H1 | 1 |  | Risk that the relationship with the customer breaks down | Person_407 | 2017-02-20 01:00 | 2018-11-04 01:00 | 70% | 0 | 0 | -- | 70% | 0 | 0 | H1 | 1 | Stable | TRUE | 622 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_563 | 2013-02-20 | 2023-03-22 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3682 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-004 | Project_067_Risk-004 | Threat | Project Contingency | Open | H1 | 1 |  | Creation of Serial Number for formal Software Releases | Person_327 | 2018-07-07 | 2018-10-21 | 100% | 0 | 0 | Reduce | 100% | 0 | 0 | H1 | 1 | Stable | TRUE | 106 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK060 | Project_043_RISK060 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Decrease the cost of obsolescence sweeps | Person_769 | 2014-09-13 | 2018-03-21 | 50% | 0.026348 | 0.013174 | -- | 50% | 0.026348 | 0.013174 | H1 | 1 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 80% | 0.18482 | 0.14786 | Reduce | 80% | 0.18482 | 0.14786 | H1 | 1 | Worsening | TRUE | 914 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 80% | 0.18482 | 0.14786 | Reduce | 80% | 0.18482 | 0.14786 | H1 | 1 | Worsening | TRUE | 914 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 80% | 0.18482 | 0.14786 | Reduce | 80% | 0.18482 | 0.14786 | H1 | 1 | Worsening | TRUE | 914 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | Export License | Person_359 | 2015-02-18 | 2017-08-20 | 80% | 0.18482 | 0.14786 | Reduce | 80% | 0.18482 | 0.14786 | H1 | 1 | Worsening | TRUE | 914 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 80% | 0.18482 | 0.14786 | Reduce | 80% | 0.18482 | 0.14786 | H1 | 1 | Improving | TRUE | 914 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 80% | 0.18482 | 0.14786 | Reduce | 80% | 0.18482 | 0.14786 | H1 | 1 | Improving | TRUE | 914 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | Export License | Person_359 | 2015-02-18 01:00 | 2017-08-20 01:00 | 80% | 0.18482 | 0.14786 | Reduce | 80% | 0.18482 | 0.14786 | H1 | 1 | Improving | TRUE | 914 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK004 | Project_010_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | Export License | Person_359 | 2015-02-18 | 2017-08-20 | 80% | 0.18482 | 0.14786 | Reduce | 80% | 0.18482 | 0.14786 | H1 | 1 | Improving | TRUE | 914 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK028 | Project_058_RISK028 | Threat | Project Contingency | Open | H1 | 1 |  | RFIs | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 60% | 0.39148 | 0.23489 | Reduce | 60% | 0.39148 | 0.23489 | H1 | 1 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK011 | Project_010_RISK011 | Threat | Project Contingency | Open | H1 | 1 |  | Renewing paperwork for Items which are greater than 5 years old | Person_359 | 2018-01-11 17:00 | 2023-01-12 17:00 | 70% | 0.36965 | 0.25875 | Accept | 70% | 0.36965 | 0.25875 | H1 | 1 | -- | TRUE | 1827 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK059 | Project_043_RISK059 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Decrease in the cost of codification not realised | Person_769 | 2014-09-13 | 2018-03-21 | 80% | 0.509 | 0.4072 | -- | 80% | 0.509 | 0.4072 | H1 | 1 | -- | TRUE | 1285 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK122 | Project_065_RISK122 | Threat | Project Contingency | Open | H1 | 1 |  | Incorrect Simulator functionality delivered | Person_550 | 2017-05-23 | 2018-03-21 | 80% | 0.68795 | 0.55036 | Reduce | 60% | 0.68795 | 0.41277 | H1 | 1 | -- | TRUE | 302 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK122 | Project_065_RISK122 | Threat | Project Contingency | Open | H1 | 1 |  | Incorrect Simulator functionality delivered | Person_550 | 2017-05-23 | 2018-03-21 | 80% | 0.68795 | 0.55036 | Reduce | 60% | 0.68795 | 0.41277 | H1 | 1 | -- | TRUE | 302 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK122 | Project_065_RISK122 | Threat | Project Contingency | Open | H1 | 1 |  | Incorrect Simulator functionality delivered | Person_550 | 2017-05-23 | 2018-03-21 | 80% | 0.68795 | 0.55036 | Reduce | 60% | 0.68795 | 0.41277 | H1 | 1 | -- | TRUE | 302 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK122 | Project_065_RISK122 | Threat | Project Contingency | Open | H1 | 1 |  | Incorrect Simulator functionality delivered | Person_550 | 2017-05-23 | 2018-03-21 | 80% | 0.68795 | 0.55036 | Reduce | 60% | 0.68795 | 0.41277 | H1 | 1 | -- | TRUE | 302 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK122 | Project_065_RISK122 | Threat | Project Contingency | Open | H1 | 1 |  | Incorrect Simulator functionality delivered | Person_550 | 2017-05-23 | 2018-03-21 | 80% | 0.68795 | 0.55036 | Reduce | 60% | 0.68795 | 0.41277 | H1 | 1 | -- | TRUE | 302 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK122 | Project_065_RISK122 | Threat | Project Contingency | Open | H1 | 1 |  | Incorrect Simulator functionality delivered | Person_550 | 2017-05-23 | 2018-03-21 | 80% | 0.68795 | 0.55036 | Reduce | 60% | 0.68795 | 0.41277 | H1 | 1 | -- | TRUE | 302 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK122 | Project_065_RISK122 | Threat | Project Contingency | Open | H1 | 1 |  | Incorrect Simulator functionality delivered | Person_550 | 2017-05-23 | 2018-03-21 | 80% | 0.68795 | 0.55036 | Reduce | 60% | 0.68795 | 0.41277 | H1 | 1 | -- | TRUE | 302 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--43 | Project_021_Risk--43 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Agreed contractual Position | Person_061 | 2018-07-22 | 2019-02-20 01:00 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 213.0417 |  | 1 | 1 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--36 | Project_021_Risk--36 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Schedule update due to Lessons | Person_174 | 2018-02-20 01:00 | 2018-05-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 90.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system and other Components - dependencies due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2018-03-22 | 40% | 0 | 0 | Accept | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 59.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK122 | Project_065_RISK122 | Threat | Project Contingency | Open | H1 | 1 |  | Incorrect Simulator functionality delivered | Person_550 | 2017-05-23 | 2018-03-21 | 80% | 0.68795 | 0.55036 | Reduce | 60% | 0.68795 | 0.41277 | H1 | 1 | -- | TRUE | 302 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to poor weather | Person_615 | 2018-03-23 | 2018-10-21 01:00 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 212.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--33 | Project_021_Risk--33 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Trials interrupted by Production Tests/ Embodiment support | Person_174 | 2018-01-21 01:00 | 2018-12-21 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 334 |  | 1 | 0 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Customer resource to provide timely input to Acceptance and Closure activities | Person_766 | 2018-10-22 01:00 | 2019-04-23 | 80% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_207 | 2018-02-20 01:00 | 2018-10-05 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 227 |  | 1 | 0 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_615 | 2018-09-20 01:00 | 2018-10-21 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 31 |  | 1 | 0 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 652 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--22 | Project_021_Risk--22 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_061 | 2018-02-20 01:00 | 2019-02-10 01:00 | 50% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 355 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2018-08-21 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 181.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-10-05 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 227 |  | 1 | 0 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--40 | Project_021_Risk--40 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Delay due to late receipt of CoD | Person_470 | 2018-02-20 01:00 | 2018-08-22 01:00 | 50% | 0 | 0 | Avoid | 40% | 0 | 0 | H2 | 2 | -- | TRUE | 183 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delays due to technical performacne | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 365 |  | 1 | 0 | 1
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--43 | Project_021_Risk--43 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Agreed contractual Position | Person_061 | 2018-07-22 | 2019-02-20 01:00 | 30% | 0 | 0 | Reduce | 15% | 0 | 0 | H3 | 3 | -- | FALSE | 213.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 652 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 652 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1002 | Project_091_RISK1002 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Delay to Integration platform Deliveries | Person_557 | 2018-08-22 01:00 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--47 | Project_021_Risk--47 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system and other Component dependencies due to supply chain dependencies | Person_615 | 2018-08-09 | 2018-12-21 01:00 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 134.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--46 | Project_021_Risk--46 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-08-08 | 2018-11-05 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 89.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK511 | Project_065_RISK511 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software modifications identified during integration | Person_550 | 2017-12-21 01:00 | 2018-07-22 | 20% | 0.66766 | 0.13353 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 212.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-08-20 | 50% | 9.2746 | 4.6373 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1125 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 652 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-19 01:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 550.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_563 | 2018-03-27 | 2018-06-23 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 88 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 652 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-23 01:00 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1156.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 652 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-16 01:00 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1180.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_563 | 2018-05-23 | 2023-03-22 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1764 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_563 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_563 | 2017-11-20 01:00 | 2018-08-05 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 257.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK542 | Project_065_RISK542 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Patch updates causes issues with hardening | Person_550 | 2017-10-15 01:00 | 2019-07-28 | 10% | 0.51216 | 0.051216 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 650.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK545 | Project_065_RISK545 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Joystick materials are not acceptable | Person_418 | 2018-04-17 | 2019-02-20 01:00 | 20% | 4.7345 | 0.9469 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 309.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 652 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2016-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 652 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK540 | Project_065_RISK540 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Sourcing log forwarder takes longer than expected | Person_550 | 2018-07-22 | 2019-07-28 | 50% | 0.1403 | 0.070148 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 371 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK547 | Project_065_RISK547 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Functionality to test dynamic scenarios is not provided by Customer | Person_418 | 2018-05-06 | 2020-03-21 | 90% | 5.632 | 5.0688 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 685 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Design stability drives change | Person_563 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK002 | Project_010_RISK002 | Threat | Project Contingency | Open | H1 | 1 |  | Positioning error, normal versus specific modes | Person_552 | 2014-07-10 | 2018-04-22 | 80% | 1.1089 | 0.88715 | Accept | 60% | 0.73929 | 0.44357 | H1 | 1 | Stable | TRUE | 1382 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-074 | Project_007_R-074 | Threat | Project Contingency | Open | H1 | 1 |  | System INtegration Resources | Person_386 | 2013-12-03 19:00 | 2016-05-15 | 95% | 0.51354 | 0.48787 | Reduce | 95% | 0.51354 | 0.48787 | H1 | 1 | Stable | TRUE | 893.2083 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK049 | Project_031_RISK049 | Threat | Project Contingency | Open | H1 | 1 |  | Impact of global issues. | Person_601 | 2014-08-06 | 2019-08-20 19:00 | 20% | 0.84608 | 0.16922 | -- | 60% | 0.84608 | 0.50765 | H1 | 1 | -- | TRUE | 1840.7917 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_563 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK049 | Project_031_RISK049 | Threat | Project Contingency | Open | H1 | 1 |  | Impact of global issues. | Person_601 | 2014-08-06 | 2019-08-20 18:00 | 20% | 0.84608 | 0.16922 | -- | 60% | 0.84608 | 0.50765 | H1 | 1 | -- | TRUE | 1840.75 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK049 | Project_031_RISK049 | Threat | Project Contingency | Open | H1 | 1 |  | Impact of global issues. | Person_601 | 2014-08-06 | 2019-08-20 17:00 | 20% | 0.84608 | 0.16922 | -- | 60% | 0.84608 | 0.50765 | H1 | 1 | -- | TRUE | 1840.7083 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Open | H3 | 3 | Project Management | Material budget is insufficient | Person_563 | 2016-02-21 01:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1915.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_563 | 2017-09-20 01:00 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 212.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Production start before design proving complete | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-14 01:00 | 2024-05-23 | 50% | 34.6086 | 17.3043 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2685.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK049 | Project_031_RISK049 | Threat | Project Contingency | Open | H1 | 1 |  | Impact of global issues. | Person_601 | 2014-08-06 | 2019-08-20 17:00 | 20% | 0.84608 | 0.16922 | -- | 60% | 0.84608 | 0.50765 | H1 | 1 | -- | TRUE | 1840.7083 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2018-04-08 | 2018-12-16 01:00 | 60% | 20.4355 | 12.2613 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 252.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-20 01:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 242.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK049 | Project_031_RISK049 | Threat | Project Contingency | Open | H1 | 1 |  | Impact of global issues. | Person_601 | 2014-08-06 | 2019-08-20 17:00 | 20% | 0.84608 | 0.16922 | -- | 60% | 0.84608 | 0.50765 | H1 | 1 | -- | TRUE | 1840.7083 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK049 | Project_031_RISK049 | Threat | Project Contingency | Open | H1 | 1 |  | Impact of global issues. | Person_601 | 2014-08-06 | 2019-08-20 17:00 | 20% | 0.84608 | 0.16922 | -- | 60% | 0.84608 | 0.50765 | H1 | 1 | -- | TRUE | 1840.7083 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_563 | 2015-07-22 | 2018-10-22 01:00 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1188.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK049 | Project_031_RISK049 | Threat | Project Contingency | Open | H1 | 1 |  | Impact of global issues. | Person_601 | 2014-08-06 | 2019-08-20 16:00 | 20% | 0.84608 | 0.16922 | -- | 60% | 0.84608 | 0.50765 | H1 | 1 | -- | TRUE | 1840.6667 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-20 01:00 | 2023-03-22 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3681.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_563 | 2016-09-08 01:00 | 2020-11-20 01:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK049 | Project_031_RISK049 | Threat | Project Contingency | Open | H1 | 1 |  | Impact of global issues. | Person_601 | 2014-08-06 | 2019-08-20 16:00 | 20% | 0.84608 | 0.16922 | -- | 60% | 0.84608 | 0.50765 | H1 | 1 | -- | TRUE | 1840.6667 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_563 | 2017-11-20 01:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 160.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H1 | 1 |  | Component Repair costs | Person_359 | 2015-04-04 | 2016-04-12 | 70% | 0.84985 | 0.5949 | -- | 70% | 0.84985 | 0.5949 | H1 | 1 | -- | TRUE | 374 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_563 | 2013-02-20 01:00 | 2023-03-22 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3681.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | RN-001 | Project_009_RN-001 | Threat | Project Contingency | Open | H1 | 1 |  | Customer Furnished Equipment Failures | Person_459 | 2016-02-21 01:00 | 2016-09-19 01:00 | 65.6% | 1.0376 | 0.68066 | Reduce | 65.6% | 1.0376 | 0.68066 | H1 | 1 | -- | TRUE | 211 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK020 | Project_075_RISK020 | Threat | Project Contingency | Open | H1 | 1 |  | Resonating performance | Person_003 | 2017-02-19 01:00 | 2018-09-20 01:00 | 80% | 0.98433 | 0.78746 | Accept | 80% | 0.98433 | 0.78746 | H1 | 1 | -- | TRUE | 578 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK020 | Project_075_RISK020 | Threat | Project Contingency | Open | H1 | 1 |  | Resonating performance | Person_003 | 2017-02-19 01:00 | 2018-11-20 01:00 | 80% | 0.98433 | 0.78746 | Accept | 80% | 0.98433 | 0.78746 | H1 | 1 | -- | TRUE | 639 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK511 | Project_065_RISK511 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software modifications identified during integration | Person_550 | 2017-12-20 23:00 | 2018-07-22 | 20% | 0.66766 | 0.13353 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 213.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-08-20 | 50% | 9.2746 | 4.6373 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1125 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK020 | Project_075_RISK020 | Threat | Project Contingency | Open | H1 | 1 |  | Resonating performance | Person_003 | 2017-02-19 01:00 | 2018-11-20 01:00 | 80% | 0.98433 | 0.78746 | Accept | 80% | 0.98433 | 0.78746 | H1 | 1 | -- | TRUE | 639 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK008 | Project_065_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Selection Process | Person_379 | 2017-10-18 23:00 | 2019-04-23 | 40% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 551.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK472-X | Project_065_RISK472-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Components are not received by CDR. | Person_563 | 2018-03-27 | 2018-06-23 | 20% | 1.5327 | 0.30653 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 88 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK020 | Project_075_RISK020 | Threat | Project Contingency | Open | H1 | 1 |  | Resonating performance | Person_003 | 2017-02-19 01:00 | 2018-11-20 01:00 | 80% | 0.98433 | 0.78746 | Accept | 80% | 0.98433 | 0.78746 | H1 | 1 | -- | TRUE | 639 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK094 | Project_065_RISK094 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Hardening Delay | Person_550 | 2015-06-24 | 2018-08-22 23:00 | 10% | 0.34421 | 0.034421 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1155.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK020 | Project_075_RISK020 | Threat | Project Contingency | Open | H1 | 1 |  | Resonating performance | Person_003 | 2017-02-19 01:00 | 2018-11-20 01:00 | 80% | 0.98433 | 0.78746 | Accept | 80% | 0.98433 | 0.78746 | H1 | 1 | -- | TRUE | 639 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK092 | Project_065_RISK092 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Inability of propsed HW solutions to meet target | Person_732 | 2015-06-24 | 2018-09-15 23:00 | 10% | 1.3019 | 0.13019 | Avoid | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1179.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK170-X | Project_065_RISK170-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_563 | 2018-05-23 | 2023-03-22 | 45% | 25.7768 | 11.5996 | Transfer | 0% | 25.7768 | 0 | 0 | 4 | Stable | FALSE | 1764 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK488-X | Project_065_RISK488-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | IP addresses from Customer are not provided in time to allow SW to hardcode these during development. | Person_563 | 2017-07-14 | 2018-08-04 | 50% | 0.69795 | 0.34898 | Transfer | 0% | 0.52346 | 0 | 0 | 4 | -- | FALSE | 386 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK480-X | Project_065_RISK480-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Common Infrastructure ICD prior to SRR/SFR | Person_563 | 2017-11-19 23:00 | 2018-08-05 | 60% | 2.0939 | 1.2563 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 258.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK542 | Project_065_RISK542 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Patch updates causes issues with hardening | Person_550 | 2017-10-14 23:00 | 2019-07-28 | 10% | 0.51216 | 0.051216 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 651.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK545 | Project_065_RISK545 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Joystick materials are not acceptable | Person_418 | 2018-04-17 | 2019-02-19 23:00 | 20% | 4.7345 | 0.9469 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 308.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | RISK017 | Project_093_RISK017 | Threat | Project Contingency | Open | H1 | 1 |  | Integration - Tracking | Person_342 | 2018-09-30 01:00 | 2019-05-23 | 90% | 0.91777 | 0.82599 | Accept | 90% | 0.91777 | 0.82599 | H1 | 1 | -- | TRUE | 234.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | RISK022 | Project_093_RISK022 | Threat | Project Contingency | Open | H1 | 1 |  | Insufficient Description of current research code - Object Classification | Person_342 | 2018-09-30 01:00 | 2019-05-23 | 70% | 1.3669 | 0.95682 | Accept | 70% | 1.3669 | 0.95682 | H1 | 1 | -- | TRUE | 234.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK540 | Project_065_RISK540 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Sourcing log forwarder takes longer than expected | Person_550 | 2018-07-22 | 2019-07-28 | 50% | 0.1403 | 0.070148 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 371 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK547 | Project_065_RISK547 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Functionality to test dynamic scenarios is not provided by Customer | Person_418 | 2018-05-06 | 2020-03-21 | 90% | 5.632 | 5.0688 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 685 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK032-X | Project_065_RISK032-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Design stability drives change | Person_563 | 2015-05-24 | 2018-05-21 | 55% | 2.7045 | 1.4874 | Transfer | 0% | 2.7045 | 0 | 0 | 4 | Stable | FALSE | 1093 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK498-X | Project_065_RISK498-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Supporting documentation | Person_563 | 2013-02-19 23:00 | 2023-03-22 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK109 | Project_066_RISK109 | Threat | Project Contingency | Open | H1 | 1 |  | Integrate HCI | Person_507 | 2019-02-28 01:00 | 2019-06-24 | 80% | 1.2059 | 0.96468 | Accept | 80% | 1.2059 | 0.96468 | H1 | 1 | -- | TRUE | 115.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | RISK021 | Project_093_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Resource diversion | Person_217 | 2018-09-30 01:00 | 2019-05-23 | 60% | 1.8746 | 1.1248 | Accept | 60% | 1.8746 | 1.1248 | H1 | 1 | -- | TRUE | 234.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK048 | Project_075_RISK048 | Threat | Project Contingency | Open | H1 | 1 |  | Secondary effects appearing while operating | Person_002 | 2018-04-22 | 2019-01-20 01:00 | 50% | 2.8264 | 1.4132 | Accept | 50% | 2.8264 | 1.4132 | H1 | 1 | -- | TRUE | 273.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK483-X | Project_065_RISK483-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Late Delivery of the simulator equipment requires further updates (non-patching related). | Person_563 | 2018-04-22 | 2018-05-21 | 40% | 18.392 | 7.3568 | Transfer | 0% | 10.9365 | 0 | 0 | 4 | -- | FALSE | 29 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK338 | Project_034_RISK338 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2014-12-21 18:00 | 2015-04-23 | 70% | 2.1524 | 1.5066 | Exploit | 70% | 2.1524 | 1.5066 | H1 | 1 | -- | TRUE | 122.25 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK338 | Project_034_RISK338 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2014-12-21 18:00 | 2015-04-23 | 70% | 2.1524 | 1.5066 | Exploit | 70% | 2.1524 | 1.5066 | H1 | 1 | -- | TRUE | 122.25 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK037-X | Project_065_RISK037-X | Threat | Project Contingency | Open | H3 | 3 | Project Management | Material budget is insufficient | Person_563 | 2016-02-20 23:00 | 2021-05-21 | 50% | 15.314 | 7.657 | Transfer | 0% | 15.314 | 0 | 0 | 4 | -- | FALSE | 1916.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK474-X | Project_065_RISK474-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Immaturity of release v4 leads to a longer integration period. | Person_563 | 2017-09-19 23:00 | 2018-04-21 | 80% | 4.9045 | 3.9236 | Transfer | 0% | 2.4523 | 0 | 0 | 4 | -- | FALSE | 213.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK169-X | Project_065_RISK169-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Production start before design proving complete | Person_563 | 2013-02-19 23:00 | 2023-03-22 | 50% | 10.1417 | 5.0709 | Transfer | 0% | 10.1417 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK455 | Project_065_RISK455 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Console Win10 OS goes obsolete due to schedule change requiring move to Win11. | Person_550 | 2017-01-13 23:00 | 2024-05-23 | 50% | 34.6086 | 17.3043 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 2686.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK338 | Project_034_RISK338 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2014-12-21 18:00 | 2015-04-23 | 70% | 2.1524 | 1.5066 | Exploit | 70% | 2.1524 | 1.5066 | H1 | 1 | -- | TRUE | 122.25 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2018-04-08 | 2018-12-15 23:00 | 60% | 20.4355 | 12.2613 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 251.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK468 | Project_065_RISK468 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The carcass no longer meets compliance after mods | Person_661 | 2017-09-19 23:00 | 2018-05-21 | 20% | 0.96204 | 0.19241 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 243.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK338 | Project_034_RISK338 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2014-12-21 18:00 | 2015-04-23 | 70% | 2.1524 | 1.5066 | Exploit | 70% | 2.1524 | 1.5066 | H1 | 1 | -- | TRUE | 122.25 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK106 | Project_065_RISK106 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Component Download Development | Person_550 | 2017-05-23 | 2018-04-22 | 20% | 5.6565 | 1.1313 | Avoid | 5% | 0 | 0 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK338 | Project_034_RISK338 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2014-12-21 18:00 | 2015-04-23 | 70% | 2.1524 | 1.5066 | Exploit | 70% | 2.1524 | 1.5066 | H1 | 1 | -- | TRUE | 122.25 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK011-X | Project_065_RISK011-X | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Obsolescence of critical console hardware components | Person_563 | 2015-07-22 | 2018-10-21 23:00 | 65% | 3.6814 | 2.3929 | Transfer | 0% | 1.4705 | 0 | 0 | 4 | -- | FALSE | 1187.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | RISK016 | Project_093_RISK016 | Threat | Project Contingency | Open | H1 | 1 |  | Major Requirement | Person_342 | 2018-09-30 01:00 | 2019-05-23 | 90% | 1.7574 | 1.5817 | Accept | 90% | 1.7574 | 1.5817 | H1 | 1 | -- | TRUE | 234.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK358 | Project_065_RISK358 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Lack of Data Information Documentss | Person_038 | 2013-02-19 23:00 | 2023-03-22 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK341-X | Project_065_RISK341-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | System ICD for signal & power interfaces | Person_563 | 2013-02-19 23:00 | 2023-03-22 | 15% | 2.5354 | 0.38031 | Transfer | 0% | 2.5354 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK466-X | Project_065_RISK466-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The encryption tool is not received in time to support software delivery to integration | Person_563 | 2013-02-19 23:00 | 2023-03-22 | 50% | 0.42443 | 0.21222 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK171-X | Project_065_RISK171-X | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Design / Build Issues on early Production Equipment | Person_563 | 2013-02-19 23:00 | 2023-03-22 | 40% | 20.706 | 8.2824 | Transfer | 0% | 20.706 | 0 | 0 | 4 | Stable | FALSE | 3682.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK027-X | Project_065_RISK027-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Level of rework required as a result of procurement/build prior to conclusion of Acceptance. | Person_563 | 2016-09-07 23:00 | 2020-11-19 23:00 | 60% | 18.8332 | 11.2999 | Transfer | 0% | 12.1193 | 0 | 0 | 4 | -- | FALSE | 1534 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK023 | Project_058_RISK023 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier component Delay | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 60% | 2.9361 | 1.7616 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK481-X | Project_065_RISK481-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | An agreement is not reached on the Customer Service definition prior to SRR/SFR | Person_563 | 2017-11-19 23:00 | 2018-04-30 | 60% | 1.7508 | 1.0505 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 161.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK023 | Project_058_RISK023 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier component Delay | Person_511 | 2018-01-21 01:00 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 274 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK462-X | Project_065_RISK462-X | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Late Arrival of audit from Customer | Person_563 | 2013-02-19 23:00 | 2023-03-22 | 50% | 25.1514 | 12.5757 | Transfer | 0% | 25.1514 | 0 | 0 | 4 | -- | FALSE | 3682.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--43 | Project_021_Risk--43 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Agreed contractual Position | Person_061 | 2018-07-22 | 2019-02-20 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 213.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--16 | Project_021_Risk--16 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of weather | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--15 | Project_021_Risk--15 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to lack of personnel resource | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--14 | Project_021_Risk--14 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trials delay due to late Trials Approval | Person_080 | 2018-02-20 01:00 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--35 | Project_021_Risk--35 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Delay to sub-system and other Components - dependencies due to supply chain dependencies | Person_615 | 2018-01-21 01:00 | 2019-03-23 | 40% | 0 | 0 | Accept | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 425.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--34 | Project_021_Risk--34 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to poor weather | Person_207 | 2018-03-23 | 2018-10-21 01:00 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 212.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--33 | Project_021_Risk--33 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Trials interrupted by Production Tests/ Embodiment support | Person_174 | 2018-01-21 01:00 | 2018-12-21 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 334 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--32 | Project_021_Risk--32 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Customer resource to provide timely input to Acceptance and Closure activities | Person_615 | 2018-10-22 01:00 | 2019-04-23 | 80% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--05 | Project_021_Risk--05 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification delays | Person_207 | 2018-02-20 01:00 | 2018-10-05 01:00 | 40% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 227 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--04 | Project_021_Risk--04 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Final Qual test report delayed due to insufficient supply chain resource | Person_207 | 2018-09-20 01:00 | 2018-10-21 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 31 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--25 | Project_021_Risk--25 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of supporting resource | Person_080 | 2018-06-22 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--24 | Project_021_Risk--24 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to lack of equipment | Person_080 | 2018-06-22 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 243.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--21 | Project_021_Risk--21 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Documentation Submission to support sus-system | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--09 | Project_021_Risk--09 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Component Submission delay due to Suitably Qualified and experienced staff availability Resource availability | Person_470 | 2018-02-20 01:00 | 2019-04-22 | 60% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 425.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--08 | Project_021_Risk--08 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-02-20 01:00 | 2018-11-20 01:00 | 70% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--17 | Project_021_Risk--17 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delays due to technical performacne | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--39 | Project_021_Risk--39 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay to completion of product upgrade | Person_080 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 365 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--46 | Project_021_Risk--46 | Threat | Project Contingency | Open | H2 | 2 | Customers | Component Approval delayed due to issues with Customer review & signature process | Person_470 | 2018-08-08 | 2018-11-05 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 89.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R002 | Project_044_Risk-R002 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Parts changing post ordering | Person_310 | 2018-01-20 01:00 | 2019-05-22 | 90% | 0 | 0 | Accept | 90% | 0 | 0 | H1 | 1 | Stable | TRUE | 486.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1002 | Project_091_RISK1002 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Delay to Integration platform Deliveries | Person_557 | 2018-09-21 01:00 | 2018-11-20 01:00 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H1 | 1 | -- | TRUE | 60 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | Risk244 | Project_049_Risk244 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Supplier Quality | Person_526 | 2018-03-23 | 2020-02-06 01:00 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 685.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | Risk243 | Project_049_Risk243 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Supplier Dependency Timescales | Person_218 | 2018-03-23 | 2019-05-23 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 426 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | Risk306 | Project_049_Risk306 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Reduction of two long Tasks driving the Critical Path | Person_218 | 2018-03-23 | 2018-06-22 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 91 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK232 | Project_049_RISK232 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Construction of New product System | Person_218 | 2017-08-23 01:00 | 2021-12-20 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 1580 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1011 | Project_091_RISK1011 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier stud nut rework takes too long | Person_261 | 2018-09-27 01:00 | 2018-10-28 01:00 | 70% | 0 | 0 | Reduce | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 31 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK023 | Project_058_RISK023 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier component Delay | Person_511 | 2018-01-21 01:00 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 274 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-030 | Project_077_T-030 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Rig No longer available. | Person_203 | 2018-10-22 01:00 | 2020-02-21 01:00 | 50% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 487 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK022 | Project_058_RISK022 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier Delay | Person_511 | 2018-03-22 | 2019-05-23 | 60% | 2.9361 | 1.7616 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 427 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_072 | RISK111 | Project_072_RISK111 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Multiplex Qualification Build Delay | Person_285 | 2018-09-01 01:00 | 2019-06-22 | 60% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Improving | FALSE | 293.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK015 | Project_068_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Equipment failure | Person_082 | 2017-07-21 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 471.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK017 | Project_068_RISK017 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Standard waiver | Person_082 | 2018-08-22 01:00 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 74 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK021 | Project_068_RISK021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | New Standard Messages | Person_514 | 2017-02-20 01:00 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Improving | FALSE | 622 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK013 | Project_068_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Platform Modifications (Including Power) | Person_407 | 2017-07-21 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 471.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK002 | Project_068_RISK002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Supplier Schedule | Person_407 | 2017-07-21 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Worsening | FALSE | 471.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK012 | Project_068_RISK012 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final Teast and Acceptance Approvals | Person_407 | 2017-02-20 01:00 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 622 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK023 | Project_058_RISK023 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier component Delay | Person_511 | 2018-01-21 01:00 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 274 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK008 | Project_068_RISK008 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Sub-system Suitably Qualified and experienced staff availability | Person_407 | 2017-07-21 | 2018-11-04 01:00 | 0% | 0 | 0 | Transfer | 0% | 0 | 0 | H1 | 1 | Worsening | TRUE | 471.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_068 | RISK007 | Project_068_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Equipment Scheduling | Person_407 | 2017-07-21 | 2018-11-04 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 471.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK022 | Project_058_RISK022 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier Delay | Person_511 | 2018-03-22 | 2019-05-23 | 60% | 2.9361 | 1.7616 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 427 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK023 | Project_058_RISK023 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier component Delay | Person_511 | 2018-01-21 01:00 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 274 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-001 | Project_098_Risk-001 | Threat | Project Contingency | Open | H3 | 3 | Customers | Support of platforms beyond OSD | Person_360 | 2018-05-24 | 2021-05-15 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1087 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-002 | Project_098_Risk-002 | Threat | Project Contingency | Open | H1 | 1 | Customers | Support of platforms beyond OSD (not external subsystem) | Person_360 | 2018-05-24 | 2021-05-15 | 0% | 0 | 0 | Reduce | 0% | 0 | 0 | H1 | 1 | -- | TRUE | 1087 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-004 | Project_098_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Level of Obsolescence | Person_360 | 2019-05-25 | 2027-05-16 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 2913 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-008 | Project_098_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Efficiency Targets Not realised | Person_360 | 2018-05-24 | 2027-05-23 | 30% | 0 | 0 | Accept | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 3286 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-005 | Project_098_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | POOR SUPPLIER QUALITY | Person_660 | 2018-05-23 | 2033-05-22 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 5478 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-004 | Project_098_Risk-004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | PROCUREMENT WORKBENCH INADEQUACIES | Person_660 | 2018-05-23 | 2033-05-22 | 30% | 1.4207 | 0.42621 | Reduce | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 5478 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-003 | Project_098_Risk-003 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | External Sub-system CAPACITY | Person_660 | 2018-05-23 | 2033-05-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H1 | 1 | Stable | TRUE | 5478 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK091 | Project_076_RISK091 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Peer review teams unavailable for the required project timescales | Person_484 | 2018-09-21 01:00 | 2019-05-16 | 30% | 0 | 0 | Accept | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 236.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK022 | Project_058_RISK022 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier Delay | Person_511 | 2018-03-22 | 2019-05-23 | 60% | 2.9361 | 1.7616 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 427 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK023 | Project_058_RISK023 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier component Delay | Person_511 | 2018-01-21 01:00 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 274 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK023 | Project_058_RISK023 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier component Delay | Person_511 | 2018-01-21 01:00 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 274 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK023 | Project_058_RISK023 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier component Delay | Person_511 | 2018-01-21 01:00 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 60% | 2.9361 | 1.7616 | H1 | 1 | -- | TRUE | 274 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK002 | Project_099_RISK002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment used by supplier is different to our recommended equipment | Person_002 | 2018-12-20 01:00 | 2020-03-22 | 10% | 0.67893 | 0.067893 | Avoid | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 457.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK284 | Project_024_RISK284 | Threat | Project Contingency | Open | H1 | 1 |  | Gaps in SSS Flowdown in SW | Person_290 | 2016-08-05 | 2018-03-22 | 40% | 4.6739 | 1.8696 | Accept | 40% | 4.6739 | 1.8696 | H1 | 1 | -- | TRUE | 594 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK012 | Project_099_RISK012 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Legecy Components not acceptable | Person_366 | 2017-09-21 01:00 | 2018-08-19 | 15% | 14.8888 | 2.2333 | Avoid | 0% | 14.8888 | 0 | 0 | 4 | -- | FALSE | 331.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK284 | Project_024_RISK284 | Threat | Project Contingency | Open | H1 | 1 |  | Gaps in SSS Flowdown in SW | Person_290 | 2016-08-05 | 2018-03-22 | 40% | 4.6739 | 1.8696 | Accept | 40% | 4.6739 | 1.8696 | H1 | 1 | -- | TRUE | 594 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK284 | Project_024_RISK284 | Threat | Project Contingency | Open | H1 | 1 |  | Gaps in SSS Flowdown in SW | Person_290 | 2016-08-05 | 2018-03-22 | 40% | 4.6739 | 1.8696 | Accept | 40% | 4.6739 | 1.8696 | H1 | 1 | -- | TRUE | 594 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK025 | Project_058_RISK025 | Threat | Project Contingency | Open | H1 | 1 |  | Material / Supply chain delays (generic) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 70% | 2.9361 | 2.0552 | Reduce | 70% | 2.9361 | 2.0552 | H1 | 1 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--110 | Project_100_Risk--110 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Tech Pubs & Resources | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--101 | Project_100_Risk--101 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Resourcing - No financial Impact. | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | Worsening | FALSE | 1094 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK021 | Project_058_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Sub System Supplier Delay | Person_511 | 2018-03-22 | 2018-06-23 | 80% | 2.9361 | 2.3489 | Reduce | 70% | 2.9361 | 2.0552 | H1 | 1 | -- | TRUE | 93 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK021 | Project_058_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Sub System Supplier Delay | Person_511 | 2018-03-22 | 2018-06-23 | 80% | 2.9361 | 2.3489 | Reduce | 70% | 2.9361 | 2.0552 | H1 | 1 | -- | TRUE | 93 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK021 | Project_058_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Sub System Supplier Delay | Person_511 | 2018-03-22 | 2018-06-23 | 80% | 2.9361 | 2.3489 | Reduce | 70% | 2.9361 | 2.0552 | H1 | 1 | -- | TRUE | 93 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK021 | Project_058_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Sub System Supplier Delay | Person_511 | 2018-03-22 | 2018-06-23 | 80% | 2.9361 | 2.3489 | Reduce | 70% | 2.9361 | 2.0552 | H1 | 1 | -- | TRUE | 93 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK021 | Project_058_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Sub System Supplier Delay | Person_511 | 2018-03-22 | 2019-05-23 | 80% | 2.9361 | 2.3489 | Reduce | 70% | 2.9361 | 2.0552 | H1 | 1 | -- | TRUE | 427 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK010 | Project_073_RISK010 | Threat | Project Contingency | Open | H1 | 1 |  | Reliability of module | Person_493 | 2018-10-22 01:00 | 2019-08-01 | 80% | 7.5242 | 6.0193 | Reduce | 50% | 4.1801 | 2.0901 | H1 | 1 | -- | TRUE | 282.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK021 | Project_058_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Sub System Supplier Delay | Person_511 | 2018-03-22 | 2019-05-23 | 80% | 2.9361 | 2.3489 | Reduce | 75% | 2.9361 | 2.2021 | H1 | 1 | -- | TRUE | 427 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK021 | Project_058_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Sub System Supplier Delay | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 80% | 2.9361 | 2.3489 | H1 | 1 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-005 | Project_096_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Availability of test site and Customer Furnished Equipment dependencies | Person_639 | 2019-03-02 01:00 | 2019-04-23 | 10% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 51.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-001 | Project_096_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Suitably Qualified and experienced staff availability Resource availability | Person_083 | 2018-05-23 | 2018-12-22 01:00 | 30% | 0 | 0 | Reduce | 20% | 0 | 0 | H2 | 2 | Improving | TRUE | 213.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK024 | Project_058_RISK024 | Threat | Project Contingency | Open | H1 | 1 |  | Connector Delay | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 80% | 2.9361 | 2.3489 | H1 | 1 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-100 | Project_029_Risk-100 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Non-Functional Customer Furnished Equipmnet supplied to Customer for Compatibility Trials | Person_585 | 2017-09-02 01:00 | 2020-04-26 | 10% | 6.4168 | 0.64168 | Transfer | 10% | 0 | 0 | H2 | 2 | Stable | TRUE | 966.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK037 | Project_029_Risk-RISK037 | Opportunitity | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Reduction of tests and demonstrations for platform | Person_102 | 2019-12-22 01:00 | 2021-07-20 | 70% | 1.2834 | 0.89835 | -- | 0% | 0 | 0 | 0 | 4 | Stable | FALSE | 575.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-092 | Project_029_Risk-092 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Penetration testing (of our SW) at the System level on product platform - performed by 3rd parties | Person_102 | 2015-01-22 01:00 | 2020-10-21 01:00 | 40% | 0 | 0 | Transfer | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 2099 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_694 | 2017-05-23 | 2019-08-04 | 30% | 0 | 0 | Transfer | 10% | 0 | 0 | H3 | 3 | Stable | TRUE | 803 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2019-05-16 | 30% | 0 | 0 | Transfer | 30% | 0 | 0 | 0 | 4 | Stable | FALSE | 1361.9583 | Gap in data | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK024 | Project_058_RISK024 | Threat | Project Contingency | Open | H1 | 1 |  | Connector Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 80% | 2.9361 | 2.3489 | H1 | 1 | -- | TRUE | 214.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK024 | Project_058_RISK024 | Threat | Project Contingency | Open | H1 | 1 |  | Connector Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 80% | 2.9361 | 2.3489 | Reduce | 80% | 2.9361 | 2.3489 | H1 | 1 | -- | TRUE | 214.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK021 | Project_058_RISK021 | Threat | Project Contingency | Open | H1 | 1 |  | Sub System Supplier Delay | Person_511 | 2018-03-22 | 2019-05-23 | 80% | 2.9361 | 2.3489 | Accept | 80% | 2.9361 | 2.3489 | H1 | 1 | -- | TRUE | 427 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK043 | Project_075_RISK043 | Threat | Project Contingency | Open | H1 | 1 |  | Reduction of Qual units | Person_627 | 2017-05-23 | 2018-11-20 01:00 | 70% | 4.0498 | 2.8349 | Accept | 70% | 4.0498 | 2.8349 | H1 | 1 | -- | TRUE | 546.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK043 | Project_075_RISK043 | Threat | Project Contingency | Open | H1 | 1 |  | Reduction of Qual units | Person_627 | 2017-05-23 | 2018-11-20 01:00 | 70% | 4.0498 | 2.8349 | Accept | 70% | 4.0498 | 2.8349 | H1 | 1 | -- | TRUE | 546.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK043 | Project_075_RISK043 | Threat | Project Contingency | Open | H1 | 1 |  | Reduction of Qual units | Person_627 | 2017-05-23 | 2018-11-20 01:00 | 70% | 4.0498 | 2.8349 | Accept | 70% | 4.0498 | 2.8349 | H1 | 1 | -- | TRUE | 546.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK043 | Project_075_RISK043 | Threat | Project Contingency | Open | H1 | 1 |  | Reduction of Qual units | Person_627 | 2017-05-23 | 2018-11-20 01:00 | 70% | 4.0498 | 2.8349 | Accept | 70% | 4.0498 | 2.8349 | H1 | 1 | -- | TRUE | 546.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK043 | Project_075_RISK043 | Threat | Project Contingency | Open | H1 | 1 |  | Reduction of Qual units | Person_627 | 2017-05-23 | 2018-11-20 01:00 | 70% | 4.0498 | 2.8349 | Accept | 70% | 4.0498 | 2.8349 | H1 | 1 | -- | TRUE | 546.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK008 | Project_086_RISK008 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Resource Deployment in Supplier | Person_048 | 2017-11-22 01:00 | 2018-11-22 01:00 | 50% | 0 | 0 | Accept | 50% | 0 | 0 | H1 | 1 | Improving | TRUE | 365 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 1 |  | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-09-19 01:00 | 65% | 5.6817 | 3.6931 | Reduce | 51.2% | 5.6817 | 2.909 | H1 | 1 | Stable | TRUE | 1580.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK153 | Project_092_RISK153 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Cyber Security | Person_661 | 2018-02-20 01:00 | 2033-05-22 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5569.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 1 |  | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-10-19 01:00 | 65% | 5.6817 | 3.6931 | Reduce | 51.2% | 5.6817 | 2.909 | H1 | 1 | Stable | TRUE | 1610.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK155 | Project_092_RISK155 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Processor Architecture | Person_661 | 2018-02-20 01:00 | 2033-05-22 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5569.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK150 | Project_092_RISK150 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Interface issues | Person_661 | 2018-02-20 01:00 | 2033-05-22 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5569.9583 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 1 |  | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-11-19 01:00 | 65% | 5.6817 | 3.6931 | Reduce | 51.2% | 5.6817 | 2.909 | H1 | 1 | Stable | TRUE | 1641.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK152 | Project_092_RISK152 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment availability - Production Testing | Person_661 | 2018-02-20 01:00 | 2033-05-22 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5569.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 1 |  | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-11-19 01:00 | 65% | 5.6817 | 3.6931 | Reduce | 51.2% | 5.6817 | 2.909 | H1 | 1 | Stable | TRUE | 1641.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK151 | Project_092_RISK151 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | No test equipment available - Bench testing | Person_316 | 2018-02-20 01:00 | 2033-05-22 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 5569.9583 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 1 |  | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-11-19 01:00 | 65% | 5.6817 | 3.6931 | Reduce | 51.2% | 5.6817 | 2.909 | H1 | 1 | Stable | TRUE | 1641.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--30 | Project_021_Risk--30 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Emergent safety requirements for Client Server update | Person_061 | 2018-02-20 01:00 | 2019-09-20 01:00 | 0% | 0 | 0 | -- | 0% | 0 | 0 | 0 | 4 | -- | FALSE | 577 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-08 | Project_022_RISK-08 | Threat | Project Contingency | Open | H1 | 1 |  | Poor performance during acceptance phases | Person_248 | 2012-05-23 | 2016-11-19 01:00 | 65% | 5.6817 | 3.6931 | Reduce | 51.2% | 5.6817 | 2.909 | H1 | 1 | Stable | TRUE | 1641.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-20 01:00 | 2018-05-22 | 50% | 3.1083 | 1.5542 | Exploit | 100% | 3.1083 | 3.1083 | H1 | 1 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 01:00 | 10% | 0.0046972 | 0.00046972 | Avoid | 10% | 0.0046972 | 0.00046972 | H3 | 3 | Stable | TRUE | 455.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 01:00 | 10% | 0.0046972 | 0.00046972 | Avoid | 10% | 0.0046972 | 0.00046972 | H3 | 3 | Stable | TRUE | 455.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 01:00 | 10% | 0.0046972 | 0.00046972 | Avoid | 10% | 0.0046972 | 0.00046972 | H3 | 3 | Stable | TRUE | 455.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 01:00 | 10% | 0.0046972 | 0.00046972 | Avoid | 10% | 0.0046972 | 0.00046972 | H3 | 3 | Stable | TRUE | 455.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 10% | 0.0046972 | 0.00046972 | Avoid | 10% | 0.0046972 | 0.00046972 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 10% | 0.0046972 | 0.00046972 | Avoid | 10% | 0.0046972 | 0.00046972 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 10% | 0.0046972 | 0.00046972 | Avoid | 10% | 0.0046972 | 0.00046972 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK006 | Project_003_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2015-07-22 | 2016-10-19 | 10% | 0.0046972 | 0.00046972 | Avoid | 10% | 0.0046972 | 0.00046972 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 41% | 0.071669 | 0.029384 | Reduce | 10% | 0.0088847 | 0.00088847 | H3 | 3 | Stable | FALSE | 770 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 41% | 0.071669 | 0.029384 | Reduce | 10% | 0.0088847 | 0.00088847 | H3 | 3 | Stable | FALSE | 770 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 41% | 0.071669 | 0.029384 | Reduce | 10% | 0.0088847 | 0.00088847 | H3 | 3 | Stable | FALSE | 770 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 41% | 0.071669 | 0.029384 | Reduce | 10% | 0.0088847 | 0.00088847 | H3 | 3 | Stable | FALSE | 770 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 41% | 0.071669 | 0.029384 | Reduce | 10% | 0.0088847 | 0.00088847 | H3 | 3 | Stable | FALSE | 770 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 41% | 0.071669 | 0.029384 | Reduce | 10% | 0.0088847 | 0.00088847 | H3 | 3 | Stable | FALSE | 770 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 41% | 0.071669 | 0.029384 | Reduce | 10% | 0.0088847 | 0.00088847 | H3 | 3 | Stable | FALSE | 770 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk011 | Project_002_Risk011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Testing | Person_175 | 2014-06-29 | 2016-08-07 | 41% | 0.071669 | 0.029384 | Reduce | 10% | 0.0088847 | 0.00088847 | H3 | 3 | Stable | FALSE | 770 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0.0056822 | 0.0011364 | Avoid | 20% | 0.0056822 | 0.0011364 | H3 | 3 | Stable | FALSE | 455.0417 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0.0056822 | 0.0011364 | Avoid | 20% | 0.0056822 | 0.0011364 | H3 | 3 | Stable | FALSE | 455.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0.0056822 | 0.0011364 | Avoid | 20% | 0.0056822 | 0.0011364 | H3 | 3 | Stable | FALSE | 455.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0.0056822 | 0.0011364 | Avoid | 20% | 0.0056822 | 0.0011364 | H3 | 3 | Stable | FALSE | 455.0417 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0.0056822 | 0.0011364 | Avoid | 20% | 0.0056822 | 0.0011364 | H3 | 3 | Stable | FALSE | 455 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0.0056822 | 0.0011364 | Avoid | 20% | 0.0056822 | 0.0011364 | H3 | 3 | Stable | FALSE | 455 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0.0056822 | 0.0011364 | Avoid | 20% | 0.0056822 | 0.0011364 | H3 | 3 | Stable | FALSE | 455 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK003 | Project_003_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0.0056822 | 0.0011364 | Avoid | 20% | 0.0056822 | 0.0011364 | H3 | 3 | Stable | FALSE | 455 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 10% | 0.01925 | 0.001925 | Avoid | 10% | 0.01925 | 0.001925 | H3 | 3 | Stable | TRUE | 785 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 10% | 0.01925 | 0.001925 | Avoid | 10% | 0.01925 | 0.001925 | H3 | 3 | Stable | TRUE | 785 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 10% | 0.01925 | 0.001925 | Avoid | 10% | 0.01925 | 0.001925 | H3 | 3 | Stable | TRUE | 785 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 10% | 0.01925 | 0.001925 | Avoid | 10% | 0.01925 | 0.001925 | H3 | 3 | Stable | TRUE | 785 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 10% | 0.01925 | 0.001925 | Avoid | 10% | 0.01925 | 0.001925 | H3 | 3 | Stable | TRUE | 785 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 10% | 0.01925 | 0.001925 | Avoid | 10% | 0.01925 | 0.001925 | H3 | 3 | Stable | TRUE | 785 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 10% | 0.01925 | 0.001925 | Avoid | 10% | 0.01925 | 0.001925 | H3 | 3 | Stable | TRUE | 785 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk009 | Project_002_Risk009 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-06-14 | 2016-08-07 | 10% | 0.01925 | 0.001925 | Avoid | 10% | 0.01925 | 0.001925 | H3 | 3 | Stable | TRUE | 785 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK040 | Project_097_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data is inconsistent with the Data Specification | Person_560 | 2018-11-21 01:00 | 2019-09-21 01:00 | 20% | 0.040806 | 0.0081612 | Transfer | 5% | 0.040806 | 0.0020403 | H2 | 2 | Stable | TRUE | 304 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0.013865 | 0.0027729 | Avoid | 20% | 0.013865 | 0.0027729 | H3 | 3 | Stable | TRUE | 455.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0.013865 | 0.0027729 | Avoid | 20% | 0.013865 | 0.0027729 | H3 | 3 | Stable | TRUE | 455.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0.013865 | 0.0027729 | Avoid | 20% | 0.013865 | 0.0027729 | H3 | 3 | Stable | TRUE | 455.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 01:00 | 20% | 0.013865 | 0.0027729 | Avoid | 20% | 0.013865 | 0.0027729 | H3 | 3 | Stable | TRUE | 455.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0.013865 | 0.0027729 | Avoid | 20% | 0.013865 | 0.0027729 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0.013865 | 0.0027729 | Avoid | 20% | 0.013865 | 0.0027729 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0.013865 | 0.0027729 | Avoid | 20% | 0.013865 | 0.0027729 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK004 | Project_003_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2015-07-22 | 2016-10-19 | 20% | 0.013865 | 0.0027729 | Avoid | 20% | 0.013865 | 0.0027729 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-10-19 01:00 | 20% | 0.014395 | 0.002879 | Reduce | 20% | 0.014395 | 0.002879 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-10-19 01:00 | 20% | 0.014395 | 0.002879 | Reduce | 20% | 0.014395 | 0.002879 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-10-19 01:00 | 20% | 0.014395 | 0.002879 | Reduce | 20% | 0.014395 | 0.002879 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-10-19 01:00 | 20% | 0.014395 | 0.002879 | Reduce | 20% | 0.014395 | 0.002879 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 20% | 0.014395 | 0.002879 | Reduce | 20% | 0.014395 | 0.002879 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 20% | 0.014395 | 0.002879 | Reduce | 20% | 0.014395 | 0.002879 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 20% | 0.014395 | 0.002879 | Reduce | 20% | 0.014395 | 0.002879 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK007 | Project_003_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-10-19 | 20% | 0.014395 | 0.002879 | Reduce | 20% | 0.014395 | 0.002879 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier Delay | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 80% | 3.9148 | 3.1318 | Reduce | 80% | 3.9148 | 3.1318 | H1 | 1 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK053 | Project_075_RISK053 | Opportunitity | Project Contingency | Open | H1 | 1 |  | There is an opportunity to sell the 3rd unit to Sales and Marketing or stock build | Person_627 | 2018-09-15 01:00 | 2019-05-16 | 80% | 4.2185 | 3.3748 | Exploit | 80% | 4.2185 | 3.3748 | H1 | 1 | -- | TRUE | 242.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK052 | Project_075_RISK052 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Opportunity to transfer costs from current contract to future stock build | Person_627 | 2018-09-15 01:00 | 2019-05-16 | 50% | 7.5934 | 3.7967 | Exploit | 50% | 7.5934 | 3.7967 | H1 | 1 | -- | TRUE | 242.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 10% | 0.034059 | 0.0034059 | Accept | 10% | 0.034059 | 0.0034059 | H3 | 3 | Worsening | FALSE | 785 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 10% | 0.034059 | 0.0034059 | Accept | 10% | 0.034059 | 0.0034059 | H3 | 3 | Worsening | FALSE | 785 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 10% | 0.034059 | 0.0034059 | Accept | 10% | 0.034059 | 0.0034059 | H3 | 3 | Worsening | FALSE | 785 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 10% | 0.034059 | 0.0034059 | Accept | 10% | 0.034059 | 0.0034059 | H3 | 3 | Worsening | FALSE | 785 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 10% | 0.034059 | 0.0034059 | Accept | 10% | 0.034059 | 0.0034059 | H3 | 3 | Worsening | FALSE | 785 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 10% | 0.034059 | 0.0034059 | Accept | 10% | 0.034059 | 0.0034059 | H3 | 3 | Worsening | FALSE | 785 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 10% | 0.034059 | 0.0034059 | Accept | 10% | 0.034059 | 0.0034059 | H3 | 3 | Worsening | FALSE | 785 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk010 | Project_002_Risk010 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability | Person_357 | 2014-06-14 | 2016-08-07 | 10% | 0.034059 | 0.0034059 | Accept | 10% | 0.034059 | 0.0034059 | H3 | 3 | Worsening | FALSE | 785 |  | 1 | 1 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK041 | Project_097_RISK041 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Obsolescence - System instalations | Person_667 | 2019-08-22 01:00 | 2019-11-21 01:00 | 25% | 0.068727 | 0.017182 | Reduce | 5% | 0.068727 | 0.0034364 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK051 | Project_097_RISK051 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Obsolescence - SME Resource Availability during rollout | Person_667 | 2019-10-22 01:00 | 2020-01-20 01:00 | 40% | 0.070874 | 0.02835 | Reduce | 5% | 0.070874 | 0.0035437 | H2 | 2 | Stable | TRUE | 90 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK002 | Project_097_RISK002 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | SW Uplift - Additional Software Release | Person_667 | 2018-10-06 01:00 | 2018-10-27 01:00 | 10% | 0.080539 | 0.0080539 | Reduce | 5% | 0.080539 | 0.004027 | H2 | 2 | Stable | TRUE | 21 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-11-19 01:00 | 2016-03-21 01:00 | 10% | 0.049978 | 0.0049978 | Avoid | 10% | 0.049978 | 0.0049978 | H3 | 3 | Stable | TRUE | 488 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-11-19 01:00 | 2016-03-21 01:00 | 10% | 0.049978 | 0.0049978 | Avoid | 10% | 0.049978 | 0.0049978 | H3 | 3 | Stable | TRUE | 488 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-11-19 01:00 | 2016-03-21 01:00 | 10% | 0.049978 | 0.0049978 | Avoid | 10% | 0.049978 | 0.0049978 | H3 | 3 | Stable | TRUE | 488 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-11-19 01:00 | 2016-03-21 01:00 | 10% | 0.049978 | 0.0049978 | Avoid | 10% | 0.049978 | 0.0049978 | H3 | 3 | Stable | TRUE | 488 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-11-19 | 2016-03-21 | 10% | 0.049978 | 0.0049978 | Avoid | 10% | 0.049978 | 0.0049978 | H3 | 3 | Stable | TRUE | 488 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-11-19 | 2016-03-21 | 10% | 0.049978 | 0.0049978 | Avoid | 10% | 0.049978 | 0.0049978 | H3 | 3 | Stable | TRUE | 488 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK006 | Project_004_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Tooling | Person_133 | 2014-11-18 23:00 | 2016-03-20 23:00 | 10% | 0.049978 | 0.0049978 | Avoid | 10% | 0.049978 | 0.0049978 | H3 | 3 | Stable | TRUE | 488 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK042 | Project_097_RISK042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence - Supplier lead times | Person_659 | 2018-10-22 01:00 | 2019-01-22 01:00 | 30% | 0.034363 | 0.010309 | Reduce | 15% | 0.034363 | 0.0051544 | H2 | 2 | Stable | TRUE | 92 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-322 | Project_032_Risk-322 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data/Information Management Systems and Technology Toolset | Person_629 | 2016-04-08 | 2017-08-20 01:00 | 33% | 0.20788 | 0.068599 | Accept | 11% | 0.052336 | 0.0057569 | H3 | 3 | -- | FALSE | 499.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-322 | Project_032_Risk-322 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data/Information Management Systems and Technology Toolset | Person_629 | 2016-04-08 | 2017-08-20 01:00 | 33% | 0.20788 | 0.068599 | Accept | 11% | 0.052336 | 0.0057569 | H3 | 3 | -- | FALSE | 499.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-322 | Project_032_Risk-322 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data/Information Management Systems and Technology Toolset | Person_629 | 2016-04-08 | 2017-08-20 01:00 | 33% | 0.20788 | 0.068599 | Accept | 11% | 0.052336 | 0.0057569 | H3 | 3 | -- | FALSE | 499.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-322 | Project_032_Risk-322 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data/Information Management Systems and Technology Toolset | Person_629 | 2016-04-08 | 2017-08-20 01:00 | 33% | 0.20788 | 0.068599 | Accept | 11% | 0.052336 | 0.0057569 | H3 | 3 | -- | FALSE | 499.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 30% | 0.10626 | 0.031878 | -- | 30% | 0.01932 | 0.005796 | H3 | 3 | Stable | TRUE | 452 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 30% | 0.10626 | 0.031878 | -- | 30% | 0.01932 | 0.005796 | H3 | 3 | Stable | TRUE | 452 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 30% | 0.10626 | 0.031878 | -- | 30% | 0.01932 | 0.005796 | H3 | 3 | Stable | TRUE | 452 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 30% | 0.10626 | 0.031878 | -- | 30% | 0.01932 | 0.005796 | H3 | 3 | Stable | TRUE | 452 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 30% | 0.10626 | 0.031878 | -- | 30% | 0.01932 | 0.005796 | H3 | 3 | Stable | TRUE | 452 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-098 | Project_011_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | Customers | Required to produce a more comprehensive data pack than originally expected | Person_230 | 2017-05-24 | 2018-08-19 | 30% | 0.10626 | 0.031878 | -- | 30% | 0.01932 | 0.005796 | H3 | 3 | Stable | TRUE | 452 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK274 | Project_024_RISK274 | Threat | Project Contingency | Open | H1 | 1 |  | Software platform (OS/Drivers/Libraries) | Person_331 | 2016-07-13 | 2016-10-20 01:00 | 40% | 9.8671 | 3.9468 | Accept | 40% | 9.8671 | 3.9468 | H1 | 1 | -- | TRUE | 99.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK020 | Project_097_RISK020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SW Uplift - Late Delivery of Software Sub-Systems | Person_574 | 2018-09-21 01:00 | 2019-01-21 01:00 | 20% | 0.12886 | 0.025772 | Reduce | 5% | 0.12886 | 0.0064431 | H2 | 2 | Stable | TRUE | 122 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK009 | Project_075_RISK009 | Threat | Project Contingency | Open | H1 | 1 |  | Suppliers can't meet timescales. | Person_627 | 2016-12-20 01:00 | 2018-11-20 01:00 | 70% | 22.2176 | 15.5523 | Reduce | 60% | 6.7497 | 4.0498 | H1 | 1 | Stable | TRUE | 700 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK009 | Project_075_RISK009 | Threat | Project Contingency | Open | H1 | 1 |  | Suppliers can't meet timescales. | Person_627 | 2016-12-20 01:00 | 2018-11-20 01:00 | 70% | 22.2176 | 15.5523 | Reduce | 60% | 6.7497 | 4.0498 | H1 | 1 | Stable | TRUE | 700 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 0.12983 | 0.10386 | Reduce | 5% | 0.12983 | 0.0064915 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 0.12983 | 0.10386 | Reduce | 5% | 0.12983 | 0.0064915 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 0.12983 | 0.10386 | Reduce | 5% | 0.12983 | 0.0064915 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 0.12983 | 0.10386 | Reduce | 5% | 0.12983 | 0.0064915 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 0.12983 | 0.10386 | Reduce | 5% | 0.12983 | 0.0064915 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 0.12983 | 0.10386 | Reduce | 5% | 0.12983 | 0.0064915 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK256 | Project_024_RISK256 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet spare capacity requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 0.12983 | 0.10386 | Reduce | 5% | 0.12983 | 0.0064915 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK015 | Project_097_RISK015 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SW Uplift - Failure of test environment | Person_667 | 2018-11-21 01:00 | 2019-09-21 01:00 | 20% | 0.065773 | 0.013155 | Reduce | 10% | 0.065773 | 0.0065773 | H2 | 2 | Stable | TRUE | 304 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK049 | Project_097_RISK049 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence - Hardware Failure | Person_659 | 2018-09-21 01:00 | 2019-10-20 01:00 | 20% | 0.1396 | 0.02792 | Reduce | 5% | 0.1396 | 0.0069801 | H2 | 2 | Stable | TRUE | 394 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK009 | Project_075_RISK009 | Threat | Project Contingency | Open | H1 | 1 |  | Suppliers can't meet timescales. | Person_627 | 2016-12-20 01:00 | 2018-11-20 01:00 | 70% | 22.2176 | 15.5523 | Reduce | 60% | 6.7497 | 4.0498 | H1 | 1 | Stable | TRUE | 700 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 01:00 | 50% | 0.014395 | 0.0071976 | Avoid | 50% | 0.014395 | 0.0071976 | H2 | 2 | Improving | TRUE | 425.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 01:00 | 50% | 0.014395 | 0.0071976 | Avoid | 50% | 0.014395 | 0.0071976 | H2 | 2 | Improving | TRUE | 425.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 01:00 | 50% | 0.014395 | 0.0071976 | Avoid | 50% | 0.014395 | 0.0071976 | H2 | 2 | Improving | TRUE | 425.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 01:00 | 50% | 0.014395 | 0.0071976 | Avoid | 50% | 0.014395 | 0.0071976 | H2 | 2 | Improving | TRUE | 425.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 50% | 0.014395 | 0.0071976 | Avoid | 50% | 0.014395 | 0.0071976 | H2 | 2 | Improving | TRUE | 425 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 50% | 0.014395 | 0.0071976 | Avoid | 50% | 0.014395 | 0.0071976 | H2 | 2 | Improving | TRUE | 425 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 50% | 0.014395 | 0.0071976 | Avoid | 50% | 0.014395 | 0.0071976 | H2 | 2 | Improving | TRUE | 425 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_003 | RISK002 | Project_003_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2015-07-22 | 2016-09-19 | 50% | 0.014395 | 0.0071976 | Avoid | 50% | 0.014395 | 0.0071976 | H2 | 2 | Improving | TRUE | 425 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK001 | Project_097_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SW Uplift - Additional Software Release | Person_667 | 2018-09-15 01:00 | 2018-10-20 01:00 | 25% | 0.15463 | 0.038659 | Reduce | 5% | 0.15463 | 0.0077317 | H2 | 2 | Stable | TRUE | 35 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK009 | Project_075_RISK009 | Threat | Project Contingency | Open | H1 | 1 |  | Suppliers can't meet timescales. | Person_627 | 2016-12-20 01:00 | 2018-11-20 01:00 | 70% | 22.2176 | 15.5523 | Reduce | 60% | 6.7497 | 4.0498 | H1 | 1 | Stable | TRUE | 700 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK269 | Project_038_RISK269 | Threat | Project Contingency | Open | H1 | 1 |  | Resource issue in card to provide real time data due to adding 2nd interface | Person_303 | 2015-07-22 | 2016-08-14 | 80% | 5.6182 | 4.4946 | Accept | 80% | 5.6182 | 4.4946 | H1 | 1 | Stable | TRUE | 389 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK269 | Project_038_RISK269 | Threat | Project Contingency | Open | H1 | 1 |  | Resource issue in card to provide real time data due to adding 2nd interface | Person_303 | 2015-07-22 | 2016-08-14 | 80% | 5.6182 | 4.4946 | Accept | 80% | 5.6182 | 4.4946 | H1 | 1 | Stable | TRUE | 389 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK339 | Project_033_RISK339 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 70% | 9.6967 | 6.7877 | Exploit | 70% | 6.4358 | 4.5051 | H1 | 1 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK008 | Project_097_RISK008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SW Uplift - implementation of New Scope | Person_560 | 2019-09-04 01:00 | 2019-10-06 01:00 | 30% | 0.1745 | 0.05235 | Reduce | 5% | 0.1745 | 0.008725 | H2 | 2 | Stable | TRUE | 32 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 25% | 0.035539 | 0.0088847 | Avoid | 25% | 0.035539 | 0.0088847 | H2 | 2 | Stable | TRUE | 786 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 25% | 0.035539 | 0.0088847 | Avoid | 25% | 0.035539 | 0.0088847 | H2 | 2 | Stable | TRUE | 786 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 25% | 0.035539 | 0.0088847 | Avoid | 25% | 0.035539 | 0.0088847 | H2 | 2 | Stable | TRUE | 786 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 25% | 0.035539 | 0.0088847 | Avoid | 25% | 0.035539 | 0.0088847 | H2 | 2 | Stable | TRUE | 786 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 25% | 0.035539 | 0.0088847 | Avoid | 25% | 0.035539 | 0.0088847 | H2 | 2 | Stable | TRUE | 786 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 25% | 0.035539 | 0.0088847 | Avoid | 25% | 0.035539 | 0.0088847 | H2 | 2 | Stable | TRUE | 786 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 25% | 0.035539 | 0.0088847 | Avoid | 25% | 0.035539 | 0.0088847 | H2 | 2 | Stable | TRUE | 786 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk006 | Project_002_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Pressure Testing | Person_650 | 2014-06-14 | 2016-08-08 | 25% | 0.035539 | 0.0088847 | Avoid | 25% | 0.035539 | 0.0088847 | H2 | 2 | Stable | TRUE | 786 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK039 | Project_097_RISK039 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Obsolescence - Encrypted Hardware Approval to purchase | Person_574 | 2018-10-22 01:00 | 2019-04-23 | 30% | 0.048323 | 0.014497 | Reduce | 20% | 0.048323 | 0.0096647 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-020 | Project_011_Risk-020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | There is a risk that Windows XP Obsolescence will require SW work arounds to overcome major issues | Person_141 | 2013-08-21 01:00 | 2018-08-21 | 10% | 0.098873 | 0.0098873 | Accept | 10% | 0.098873 | 0.0098873 | H3 | 3 | -- | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-020 | Project_011_Risk-020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | There is a risk that Windows XP Obsolescence will require SW work arounds to overcome major issues | Person_141 | 2013-08-21 | 2018-08-21 | 10% | 0.098873 | 0.0098873 | Accept | 10% | 0.098873 | 0.0098873 | H3 | 3 | -- | FALSE | 1826 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-020 | Project_011_Risk-020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | There is a risk that Windows XP Obsolescence will require SW work arounds to overcome major issues | Person_141 | 2013-08-21 | 2018-08-21 | 10% | 0.098873 | 0.0098873 | Accept | 10% | 0.098873 | 0.0098873 | H3 | 3 | -- | FALSE | 1826 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-020 | Project_011_Risk-020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | There is a risk that Windows XP Obsolescence will require SW work arounds to overcome major issues | Person_141 | 2013-08-21 01:00 | 2018-08-21 | 10% | 0.098873 | 0.0098873 | Accept | 10% | 0.098873 | 0.0098873 | H3 | 3 | -- | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-020 | Project_011_Risk-020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | There is a risk that Windows XP Obsolescence will require SW work arounds to overcome major issues | Person_141 | 2013-08-21 01:00 | 2018-08-21 | 10% | 0.098873 | 0.0098873 | Accept | 10% | 0.098873 | 0.0098873 | H3 | 3 | -- | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-020 | Project_011_Risk-020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | There is a risk that Windows XP Obsolescence will require SW work arounds to overcome major issues | Person_141 | 2013-08-21 01:00 | 2018-08-21 | 10% | 0.098873 | 0.0098873 | Accept | 10% | 0.098873 | 0.0098873 | H3 | 3 | -- | FALSE | 1825.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK021 | Project_097_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | SW Uplift - Late Delivery of our Dependencies | Person_574 | 2018-09-21 01:00 | 2019-01-21 01:00 | 30% | 0.20403 | 0.06121 | Reduce | 5% | 0.20403 | 0.010202 | H2 | 2 | Stable | TRUE | 122 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK037 | Project_097_RISK037 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Migration - may have a detrimental effect | Person_648 | 2018-11-21 01:00 | 2019-09-21 01:00 | 25% | 0.068727 | 0.017182 | Reduce | 15% | 0.068727 | 0.010309 | H2 | 2 | Stable | TRUE | 304 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK339 | Project_033_RISK339 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 70% | 9.6967 | 6.7877 | Exploit | 70% | 6.4358 | 4.5051 | H1 | 1 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK050 | Project_097_RISK050 | Threat | Management Contingency | Open | H2 | 2 | Logistic support and Services | Obsolescence - FSE Availability during rollout | Person_234 | 2019-10-22 01:00 | 2019-12-22 01:00 | 25% | 0.070874 | 0.017719 | Reduce | 15% | 0.070874 | 0.010631 | H2 | 2 | Stable | TRUE | 61 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 30% | 0.035539 | 0.010662 | Avoid | 30% | 0.035539 | 0.010662 | H2 | 2 | Worsening | TRUE | 786 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 30% | 0.035539 | 0.010662 | Avoid | 30% | 0.035539 | 0.010662 | H2 | 2 | Worsening | TRUE | 786 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 30% | 0.035539 | 0.010662 | Avoid | 30% | 0.035539 | 0.010662 | H2 | 2 | Worsening | TRUE | 786 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 30% | 0.035539 | 0.010662 | Avoid | 30% | 0.035539 | 0.010662 | H2 | 2 | Worsening | TRUE | 786 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 30% | 0.035539 | 0.010662 | Avoid | 30% | 0.035539 | 0.010662 | H2 | 2 | Worsening | TRUE | 786 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 30% | 0.035539 | 0.010662 | Avoid | 30% | 0.035539 | 0.010662 | H2 | 2 | Worsening | TRUE | 786 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 30% | 0.035539 | 0.010662 | Avoid | 30% | 0.035539 | 0.010662 | H2 | 2 | Worsening | TRUE | 786 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk005 | Project_002_Risk005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2014-06-14 | 2016-08-08 | 30% | 0.035539 | 0.010662 | Avoid | 30% | 0.035539 | 0.010662 | H2 | 2 | Worsening | TRUE | 786 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 20% | 0.05627 | 0.011254 | Reduce | 20% | 0.05627 | 0.011254 | H3 | 3 | Stable | FALSE | 260 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 20% | 0.05627 | 0.011254 | Reduce | 20% | 0.05627 | 0.011254 | H3 | 3 | Stable | FALSE | 260 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 20% | 0.05627 | 0.011254 | Reduce | 20% | 0.05627 | 0.011254 | H3 | 3 | Stable | FALSE | 260 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 20% | 0.05627 | 0.011254 | Reduce | 20% | 0.05627 | 0.011254 | H3 | 3 | Stable | FALSE | 260 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 20% | 0.05627 | 0.011254 | Reduce | 20% | 0.05627 | 0.011254 | H3 | 3 | Stable | FALSE | 260 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-20 23:00 | 2016-08-07 | 20% | 0.05627 | 0.011254 | Reduce | 20% | 0.05627 | 0.011254 | H3 | 3 | Stable | FALSE | 260.0417 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 20% | 0.05627 | 0.011254 | Reduce | 20% | 0.05627 | 0.011254 | H3 | 3 | Stable | FALSE | 260 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | RISK012 | Project_002_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Resourcing Suitably Qualified and experienced staff availability | Person_650 | 2015-11-21 | 2016-08-07 | 20% | 0.05627 | 0.011254 | Reduce | 20% | 0.05627 | 0.011254 | H3 | 3 | Stable | FALSE | 260 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-197 | Project_039_Risk-197 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Key Test facilities Availability | Person_185 | 2016-09-20 01:00 | 2017-02-19 01:00 | 20% | 0.46506 | 0.093012 | Reduce | 5% | 0.23253 | 0.011627 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 01:00 | 20% | 0.060459 | 0.012092 | Avoid | 20% | 0.060459 | 0.012092 | H3 | 3 | Stable | FALSE | 302.0417 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 01:00 | 20% | 0.060459 | 0.012092 | Avoid | 20% | 0.060459 | 0.012092 | H3 | 3 | Stable | FALSE | 302.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 01:00 | 20% | 0.060459 | 0.012092 | Avoid | 20% | 0.060459 | 0.012092 | H3 | 3 | Stable | FALSE | 302.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 01:00 | 20% | 0.060459 | 0.012092 | Avoid | 20% | 0.060459 | 0.012092 | H3 | 3 | Stable | FALSE | 302.0417 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 | 20% | 0.060459 | 0.012092 | Avoid | 20% | 0.060459 | 0.012092 | H3 | 3 | Stable | FALSE | 302 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-21 | 20% | 0.060459 | 0.012092 | Avoid | 20% | 0.060459 | 0.012092 | H3 | 3 | Stable | FALSE | 302 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK003 | Project_004_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Test Facility | Person_650 | 2015-05-24 | 2016-03-20 23:00 | 20% | 0.060459 | 0.012092 | Avoid | 20% | 0.060459 | 0.012092 | H3 | 3 | Stable | FALSE | 301.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK339 | Project_033_RISK339 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 70% | 9.6967 | 6.7877 | Exploit | 70% | 6.4358 | 4.5051 | H1 | 1 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK339 | Project_033_RISK339 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 70% | 9.6967 | 6.7877 | Exploit | 70% | 6.4358 | 4.5051 | H1 | 1 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK339 | Project_033_RISK339 | Opportunitity | Project Contingency | Open | H1 | 1 |  | cost savings | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 70% | 9.6967 | 6.7877 | Exploit | 70% | 6.4358 | 4.5051 | H1 | 1 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-05-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2889 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-05-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2889 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-05-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2889 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK056 | Project_097_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Obsolescence - Additional testing required following review of VCRM | Person_667 | 2019-07-22 | 2019-12-22 01:00 | 40% | 0.32323 | 0.12929 | Reduce | 5% | 0.32323 | 0.016162 | H2 | 2 | Stable | TRUE | 153.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 20% | 0.081443 | 0.016289 | Avoid | 20% | 0.081443 | 0.016289 | H3 | 3 | Stable | FALSE | 866 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 20% | 0.081443 | 0.016289 | Avoid | 20% | 0.081443 | 0.016289 | H3 | 3 | Stable | FALSE | 866 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 20% | 0.081443 | 0.016289 | Avoid | 20% | 0.081443 | 0.016289 | H3 | 3 | Stable | FALSE | 866 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 20% | 0.081443 | 0.016289 | Avoid | 20% | 0.081443 | 0.016289 | H3 | 3 | Stable | FALSE | 866 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 20% | 0.081443 | 0.016289 | Avoid | 20% | 0.081443 | 0.016289 | H3 | 3 | Stable | FALSE | 866 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 20% | 0.081443 | 0.016289 | Avoid | 20% | 0.081443 | 0.016289 | H3 | 3 | Stable | FALSE | 866 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 20% | 0.081443 | 0.016289 | Avoid | 20% | 0.081443 | 0.016289 | H3 | 3 | Stable | FALSE | 866 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk004 | Project_002_Risk004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Test Equipment | Person_133 | 2014-03-26 | 2016-08-08 | 20% | 0.081443 | 0.016289 | Avoid | 20% | 0.081443 | 0.016289 | H3 | 3 | Stable | FALSE | 866 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2980.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-153 | Project_026_Risk-153 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Installed Equipment Security | Person_298 | 2018-05-13 | 2022-10-28 01:00 | 5% | 0.37307 | 0.018653 | Reduce | 5% | 0.37307 | 0.018653 | H3 | 3 | -- | TRUE | 1629.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-153 | Project_026_Risk-153 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Installed Equipment Security | Person_298 | 2018-05-13 | 2022-10-28 01:00 | 5% | 0.37307 | 0.018653 | Reduce | 5% | 0.37307 | 0.018653 | H3 | 3 | -- | TRUE | 1629.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-153 | Project_026_Risk-153 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Installed Equipment Security | Person_298 | 2018-05-13 | 2022-10-28 01:00 | 5% | 0.37307 | 0.018653 | Reduce | 5% | 0.37307 | 0.018653 | H3 | 3 | -- | TRUE | 1629.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-153 | Project_026_Risk-153 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Installed Equipment Security | Person_298 | 2018-05-13 | 2022-10-28 01:00 | 5% | 0.37307 | 0.018653 | Reduce | 5% | 0.37307 | 0.018653 | H3 | 3 | -- | TRUE | 1629.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-153 | Project_026_Risk-153 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Installed Equipment Security | Person_298 | 2018-05-13 | 2022-10-28 01:00 | 5% | 0.37307 | 0.018653 | Reduce | 5% | 0.37307 | 0.018653 | H3 | 3 | -- | TRUE | 1629.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-153 | Project_026_Risk-153 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Installed Equipment Security | Person_298 | 2018-05-13 | 2022-10-28 01:00 | 5% | 0.37307 | 0.018653 | Reduce | 5% | 0.37307 | 0.018653 | H3 | 3 | -- | TRUE | 1629.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-153 | Project_026_Risk-153 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Installed Equipment Security | Person_298 | 2018-05-13 | 2022-10-28 01:00 | 5% | 0.37307 | 0.018653 | Reduce | 5% | 0.37307 | 0.018653 | H3 | 3 | -- | TRUE | 1629.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-153 | Project_026_Risk-153 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Installed Equipment Security | Person_298 | 2018-05-13 | 2022-10-28 01:00 | 5% | 0.37307 | 0.018653 | Reduce | 5% | 0.37307 | 0.018653 | H3 | 3 | -- | TRUE | 1629.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK031 | Project_097_RISK031 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | SW Uplift - Additional support | Person_659 | 2019-10-22 01:00 | 2019-12-22 01:00 | 20% | 0.18792 | 0.037585 | Reduce | 10% | 0.18792 | 0.018792 | H2 | 2 | Improving | TRUE | 61 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2980.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2980.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK010 | Project_097_RISK010 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | SW Uplift - Test Report Efficiencies | Person_667 | 2019-08-22 01:00 | 2019-10-22 01:00 | 5% | 0.077317 | 0.0038659 | Exploit | 25% | 0.077317 | 0.019329 | H2 | 2 | Stable | TRUE | 61 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2980.0417 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2980.0417 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 01:00 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2980.0417 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_427 | 2009-06-23 | 2017-08-20 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2980 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2017-08-20 01:00 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 2980.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK004 | Project_097_RISK004 | Threat | Project Contingency | Open | H2 | 2 | Project Management | SW Uplift Core - Core Software Engineer Resource Availability | Person_667 | 2018-09-15 01:00 | 2019-01-20 01:00 | 40% | 0.19866 | 0.079465 | Reduce | 10% | 0.19866 | 0.019866 | H2 | 2 | Worsening | TRUE | 127 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 3346 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-21 01:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 497.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-21 01:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 497.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-21 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 498 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-21 01:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 497.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-20 23:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 498.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-20 22:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 498.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-20 23:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 498.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-21 01:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 497.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-20 22:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 498.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-21 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 498 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-21 01:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 497.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK118 | Project_065_RISK118 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Software Bugs Take Excessive Time to Resolve For Software Engineering Releases | Person_550 | 2016-12-20 23:00 | 2018-05-03 | 60% | 0.43948 | 0.26369 | Reduce | 30% | 0.06761 | 0.020283 | H3 | 3 | -- | TRUE | 498.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 20% | 0.10171 | 0.020343 | -- | 20% | 0.10171 | 0.020343 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 20% | 0.10171 | 0.020343 | -- | 20% | 0.10171 | 0.020343 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 20% | 0.10171 | 0.020343 | -- | 20% | 0.10171 | 0.020343 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 20% | 0.10171 | 0.020343 | -- | 20% | 0.10171 | 0.020343 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 20% | 0.10171 | 0.020343 | -- | 20% | 0.10171 | 0.020343 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-114 | Project_011_Risk-114 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rentention of Key Skills | Person_147 | 2016-07-21 | 2018-08-21 | 20% | 0.10171 | 0.020343 | -- | 20% | 0.10171 | 0.020343 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK012 | Project_097_RISK012 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SW Uplift - Scan | Person_667 | 2018-12-01 01:00 | 2019-02-09 01:00 | 30% | 0.21209 | 0.063626 | Reduce | 10% | 0.21209 | 0.021209 | H2 | 2 | Stable | TRUE | 70 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK006 | Project_097_RISK006 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | SW Uplift - Compliance | Person_667 | 2019-05-24 | 2019-10-06 01:00 | 40% | 0.21477 | 0.085908 | Reduce | 10% | 0.21477 | 0.021477 | H2 | 2 | Stable | TRUE | 135.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-03-21 01:00 | 20% | 0.15317 | 0.030633 | Reduce | 20% | 0.10883 | 0.021765 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-03-21 01:00 | 20% | 0.15317 | 0.030633 | Reduce | 20% | 0.10883 | 0.021765 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-03-21 01:00 | 20% | 0.15317 | 0.030633 | Reduce | 20% | 0.10883 | 0.021765 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 01:00 | 2016-03-21 01:00 | 20% | 0.15317 | 0.030633 | Reduce | 20% | 0.10883 | 0.021765 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-03-21 | 20% | 0.15317 | 0.030633 | Reduce | 20% | 0.10883 | 0.021765 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-21 | 2016-03-21 | 20% | 0.15317 | 0.030633 | Reduce | 20% | 0.10883 | 0.021765 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK007 | Project_004_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suitably Qualified and experienced staff availability Resource | Person_650 | 2015-11-20 23:00 | 2016-03-20 23:00 | 20% | 0.15317 | 0.030633 | Reduce | 20% | 0.10883 | 0.021765 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-141 | Project_026_Risk-141 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Export Controls | Person_272 | 2015-02-21 01:00 | 2022-10-28 01:00 | 10% | 0.22384 | 0.022384 | Reduce | 10% | 0.22384 | 0.022384 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-141 | Project_026_Risk-141 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Export Controls | Person_272 | 2015-02-21 01:00 | 2022-10-28 01:00 | 10% | 0.22384 | 0.022384 | Reduce | 10% | 0.22384 | 0.022384 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-141 | Project_026_Risk-141 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Export Controls | Person_272 | 2015-02-21 01:00 | 2022-10-28 01:00 | 10% | 0.22384 | 0.022384 | Reduce | 10% | 0.22384 | 0.022384 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-141 | Project_026_Risk-141 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Export Controls | Person_272 | 2015-02-21 01:00 | 2022-10-28 01:00 | 10% | 0.22384 | 0.022384 | Reduce | 10% | 0.22384 | 0.022384 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-141 | Project_026_Risk-141 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Export Controls | Person_272 | 2015-02-21 01:00 | 2022-10-28 01:00 | 10% | 0.22384 | 0.022384 | Reduce | 10% | 0.22384 | 0.022384 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-141 | Project_026_Risk-141 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Export Controls | Person_272 | 2015-02-21 01:00 | 2022-10-28 01:00 | 10% | 0.22384 | 0.022384 | Reduce | 10% | 0.22384 | 0.022384 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-141 | Project_026_Risk-141 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Export Controls | Person_272 | 2015-02-21 01:00 | 2022-10-28 01:00 | 10% | 0.22384 | 0.022384 | Reduce | 10% | 0.22384 | 0.022384 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-141 | Project_026_Risk-141 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Export Controls | Person_272 | 2015-02-21 01:00 | 2022-10-28 01:00 | 10% | 0.22384 | 0.022384 | Reduce | 10% | 0.22384 | 0.022384 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 5% | 2.3457 | 0.11728 | Accept | 1% | 2.3457 | 0.023457 | H2 | 2 | Stable | TRUE | 335.125 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 5% | 2.3457 | 0.11728 | Accept | 1% | 2.3457 | 0.023457 | H2 | 2 | Stable | TRUE | 335.125 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 5% | 2.3457 | 0.11728 | Accept | 1% | 2.3457 | 0.023457 | H2 | 2 | Stable | TRUE | 335.125 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 5% | 2.3457 | 0.11728 | Accept | 1% | 2.3457 | 0.023457 | H2 | 2 | Stable | TRUE | 335.125 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 5% | 2.3457 | 0.11728 | Accept | 1% | 2.3457 | 0.023457 | H2 | 2 | Stable | TRUE | 335.125 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_040 | RISK174 | Project_040_RISK174 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Supplier Power Supply quality | Person_687 | 2013-08-20 21:00 | 2014-07-22 | 5% | 2.3457 | 0.11728 | Accept | 1% | 2.3457 | 0.023457 | H2 | 2 | Stable | TRUE | 335.125 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 3346 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 20% | 0.12388 | 0.024775 | Reduce | 20% | 0.12388 | 0.024775 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 20% | 0.12388 | 0.024775 | Reduce | 20% | 0.12388 | 0.024775 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 20% | 0.12388 | 0.024775 | Reduce | 20% | 0.12388 | 0.024775 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 20% | 0.12388 | 0.024775 | Reduce | 20% | 0.12388 | 0.024775 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 20% | 0.12388 | 0.024775 | Reduce | 20% | 0.12388 | 0.024775 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-105 | Project_011_Risk-105 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Supplier unable to deliver | Person_147 | 2016-07-21 | 2017-04-21 | 20% | 0.12388 | 0.024775 | Reduce | 20% | 0.12388 | 0.024775 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Sub-system / product system accreditation hindered by Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 10% | 0.25667 | 0.025667 | Transfer | 10% | 0.25667 | 0.025667 | H3 | 3 | Stable | FALSE | 2037.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK045 | Project_097_RISK045 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Obsolescence - solution more expensive than previously thought | Person_560 | 2018-08-22 01:00 | 2019-03-23 | 30% | 0.51545 | 0.15463 | Reduce | 5% | 0.51545 | 0.025772 | H2 | 2 | Stable | TRUE | 212.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK029 | Project_097_RISK029 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | SW Uplift - Test period extended | Person_574 | 2019-08-22 01:00 | 2019-09-21 01:00 | 30% | 0.12886 | 0.038659 | Reduce | 20% | 0.12886 | 0.025772 | H2 | 2 | Stable | TRUE | 30 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 3346 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 3346 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-104 | Project_039_Risk-104 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Not able to accurately measure past limits | Person_176 | 2015-08-06 | 2016-05-23 | 20% | 0.54026 | 0.10805 | Reduce | 5% | 0.54062 | 0.027031 | H3 | 3 | Stable | TRUE | 291 |  | 0 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK024 | Project_097_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SW Uplift - regression testing not sufficient | Person_560 | 2018-09-21 01:00 | 2018-11-21 01:00 | 40% | 0.95358 | 0.38143 | Reduce | 5% | 0.54122 | 0.027061 | H2 | 2 | Stable | TRUE | 61 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-126 | Project_011_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Increase in regression testing | Person_140 | 2017-04-22 | 2018-05-21 | 25% | 0.11081 | 0.027702 | -- | 25% | 0.11081 | 0.027702 | H2 | 2 | -- | TRUE | 394 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-126 | Project_011_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Increase in regression testing | Person_140 | 2017-04-22 | 2018-05-21 | 25% | 0.11081 | 0.027702 | -- | 25% | 0.11081 | 0.027702 | H2 | 2 | -- | TRUE | 394 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-126 | Project_011_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Increase in regression testing | Person_140 | 2017-04-22 | 2018-05-21 | 25% | 0.11081 | 0.027702 | -- | 25% | 0.11081 | 0.027702 | H2 | 2 | -- | TRUE | 394 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 722 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 722 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 722 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 | 2017-08-20 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 722 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 722 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 722 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 01:00 | 2017-08-20 01:00 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 722 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-29 | 2017-08-20 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 722 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk28 | Project_010_Risk28 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Bond failures due to the Auto bonder not working could cause more Warranty returns | Person_226 | 2015-08-28 17:00 | 2018-05-22 | 10% | 0.55447 | 0.055447 | Reduce | 5% | 0.55447 | 0.027723 | H3 | 3 | Stable | FALSE | 997.2917 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_693 | 2017-04-22 | 2019-05-16 | 15% | 0.55736 | 0.083603 | Accept | 5% | 0.55736 | 0.027868 | H3 | 3 | Stable | TRUE | 754 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK047 | Project_042_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 20% | 0.56365 | 0.11273 | Accept | 10% | 0.28182 | 0.028182 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK046 | Project_042_RISK046 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables - June | Person_455 | 2018-11-21 01:00 | 2020-11-19 01:00 | 20% | 0.56365 | 0.11273 | Accept | 10% | 0.28182 | 0.028182 | H2 | 2 | Stable | TRUE | 729 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 3346 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 3346 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 3346 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2009-06-23 | 2018-08-21 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 3346 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 20% | 0.14752 | 0.029504 | Avoid | 20% | 0.14752 | 0.029504 | H3 | 3 | Stable | TRUE | 487 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 20% | 0.14752 | 0.029504 | Avoid | 20% | 0.14752 | 0.029504 | H3 | 3 | Stable | TRUE | 487 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 20% | 0.14752 | 0.029504 | Avoid | 20% | 0.14752 | 0.029504 | H3 | 3 | Stable | TRUE | 487 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 20% | 0.14752 | 0.029504 | Avoid | 20% | 0.14752 | 0.029504 | H3 | 3 | Stable | TRUE | 487 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 | 2016-03-21 | 20% | 0.14752 | 0.029504 | Avoid | 20% | 0.14752 | 0.029504 | H3 | 3 | Stable | TRUE | 487 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-20 | 2016-03-21 | 20% | 0.14752 | 0.029504 | Avoid | 20% | 0.14752 | 0.029504 | H3 | 3 | Stable | TRUE | 487 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK004 | Project_004_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework Post Pressure Testing | Person_650 | 2014-11-19 23:00 | 2016-03-20 23:00 | 20% | 0.14752 | 0.029504 | Avoid | 20% | 0.14752 | 0.029504 | H3 | 3 | Stable | TRUE | 487 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1010 | Project_091_RISK1010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Supplier may not be approved for Dip Brazed Manufacture | Person_675 | 2018-09-27 01:00 | 2018-12-21 01:00 | 5% | 0.59721 | 0.02986 | Accept | 5% | 0.59721 | 0.02986 | H2 | 2 | Stable | TRUE | 85 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK036 | Project_097_RISK036 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Migration - Software defect identified during formal Testing | Person_667 | 2018-11-21 01:00 | 2019-09-21 01:00 | 20% | 0.31142 | 0.062283 | Reduce | 10% | 0.31142 | 0.031142 | H2 | 2 | Stable | TRUE | 304 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK005 | Project_097_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | SW Uplift Core - Additional Core Software Release | Person_667 | 2018-09-15 01:00 | 2019-01-20 01:00 | 40% | 0.31571 | 0.12629 | Reduce | 10% | 0.31571 | 0.031571 | H2 | 2 | -- | TRUE | 127 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK079 | Project_065_RISK079 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Safety - Failure to provide adequate project information | Person_732 | 2015-06-24 | 2018-07-16 | 25% | 0.63626 | 0.15906 | Reduce | 5% | 0.63626 | 0.031813 | H3 | 3 | Stable | TRUE | 1118 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK032 | Project_097_RISK032 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | SW Uplift - Bugs | Person_659 | 2018-12-22 01:00 | 2019-09-21 01:00 | 20% | 0.64431 | 0.12886 | Reduce | 5% | 0.64431 | 0.032216 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK070 | Project_043_RISK070 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | More Tech Pubs Update than estimated | Person_769 | 2014-09-13 | 2018-03-21 | 25% | 0.32576 | 0.08144 | -- | 10% | 0.32576 | 0.032576 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_061 | RISK003 | Project_061_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Test equipment reliability | Person_104 | 2017-05-23 | 2020-11-18 19:00 | 40% | 0.11013 | 0.044051 | Reduce | 30% | 0.11013 | 0.033038 | H2 | 2 | Stable | TRUE | 1275.7917 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers not meeting configuration management expectations | Person_519 | 2014-11-21 01:00 | 2019-02-20 01:00 | 15% | 0.33576 | 0.050364 | Avoid | 10% | 0.33576 | 0.033576 | H3 | 3 | -- | FALSE | 1552 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers not meeting configuration management expectations | Person_519 | 2014-11-21 01:00 | 2019-02-20 01:00 | 15% | 0.33576 | 0.050364 | Avoid | 10% | 0.33576 | 0.033576 | H3 | 3 | -- | FALSE | 1552 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers not meeting configuration management expectations | Person_519 | 2014-11-21 01:00 | 2019-02-20 01:00 | 15% | 0.33576 | 0.050364 | Avoid | 10% | 0.33576 | 0.033576 | H3 | 3 | -- | FALSE | 1552 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers not meeting configuration management expectations | Person_519 | 2014-11-21 01:00 | 2019-02-20 01:00 | 15% | 0.33576 | 0.050364 | Avoid | 10% | 0.33576 | 0.033576 | H3 | 3 | -- | FALSE | 1552 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers not meeting configuration management expectations | Person_519 | 2014-11-21 01:00 | 2019-02-20 01:00 | 15% | 0.33576 | 0.050364 | Avoid | 10% | 0.33576 | 0.033576 | H3 | 3 | -- | FALSE | 1552 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers not meeting configuration management expectations | Person_519 | 2014-11-21 01:00 | 2019-02-20 01:00 | 15% | 0.33576 | 0.050364 | Avoid | 10% | 0.33576 | 0.033576 | H3 | 3 | -- | FALSE | 1552 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers not meeting configuration management expectations | Person_519 | 2014-11-21 01:00 | 2019-02-20 01:00 | 15% | 0.33576 | 0.050364 | Avoid | 10% | 0.33576 | 0.033576 | H3 | 3 | -- | FALSE | 1552 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers not meeting configuration management expectations | Person_519 | 2014-11-21 01:00 | 2019-02-20 01:00 | 15% | 0.33576 | 0.050364 | Avoid | 10% | 0.33576 | 0.033576 | H3 | 3 | -- | FALSE | 1552 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 10% | 0.34094 | 0.034094 | -- | 10% | 0.34094 | 0.034094 | H3 | 3 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 10% | 0.34094 | 0.034094 | -- | 10% | 0.34094 | 0.034094 | H3 | 3 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 10% | 0.34094 | 0.034094 | -- | 10% | 0.34094 | 0.034094 | H3 | 3 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 10% | 0.34094 | 0.034094 | -- | 10% | 0.34094 | 0.034094 | H3 | 3 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 10% | 0.34094 | 0.034094 | -- | 10% | 0.34094 | 0.034094 | H3 | 3 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-108 | Project_011_Risk-108 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Offer additional functionality to the customer | Person_147 | 2017-04-22 | 2018-08-21 | 10% | 0.34094 | 0.034094 | -- | 10% | 0.34094 | 0.034094 | H3 | 3 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 25% | 0.68598 | 0.17149 | Reduce | 5% | 0.68598 | 0.034299 | H3 | 3 | -- | FALSE | 547.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 25% | 0.68598 | 0.17149 | Reduce | 5% | 0.68598 | 0.034299 | H3 | 3 | Stable | FALSE | 547.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-20 | 2018-05-22 | 25% | 0.68598 | 0.17149 | Reduce | 5% | 0.68598 | 0.034299 | H3 | 3 | Stable | FALSE | 548 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 25% | 0.68598 | 0.17149 | Reduce | 5% | 0.68598 | 0.034299 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 25% | 0.68598 | 0.17149 | Reduce | 5% | 0.68598 | 0.034299 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 25% | 0.68598 | 0.17149 | Reduce | 5% | 0.68598 | 0.034299 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R27 | Project_041_R27 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Test Equipment | Person_515 | 2016-11-19 22:00 | 2018-05-22 | 25% | 0.68598 | 0.17149 | Reduce | 5% | 0.68598 | 0.034299 | H3 | 3 | Stable | FALSE | 548.0833 |  | 1 | 0 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK009 | Project_097_RISK009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | SW Uplift - Customer Trial | Person_560 | 2019-08-22 01:00 | 2019-09-20 01:00 | 40% | 0.34712 | 0.13885 | Reduce | 10% | 0.34712 | 0.034712 | H2 | 2 | Stable | TRUE | 29 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 0.35487 | 0.035487 | Accept | 10% | 0.35487 | 0.035487 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 0.35487 | 0.035487 | Accept | 10% | 0.35487 | 0.035487 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 0.35487 | 0.035487 | Accept | 10% | 0.35487 | 0.035487 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 0.35487 | 0.035487 | Accept | 10% | 0.35487 | 0.035487 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK206 | Project_024_RISK206 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Simulator Updates | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 0.35487 | 0.035487 | Accept | 10% | 0.35487 | 0.035487 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2016-05-15 | 50% | 0.35617 | 0.17808 | Reduce | 10% | 0.35617 | 0.035617 | H3 | 3 | Stable | TRUE | 83.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2016-05-15 | 50% | 0.35617 | 0.17808 | Reduce | 10% | 0.35617 | 0.035617 | H3 | 3 | Stable | TRUE | 83.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 25% | 0.14661 | 0.036651 | -- | 25% | 0.14661 | 0.036651 | H3 | 3 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 25% | 0.14661 | 0.036651 | -- | 25% | 0.14661 | 0.036651 | H3 | 3 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 25% | 0.14661 | 0.036651 | -- | 25% | 0.14661 | 0.036651 | H3 | 3 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 25% | 0.14661 | 0.036651 | -- | 25% | 0.14661 | 0.036651 | H3 | 3 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 25% | 0.14661 | 0.036651 | -- | 25% | 0.14661 | 0.036651 | H3 | 3 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-109 | Project_011_Risk-109 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Environment complexity | Person_187 | 2016-07-21 | 2018-08-21 | 25% | 0.14661 | 0.036651 | -- | 25% | 0.14661 | 0.036651 | H3 | 3 | Stable | TRUE | 761 |  | 1 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--18 | Project_021_Risk--18 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extends beyond 50% SRA date | Person_174 | 2018-01-21 01:00 | 2019-10-21 01:00 | 70% | 20.3948 | 14.2764 | Reduce | 50% | 10.1974 | 5.0987 | H1 | 1 | Stable | TRUE | 638 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK048 | Project_097_RISK048 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Obsolescence - Data Migration takes longer than expected | Person_574 | 2019-05-24 | 2020-01-22 01:00 | 30% | 0.12886 | 0.038659 | Accept | 30% | 0.12886 | 0.038659 | H2 | 2 | Stable | TRUE | 243.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK056 | Project_017_RISK056 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier Value for Money | Person_279 | 2016-01-21 20:00 | 2023-02-19 20:00 | 50% | 11.4342 | 5.7171 | Reduce | 50% | 11.4342 | 5.7171 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Local customer Engineers in country | Person_455 | 2018-12-20 01:00 | 2021-05-22 | 5% | 0.79775 | 0.039887 | Accept | 5% | 0.79775 | 0.039887 | H2 | 2 | Stable | TRUE | 883.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 | 10% | 0.81199 | 0.081199 | Accept | 5% | 0.81199 | 0.0406 | H3 | 3 | Stable | FALSE | 818 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 10% | 0.81199 | 0.081199 | Accept | 5% | 0.81199 | 0.0406 | H3 | 3 | Stable | FALSE | 818.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 10% | 0.81199 | 0.081199 | Accept | 5% | 0.81199 | 0.0406 | H3 | 3 | Stable | FALSE | 818.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 10% | 0.81199 | 0.081199 | Accept | 5% | 0.81199 | 0.0406 | H3 | 3 | Stable | FALSE | 818.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 10% | 0.81199 | 0.081199 | Accept | 5% | 0.81199 | 0.0406 | H3 | 3 | Stable | FALSE | 818.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 10% | 0.81199 | 0.081199 | Accept | 5% | 0.81199 | 0.0406 | H3 | 3 | Stable | FALSE | 818.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 10% | 0.81199 | 0.081199 | Accept | 5% | 0.81199 | 0.0406 | H3 | 3 | Stable | FALSE | 818.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-060 | Project_028_Risk-060 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Further Software Development | Person_542 | 2015-05-24 | 2017-08-19 01:00 | 10% | 0.81199 | 0.081199 | Accept | 5% | 0.81199 | 0.0406 | H3 | 3 | Stable | FALSE | 818.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK273 | Project_024_RISK273 | Threat | Project Contingency | Open | H1 | 1 |  | Win 7 update to Win 10 OS | Person_318 | 2016-09-20 01:00 | 2017-06-23 | 40% | 15.5796 | 6.2318 | Accept | 40% | 15.5796 | 6.2318 | H1 | 1 | -- | TRUE | 275.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK273 | Project_024_RISK273 | Threat | Project Contingency | Open | H1 | 1 |  | Win 7 update to Win 10 OS | Person_318 | 2016-09-20 01:00 | 2017-06-23 | 40% | 15.5796 | 6.2318 | Accept | 40% | 15.5796 | 6.2318 | H1 | 1 | -- | TRUE | 275.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-022 | Project_026_Risk-022 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Availability of platform Systems/Equipment for Training | Person_525 | 2016-10-21 01:00 | 2017-05-22 | 20% | 0.20519 | 0.041037 | Reduce | 20% | 0.20519 | 0.041037 | H3 | 3 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-022 | Project_026_Risk-022 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Availability of platform Systems/Equipment for Training | Person_525 | 2016-10-21 01:00 | 2017-05-22 | 20% | 0.20519 | 0.041037 | Reduce | 20% | 0.20519 | 0.041037 | H3 | 3 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-022 | Project_026_Risk-022 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Availability of platform Systems/Equipment for Training | Person_525 | 2016-10-21 01:00 | 2017-05-22 | 20% | 0.20519 | 0.041037 | Reduce | 20% | 0.20519 | 0.041037 | H3 | 3 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-022 | Project_026_Risk-022 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Availability of platform Systems/Equipment for Training | Person_525 | 2016-10-21 01:00 | 2017-05-22 | 20% | 0.20519 | 0.041037 | Reduce | 20% | 0.20519 | 0.041037 | H3 | 3 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 20% | 2.5604 | 0.51208 | Reduce | 2% | 2.0527 | 0.041055 | H2 | 2 | Improving | TRUE | 243.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-06-22 | 20% | 2.5604 | 0.51208 | Reduce | 2% | 2.0527 | 0.041055 | H2 | 2 | Improving | TRUE | 243.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 20% | 0.41055 | 0.082109 | Reduce | 10% | 0.41055 | 0.041055 | H2 | 2 | Improving | TRUE | 130 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 20% | 0.41055 | 0.082109 | Reduce | 10% | 0.41055 | 0.041055 | H2 | 2 | Improving | TRUE | 130 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 20% | 0.41055 | 0.082109 | Reduce | 10% | 0.41055 | 0.041055 | H2 | 2 | Improving | TRUE | 130 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK005 | Project_086_RISK005 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Trainer Learning Curve | Person_120 | 2017-11-22 01:00 | 2018-10-21 01:00 | 50% | 0.27801 | 0.139 | Reduce | 20% | 0.21153 | 0.042305 | H2 | 2 | -- | TRUE | 333 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK054 | Project_097_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Obsolescence - Picture of obsolescence changes between estimation and realisation | Person_574 | 2018-08-22 01:00 | 2019-10-22 01:00 | 30% | 0.17182 | 0.051545 | Reduce | 25% | 0.17182 | 0.042954 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 15% | 0.28639 | 0.042959 | -- | 15% | 0.28639 | 0.042959 | H2 | 2 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 | 15% | 0.28639 | 0.042959 | -- | 15% | 0.28639 | 0.042959 | H2 | 2 | Stable | TRUE | 213 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 | 15% | 0.28639 | 0.042959 | -- | 15% | 0.28639 | 0.042959 | H2 | 2 | Stable | TRUE | 213 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 15% | 0.28639 | 0.042959 | -- | 15% | 0.28639 | 0.042959 | H2 | 2 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 15% | 0.28639 | 0.042959 | -- | 15% | 0.28639 | 0.042959 | H2 | 2 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-122 | Project_011_Risk-122 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Reduce PR Fixing time in Test and Acceptance | Person_187 | 2016-07-21 | 2017-02-19 01:00 | 15% | 0.28639 | 0.042959 | -- | 15% | 0.28639 | 0.042959 | H2 | 2 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK273 | Project_024_RISK273 | Threat | Project Contingency | Open | H1 | 1 |  | Win 7 update to Win 10 OS | Person_318 | 2016-09-20 01:00 | 2017-06-23 | 40% | 15.5796 | 6.2318 | Accept | 40% | 15.5796 | 6.2318 | H1 | 1 | -- | TRUE | 275.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK273 | Project_024_RISK273 | Threat | Project Contingency | Open | H1 | 1 |  | Win 7 update to Win 10 OS | Person_318 | 2016-09-20 01:00 | 2017-06-23 | 40% | 15.5796 | 6.2318 | Accept | 40% | 15.5796 | 6.2318 | H1 | 1 | -- | TRUE | 275.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK273 | Project_024_RISK273 | Threat | Project Contingency | Open | H1 | 1 |  | Win 7 update to Win 10 OS | Person_318 | 2016-09-20 01:00 | 2017-06-23 | 40% | 15.5796 | 6.2318 | Accept | 40% | 15.5796 | 6.2318 | H1 | 1 | -- | TRUE | 275.9583 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK026 | Project_058_RISK026 | Threat | Project Contingency | Open | H1 | 1 |  | Liquidated Damages | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 80% | 7.8295 | 6.2636 | Reduce | 80% | 7.8295 | 6.2636 | H1 | 1 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H1 | 1 |  | Technical Acceptance proves to be more difficult than anticipated | Person_470 | 2013-09-20 | 2017-01-20 | 60% | 12.6474 | 7.5885 | Reduce | 50% | 12.6474 | 6.3237 | H1 | 1 | Stable | TRUE | 1218 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-066 | Project_026_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Environmental Case | Person_364 | 2015-05-24 | 2018-12-27 01:00 | 30% | 0.44768 | 0.1343 | Reduce | 10% | 0.44768 | 0.044768 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-066 | Project_026_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Environmental Case | Person_364 | 2015-05-24 | 2018-12-27 01:00 | 30% | 0.44768 | 0.1343 | Reduce | 10% | 0.44768 | 0.044768 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-066 | Project_026_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Environmental Case | Person_364 | 2015-05-24 | 2018-12-27 01:00 | 30% | 0.44768 | 0.1343 | Reduce | 10% | 0.44768 | 0.044768 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-066 | Project_026_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Environmental Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 30% | 0.44768 | 0.1343 | Reduce | 10% | 0.44768 | 0.044768 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-066 | Project_026_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Environmental Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 30% | 0.44768 | 0.1343 | Reduce | 10% | 0.44768 | 0.044768 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-066 | Project_026_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Environmental Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 30% | 0.44768 | 0.1343 | Reduce | 10% | 0.44768 | 0.044768 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-066 | Project_026_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Environmental Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 30% | 0.44768 | 0.1343 | Reduce | 10% | 0.44768 | 0.044768 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-066 | Project_026_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Environmental Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 30% | 0.44768 | 0.1343 | Reduce | 10% | 0.44768 | 0.044768 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK027 | Project_097_RISK027 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SW Uplift - Must-Fix Defects are identified during roll-out period. | Person_667 | 2019-10-22 01:00 | 2020-01-22 01:00 | 10% | 0.90204 | 0.090204 | Reduce | 5% | 0.90204 | 0.045102 | H2 | 2 | Stable | TRUE | 92 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK019 | Project_097_RISK019 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | SW Uplift - Significant Defect Identified | Person_669 | 2018-12-14 01:00 | 2019-07-21 | 20% | 0.91814 | 0.18363 | Reduce | 5% | 0.91814 | 0.045907 | H2 | 2 | -- | TRUE | 218.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1008 | Project_091_RISK1008 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Late supplier delivery of components could impact customer deliveries | Person_261 | 2018-09-21 01:00 | 2026-05-21 | 70% | 0.15989 | 0.11192 | Reduce | 30% | 0.15989 | 0.047966 | H2 | 2 | -- | TRUE | 2798.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 20% | 0.24207 | 0.048414 | -- | 20% | 0.24207 | 0.048414 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 20% | 0.24207 | 0.048414 | -- | 20% | 0.24207 | 0.048414 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 20% | 0.24207 | 0.048414 | -- | 20% | 0.24207 | 0.048414 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H1 | 1 |  | Technical Acceptance proves to be more difficult than anticipated | Person_470 | 2013-09-19 23:00 | 2017-01-19 23:00 | 60% | 12.6474 | 7.5885 | Reduce | 50% | 12.6474 | 6.3237 | H1 | 1 | Stable | TRUE | 1218 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | Stable | TRUE | 183.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | Stable | TRUE | 183.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | Stable | TRUE | 183.0417 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | Stable | TRUE | 183.0417 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | Stable | TRUE | 242.0417 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-07-21 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | Stable | TRUE | 183.0417 |  | 1 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | Stable | TRUE | 242 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | Stable | TRUE | 242.0417 |  | 1 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H3 | 3 | Stable | FALSE | 242.0417 |  | 1 | 1 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_279 | 2017-05-23 | 2018-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK042 | Project_017_RISK042 | Threat | Project Contingency | Open | H1 | 1 |  | Short supplier validities due to uncertain market conditions | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 45% | 15.0654 | 6.7794 | Accept | 45% | 15.0654 | 6.7794 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK042 | Project_017_RISK042 | Threat | Project Contingency | Open | H1 | 1 |  | Short supplier validities due to uncertain market conditions | Person_374 | 2016-01-22 01:00 | 2023-02-20 01:00 | 45% | 15.0654 | 6.7794 | Accept | 45% | 15.0654 | 6.7794 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK042 | Project_017_RISK042 | Threat | Project Contingency | Open | H1 | 1 |  | Short supplier validities due to uncertain market conditions | Person_374 | 2016-01-22 | 2023-02-20 | 45% | 15.0654 | 6.7794 | Accept | 45% | 15.0654 | 6.7794 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK042 | Project_017_RISK042 | Threat | Project Contingency | Open | H1 | 1 |  | Short supplier validities due to uncertain market conditions | Person_374 | 2016-01-22 | 2023-02-20 | 45% | 15.0654 | 6.7794 | Accept | 45% | 15.0654 | 6.7794 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK042 | Project_017_RISK042 | Threat | Project Contingency | Open | H1 | 1 |  | Short supplier validities due to uncertain market conditions | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 45% | 15.0654 | 6.7794 | Accept | 45% | 15.0654 | 6.7794 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK042 | Project_017_RISK042 | Threat | Project Contingency | Open | H1 | 1 |  | Short supplier validities due to uncertain market conditions | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 45% | 15.0654 | 6.7794 | Accept | 45% | 15.0654 | 6.7794 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK042 | Project_017_RISK042 | Threat | Project Contingency | Open | H1 | 1 |  | Short supplier validities due to uncertain market conditions | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 45% | 15.0654 | 6.7794 | Accept | 45% | 15.0654 | 6.7794 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK042 | Project_017_RISK042 | Threat | Project Contingency | Open | H1 | 1 |  | Short supplier validities due to uncertain market conditions | Person_374 | 2016-01-21 21:00 | 2023-02-19 21:00 | 45% | 15.0654 | 6.7794 | Accept | 45% | 15.0654 | 6.7794 | H1 | 1 | -- | TRUE | 2586 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK024 | Project_079_RISK024 | Threat | Project Contingency | Open | H1 | 1 |  | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 50% | 14.4992 | 7.2496 | Reduce | 50% | 14.4992 | 7.2496 | H1 | 1 | Stable | TRUE | 809.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK024 | Project_079_RISK024 | Threat | Project Contingency | Open | H1 | 1 |  | Procurement/Supply chain and lead time on parts | Person_261 | 2018-02-02 01:00 | 2020-04-22 | 50% | 14.4992 | 7.2496 | Reduce | 50% | 14.4992 | 7.2496 | H1 | 1 | Stable | TRUE | 809.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 1 |  | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 50% | 15.0863 | 7.5431 | Accept | 50% | 15.0863 | 7.5431 | H1 | 1 | Worsening | TRUE | 303.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 1 |  | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 50% | 15.0863 | 7.5431 | Accept | 50% | 15.0863 | 7.5431 | H1 | 1 | Worsening | TRUE | 303.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 1 |  | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 50% | 15.0863 | 7.5431 | Accept | 50% | 15.0863 | 7.5431 | H1 | 1 | Worsening | TRUE | 303.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 1 |  | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 50% | 15.0863 | 7.5431 | Reduce | 50% | 15.0863 | 7.5431 | H1 | 1 | Worsening | TRUE | 303.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 1 |  | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 50% | 15.0863 | 7.5431 | Reduce | 50% | 15.0863 | 7.5431 | H1 | 1 | Worsening | TRUE | 303.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK219 | Project_024_RISK219 | Threat | Project Contingency | Open | H1 | 1 |  | STTE additional work | Person_289 | 2016-09-20 01:00 | 2017-07-21 | 50% | 15.0863 | 7.5431 | Reduce | 50% | 15.0863 | 7.5431 | H1 | 1 | Worsening | TRUE | 303.9583 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK017 | Project_058_RISK017 | Threat | Project Contingency | Open | H1 | 1 |  | Supplier late deliveries | Person_294 | 2017-12-29 01:00 | 2019-08-21 01:00 | 80% | 9.7869 | 7.8295 | -- | 80% | 9.7869 | 7.8295 | H1 | 1 | -- | TRUE | 600 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-026 | Project_077_T-026 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Insufficient Config Option capacity | Person_544 | 2018-04-22 | 2020-02-21 01:00 | 20% | 1.0019 | 0.20038 | Avoid | 5% | 1.0019 | 0.050095 | H3 | 3 | Stable | FALSE | 670.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unidentified Change Requests | Person_368 | 2016-11-20 01:00 | 2017-09-20 01:00 | 50% | 1.2005 | 0.60023 | Reduce | 10% | 0.51019 | 0.051019 | H3 | 3 | -- | FALSE | 304 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-20 01:00 | 2017-09-20 01:00 | 50% | 1.2005 | 0.60023 | Reduce | 10% | 0.51019 | 0.051019 | H3 | 3 | Stable | FALSE | 304 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-20 | 2017-09-20 | 50% | 1.2005 | 0.60023 | Reduce | 10% | 0.51019 | 0.051019 | H3 | 3 | Stable | FALSE | 304 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-19 23:00 | 2017-09-19 23:00 | 50% | 1.2005 | 0.60023 | Reduce | 10% | 0.51019 | 0.051019 | H3 | 3 | Stable | FALSE | 304 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-19 23:00 | 2017-09-19 23:00 | 50% | 1.2005 | 0.60023 | Reduce | 10% | 0.51019 | 0.051019 | H3 | 3 | Stable | FALSE | 304 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-19 23:00 | 2017-09-19 23:00 | 50% | 1.2005 | 0.60023 | Reduce | 10% | 0.51019 | 0.051019 | H3 | 3 | Stable | FALSE | 304 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R09 | Project_041_R09 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unidentified Change Requests | Person_693 | 2016-11-19 22:00 | 2017-09-19 22:00 | 50% | 1.2005 | 0.60023 | Reduce | 10% | 0.51019 | 0.051019 | H3 | 3 | Stable | FALSE | 304 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-108 | Project_039_Risk-108 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Product Redesign | Person_224 | 2015-06-24 | 2015-11-21 01:00 | 30% | 0.42929 | 0.12879 | Reduce | 10% | 0.51515 | 0.051515 | H3 | 3 | Stable | TRUE | 150.0417 |  | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK055 | Project_075_RISK055 | Opportunitity | Project Contingency | Open | H1 | 1 |  | There is an opportunity to buy back the 2-off delivered units from the customer | Person_627 | 2018-09-15 01:00 | 2019-05-16 | 70% | 11.8119 | 8.2683 | Exploit | 70% | 11.8119 | 8.2683 | H1 | 1 | -- | TRUE | 242.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R010 | Project_044_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Line of sight | Person_044 | 2017-11-20 01:00 | 2019-06-23 | 15% | 1.0503 | 0.15755 | Reduce | 5% | 1.0503 | 0.052517 | H3 | 3 | Stable | FALSE | 579.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 | 2017-03-21 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 402 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-12 23:00 | 2017-03-20 23:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 402 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2017-03-21 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 402 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 | 2016-11-19 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 280 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2016-11-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 280 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2016-12-20 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 311 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2016-12-20 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 311 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2017-03-21 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 402 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2017-05-07 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 448.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2017-05-07 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 448.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_766 | 2016-02-13 01:00 | 2017-05-07 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 448.9583 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 | 2017-05-07 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 449 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2017-05-07 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 448.9583 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H3 | 3 | Stable | TRUE | 706 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 706 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 706 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 706 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 706 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 706 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 706 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R019 | Project_021_Risk-R019 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_482 | 2016-02-13 01:00 | 2018-01-19 01:00 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 706 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 395.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 395.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 395.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 395.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 395.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 395.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 395.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--02 | Project_021_Risk--02 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact from Regulations | Person_061 | 2018-02-20 01:00 | 2019-03-23 | 30% | 2.6487 | 0.7946 | Reduce | 10% | 0.52974 | 0.052974 | H2 | 2 | Stable | TRUE | 395.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK073 | Project_076_RISK073 | Threat | Project Contingency | Open | H1 | 1 |  | Competence Centre Level of effort | Person_152 | 2018-05-23 | 2018-12-22 01:00 | 70% | 16.5844 | 11.6091 | Accept | 70% | 16.5844 | 11.6091 | H1 | 1 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK010 | Project_075_RISK010 | Threat | Project Contingency | Open | H1 | 1 |  | We do not achieve Standard compliant energy over temperature | Person_449 | 2017-07-21 | 2018-09-20 01:00 | 50% | 26.0143 | 13.0071 | Accept | 50% | 26.0143 | 13.0071 | H1 | 1 | Stable | TRUE | 426.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK010 | Project_075_RISK010 | Threat | Project Contingency | Open | H1 | 1 |  | We do not achieve Standard compliant energy over temperature | Person_449 | 2017-07-21 | 2018-09-20 01:00 | 50% | 26.0143 | 13.0071 | Accept | 50% | 26.0143 | 13.0071 | H1 | 1 | Stable | TRUE | 426.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK010 | Project_075_RISK010 | Threat | Project Contingency | Open | H1 | 1 |  | We do not achieve Standard compliant energy over temperature | Person_449 | 2017-07-21 | 2018-09-20 01:00 | 50% | 26.0143 | 13.0071 | Accept | 50% | 26.0143 | 13.0071 | H1 | 1 | Stable | TRUE | 426.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK010 | Project_075_RISK010 | Threat | Project Contingency | Open | H1 | 1 |  | We do not achieve Standard compliant energy over temperature | Person_449 | 2017-07-21 | 2018-09-20 01:00 | 50% | 26.0143 | 13.0071 | Accept | 50% | 26.0143 | 13.0071 | H1 | 1 | Stable | TRUE | 426.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK282 | Project_024_RISK282 | Threat | Project Contingency | Open | H1 | 1 |  | Acceptance Technical Debt | Person_290 | 2011-04-22 | 2019-05-23 | 66% | 29.1079 | 19.2112 | Accept | 51% | 29.1079 | 14.845 | H1 | 1 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK282 | Project_024_RISK282 | Threat | Project Contingency | Open | H1 | 1 |  | Acceptance Technical Debt | Person_290 | 2011-04-22 | 2019-05-23 | 66% | 29.1079 | 19.2112 | Accept | 51% | 29.1079 | 14.845 | H1 | 1 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK282 | Project_024_RISK282 | Threat | Project Contingency | Open | H1 | 1 |  | Acceptance Technical Debt | Person_290 | 2011-04-22 | 2018-05-22 | 66% | 29.1079 | 19.2112 | Accept | 51% | 29.1079 | 14.845 | H1 | 1 | -- | TRUE | 2587 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK282 | Project_024_RISK282 | Threat | Project Contingency | Open | H1 | 1 |  | Acceptance Technical Debt | Person_290 | 2011-04-22 | 2019-05-23 | 66% | 29.1079 | 19.2112 | Accept | 51% | 29.1079 | 14.845 | H1 | 1 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK282 | Project_024_RISK282 | Threat | Project Contingency | Open | H1 | 1 |  | Acceptance Technical Debt | Person_290 | 2016-07-20 | 2017-03-22 | 66% | 29.1079 | 19.2112 | Accept | 51% | 29.1079 | 14.845 | H1 | 1 | -- | TRUE | 245 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 30% | 5.4459 | 1.6338 | Accept | 30% | 0.18151 | 0.054453 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 30% | 5.4459 | 1.6338 | Accept | 30% | 0.18151 | 0.054453 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 30% | 5.4459 | 1.6338 | Accept | 30% | 0.18151 | 0.054453 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 30% | 5.4459 | 1.6338 | Accept | 30% | 0.18151 | 0.054453 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 30% | 5.4459 | 1.6338 | Accept | 30% | 0.18151 | 0.054453 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2016-06-22 | 30% | 5.4459 | 1.6338 | Accept | 30% | 0.18151 | 0.054453 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2017-01-20 01:00 | 30% | 5.4459 | 1.6338 | Accept | 30% | 0.18151 | 0.054453 | H2 | 2 | Stable | TRUE | 456 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-016 | Project_023_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Damage to equipment (Unable to replace due to obsolescence) | Person_703 | 2015-10-22 01:00 | 2017-01-20 01:00 | 30% | 5.4459 | 1.6338 | Accept | 30% | 0.18151 | 0.054453 | H2 | 2 | Stable | TRUE | 456 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO23 | Project_021_Risk-RO23 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Facility Maintenance Team Costs | Person_126 | 2001-05-23 | 2018-02-19 01:00 | 100% | 14.8988 | 14.8988 | -- | 100% | 14.8988 | 14.8988 | H1 | 1 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO23 | Project_021_Risk-RO23 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Facility Maintenance Team Costs | Person_126 | 2001-05-23 | 2018-02-19 01:00 | 100% | 14.8988 | 14.8988 | -- | 100% | 14.8988 | 14.8988 | H1 | 1 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_661 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_661 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_661 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_661 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_661 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_661 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_661 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_020 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_661 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_020 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_020 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK486 | Project_065_RISK486 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Issues experienced during EMC testing cannot be resolved within 1 month | Person_020 | 2020-04-19 | 2020-05-02 | 20% | 3.0073 | 0.60145 | Reduce | 5% | 1.1115 | 0.055575 | H3 | 3 | -- | FALSE | 13 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-184 | Project_026_Risk-184 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Repeat Trials | Person_272 | 2018-05-23 | 2018-11-14 01:00 | 10% | 0.5596 | 0.05596 | Accept | 10% | 0.5596 | 0.05596 | H3 | 3 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-184 | Project_026_Risk-184 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Repeat Trials | Person_272 | 2018-05-23 | 2018-11-14 01:00 | 10% | 0.5596 | 0.05596 | Accept | 10% | 0.5596 | 0.05596 | H3 | 3 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-184 | Project_026_Risk-184 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Repeat Trials | Person_272 | 2018-05-23 | 2018-11-14 01:00 | 10% | 0.5596 | 0.05596 | Accept | 10% | 0.5596 | 0.05596 | H3 | 3 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-184 | Project_026_Risk-184 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Repeat Trials | Person_272 | 2018-05-23 | 2018-11-14 01:00 | 10% | 0.5596 | 0.05596 | Accept | 10% | 0.5596 | 0.05596 | H3 | 3 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-184 | Project_026_Risk-184 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Repeat Trials | Person_272 | 2018-05-23 | 2018-11-14 01:00 | 10% | 0.5596 | 0.05596 | Accept | 10% | 0.5596 | 0.05596 | H3 | 3 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-184 | Project_026_Risk-184 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Repeat Trials | Person_272 | 2018-05-23 | 2018-11-14 01:00 | 10% | 0.5596 | 0.05596 | Accept | 10% | 0.5596 | 0.05596 | H3 | 3 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-184 | Project_026_Risk-184 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Repeat Trials | Person_272 | 2018-05-23 | 2018-11-14 01:00 | 10% | 0.5596 | 0.05596 | Accept | 10% | 0.5596 | 0.05596 | H3 | 3 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-184 | Project_026_Risk-184 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Repeat Trials | Person_272 | 2018-05-23 | 2018-11-14 01:00 | 10% | 0.5596 | 0.05596 | Accept | 10% | 0.5596 | 0.05596 | H3 | 3 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO23 | Project_021_Risk-RO23 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Facility Maintenance Team Costs | Person_126 | 2001-05-23 | 2018-02-19 01:00 | 100% | 14.8988 | 14.8988 | -- | 100% | 14.8988 | 14.8988 | H1 | 1 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO23 | Project_021_Risk-RO23 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Facility Maintenance Team Costs | Person_126 | 2001-05-23 | 2018-02-19 | 100% | 14.8988 | 14.8988 | -- | 100% | 14.8988 | 14.8988 | H1 | 1 | -- | TRUE | 6116 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO23 | Project_021_Risk-RO23 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Facility Maintenance Team Costs | Person_126 | 2001-05-23 | 2018-02-19 01:00 | 100% | 14.8988 | 14.8988 | -- | 100% | 14.8988 | 14.8988 | H1 | 1 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO23 | Project_021_Risk-RO23 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Facility Maintenance Team Costs | Person_126 | 2001-05-23 | 2018-02-19 01:00 | 100% | 14.8988 | 14.8988 | -- | 100% | 14.8988 | 14.8988 | H1 | 1 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO23 | Project_021_Risk-RO23 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Facility Maintenance Team Costs | Person_126 | 2001-05-23 | 2018-02-19 01:00 | 100% | 14.8988 | 14.8988 | -- | 100% | 14.8988 | 14.8988 | H1 | 1 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK010 | Project_092_RISK010 | Threat | Project Contingency | Open | H1 | 1 |  | Material estimate is incorrect | Person_579 | 2018-02-20 01:00 | 2033-05-22 | 70% | 21.5664 | 15.0965 | Reduce | 70% | 21.5664 | 15.0965 | H1 | 1 | -- | TRUE | 5569.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extension | Person_428 | 2009-06-23 | 2017-05-21 | 70% | 32.645 | 22.8515 | Reduce | 50% | 32.645 | 16.3225 | H1 | 1 | Stable | TRUE | 2889 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | POPRisk-R65 | Project_021_POPRisk-R65 | Threat | Project Contingency | Open | H1 | 1 |  | Programme extension | Person_428 | 2009-06-23 | 2017-05-21 | 70% | 32.645 | 22.8515 | Reduce | 50% | 32.645 | 16.3225 | H1 | 1 | Stable | TRUE | 2889 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK401 | Project_038_RISK401 | Threat | Project Contingency | Open | H1 | 1 |  | System Cable | Person_663 | 2016-09-19 01:00 | 2017-05-15 | 80% | 26.0685 | 20.8548 | -- | 90% | 19.7761 | 17.7985 | H1 | 1 | -- | TRUE | 237.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK401 | Project_038_RISK401 | Threat | Project Contingency | Open | H1 | 1 |  | System Cable | Person_663 | 2016-09-19 01:00 | 2017-05-15 | 80% | 26.0685 | 20.8548 | -- | 90% | 19.7761 | 17.7985 | H1 | 1 | -- | TRUE | 237.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK401 | Project_038_RISK401 | Threat | Project Contingency | Open | H1 | 1 |  | System Cable | Person_663 | 2016-09-19 01:00 | 2017-05-15 | 80% | 26.0685 | 20.8548 | -- | 90% | 19.7761 | 17.7985 | H1 | 1 | -- | TRUE | 237.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK401 | Project_038_RISK401 | Threat | Project Contingency | Open | H1 | 1 |  | System Cable | Person_663 | 2016-09-19 01:00 | 2017-05-15 | 80% | 26.0685 | 20.8548 | -- | 90% | 19.7761 | 17.7985 | H1 | 1 | -- | TRUE | 237.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK010 | Project_041_RISK010 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Digital Assembly - Testing | Person_547 | 2018-04-11 | 2019-05-16 | 15% | 0.57879 | 0.086819 | Accept | 10% | 0.57879 | 0.057879 | H3 | 3 | Improving | FALSE | 400 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R025 | Project_044_Risk-R025 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Obsolescence | Person_044 | 2017-11-20 01:00 | 2019-02-10 01:00 | 20% | 1.1831 | 0.23663 | Reduce | 5% | 1.1831 | 0.059157 | H3 | 3 | Stable | FALSE | 447 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-20 01:00 | 2017-08-20 01:00 | 50% | 0.59165 | 0.29583 | Reduce | 10% | 0.59165 | 0.059165 | H3 | 3 | -- | FALSE | 273 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-20 01:00 | 2017-08-20 01:00 | 50% | 0.59165 | 0.29583 | Reduce | 10% | 0.59165 | 0.059165 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-20 01:00 | 2017-08-20 01:00 | 50% | 0.59165 | 0.29583 | Reduce | 10% | 0.59165 | 0.059165 | H3 | 3 | -- | FALSE | 273 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-20 | 2017-08-20 | 50% | 0.59165 | 0.29583 | Reduce | 10% | 0.59165 | 0.059165 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-19 23:00 | 2017-08-19 23:00 | 50% | 0.59165 | 0.29583 | Reduce | 10% | 0.59165 | 0.059165 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-19 23:00 | 2017-08-19 23:00 | 50% | 0.59165 | 0.29583 | Reduce | 10% | 0.59165 | 0.059165 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-19 23:00 | 2017-08-19 23:00 | 50% | 0.59165 | 0.29583 | Reduce | 10% | 0.59165 | 0.059165 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R13 | Project_041_R13 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Loss of key personnel | Person_359 | 2016-11-19 22:00 | 2017-08-19 22:00 | 50% | 0.59165 | 0.29583 | Reduce | 10% | 0.59165 | 0.059165 | H3 | 3 | Stable | FALSE | 273 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK401 | Project_038_RISK401 | Threat | Project Contingency | Open | H1 | 1 |  | System Cable | Person_663 | 2016-09-19 01:00 | 2017-05-15 | 80% | 26.0685 | 20.8548 | -- | 90% | 19.7761 | 17.7985 | H1 | 1 | -- | TRUE | 237.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK282 | Project_024_RISK282 | Threat | Project Contingency | Open | H1 | 1 |  | Acceptance Technical Debt | Person_290 | 2011-04-22 | 2019-05-23 | 66% | 29.1079 | 19.2112 | -- | 66% | 29.1079 | 19.2112 | H1 | 1 | -- | TRUE | 2953 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK401 | Project_038_RISK401 | Threat | Project Contingency | Open | H1 | 1 |  | System Cable | Person_330 | 2016-09-19 01:00 | 2017-05-15 | 80% | 26.0685 | 20.8548 | -- | 80% | 26.0685 | 20.8548 | H1 | 1 | -- | TRUE | 237.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK487 | Project_065_RISK487 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Informal integration and testing highlight issues that need to be addressed | Person_661 | 2020-04-19 | 2020-05-02 | 50% | 4.0321 | 2.016 | Reduce | 5% | 1.2261 | 0.061307 | H3 | 3 | -- | TRUE | 13 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 20% | 0.30685 | 0.06137 | Accept | 20% | 0.30685 | 0.06137 | H2 | 2 | Stable | TRUE | 789 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 20% | 0.30685 | 0.06137 | Accept | 20% | 0.30685 | 0.06137 | H2 | 2 | Stable | TRUE | 789 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 20% | 0.30685 | 0.06137 | Accept | 20% | 0.30685 | 0.06137 | H2 | 2 | Stable | TRUE | 789 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 20% | 0.30685 | 0.06137 | Accept | 20% | 0.30685 | 0.06137 | H2 | 2 | Stable | TRUE | 789 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 20% | 0.30685 | 0.06137 | Accept | 20% | 0.30685 | 0.06137 | H2 | 2 | Stable | TRUE | 789 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-103 | Project_011_Risk-103 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unreliability of Hardware | Person_230 | 2016-06-23 | 2018-08-21 | 20% | 0.30685 | 0.06137 | Accept | 20% | 0.30685 | 0.06137 | H2 | 2 | Stable | TRUE | 789 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk309 | Project_009_Risk309 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Obsolescence | Person_284 | 2015-08-16 | 2016-09-19 01:00 | 10% | 0.63985 | 0.063985 | Accept | 9.7% | 0.63985 | 0.062065 | H3 | 3 | -- | TRUE | 400.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK065 | Project_076_RISK065 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Safety Analysis Feedback Delay | Person_771 | 2018-05-23 | 2020-05-23 | 30% | 0.41461 | 0.12438 | Reduce | 15% | 0.41461 | 0.062191 | H3 | 3 | -- | TRUE | 731 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK065 | Project_076_RISK065 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Safety Analysis Feedback Delay | Person_771 | 2018-05-23 | 2020-05-23 | 30% | 0.41461 | 0.12438 | Reduce | 15% | 0.41461 | 0.062191 | H3 | 3 | -- | TRUE | 731 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK065 | Project_076_RISK065 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Safety Analysis Feedback Delay | Person_771 | 2018-05-23 | 2020-05-23 | 30% | 0.41461 | 0.12438 | Reduce | 15% | 0.41461 | 0.062191 | H3 | 3 | -- | TRUE | 731 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-046 | Project_026_Risk-046 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Accreditation | Person_519 | 2014-11-21 01:00 | 2018-12-27 01:00 | 15% | 0.67152 | 0.10073 | Reduce | 10% | 0.67152 | 0.067152 | H2 | 2 | -- | TRUE | 1497 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-046 | Project_026_Risk-046 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Accreditation | Person_519 | 2014-11-21 01:00 | 2018-12-27 01:00 | 15% | 0.67152 | 0.10073 | Reduce | 10% | 0.67152 | 0.067152 | H2 | 2 | -- | TRUE | 1497 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-046 | Project_026_Risk-046 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Accreditation | Person_519 | 2014-11-21 01:00 | 2018-12-27 01:00 | 15% | 0.67152 | 0.10073 | Reduce | 10% | 0.67152 | 0.067152 | H2 | 2 | -- | TRUE | 1497 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-046 | Project_026_Risk-046 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Accreditation | Person_519 | 2014-11-21 01:00 | 2018-12-27 01:00 | 15% | 0.67152 | 0.10073 | Reduce | 10% | 0.67152 | 0.067152 | H2 | 2 | -- | TRUE | 1497 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-046 | Project_026_Risk-046 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Accreditation | Person_519 | 2014-11-21 01:00 | 2018-12-27 01:00 | 15% | 0.67152 | 0.10073 | Reduce | 10% | 0.67152 | 0.067152 | H2 | 2 | -- | TRUE | 1497 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-046 | Project_026_Risk-046 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Accreditation | Person_519 | 2014-11-21 01:00 | 2018-12-27 01:00 | 15% | 0.67152 | 0.10073 | Reduce | 10% | 0.67152 | 0.067152 | H2 | 2 | -- | TRUE | 1497 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-046 | Project_026_Risk-046 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Accreditation | Person_519 | 2014-11-21 01:00 | 2018-12-27 01:00 | 15% | 0.67152 | 0.10073 | Reduce | 10% | 0.67152 | 0.067152 | H2 | 2 | -- | TRUE | 1497 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-046 | Project_026_Risk-046 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Accreditation | Person_519 | 2014-11-21 01:00 | 2018-12-27 01:00 | 15% | 0.67152 | 0.10073 | Reduce | 10% | 0.67152 | 0.067152 | H2 | 2 | -- | TRUE | 1497 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK003 | Project_086_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Qualification | Person_528 | 2017-11-22 01:00 | 2018-10-21 01:00 | 30% | 0.33844 | 0.10153 | Reduce | 20% | 0.33844 | 0.067689 | H2 | 2 | Worsening | TRUE | 333 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK004 | Project_086_RISK004 | Threat | Project Contingency | Open | H2 | 2 | Customers | Problems with Customer Delivery | Person_528 | 2017-11-22 01:00 | 2018-11-20 01:00 | 20% | 0.33844 | 0.067689 | Accept | 20% | 0.33844 | 0.067689 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 2 | Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2016-07-21 | 2018-05-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 2 | Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2016-07-21 | 2018-05-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 2 | Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2016-07-21 | 2018-05-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 669 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 2 | Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 211.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 2 | Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 211.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-106 | Project_011_Risk-106 | Threat | Project Contingency | Open | H2 | 2 | Customers | Payload Fidelity | Person_187 | 2016-07-21 | 2018-08-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-110 | Project_011_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Fidelity of Failures post Factory Acceptance Test | Person_140 | 2017-10-21 01:00 | 2018-05-21 | 40% | 0.1699 | 0.067961 | -- | 40% | 0.1699 | 0.067961 | H2 | 2 | Stable | TRUE | 211.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK170 | Project_024_RISK170 | Threat | Project Contingency | Open | H1 | 1 |  | Engineering team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 30.562 | 24.4496 | -- | 80% | 30.562 | 24.4496 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK170 | Project_024_RISK170 | Threat | Project Contingency | Open | H1 | 1 |  | Engineering team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 30.562 | 24.4496 | Accept | 80% | 30.562 | 24.4496 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK170 | Project_024_RISK170 | Threat | Project Contingency | Open | H1 | 1 |  | Engineering team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 30.562 | 24.4496 | Accept | 80% | 30.562 | 24.4496 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-322 | Project_032_Risk-322 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data/Information Management Systems and Technology Toolset | Person_629 | 2016-04-08 | 2017-08-20 01:00 | 33% | 0.20788 | 0.068599 | Accept | 33% | 0.20788 | 0.068599 | H2 | 2 | -- | TRUE | 499.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-322 | Project_032_Risk-322 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data/Information Management Systems and Technology Toolset | Person_629 | 2016-04-08 | 2017-08-20 | 33% | 0.20788 | 0.068599 | Accept | 33% | 0.20788 | 0.068599 | H2 | 2 | -- | TRUE | 499 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-322 | Project_032_Risk-322 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data/Information Management Systems and Technology Toolset | Person_629 | 2016-04-08 | 2017-08-20 | 33% | 0.20788 | 0.068599 | Accept | 33% | 0.20788 | 0.068599 | H2 | 2 | -- | TRUE | 499 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-322 | Project_032_Risk-322 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Data/Information Management Systems and Technology Toolset | Person_629 | 2016-04-08 | 2017-08-20 | 33% | 0.20788 | 0.068599 | Accept | 33% | 0.20788 | 0.068599 | H2 | 2 | -- | TRUE | 499 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK170 | Project_024_RISK170 | Threat | Project Contingency | Open | H1 | 1 |  | Engineering team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 30.562 | 24.4496 | Accept | 80% | 30.562 | 24.4496 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Source Change | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 10% | 7.0313 | 0.70313 | Reduce | 1% | 7.0313 | 0.070313 | H2 | 2 | Improving | TRUE | 547.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK170 | Project_024_RISK170 | Threat | Project Contingency | Open | H1 | 1 |  | Engineering team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 30.562 | 24.4496 | Accept | 80% | 30.562 | 24.4496 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 30% | 1.4386 | 0.43158 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 946.9583 |  | 0 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 30% | 1.4386 | 0.43158 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 946.9583 |  | 0 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-19 | 2019-03-24 | 30% | 1.4386 | 0.43158 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 947 |  | 0 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 30% | 1.4386 | 0.43158 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 946.9583 |  | 0 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-18 23:00 | 2019-03-24 | 30% | 1.4386 | 0.43158 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 947.0417 |  | 0 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-18 22:00 | 2019-03-24 | 30% | 1.4386 | 0.43158 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 947.0833 |  | 0 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-18 23:00 | 2019-03-24 | 30% | 1.4386 | 0.43158 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 947.0417 |  | 0 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 20% | 1.4386 | 0.28772 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 946.9583 |  | 0 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-18 22:00 | 2019-03-24 | 30% | 1.4386 | 0.43158 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 947.0833 |  | 0 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-19 | 2019-03-24 | 20% | 1.4386 | 0.28772 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 947 |  | 0 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 20% | 1.4386 | 0.28772 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 946.9583 |  | 0 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK105 | Project_065_RISK105 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Control Novel Techniques Fail To Mature and Solution is Not Viable | Person_404 | 2016-08-18 23:00 | 2019-03-24 | 20% | 1.4386 | 0.28772 | Reduce | 5% | 1.4401 | 0.072006 | H3 | 3 | -- | FALSE | 947.0417 |  | 0 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-08-19 | 5% | 1.4532 | 0.072661 | Accept | 5% | 1.4532 | 0.072661 | H3 | 3 | Stable | FALSE | 499 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-09-19 01:00 | 5% | 1.4532 | 0.072661 | Accept | 5% | 1.4532 | 0.072661 | H3 | 3 | Stable | FALSE | 530.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-09-19 01:00 | 5% | 1.4532 | 0.072661 | Accept | 5% | 1.4532 | 0.072661 | H3 | 3 | Stable | FALSE | 530.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 5% | 1.4532 | 0.072661 | Accept | 5% | 1.4532 | 0.072661 | H3 | 3 | Stable | FALSE | 591.0417 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-12-18 01:00 | 5% | 1.4532 | 0.072661 | Accept | 5% | 1.4532 | 0.072661 | H3 | 3 | Stable | FALSE | 620.0417 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-049 | Project_028_Risk-049 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | More integration required | Person_542 | 2015-04-08 | 2016-12-18 01:00 | 5% | 1.4532 | 0.072661 | Accept | 5% | 1.4532 | 0.072661 | H3 | 3 | Stable | FALSE | 620.0417 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-100 | Project_039_Risk-100 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Integration performance | Person_176 | 2016-01-22 01:00 | 2016-06-22 | 30% | 0.48597 | 0.14579 | Accept | 15% | 0.48573 | 0.072859 | H3 | 3 | Stable | FALSE | 151.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK170 | Project_024_RISK170 | Threat | Project Contingency | Open | H1 | 1 |  | Engineering team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 30.562 | 24.4496 | Accept | 80% | 30.562 | 24.4496 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP232 | Project_024_OPP232 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Engineering Competitiveness | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 40% | 64.915 | 25.966 | -- | 40% | 64.915 | 25.966 | H1 | 1 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP232 | Project_024_OPP232 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Engineering Competitiveness | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 40% | 64.915 | 25.966 | -- | 40% | 64.915 | 25.966 | H1 | 1 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP232 | Project_024_OPP232 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Engineering Competitiveness | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 40% | 64.915 | 25.966 | -- | 40% | 64.915 | 25.966 | H1 | 1 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP232 | Project_024_OPP232 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Engineering Competitiveness | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 40% | 64.915 | 25.966 | -- | 40% | 64.915 | 25.966 | H1 | 1 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP232 | Project_024_OPP232 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Engineering Competitiveness | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 40% | 64.915 | 25.966 | -- | 40% | 64.915 | 25.966 | H1 | 1 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-107 | Project_039_Risk-107 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Impact of the Component on performace | Person_224 | 2015-07-29 | 2016-07-20 | 50% | 0.29211 | 0.14605 | Reduce | 25% | 0.29211 | 0.073027 | H2 | 2 | Stable | TRUE | 357 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK334 | Project_034_RISK334 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 0.74615 | 0.14923 | Avoid | 10% | 0.74615 | 0.074615 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK334 | Project_034_RISK334 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 0.74615 | 0.14923 | Avoid | 10% | 0.74615 | 0.074615 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK334 | Project_034_RISK334 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 0.74615 | 0.14923 | Avoid | 10% | 0.74615 | 0.074615 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK334 | Project_034_RISK334 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 0.74615 | 0.14923 | Avoid | 10% | 0.74615 | 0.074615 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK334 | Project_034_RISK334 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 0.74615 | 0.14923 | Avoid | 10% | 0.74615 | 0.074615 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP232 | Project_024_OPP232 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Engineering Competitiveness | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 40% | 64.915 | 25.966 | -- | 40% | 64.915 | 25.966 | H1 | 1 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP232 | Project_024_OPP232 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Engineering Competitiveness | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 40% | 64.915 | 25.966 | -- | 40% | 64.915 | 25.966 | H1 | 1 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP221 | Project_024_OPP221 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Service charge for the Training rig under the Training ISS | Person_351 | 2017-03-21 01:00 | 2017-05-22 | 70% | 48.0371 | 33.626 | Exploit | 70% | 48.0371 | 33.626 | H1 | 1 | -- | TRUE | 61.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP221 | Project_024_OPP221 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Service charge for the Training rig under the Training ISS | Person_351 | 2017-03-21 01:00 | 2017-05-22 | 70% | 48.0371 | 33.626 | Exploit | 70% | 48.0371 | 33.626 | H1 | 1 | -- | TRUE | 61.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP221 | Project_024_OPP221 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Service charge for the Training rig under the Training ISS | Person_351 | 2017-03-21 01:00 | 2017-05-22 | 70% | 48.0371 | 33.626 | Exploit | 70% | 48.0371 | 33.626 | H1 | 1 | -- | TRUE | 61.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP221 | Project_024_OPP221 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Service charge for the Training rig under the Training ISS | Person_351 | 2017-03-21 01:00 | 2017-05-22 | 70% | 48.0371 | 33.626 | Exploit | 70% | 48.0371 | 33.626 | H1 | 1 | -- | TRUE | 61.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK030 | Project_079_RISK030 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Production Build / Touch Labour | Person_683 | 2018-11-21 01:00 | 2020-04-22 | 80% | 46.4619 | 37.1695 | -- | 80% | 46.4619 | 37.1695 | H1 | 1 | Stable | TRUE | 517.9583 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK030 | Project_079_RISK030 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Production Build / Touch Labour | Person_683 | 2018-11-21 01:00 | 2020-04-22 | 80% | 46.4619 | 37.1695 | -- | 80% | 46.4619 | 37.1695 | H1 | 1 | Stable | TRUE | 517.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-05-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1035 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-05-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1035 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-05-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1035 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-05-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1035 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-05-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1035 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-05-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1035 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-07-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-07-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-07-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK067 | Project_065_RISK067 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer penetration testing could result in software design changes | Person_550 | 2015-07-22 | 2018-07-22 | 20% | 1.5162 | 0.30324 | Reduce | 5% | 1.5162 | 0.075809 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-20 01:00 | 2023-02-20 01:00 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-20 01:00 | 2023-02-20 01:00 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-20 | 2023-02-20 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-20 01:00 | 2023-02-20 01:00 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-19 23:00 | 2023-02-19 23:00 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-19 22:00 | 2023-02-19 22:00 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-20 01:00 | 2023-03-22 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3681.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-19 22:00 | 2023-02-19 22:00 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-20 | 2023-03-22 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3682 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-20 01:00 | 2023-03-22 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3681.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK224 | Project_065_RISK224 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | STTE - Reduce design repetition | Person_568 | 2013-02-19 23:00 | 2023-03-22 | 15% | 0.50709 | 0.076063 | Exploit | 15% | 0.50709 | 0.076063 | H3 | 3 | -- | TRUE | 3682.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK030 | Project_079_RISK030 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Production Build / Touch Labour | Person_683 | 2018-11-21 01:00 | 2020-04-22 | 80% | 46.4619 | 37.1695 | -- | 80% | 46.4619 | 37.1695 | H1 | 1 | Stable | TRUE | 517.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK168 | Project_024_RISK168 | Threat | Project Contingency | Open | H1 | 1 |  | Safety team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 50.7895 | 40.6316 | -- | 80% | 50.7895 | 40.6316 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK168 | Project_024_RISK168 | Threat | Project Contingency | Open | H1 | 1 |  | Safety team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 50.7895 | 40.6316 | Accept | 80% | 50.7895 | 40.6316 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK168 | Project_024_RISK168 | Threat | Project Contingency | Open | H1 | 1 |  | Safety team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 50.7895 | 40.6316 | Accept | 80% | 50.7895 | 40.6316 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK168 | Project_024_RISK168 | Threat | Project Contingency | Open | H1 | 1 |  | Safety team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 50.7895 | 40.6316 | Accept | 80% | 50.7895 | 40.6316 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK168 | Project_024_RISK168 | Threat | Project Contingency | Open | H1 | 1 |  | Safety team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 50.7895 | 40.6316 | Accept | 80% | 50.7895 | 40.6316 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK168 | Project_024_RISK168 | Threat | Project Contingency | Open | H1 | 1 |  | Safety team extension to cover final year activities | Person_351 | 2017-05-23 | 2018-02-19 01:00 | 80% | 50.7895 | 40.6316 | Accept | 80% | 50.7895 | 40.6316 | H1 | 1 | -- | TRUE | 272.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R039 | Project_085_R039 | Threat | Project Contingency | Open | H1 | 1 |  | Telemetry solution needs additional design effort | Person_539 | 2017-11-20 | 2021-05-22 | 70% | 71.0813 | 49.7569 | Reduce | 60% | 71.0813 | 42.6488 | H1 | 1 | -- | TRUE | 1279 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK004 | Project_088_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | We do not receive the relevant paperwork in order for us to process platformment of production unit... | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 75% | 69.176 | 51.882 | Accept | 75% | 69.176 | 51.882 | H1 | 1 | -- | TRUE | 1389.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK009 | Project_088_RISK009 | Threat | Project Contingency | Open | H1 | 1 |  | Customer may return/reject units due to workmanplatform issues | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 95% | 69.176 | 65.7172 | Reduce | 75% | 69.176 | 51.882 | H1 | 1 | -- | TRUE | 1389.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK009 | Project_088_RISK009 | Threat | Project Contingency | Open | H1 | 1 |  | Customer may return/reject units due to workmanplatform issues | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 95% | 69.176 | 65.7172 | Reduce | 75% | 69.176 | 51.882 | H1 | 1 | -- | TRUE | 1389.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R016 | Project_085_R016 | Threat | Project Contingency | Open | H1 | 1 |  | Design Additional effort required | Person_014 | 2017-12-21 | 2021-05-22 | 60% | 118.5872 | 71.1523 | Reduce | 49% | 118.5872 | 58.1077 | H1 | 1 | -- | TRUE | 1248 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 50% | 0.15317 | 0.076583 | Avoid | 50% | 0.15317 | 0.076583 | H2 | 2 | Improving | TRUE | 487 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 50% | 0.15317 | 0.076583 | Avoid | 50% | 0.15317 | 0.076583 | H2 | 2 | Improving | TRUE | 487 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 50% | 0.15317 | 0.076583 | Avoid | 50% | 0.15317 | 0.076583 | H2 | 2 | Improving | TRUE | 487 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2014-11-20 01:00 | 2016-03-21 01:00 | 50% | 0.15317 | 0.076583 | Avoid | 50% | 0.15317 | 0.076583 | H2 | 2 | Improving | TRUE | 487 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2014-11-20 | 2016-03-21 | 50% | 0.15317 | 0.076583 | Avoid | 50% | 0.15317 | 0.076583 | H2 | 2 | Improving | TRUE | 487 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2014-11-20 | 2016-03-21 | 50% | 0.15317 | 0.076583 | Avoid | 50% | 0.15317 | 0.076583 | H2 | 2 | Improving | TRUE | 487 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_004 | RISK002 | Project_004_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Overmould impact | Person_650 | 2014-11-19 23:00 | 2016-03-20 23:00 | 50% | 0.15317 | 0.076583 | Avoid | 50% | 0.15317 | 0.076583 | H2 | 2 | Improving | TRUE | 487 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK004 | Project_088_RISK004 | Threat | Project Contingency | Open | H1 | 1 |  | We do not receive the relevant paperwork in order for us to process platformment of production unit... | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 85% | 69.176 | 58.7996 | Accept | 85% | 69.176 | 58.7996 | H1 | 1 | -- | TRUE | 1389.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H1 | 1 |  | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_428 | 2012-11-20 | 2017-05-21 | 10% | 165.5424 | 16.5542 | Reduce | 50% | 165.5424 | 82.7712 | H1 | 1 | Worsening | TRUE | 1643 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H1 | 1 |  | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_428 | 2012-11-19 23:00 | 2017-05-21 | 10% | 165.5424 | 16.5542 | Reduce | 50% | 165.5424 | 82.7712 | H1 | 1 | Worsening | TRUE | 1643.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK023 | Project_029_RISK023 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Test Equipment for Industry platform Set Builds | Person_150 | 2019-02-21 01:00 | 2024-09-18 01:00 | 40% | 0.77001 | 0.30801 | Reduce | 10% | 0.77001 | 0.077001 | H3 | 3 | -- | FALSE | 2036 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 25% | 0.77172 | 0.19293 | Reduce | 10% | 0.77172 | 0.077172 | H3 | 3 | -- | TRUE | 547.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 25% | 0.77172 | 0.19293 | Reduce | 10% | 0.77172 | 0.077172 | H3 | 3 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-20 | 2018-05-22 | 25% | 0.77172 | 0.19293 | Reduce | 10% | 0.77172 | 0.077172 | H3 | 3 | Stable | TRUE | 548 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 0.77172 | 0.19293 | Reduce | 10% | 0.77172 | 0.077172 | H3 | 3 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 0.77172 | 0.19293 | Reduce | 10% | 0.77172 | 0.077172 | H3 | 3 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 0.77172 | 0.19293 | Reduce | 10% | 0.77172 | 0.077172 | H3 | 3 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Procurement - Outstanding Change Requests | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 25% | 0.77172 | 0.19293 | Reduce | 10% | 0.77172 | 0.077172 | H3 | 3 | Stable | TRUE | 548.0833 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 30% | 0.51931 | 0.15579 | -- | 15% | 0.51931 | 0.077897 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 30% | 0.51931 | 0.15579 | -- | 15% | 0.51931 | 0.077897 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 30% | 0.51931 | 0.15579 | -- | 15% | 0.51931 | 0.077897 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 30% | 0.51931 | 0.15579 | -- | 15% | 0.51931 | 0.077897 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 30% | 0.51931 | 0.15579 | -- | 15% | 0.51931 | 0.077897 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-102 | Project_011_Risk-102 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Gold Rig is unavailable when required | Person_230 | 2016-07-21 | 2017-04-21 | 30% | 0.51931 | 0.15579 | -- | 15% | 0.51931 | 0.077897 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP229 | Project_024_OPP229 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Service charge for the Programme rigs under the support contract | Person_351 | 2017-03-21 01:00 | 2017-05-22 | 70% | 135.0233 | 94.5163 | Exploit | 70% | 135.0233 | 94.5163 | H1 | 1 | -- | TRUE | 61.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP229 | Project_024_OPP229 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Service charge for the Programme rigs under the support contract | Person_351 | 2017-03-21 01:00 | 2017-05-22 | 70% | 135.0233 | 94.5163 | Exploit | 70% | 135.0233 | 94.5163 | H1 | 1 | -- | TRUE | 61.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP229 | Project_024_OPP229 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Service charge for the Programme rigs under the support contract | Person_351 | 2017-03-21 01:00 | 2017-05-22 | 70% | 135.0233 | 94.5163 | Exploit | 70% | 135.0233 | 94.5163 | H1 | 1 | -- | TRUE | 61.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK018 | Project_097_RISK018 | Threat | Project Contingency | Open | H2 | 2 | Project Management | SW Uplift - Loss of Key resource | Person_668 | 2018-09-21 01:00 | 2020-05-22 | 25% | 0.78391 | 0.19598 | Reduce | 10% | 0.78391 | 0.078391 | H2 | 2 | Stable | TRUE | 608.9583 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2018-04-21 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 333 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK493 | Project_065_RISK493 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unavailability of material results in redesign | Person_305 | 2017-05-23 | 2019-05-22 | 70% | 26.4783 | 18.5348 | Reduce | 20% | 0.39722 | 0.079443 | H3 | 3 | -- | FALSE | 729 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP229 | Project_024_OPP229 | Opportunitity | Project Contingency | Open | H1 | 1 |  | Service charge for the Programme rigs under the support contract | Person_351 | 2017-03-21 01:00 | 2017-05-22 | 70% | 135.0233 | 94.5163 | Exploit | 70% | 135.0233 | 94.5163 | H1 | 1 | -- | TRUE | 61.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_072 | RISK099 | Project_072_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Multiplex Development Delay | Person_285 | 2018-07-21 | 2021-08-20 01:00 | 10% | 0.80789 | 0.080789 | Accept | 10% | 0.80789 | 0.080789 | H3 | 3 | Improving | FALSE | 1126.0417 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-004 | Project_029_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Functionality shortfalls of sub-system Application Software Integration with the system | Person_199 | 2015-11-21 01:00 | 2016-09-19 01:00 | 20% | 0.53901 | 0.1078 | Reduce | 15% | 0.53901 | 0.080852 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-004 | Project_029_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Functionality shortfalls of sub-system Application Software Integration with the system | Person_199 | 2015-11-21 01:00 | 2016-09-19 01:00 | 20% | 0.53901 | 0.1078 | Reduce | 15% | 0.53901 | 0.080852 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2016-08-21 | 40% | 0.40661 | 0.16264 | Accept | 20% | 0.40661 | 0.081321 | H2 | 2 | Stable | TRUE | 59 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2016-08-21 01:00 | 40% | 0.40661 | 0.16264 | Accept | 20% | 0.40661 | 0.081321 | H2 | 2 | Stable | TRUE | 59.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2016-10-15 01:00 | 40% | 0.40661 | 0.16264 | Accept | 20% | 0.40661 | 0.081321 | H2 | 2 | Stable | TRUE | 114.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-03-22 | 40% | 0.40661 | 0.16264 | Accept | 20% | 0.40661 | 0.081321 | H2 | 2 | Stable | TRUE | 272 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-04-21 | 40% | 0.40661 | 0.16264 | Accept | 20% | 0.40661 | 0.081321 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-04-21 | 40% | 0.40661 | 0.16264 | Accept | 20% | 0.40661 | 0.081321 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-04-21 | 40% | 0.40661 | 0.16264 | Accept | 20% | 0.40661 | 0.081321 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-006 | Project_028_Risk-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Electromagnetic Compatibility ( EMC ) | Person_070 | 2016-06-23 | 2017-04-21 | 40% | 0.40661 | 0.16264 | Accept | 20% | 0.40661 | 0.081321 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-10-18 01:00 | 50% | 1.6266 | 0.8133 | Accept | 5% | 1.6266 | 0.08133 | H3 | 3 | Stable | TRUE | 860.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-10-18 01:00 | 50% | 1.6266 | 0.8133 | Accept | 5% | 1.6266 | 0.08133 | H3 | 3 | Stable | TRUE | 860.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-10-18 01:00 | 50% | 1.6266 | 0.8133 | Accept | 5% | 1.6266 | 0.08133 | H3 | 3 | Stable | TRUE | 860.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2017-01-20 01:00 | 50% | 1.6266 | 0.8133 | Accept | 5% | 1.6266 | 0.08133 | H3 | 3 | Stable | TRUE | 954.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2017-01-20 01:00 | 50% | 1.6266 | 0.8133 | Accept | 5% | 1.6266 | 0.08133 | H3 | 3 | Stable | TRUE | 954.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK354 | Project_035_RISK354 | Threat | Project Contingency | Open | H2 | 2 |  | Product Team support for dependent projects | Person_151 | 2015-05-24 | 2016-08-13 | 50% | 0 | 0 | -- | 50% | 0 | 0 | H2 | 2 | Worsening | TRUE | 447 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 221.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP006 | Project_021_OPP006 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 105.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R041 | Project_021_Risk-R041 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to system serviceability | Person_174 | 2016-08-17 01:00 | 2016-09-03 01:00 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 17 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 | 2017-04-21 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 222 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP006 | Project_021_OPP006 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-08-06 | 2016-11-19 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 105 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R025 | Project_021_Risk-R025 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Analysis of Trials data may require further info or action to complete | Person_470 | 2016-02-18 | 2017-06-22 | 25% | 0.33108 | 0.082771 | Accept | 25% | 0.33108 | 0.082771 | H2 | 2 | Stable | TRUE | 490 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R025 | Project_021_Risk-R025 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Analysis of Trials data may require further info or action to complete | Person_470 | 2016-02-17 23:00 | 2017-06-22 | 25% | 0.33108 | 0.082771 | Accept | 25% | 0.33108 | 0.082771 | H2 | 2 | Stable | TRUE | 490.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Stable | TRUE | 1421 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Stable | TRUE | 1421 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Stable | TRUE | 1421 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Stable | TRUE | 1421 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Stable | TRUE | 1421 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Stable | TRUE | 1421 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Stable | TRUE | 1421 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_702 | 2012-06-01 | 2016-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Stable | TRUE | 1421 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk29 | Project_010_Risk29 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Down-time of the Test Facilities during warranty period | Person_693 | 2012-06-01 | 2018-04-22 | 50% | 0.27723 | 0.13862 | Reduce | 30% | 0.27723 | 0.08317 | H2 | 2 | Improving | TRUE | 2151 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R041 | Project_021_Risk-R041 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to system serviceability | Person_174 | 2016-08-17 | 2016-09-03 | 30% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 17 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-03 01:00 | 2018-04-13 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 40.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-03 01:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 78.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-03 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 79 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-03 01:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 78.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-02 23:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 79.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-02 22:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 79.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-02 23:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 79.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-03 01:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 78.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-02 22:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 79.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-03 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 79 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-03 01:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 78.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK471 | Project_065_RISK471 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | UKCA marking of the sub-system cannot be achieved against relevant standards | Person_661 | 2018-03-02 23:00 | 2018-05-21 | 25% | 1.8756 | 0.46889 | Reduce | 10% | 0.83669 | 0.083669 | H3 | 3 | -- | TRUE | 79.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 221.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP006 | Project_021_OPP006 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 105.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 221.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 221.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-005 | Project_021_Risk-005 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to accelerate Component Approval through closer working efficiencies | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 10% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 221.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk017 | Project_042_Risk017 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 0 | 0 | Accept | 40% | 0 | 0 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK037 | Project_043_RISK037 | Threat | Project Contingency | Open | H2 | 2 |  | product not repairable in the Turn araound time | Person_307 | 2014-09-13 01:00 | 2018-03-21 | 20% | 0 | 0 | -- | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 1284.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK037 | Project_043_RISK037 | Threat | Project Contingency | Open | H2 | 2 |  | product not repairable in the Turn araound time | Person_307 | 2014-09-13 | 2018-03-21 | 20% | 0 | 0 | -- | 20% | 0 | 0 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 |  | Trial delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 |  | Trial delay due to weather | Person_174 | 2016-11-18 | 2017-06-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 216 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 |  | Trial delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 |  | Trial delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R046 | Project_021_Risk-R046 | Threat | Project Contingency | Open | H2 | 2 |  | Trial delay due to weather | Person_174 | 2016-11-18 01:00 | 2017-06-22 | 50% | 0 | 0 | Reduce | 30% | 0 | 0 | H2 | 2 | Stable | TRUE | 215.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--23 | Project_021_Risk--23 | Threat | Project Contingency | Open | H2 | 2 |  | Requirement for Component Extension | Person_061 | 2018-06-22 | 2018-07-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 30 |  | 1 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--23 | Project_021_Risk--23 | Threat | Project Contingency | Open | H2 | 2 |  | Requirement for Component Extension | Person_061 | 2018-06-22 | 2018-07-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 30 |  | 1 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--23 | Project_021_Risk--23 | Threat | Project Contingency | Open | H2 | 2 |  | Requirement for Component Extension | Person_061 | 2018-06-22 | 2018-07-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 30 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 30% | 0.28639 | 0.085917 | Reduce | 30% | 0.28639 | 0.085917 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 30% | 0.28639 | 0.085917 | Reduce | 30% | 0.28639 | 0.085917 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 30% | 0.28639 | 0.085917 | Reduce | 30% | 0.28639 | 0.085917 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 30% | 0.28639 | 0.085917 | Reduce | 30% | 0.28639 | 0.085917 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 30% | 0.28639 | 0.085917 | Reduce | 30% | 0.28639 | 0.085917 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-113 | Project_011_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | LOE Documentation takes longer to produce | Person_147 | 2016-07-21 | 2018-08-21 | 30% | 0.28639 | 0.085917 | Reduce | 30% | 0.28639 | 0.085917 | H2 | 2 | Stable | TRUE | 761 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 946.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 946.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-19 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 947 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 946.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-18 23:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 947.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-18 22:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 947.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 946.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-18 22:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 947.0833 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-19 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 947 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-19 01:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 946.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK104 | Project_065_RISK104 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hardware Architecture from SFR&D cannot support software and stabilisation performance needs. | Person_404 | 2016-08-18 23:00 | 2019-03-24 | 30% | 1.7265 | 0.51794 | Reduce | 5% | 1.7241 | 0.086205 | H3 | 3 | -- | FALSE | 947.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--23 | Project_021_Risk--23 | Threat | Project Contingency | Open | H2 | 2 |  | Requirement for Component Extension | Person_061 | 2018-06-22 | 2018-07-22 | 50% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 30 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--100 | Project_100_Risk--100 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation. | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 25% | 0.34687 | 0.086718 | Accept | 25% | 0.34687 | 0.086718 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 80% | 0.10892 | 0.087134 | Exploit | 80% | 0.10892 | 0.087134 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 80% | 0.10892 | 0.087134 | Exploit | 80% | 0.10892 | 0.087134 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 80% | 0.10892 | 0.087134 | Exploit | 80% | 0.10892 | 0.087134 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 80% | 0.10892 | 0.087134 | Exploit | 80% | 0.10892 | 0.087134 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK021 | Project_075_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Failure of Compliance to Product specification | Person_449 | 2017-10-21 01:00 | 2018-10-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 50% | 0.35539 | 0.17769 | Accept | 25% | 0.35539 | 0.088847 | H2 | 2 | Worsening | TRUE | 795 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 50% | 0.35539 | 0.17769 | Accept | 25% | 0.35539 | 0.088847 | H2 | 2 | Worsening | TRUE | 795 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 50% | 0.35539 | 0.17769 | Accept | 25% | 0.35539 | 0.088847 | H2 | 2 | Worsening | TRUE | 795 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 50% | 0.35539 | 0.17769 | Accept | 25% | 0.35539 | 0.088847 | H2 | 2 | Worsening | TRUE | 795 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 50% | 0.35539 | 0.17769 | Accept | 25% | 0.35539 | 0.088847 | H2 | 2 | Worsening | TRUE | 795 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 50% | 0.35539 | 0.17769 | Accept | 25% | 0.35539 | 0.088847 | H2 | 2 | Worsening | TRUE | 795 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 50% | 0.35539 | 0.17769 | Accept | 25% | 0.35539 | 0.088847 | H2 | 2 | Worsening | TRUE | 795 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_002 | Risk002 | Project_002_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Transducer Element Failures | Person_650 | 2014-06-04 | 2016-08-07 | 50% | 0.35539 | 0.17769 | Accept | 25% | 0.35539 | 0.088847 | H2 | 2 | Worsening | TRUE | 795 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk241 | Project_009_Risk241 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Noise | Person_248 | 2013-04-26 | 2016-09-19 01:00 | 80% | 2.594 | 2.0752 | Reduce | 10% | 0.89348 | 0.089348 | H3 | 3 | -- | FALSE | 1242.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-023 | Project_026_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | The training solution does not allow the delivery of training | Person_525 | 2021-05-29 | 2022-10-28 01:00 | 90% | 0.44768 | 0.40291 | Reduce | 20% | 0.44768 | 0.089536 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-065 | Project_026_Risk-065 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Safety Case | Person_364 | 2015-05-24 | 2018-12-27 01:00 | 50% | 0.44768 | 0.22384 | Reduce | 20% | 0.44768 | 0.089536 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-023 | Project_026_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | The training solution does not allow the delivery of training | Person_525 | 2021-05-29 | 2022-10-28 01:00 | 90% | 0.44768 | 0.40291 | Reduce | 20% | 0.44768 | 0.089536 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-065 | Project_026_Risk-065 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Safety Case | Person_364 | 2015-05-24 | 2018-12-27 01:00 | 50% | 0.44768 | 0.22384 | Reduce | 20% | 0.44768 | 0.089536 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-023 | Project_026_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | The training solution does not allow the delivery of training | Person_525 | 2021-05-29 | 2022-10-28 01:00 | 90% | 0.44768 | 0.40291 | Reduce | 20% | 0.44768 | 0.089536 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-065 | Project_026_Risk-065 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Safety Case | Person_364 | 2015-05-24 | 2018-12-27 01:00 | 50% | 0.44768 | 0.22384 | Reduce | 20% | 0.44768 | 0.089536 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-023 | Project_026_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | The training solution does not allow the delivery of training | Person_525 | 2021-05-29 | 2022-10-28 01:00 | 90% | 0.44768 | 0.40291 | Reduce | 20% | 0.44768 | 0.089536 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-065 | Project_026_Risk-065 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Safety Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 50% | 0.44768 | 0.22384 | Reduce | 20% | 0.44768 | 0.089536 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-023 | Project_026_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | The training solution does not allow the delivery of training | Person_525 | 2021-05-29 | 2022-10-28 01:00 | 90% | 0.44768 | 0.40291 | Reduce | 20% | 0.44768 | 0.089536 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-065 | Project_026_Risk-065 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Safety Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 50% | 0.44768 | 0.22384 | Reduce | 20% | 0.44768 | 0.089536 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-023 | Project_026_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | The training solution does not allow the delivery of training | Person_525 | 2021-05-29 | 2022-10-28 01:00 | 90% | 0.44768 | 0.40291 | Reduce | 20% | 0.44768 | 0.089536 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-065 | Project_026_Risk-065 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Safety Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 50% | 0.44768 | 0.22384 | Reduce | 20% | 0.44768 | 0.089536 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-023 | Project_026_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | The training solution does not allow the delivery of training | Person_525 | 2021-05-29 | 2022-10-28 01:00 | 90% | 0.44768 | 0.40291 | Reduce | 20% | 0.44768 | 0.089536 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-065 | Project_026_Risk-065 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Safety Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 50% | 0.44768 | 0.22384 | Reduce | 20% | 0.44768 | 0.089536 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-023 | Project_026_Risk-023 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | The training solution does not allow the delivery of training | Person_525 | 2021-05-29 | 2022-10-28 01:00 | 90% | 0.44768 | 0.40291 | Reduce | 20% | 0.44768 | 0.089536 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-065 | Project_026_Risk-065 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Completeness and acceptability of the Safety Case | Person_094 | 2015-05-24 | 2018-12-27 01:00 | 50% | 0.44768 | 0.22384 | Reduce | 20% | 0.44768 | 0.089536 | H2 | 2 | -- | TRUE | 1313.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Worsening | TRUE | 1539.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Worsening | TRUE | 1539.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Worsening | TRUE | 1539.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Worsening | TRUE | 1539 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Worsening | TRUE | 1539.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Worsening | TRUE | 1539.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Worsening | TRUE | 1539.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2016-08-19 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Worsening | TRUE | 1539 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK69 | Project_010_RISK69 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of Staff from the project to other projects | Person_359 | 2012-06-02 | 2018-05-21 | 80% | 0.18482 | 0.14786 | Avoid | 50% | 0.18482 | 0.092411 | H1 | 1 | Stable | TRUE | 2179 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK010 | Project_010_RISK010 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Use of Lead components | Person_359 | 2012-05-23 | 2025-04-22 | 5% | 1.8482 | 0.092411 | Reduce | 5% | 1.8482 | 0.092411 | H3 | 3 | Stable | FALSE | 4717 |  | 1 | 1 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--23 | Project_021_Risk--23 | Threat | Project Contingency | Open | H2 | 2 |  | Requirement for Component Extension | Person_061 | 2018-06-22 | 2018-07-22 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 30 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK055 | Project_097_RISK055 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SW Uplift - Additional technical impact | Person_560 | 2019-05-24 | 2019-10-22 01:00 | 30% | 0.31142 | 0.093425 | Accept | 30% | 0.31142 | 0.093425 | H2 | 2 | Stable | TRUE | 151.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK259 | Project_024_RISK259 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Have to provide licenses | Person_318 | 2016-04-22 | 2016-08-19 01:00 | 10% | 1.8696 | 0.18696 | Reduce | 5% | 1.8696 | 0.093478 | H3 | 3 | -- | TRUE | 119.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK259 | Project_024_RISK259 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Have to provide licenses | Person_318 | 2016-04-22 | 2016-08-19 01:00 | 10% | 1.8696 | 0.18696 | Reduce | 5% | 1.8696 | 0.093478 | H3 | 3 | -- | TRUE | 119.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK259 | Project_024_RISK259 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Have to provide licenses | Person_318 | 2016-04-22 | 2016-08-19 01:00 | 10% | 1.8696 | 0.18696 | Reduce | 5% | 1.8696 | 0.093478 | H3 | 3 | -- | TRUE | 119.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK259 | Project_024_RISK259 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Have to provide licenses | Person_318 | 2016-04-22 | 2016-08-19 01:00 | 10% | 1.8696 | 0.18696 | Reduce | 5% | 1.8696 | 0.093478 | H3 | 3 | -- | TRUE | 119.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK259 | Project_024_RISK259 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Have to provide licenses | Person_318 | 2016-04-22 | 2016-12-20 01:00 | 10% | 1.8696 | 0.18696 | Reduce | 5% | 1.8696 | 0.093478 | H3 | 3 | -- | TRUE | 242.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK259 | Project_024_RISK259 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Have to provide licenses | Person_318 | 2016-04-22 | 2016-12-20 01:00 | 10% | 1.8696 | 0.18696 | Reduce | 5% | 1.8696 | 0.093478 | H3 | 3 | -- | TRUE | 242.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK259 | Project_024_RISK259 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Have to provide licenses | Person_318 | 2016-04-22 | 2017-03-22 | 10% | 1.8696 | 0.18696 | Reduce | 5% | 1.8696 | 0.093478 | H3 | 3 | -- | TRUE | 334 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK021 | Project_075_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Failure of Compliance to Product specification | Person_449 | 2017-10-21 01:00 | 2018-10-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK027 | Project_079_RISK027 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Trials | Person_002 | 2018-07-22 | 2018-08-21 | 30% | 0 | 0 | -- | 30% | 0 | 0 | H2 | 2 | -- | TRUE | 30 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK021 | Project_075_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Failure of Compliance to Product specification | Person_449 | 2017-10-21 01:00 | 2018-10-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--23 | Project_021_Risk--23 | Threat | Project Contingency | Open | H2 | 2 |  | Requirement for Component Extension | Person_061 | 2018-06-22 | 2018-07-22 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 30 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--23 | Project_021_Risk--23 | Threat | Project Contingency | Open | H2 | 2 |  | Requirement for Component Extension | Person_061 | 2018-06-22 | 2018-07-22 | 50% | 0 | 0 | Reduce | 25% | 0 | 0 | H2 | 2 | -- | TRUE | 30 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK021 | Project_075_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Failure of Compliance to Product specification | Person_449 | 2017-10-21 01:00 | 2018-10-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK021 | Project_075_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Failure of Compliance to Product specification | Person_449 | 2017-10-21 01:00 | 2018-10-20 01:00 | 0% | 0 | 0 | Accept | 0% | 0 | 0 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-025 | Project_077_T-025 | Threat | Project Contingency | Open | H2 | 2 |  | Delayed Config File delivery | Person_426 | 2019-05-24 | 2020-02-21 01:00 | 50% | 3.3696 | 1.6848 | Avoid | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 273.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK003 | Project_074_RISK003 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Extra test equipment | Person_493 | 2017-09-20 01:00 | 2019-11-21 01:00 | 50% | 0 | 0 | Exploit | 50% | 0 | 0 | H2 | 2 | -- | TRUE | 792 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | P006 | Project_067_P006 | Threat | Project Contingency | Open | H2 | 2 |  | Complete SDRL deliverables in Schedule | Person_325 | 2018-07-07 | 2018-08-05 | 30% | 0 | 0 | Reduce | 50% | 0 | 0 | H2 | 2 | Stable | TRUE | 29 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK003 | Project_088_RISK003 | Threat | Project Contingency | Open | H2 | 2 |  | If any unit requires opened then there is a risk the connector fails. | Person_399 | 2015-05-27 | 2019-03-16 01:00 | 5% | 0.57647 | 0.028823 | Reduce | 1% | 0.28823 | 0.0028823 | H2 | 2 | -- | TRUE | 1389.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK013 | Project_001_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Heavy reliance on contractors | Person_674 | 2015-12-22 01:00 | 2016-06-19 | 30% | 0.95502 | 0.2865 | Reduce | 10% | 0.95502 | 0.095502 | H3 | 3 | -- | TRUE | 179.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK013 | Project_001_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Heavy reliance on contractors | Person_674 | 2015-12-22 01:00 | 2016-06-19 | 30% | 0.95502 | 0.2865 | Reduce | 10% | 0.95502 | 0.095502 | H3 | 3 | -- | TRUE | 179.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK013 | Project_001_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Heavy reliance on contractors | Person_674 | 2015-12-22 | 2016-06-19 | 30% | 0.95502 | 0.2865 | Reduce | 10% | 0.95502 | 0.095502 | H3 | 3 | -- | TRUE | 180 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK013 | Project_001_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Heavy reliance on contractors | Person_674 | 2015-12-21 23:00 | 2016-06-19 | 30% | 0.95502 | 0.2865 | Reduce | 10% | 0.95502 | 0.095502 | H3 | 3 | -- | TRUE | 180.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK013 | Project_001_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Heavy reliance on contractors | Person_674 | 2015-12-21 22:00 | 2016-06-19 | 30% | 0.95502 | 0.2865 | Reduce | 10% | 0.95502 | 0.095502 | H3 | 3 | -- | TRUE | 180.0833 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK013 | Project_001_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Heavy reliance on contractors | Person_674 | 2015-12-21 21:00 | 2016-06-19 | 30% | 0.95502 | 0.2865 | Reduce | 10% | 0.95502 | 0.095502 | H3 | 3 | -- | TRUE | 180.125 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK003 | Project_088_RISK003 | Threat | Project Contingency | Open | H2 | 2 |  | If any unit requires opened then there is a risk the connector fails. | Person_399 | 2015-05-27 | 2019-03-16 01:00 | 5% | 0.57647 | 0.028823 | Reduce | 1% | 0.28823 | 0.0028823 | H2 | 2 | -- | TRUE | 1389.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | OPP1009 | Project_091_OPP1009 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Margin Improvement | Person_557 | 2018-08-22 01:00 | 2020-09-19 01:00 | 20% | 0.47966 | 0.095932 | Exploit | 20% | 0.47966 | 0.095932 | H3 | 3 | -- | TRUE | 759 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | OPP1009 | Project_091_OPP1009 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Margin Improvement | Person_557 | 2018-09-21 01:00 | 2020-09-19 01:00 | 20% | 0.47966 | 0.095932 | Exploit | 20% | 0.47966 | 0.095932 | H3 | 3 | -- | TRUE | 729 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2016-05-22 | 2% | 4.8296 | 0.096593 | Transfer | 2% | 4.8296 | 0.096593 | H2 | 2 | Stable | TRUE | 1004.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 | 2016-05-22 | 2% | 4.8296 | 0.096593 | Transfer | 2% | 4.8296 | 0.096593 | H2 | 2 | Stable | TRUE | 1005 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 | 2016-05-22 | 2% | 4.8296 | 0.096593 | Transfer | 2% | 4.8296 | 0.096593 | H2 | 2 | Stable | TRUE | 1005 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 | 2016-05-22 | 2% | 4.8296 | 0.096593 | Transfer | 2% | 4.8296 | 0.096593 | H2 | 2 | Stable | TRUE | 1005 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2016-05-22 | 2% | 4.8296 | 0.096593 | Transfer | 2% | 4.8296 | 0.096593 | H2 | 2 | Stable | TRUE | 1004.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2016-05-22 | 2% | 4.8296 | 0.096593 | Transfer | 2% | 4.8296 | 0.096593 | H2 | 2 | Stable | TRUE | 1004.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2016-05-22 | 2% | 4.8296 | 0.096593 | Transfer | 2% | 4.8296 | 0.096593 | H2 | 2 | Stable | TRUE | 1004.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-123 | Project_032_Risk-123 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Commercial aspects agreement | Person_480 | 2013-08-21 01:00 | 2017-05-22 | 2% | 4.8296 | 0.096593 | Transfer | 2% | 4.8296 | 0.096593 | H2 | 2 | Stable | TRUE | 1369.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK047 | Project_097_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Obsolescence - Desktops no longer available for purchase | Person_560 | 2018-09-21 01:00 | 2019-01-22 01:00 | 30% | 0.38659 | 0.11598 | Reduce | 25% | 0.38659 | 0.096647 | H2 | 2 | Stable | TRUE | 123 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 40% | 0.24207 | 0.096828 | -- | 40% | 0.24207 | 0.096828 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 40% | 0.24207 | 0.096828 | -- | 40% | 0.24207 | 0.096828 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-100 | Project_011_Risk-100 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Clarity of the main contract baseline | Person_230 | 2016-07-21 | 2017-04-21 | 40% | 0.24207 | 0.096828 | -- | 40% | 0.24207 | 0.096828 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK002 | Project_088_RISK002 | Threat | Project Contingency | Open | H2 | 2 |  | Fails pressure test. Not due to the addition of the filter. | Person_399 | 2015-05-27 | 2019-03-16 01:00 | 2% | 0.32282 | 0.0064564 | Accept | 2% | 0.32282 | 0.0064564 | H2 | 2 | -- | TRUE | 1389.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK002 | Project_088_RISK002 | Threat | Project Contingency | Open | H2 | 2 |  | Fails pressure test. Not due to the addition of the filter. | Person_399 | 2015-05-27 | 2019-03-16 01:00 | 2% | 0.32282 | 0.0064564 | Accept | 2% | 0.32282 | 0.0064564 | H2 | 2 | -- | TRUE | 1389.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK056 | Project_043_RISK056 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Acceptance Operator Courses | Person_056 | 2014-09-13 | 2018-03-21 | 30% | 0.14372 | 0.043115 | -- | 5% | 0.14372 | 0.0071859 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK061 | Project_043_RISK061 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Tech Docs not adequate | Person_769 | 2014-09-13 | 2018-03-21 | 20% | 0.16288 | 0.032576 | -- | 5% | 0.16288 | 0.008144 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK066 | Project_043_RISK066 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Publications overspend | Person_769 | 2014-09-13 | 2018-03-21 | 20% | 0.16288 | 0.032576 | -- | 5% | 0.16288 | 0.008144 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK006 | Project_073_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Issues | Person_263 | 2017-09-20 01:00 | 2019-08-01 | 20% | 0.041801 | 0.0083602 | Accept | 20% | 0.041801 | 0.0083602 | H2 | 2 | -- | TRUE | 679.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK004 | Project_073_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal Chamber | Person_493 | 2017-09-20 01:00 | 2019-08-01 | 10% | 0.20901 | 0.020901 | Reduce | 5% | 0.20901 | 0.01045 | H2 | 2 | -- | TRUE | 679.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK051 | Project_043_RISK051 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Interfaces | Person_135 | 2014-09-13 | 2018-03-21 | 30% | 0.047906 | 0.014372 | -- | 30% | 0.047906 | 0.014372 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK032 | Project_043_RISK032 | Threat | Project Contingency | Open | H2 | 2 |  | GPS failure | Person_368 | 2014-09-13 | 2018-03-21 | 20% | 0.29941 | 0.059882 | -- | 5% | 0.29941 | 0.014971 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK034 | Project_043_RISK034 | Threat | Project Contingency | Open | H2 | 2 |  | Failure of a product pre delivery | Person_368 | 2014-09-13 | 2018-03-21 | 15% | 0.11976 | 0.017965 | -- | 15% | 0.11976 | 0.017965 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-075 | Project_007_R-075 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Late Delivery | Person_386 | 2013-12-03 19:00 | 2015-12-20 19:00 | 60% | 0.48788 | 0.29273 | Reduce | 20% | 0.48788 | 0.097576 | H3 | 3 | Stable | TRUE | 747 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK005 | Project_043_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | End-End Performance | Person_051 | 2014-09-13 | 2018-03-21 | 10% | 0.38325 | 0.038325 | -- | 5% | 0.38325 | 0.019162 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK026 | Project_097_RISK026 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | SW Uplift - Estimating Bias | Person_667 | 2018-09-21 01:00 | 2019-09-21 01:00 | 30% | 0.6529 | 0.19587 | Reduce | 15% | 0.6529 | 0.097935 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.65759 | 0.098638 | Accept | 15% | 0.65759 | 0.098638 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.65759 | 0.098638 | Accept | 15% | 0.65759 | 0.098638 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.65759 | 0.098638 | Accept | 15% | 0.65759 | 0.098638 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.65759 | 0.098638 | Accept | 15% | 0.65759 | 0.098638 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.65759 | 0.098638 | Accept | 15% | 0.65759 | 0.098638 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.65759 | 0.098638 | Accept | 15% | 0.65759 | 0.098638 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk015 | Project_042_Risk015 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Hours Booking Rule | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.65759 | 0.098638 | Accept | 15% | 0.65759 | 0.098638 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK021 | Project_043_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Facilities Availability - Customer | Person_367 | 2014-09-13 | 2018-03-21 | 10% | 0.38325 | 0.038325 | -- | 5% | 0.38325 | 0.019162 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-023 | Project_077_T-023 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Sub-system legacy abilities | Person_544 | 2018-10-22 01:00 | 2020-02-21 01:00 | 10% | 1.0019 | 0.10019 | Avoid | 10% | 1.0019 | 0.10019 | H3 | 3 | Stable | FALSE | 487 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK053 | Project_043_RISK053 | Threat | Project Contingency | Open | H2 | 2 |  | System Integration Delays | Person_135 | 2014-09-13 | 2018-03-21 | 20% | 0.097009 | 0.019402 | -- | 20% | 0.097009 | 0.019402 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-011 | Project_043_Risk-011 | Threat | Project Contingency | Open | H2 | 2 |  | Lack of usage history for engine may impact | Person_724 | 2014-09-13 | 2018-03-21 | 20% | 0.11976 | 0.023953 | Reduce | 20% | 0.11976 | 0.023953 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK011 | Project_088_RISK011 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Will customer purchase rechargeable battery and charger | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 10% | 0.26902 | 0.026902 | Reject | 10% | 0.26902 | 0.026902 | H2 | 2 | -- | TRUE | 1389.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 773 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK011 | Project_088_RISK011 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Will customer purchase rechargeable battery and charger | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 10% | 0.26902 | 0.026902 | Reject | 10% | 0.26902 | 0.026902 | H2 | 2 | -- | TRUE | 1389.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R059 | Project_021_Risk-R059 | Threat | Project Contingency | Open | H2 | 2 |  | Trials delay due to the performance of the system in environmental conditions | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 5% | 2.2072 | 0.11036 | Reduce | 2% | 1.4568 | 0.029135 | H2 | 2 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 773 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R059 | Project_021_Risk-R059 | Threat | Project Contingency | Open | H2 | 2 |  | Trials delay due to the performance of the system in environmental conditions | Person_174 | 2016-11-20 | 2017-01-20 | 5% | 2.2072 | 0.11036 | Reduce | 2% | 1.4568 | 0.029135 | H2 | 2 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 773 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R059 | Project_021_Risk-R059 | Threat | Project Contingency | Open | H2 | 2 |  | Trials delay due to the performance of the system in environmental conditions | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 5% | 2.2072 | 0.11036 | Reduce | 2% | 1.4568 | 0.029135 | H2 | 2 | -- | TRUE | 61 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK046 | Project_043_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Cyber Suitably Qualified and experienced staff availability | Person_135 | 2014-09-13 | 2018-03-21 | 20% | 0.16168 | 0.032336 | -- | 20% | 0.16168 | 0.032336 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 773 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK009 | Project_012_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Production Test equipment fails | Person_515 | 2015-04-04 | 2016-03-22 01:00 | 41% | 0.86402 | 0.35425 | Reduce | 25% | 0.14164 | 0.035411 | H2 | 2 | Stable | TRUE | 353.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK003 | Project_043_RISK003 | Threat | Project Contingency | Open | H2 | 2 |  | Maturity of Mission System - Software components | Person_136 | 2014-09-13 | 2018-03-21 | 20% | 0.38325 | 0.076649 | Reduce | 10% | 0.38325 | 0.038325 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 773 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK014 | Project_043_RISK014 | Threat | Project Contingency | Open | H2 | 2 |  | Insufficient estimates | Person_135 | 2014-09-13 | 2018-03-21 | 20% | 0.19162 | 0.038325 | -- | 20% | 0.19162 | 0.038325 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 773 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK065 | Project_043_RISK065 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Publications overspend | Person_084 | 2014-09-13 | 2018-03-21 | 25% | 0.16288 | 0.04072 | -- | 25% | 0.16288 | 0.04072 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK073 | Project_043_RISK073 | Threat | Project Contingency | Open | H2 | 2 |  | Support Required to Customer EMC Testing | Person_367 | 2014-09-13 | 2018-03-21 | 25% | 0.16288 | 0.04072 | -- | 25% | 0.16288 | 0.04072 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK048 | Project_043_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Cyber Solution | Person_051 | 2014-09-13 | 2018-03-21 | 25% | 0.19402 | 0.048505 | -- | 25% | 0.19402 | 0.048505 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs and manual | Person_126 | 2017-12-21 01:00 | 2019-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 395 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-10-20 01:00 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 909.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-06-06 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 773 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs and manual | Person_126 | 2017-12-21 01:00 | 2019-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 395 |  | 1 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs and manual | Person_126 | 2017-12-21 01:00 | 2019-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 395 |  | 1 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs and manual | Person_126 | 2017-12-21 01:00 | 2019-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 395 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-10-20 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 909 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs and manual | Person_126 | 2017-12-21 01:00 | 2019-01-20 01:00 | 10% | 0.48559 | 0.048559 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 395 |  | 1 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--19 | Project_021_Risk--19 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs | Person_436 | 2018-01-21 01:00 | 2019-01-20 01:00 | 20% | 0.48559 | 0.097118 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-10-20 01:00 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 909.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--19 | Project_021_Risk--19 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs | Person_436 | 2018-01-21 01:00 | 2019-01-20 01:00 | 20% | 0.48559 | 0.097118 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--19 | Project_021_Risk--19 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs | Person_436 | 2018-01-21 01:00 | 2019-01-20 01:00 | 20% | 0.48559 | 0.097118 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2018-10-19 23:00 | 40% | 1.0142 | 0.40567 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | Stable | TRUE | 908.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--19 | Project_021_Risk--19 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs | Person_436 | 2018-01-21 01:00 | 2019-01-20 01:00 | 20% | 0.48559 | 0.097118 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--19 | Project_021_Risk--19 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs | Person_436 | 2018-01-21 01:00 | 2019-01-20 01:00 | 20% | 0.48559 | 0.097118 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--19 | Project_021_Risk--19 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs | Person_436 | 2018-01-21 01:00 | 2019-01-20 01:00 | 20% | 0.48559 | 0.097118 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--19 | Project_021_Risk--19 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs | Person_436 | 2018-01-21 01:00 | 2019-01-20 01:00 | 20% | 0.48559 | 0.097118 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--19 | Project_021_Risk--19 | Threat | Project Contingency | Open | H2 | 2 |  | Engineering support is not available to support Tech Pubs | Person_436 | 2018-01-21 01:00 | 2019-01-20 01:00 | 20% | 0.48559 | 0.097118 | Reduce | 10% | 0.48559 | 0.048559 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-073 | Project_007_R-073 | Threat | Project Contingency | Open | H2 | 2 |  | Legacy System Issues | Person_386 | 2013-12-03 19:00 | 2016-02-19 19:00 | 70% | 0.55755 | 0.39029 | Reduce | 40% | 0.12197 | 0.048788 | H2 | 2 | Stable | TRUE | 808 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 105.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2016-11-19 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 105 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 105.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-01-20 01:00 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 167.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-01-20 01:00 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 167.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-03-22 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 228 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK001 | Project_086_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rework before Factory Acceptance Test | Person_048 | 2017-11-22 01:00 | 2018-10-21 01:00 | 30% | 0.33844 | 0.10153 | Accept | 30% | 0.33844 | 0.10153 | H2 | 2 | -- | TRUE | 333 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK052 | Project_097_RISK052 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SW Uplift - Penetration Test identifies critical vulnerabilities | Person_667 | 2018-11-21 01:00 | 2019-10-22 01:00 | 40% | 0.40806 | 0.16323 | Reduce | 25% | 0.40806 | 0.10202 | H2 | 2 | Stable | TRUE | 335 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 20% | 2.5604 | 0.51208 | Reduce | 5% | 2.0527 | 0.10264 | H2 | 2 | -- | TRUE | 91 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 | 2017-01-20 | 20% | 2.5604 | 0.51208 | Reduce | 5% | 2.0527 | 0.10264 | H2 | 2 | -- | TRUE | 91 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 20% | 2.5604 | 0.51208 | Reduce | 5% | 2.0527 | 0.10264 | H2 | 2 | -- | TRUE | 91 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 20% | 2.5604 | 0.51208 | Reduce | 5% | 2.0527 | 0.10264 | H2 | 2 | Improving | TRUE | 91 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 20% | 2.5604 | 0.51208 | Reduce | 5% | 2.0527 | 0.10264 | H2 | 2 | Improving | TRUE | 91 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R050 | Project_021_Risk-R050 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Trials delay due to failure of Customer modification Telemetry | Person_174 | 2016-10-21 01:00 | 2017-01-20 01:00 | 20% | 2.5604 | 0.51208 | Reduce | 5% | 2.0527 | 0.10264 | H2 | 2 | Improving | TRUE | 91 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2016-06-23 | 80% | 0.12834 | 0.10267 | Accept | 80% | 0.12834 | 0.10267 | H2 | 2 | Stable | TRUE | 337 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2016-08-21 01:00 | 80% | 0.12834 | 0.10267 | Accept | 80% | 0.12834 | 0.10267 | H2 | 2 | Stable | TRUE | 396.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2016-10-21 01:00 | 80% | 0.12834 | 0.10267 | Accept | 80% | 0.12834 | 0.10267 | H2 | 2 | Stable | TRUE | 457.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2016-10-21 01:00 | 80% | 0.12834 | 0.10267 | Accept | 80% | 0.12834 | 0.10267 | H2 | 2 | Stable | TRUE | 457.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK063 | Project_076_RISK063 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Delay - Artefact configuration | Person_771 | 2018-05-23 | 2019-10-22 01:00 | 25% | 0.41461 | 0.10365 | Accept | 25% | 0.41461 | 0.10365 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK063 | Project_076_RISK063 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Delay - Artefact configuration | Person_771 | 2018-05-23 | 2019-10-22 01:00 | 25% | 0.41461 | 0.10365 | Accept | 25% | 0.41461 | 0.10365 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK063 | Project_076_RISK063 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Delay - Artefact configuration | Person_771 | 2018-05-23 | 2019-10-22 01:00 | 25% | 0.41461 | 0.10365 | Accept | 25% | 0.41461 | 0.10365 | H3 | 3 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-06-22 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 320 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-06-22 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 320 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-06-22 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 320 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R062 | Project_021_Risk-R062 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to acceleration plan not working. | Person_721 | 2016-08-06 | 2017-06-22 | 30% | 1.076 | 0.32281 | Reduce | 5% | 1.076 | 0.053801 | H2 | 2 | Improving | TRUE | 320 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-065 | Project_011_Risk-065 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Live system changes allows provision for EAC challenge | Person_522 | 2013-08-21 01:00 | 2018-08-21 | 40% | 0.13638 | 0.054551 | Accept | 40% | 0.13638 | 0.054551 | H2 | 2 | -- | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-065 | Project_011_Risk-065 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Live system changes allows provision for EAC challenge | Person_522 | 2013-08-21 01:00 | 2018-08-21 | 40% | 0.13638 | 0.054551 | Accept | 40% | 0.13638 | 0.054551 | H2 | 2 | -- | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | System fails to achieve required performance | Person_051 | 2014-09-13 | 2018-03-21 | 30% | 0.57487 | 0.17246 | Reduce | 10% | 0.57487 | 0.057487 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK036 | Project_043_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | product reliability | Person_368 | 2014-09-13 01:00 | 2018-03-21 | 10% | 0.59882 | 0.059882 | Accept | 10% | 0.59882 | 0.059882 | H2 | 2 | -- | TRUE | 1284.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK072 | Project_043_RISK072 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Customer Repairs - Increased VAT Costs | Person_184 | 2014-09-13 | 2018-03-21 | 25% | 1.7965 | 0.44912 | -- | 10% | 0.59882 | 0.059882 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK036 | Project_043_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | product reliability | Person_368 | 2014-09-13 | 2018-03-21 | 10% | 0.59882 | 0.059882 | Accept | 10% | 0.59882 | 0.059882 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R018 | Project_021_Risk-R018 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Component required | Person_721 | 2016-02-21 | 2016-09-19 | 50% | 0.68424 | 0.34212 | Reduce | 10% | 0.68424 | 0.068424 | H2 | 2 | -- | TRUE | 211 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R018 | Project_021_Risk-R018 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Component required | Person_721 | 2016-02-20 23:00 | 2016-09-18 23:00 | 50% | 0.68424 | 0.34212 | Reduce | 10% | 0.68424 | 0.068424 | H2 | 2 | -- | TRUE | 211 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK057 | Project_043_RISK057 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Documentation | Person_056 | 2014-09-13 | 2018-03-21 | 25% | 0.28025 | 0.070062 | -- | 25% | 0.28025 | 0.070062 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK069 | Project_043_RISK069 | Threat | Project Contingency | Open | H2 | 2 |  | Iinterim to full operational capability scope | Person_084 | 2014-09-13 | 2018-03-21 | 30% | 1.4372 | 0.43115 | -- | 5% | 1.4372 | 0.071859 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-050 | Project_011_Risk-050 | Threat | Project Contingency | Open | H2 | 2 |  | Indications associated with each agreed fault have been misunderstood | Person_187 | 2013-08-21 01:00 | 2017-08-20 01:00 | 45% | 0.16195 | 0.072876 | Accept | 45% | 0.16195 | 0.072876 | H2 | 2 | -- | TRUE | 1460 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-050 | Project_011_Risk-050 | Threat | Project Contingency | Open | H2 | 2 |  | Indications associated with each agreed fault have been misunderstood | Person_187 | 2013-08-21 | 2017-08-20 | 45% | 0.16195 | 0.072876 | Accept | 45% | 0.16195 | 0.072876 | H2 | 2 | -- | TRUE | 1460 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-050 | Project_011_Risk-050 | Threat | Project Contingency | Open | H2 | 2 |  | Indications associated with each agreed fault have been misunderstood | Person_187 | 2013-08-21 | 2017-08-20 | 45% | 0.16195 | 0.072876 | Accept | 45% | 0.16195 | 0.072876 | H2 | 2 | -- | TRUE | 1460 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-050 | Project_011_Risk-050 | Threat | Project Contingency | Open | H2 | 2 |  | Indications associated with each agreed fault have been misunderstood | Person_187 | 2013-08-21 01:00 | 2017-08-20 01:00 | 45% | 0.16195 | 0.072876 | Accept | 45% | 0.16195 | 0.072876 | H2 | 2 | -- | TRUE | 1460 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-050 | Project_011_Risk-050 | Threat | Project Contingency | Open | H2 | 2 |  | Indications associated with each agreed fault have been misunderstood | Person_187 | 2013-08-21 01:00 | 2017-08-20 01:00 | 45% | 0.16195 | 0.072876 | Accept | 45% | 0.16195 | 0.072876 | H2 | 2 | -- | TRUE | 1460 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-050 | Project_011_Risk-050 | Threat | Project Contingency | Open | H2 | 2 |  | Indications associated with each agreed fault have been misunderstood | Person_187 | 2013-08-21 01:00 | 2017-08-20 01:00 | 45% | 0.16195 | 0.072876 | Accept | 45% | 0.16195 | 0.072876 | H2 | 2 | -- | TRUE | 1460 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 2 |  | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 0.65759 | 0.065759 | Accept | 10% | 0.75153 | 0.075153 | H2 | 2 | Stable | TRUE | 1461 |  | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 2 |  | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 0.65759 | 0.065759 | Accept | 10% | 0.75153 | 0.075153 | H2 | 2 | Stable | TRUE | 1461 |  | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 2 |  | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 0.65759 | 0.065759 | Accept | 10% | 0.75153 | 0.075153 | H2 | 2 | Stable | TRUE | 1461 |  | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 2 |  | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 0.65759 | 0.065759 | Accept | 10% | 0.75153 | 0.075153 | H2 | 2 | Stable | TRUE | 1461 |  | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 2 |  | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 0.65759 | 0.065759 | Accept | 10% | 0.75153 | 0.075153 | H2 | 2 | Stable | TRUE | 1461 |  | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R80 | Project_041_R80 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Reduction in System non-recurring cost | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 33% | 0.21008 | 0.069327 | -- | 50% | 0.21008 | 0.10504 | H3 | 3 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 2 |  | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 0.65759 | 0.065759 | Accept | 10% | 0.75153 | 0.075153 | H2 | 2 | Stable | TRUE | 1461 |  | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk016 | Project_042_Risk016 | Threat | Project Contingency | Open | H2 | 2 |  | Transport/Delivery Speed | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 0.65759 | 0.065759 | Accept | 10% | 0.75153 | 0.075153 | H2 | 2 | Stable | TRUE | 1461 |  | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_080 | RISK010 | Project_080_RISK010 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Additional Spares and repairs | Person_493 | 2018-04-22 | 2018-11-21 01:00 | 50% | 0.15395 | 0.076976 | Exploit | 50% | 0.15395 | 0.076976 | H2 | 2 | -- | TRUE | 213.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_080 | RISK007 | Project_080_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Avaliablity of key resource | Person_493 | 2017-11-20 01:00 | 2018-12-21 01:00 | 70% | 0.23093 | 0.16165 | Reduce | 50% | 0.15395 | 0.076976 | H2 | 2 | -- | TRUE | 396 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_080 | RISK009 | Project_080_RISK009 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Provide quote for next generation system | Person_493 | 2012-09-20 01:00 | 2018-12-20 01:00 | 50% | 0.15395 | 0.076976 | -- | 50% | 0.15395 | 0.076976 | H2 | 2 | -- | TRUE | 2282 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK001 | Project_074_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Material Delivery date | Person_263 | 2017-09-20 01:00 | 2019-11-21 01:00 | 70% | 0.19991 | 0.13994 | Reduce | 40% | 0.19991 | 0.079966 | H2 | 2 | -- | TRUE | 792 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 30% | 0.35617 | 0.10685 | Accept | 30% | 0.35617 | 0.10685 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 30% | 0.35617 | 0.10685 | Accept | 30% | 0.35617 | 0.10685 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 30% | 0.35617 | 0.10685 | Accept | 30% | 0.35617 | 0.10685 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 30% | 0.35617 | 0.10685 | Accept | 30% | 0.35617 | 0.10685 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 | 2017-01-20 | 30% | 0.35617 | 0.10685 | Accept | 30% | 0.35617 | 0.10685 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 30% | 0.35617 | 0.10685 | Accept | 30% | 0.35617 | 0.10685 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-111 | Project_039_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Maturation results inconclusive | Person_297 | 2016-02-21 01:00 | 2017-01-20 01:00 | 30% | 0.35617 | 0.10685 | Accept | 30% | 0.35617 | 0.10685 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-19 01:00 | 2018-10-20 01:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-19 01:00 | 2018-10-20 01:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-19 | 2018-10-20 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-19 01:00 | 2018-10-20 01:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-18 23:00 | 2018-10-19 23:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-18 22:00 | 2018-10-19 22:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-18 23:00 | 2018-10-19 23:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-19 01:00 | 2018-10-20 01:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-18 22:00 | 2018-10-19 22:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-19 | 2018-10-20 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-19 01:00 | 2018-10-20 01:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK107 | Project_065_RISK107 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Integration of sub-system Developed Control Aspects with Internal systems | Person_404 | 2016-08-18 23:00 | 2018-10-19 23:00 | 30% | 1.087 | 0.32611 | Reduce | 20% | 0.54258 | 0.10852 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-098 | Project_039_Risk-098 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Supplier unable to provide compiant power source | Person_040 | 2015-07-24 | 2016-01-21 01:00 | 50% | 1.0875 | 0.54376 | Reduce | 10% | 1.0875 | 0.10875 | H3 | 3 | Stable | TRUE | 181.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-018 | Project_023_Risk-018 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Project Management | Person_703 | 2013-05-19 | 2017-05-22 | 80% | 0.10892 | 0.087134 | Exploit | 80% | 0.13615 | 0.10892 | H2 | 2 | Stable | TRUE | 1464 |  | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 20% | 0.55005 | 0.11001 | Avoid | 20% | 0.55005 | 0.11001 | H2 | 2 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 20% | 0.55005 | 0.11001 | Avoid | 20% | 0.55005 | 0.11001 | H2 | 2 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 20% | 0.55005 | 0.11001 | Avoid | 20% | 0.55005 | 0.11001 | H2 | 2 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 20% | 0.55005 | 0.11001 | Avoid | 20% | 0.55005 | 0.11001 | H2 | 2 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 20% | 0.55005 | 0.11001 | Avoid | 20% | 0.55005 | 0.11001 | H2 | 2 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-101 | Project_011_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer Acceptance of the System | Person_147 | 2017-04-22 | 2018-08-21 | 20% | 0.55005 | 0.11001 | Avoid | 20% | 0.55005 | 0.11001 | H2 | 2 | Stable | TRUE | 486 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 70% | 0.92411 | 0.64688 | Reduce | 30% | 0.36965 | 0.11089 | H2 | 2 | Worsening | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 70% | 0.92411 | 0.64688 | Reduce | 30% | 0.36965 | 0.11089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 70% | 0.92411 | 0.64688 | Reduce | 30% | 0.36965 | 0.11089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 70% | 0.92411 | 0.64688 | Reduce | 30% | 0.36965 | 0.11089 | H2 | 2 | Stable | TRUE | 1906 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 70% | 0.92411 | 0.64688 | Reduce | 30% | 0.36965 | 0.11089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 70% | 0.92411 | 0.64688 | Reduce | 30% | 0.36965 | 0.11089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 70% | 0.92411 | 0.64688 | Reduce | 30% | 0.36965 | 0.11089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 70% | 0.92411 | 0.64688 | Reduce | 30% | 0.36965 | 0.11089 | H2 | 2 | Stable | TRUE | 1906 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2016-09-11 01:00 | 2016-11-19 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 69 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK064 | Project_043_RISK064 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Publications overspend | Person_135 | 2014-09-13 | 2018-03-21 | 50% | 0.32576 | 0.16288 | -- | 25% | 0.32576 | 0.08144 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2016-09-11 | 2016-11-19 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 69 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Cable and connectors | Person_050 | 2015-11-21 | 2017-08-09 | 45% | 0.41338 | 0.18602 | Reduce | 20% | 0.41338 | 0.082677 | H2 | 2 | Stable | TRUE | 627 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2016-09-11 01:00 | 2016-11-19 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 69 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 45% | 0.41338 | 0.18602 | Reduce | 20% | 0.41338 | 0.082677 | H2 | 2 | Stable | TRUE | 626.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2016-09-11 01:00 | 2017-01-04 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 115 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2016-09-11 01:00 | 2017-01-04 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 115 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2016-09-11 01:00 | 2017-01-04 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 115 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2017-10-21 01:00 | 2017-12-20 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 60 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2017-10-21 01:00 | 2017-12-20 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 60 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2017-10-21 01:00 | 2017-12-20 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 60 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2017-10-21 01:00 | 2017-12-20 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 60 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-012 | Project_021_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Delay due to build standard issue | Person_174 | 2017-10-21 01:00 | 2017-12-20 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 60 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--01 | Project_021_Risk--01 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Qualification/ delay due to build standard issue | Person_615 | 2018-02-20 01:00 | 2018-06-22 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 45% | 0.41338 | 0.18602 | Reduce | 20% | 0.41338 | 0.082677 | H2 | 2 | Stable | TRUE | 626.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 45% | 0.41338 | 0.18602 | Reduce | 20% | 0.41338 | 0.082677 | H2 | 2 | Stable | TRUE | 626.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 45% | 0.41338 | 0.18602 | Reduce | 20% | 0.41338 | 0.082677 | H2 | 2 | Stable | TRUE | 626.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1008 | Project_091_RISK1008 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Late supplier delivery of components could impact customer deliveries | Person_261 | 2018-08-22 01:00 | 2026-05-21 | 70% | 0.15989 | 0.11192 | Reduce | 70% | 0.15989 | 0.11192 | H1 | 1 | -- | TRUE | 2828.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK029 | Project_042_RISK029 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares 1st October to 31st December | Person_455 | 2020-11-20 01:00 | 2021-05-22 | 25% | 1.8788 | 0.46971 | Accept | 10% | 1.1273 | 0.11273 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Cable and connectors | Person_050 | 2015-11-21 01:00 | 2017-08-09 | 45% | 0.41338 | 0.18602 | Reduce | 20% | 0.41338 | 0.082677 | H2 | 2 | Stable | TRUE | 626.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2017-08-09 | 45% | 0.41338 | 0.18602 | Reduce | 20% | 0.41338 | 0.082677 | H2 | 2 | Stable | TRUE | 626.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-004 | Project_028_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Cable and connectors | Person_499 | 2015-11-21 01:00 | 2017-08-09 | 45% | 0.41338 | 0.18602 | Reduce | 20% | 0.41338 | 0.082677 | H2 | 2 | Stable | TRUE | 626.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK001 | Project_073_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Material Delivery date | Person_263 | 2017-09-20 01:00 | 2019-08-01 | 70% | 0.20901 | 0.1463 | Reduce | 40% | 0.20901 | 0.083602 | H2 | 2 | -- | TRUE | 679.9583 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-06-24 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 72 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-06-24 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 72 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-06-24 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 72 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-06-24 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 72 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-06-24 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 72 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-06-24 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 72 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-06-24 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 72 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-09-14 01:00 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 154.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-06-24 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 72 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-09-14 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 154 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-09-14 01:00 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 154.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK477 | Project_065_RISK477 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Final selected components do not fit within the equipment | Person_661 | 2018-04-13 | 2018-09-13 23:00 | 80% | 2.3326 | 1.8661 | Reduce | 15% | 0.77077 | 0.11562 | H3 | 3 | -- | TRUE | 153.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-20 01:00 | 2018-05-22 | 15% | 1.1576 | 0.17364 | Reduce | 10% | 1.1576 | 0.11576 | H3 | 3 | -- | FALSE | 547.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-20 01:00 | 2018-05-22 | 15% | 1.1576 | 0.17364 | Reduce | 10% | 1.1576 | 0.11576 | H3 | 3 | Stable | FALSE | 547.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-20 | 2018-05-22 | 15% | 1.1576 | 0.17364 | Reduce | 10% | 1.1576 | 0.11576 | H3 | 3 | Stable | FALSE | 548 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-19 23:00 | 2018-05-22 | 15% | 1.1576 | 0.17364 | Reduce | 10% | 1.1576 | 0.11576 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-19 23:00 | 2018-05-22 | 15% | 1.1576 | 0.17364 | Reduce | 10% | 1.1576 | 0.11576 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-19 23:00 | 2018-05-22 | 15% | 1.1576 | 0.17364 | Reduce | 10% | 1.1576 | 0.11576 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Availability of key resource within production or Engineering | Person_359 | 2016-11-19 22:00 | 2018-05-22 | 15% | 1.1576 | 0.17364 | Reduce | 10% | 1.1576 | 0.11576 | H3 | 3 | Stable | FALSE | 548.0833 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R091 | Project_044_Risk-R091 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Receive System Performance | Person_044 | 2017-11-20 01:00 | 2018-11-21 01:00 | 5% | 2.318 | 0.1159 | Accept | 5% | 2.318 | 0.1159 | H3 | 3 | Stable | FALSE | 366 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK015 | Project_074_RISK015 | Threat | Project Contingency | Open | H2 | 2 |  | Shelf life products | Person_263 | 2017-09-20 01:00 | 2019-11-21 01:00 | 80% | 0.27988 | 0.2239 | Reduce | 30% | 0.27988 | 0.083964 | H2 | 2 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK028 | Project_075_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | Altitude impact | Person_636 | 2018-03-07 01:00 | 2018-11-20 01:00 | 45% | 0.84371 | 0.37967 | Reduce | 10% | 0.84371 | 0.084371 | H2 | 2 | -- | TRUE | 258 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK026 | Project_075_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Desiccant Solution required needs to be resolved | Person_636 | 2017-09-20 01:00 | 2018-07-21 | 50% | 0.84371 | 0.42185 | Reduce | 10% | 0.84371 | 0.084371 | H2 | 2 | -- | TRUE | 303.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK028 | Project_075_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | Altitude impact | Person_636 | 2018-03-07 01:00 | 2018-11-20 01:00 | 45% | 0.84371 | 0.37967 | Reduce | 10% | 0.84371 | 0.084371 | H2 | 2 | -- | TRUE | 258 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK026 | Project_075_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Desiccant Solution required needs to be resolved | Person_636 | 2017-09-20 01:00 | 2018-07-21 | 50% | 0.84371 | 0.42185 | Reduce | 10% | 0.84371 | 0.084371 | H2 | 2 | -- | TRUE | 303.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK028 | Project_075_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | Altitude impact | Person_636 | 2018-03-07 01:00 | 2018-11-20 01:00 | 45% | 0.84371 | 0.37967 | Reduce | 10% | 0.84371 | 0.084371 | H2 | 2 | -- | TRUE | 258 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK026 | Project_075_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Desiccant Solution required needs to be resolved | Person_636 | 2017-09-20 01:00 | 2018-07-21 | 50% | 0.84371 | 0.42185 | Reduce | 10% | 0.84371 | 0.084371 | H2 | 2 | -- | TRUE | 303.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK028 | Project_075_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | Altitude impact | Person_636 | 2018-03-07 01:00 | 2018-11-20 01:00 | 45% | 0.84371 | 0.37967 | Reduce | 10% | 0.84371 | 0.084371 | H2 | 2 | -- | TRUE | 258 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK028 | Project_075_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | Altitude impact | Person_636 | 2018-03-07 01:00 | 2018-11-20 01:00 | 45% | 0.84371 | 0.37967 | Reduce | 10% | 0.84371 | 0.084371 | H2 | 2 | -- | TRUE | 258 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK013 | Project_073_RISK013 | Threat | Project Contingency | Open | H2 | 2 |  | Shelf Life of products | Person_263 | 2017-09-20 01:00 | 2019-08-01 | 80% | 0.29261 | 0.23409 | Reduce | 30% | 0.29261 | 0.087782 | H2 | 2 | -- | TRUE | 679.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK033 | Project_043_RISK033 | Threat | Project Contingency | Open | H2 | 2 |  | Tricky repair (above the estimated cost) | Person_368 | 2014-09-13 | 2018-03-21 | 20% | 0.47906 | 0.095811 | -- | 20% | 0.47906 | 0.095811 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-08 01:00 | 2017-11-26 01:00 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-08 01:00 | 2017-11-26 01:00 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-08 | 2017-11-26 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK062 | Project_043_RISK062 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence | Person_769 | 2014-09-13 | 2018-03-21 | 20% | 0.59882 | 0.11976 | -- | 20% | 0.59882 | 0.11976 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-07 23:00 | 2017-11-25 23:00 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK042 | Project_042_RISK042 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | STTE 1st February to 14th July | Person_455 | 2020-06-23 | 2020-12-03 01:00 | 10% | 1.8788 | 0.18788 | Accept | 8% | 1.5031 | 0.12024 | H2 | 2 | Stable | TRUE | 163.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK041 | Project_042_RISK041 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | STTE 1st November to 31st Jan | Person_455 | 2020-03-23 | 2020-06-22 | 10% | 1.8788 | 0.18788 | Accept | 8% | 1.5031 | 0.12024 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK043 | Project_042_RISK043 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | STTE 1st November to 31st December | Person_455 | 2021-03-23 | 2021-05-22 | 10% | 1.8788 | 0.18788 | Accept | 8% | 1.5031 | 0.12024 | H3 | 3 | Stable | FALSE | 60 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R008 | Project_044_Risk-R008 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Engineering Skills | Person_505 | 2017-10-21 01:00 | 2018-10-22 01:00 | 20% | 1.5695 | 0.3139 | Reduce | 10% | 1.2073 | 0.12073 | H3 | 3 | Stable | FALSE | 366 |  | 1 | 0 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK003 | Project_097_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SW Uplift - Additional Software Release | Person_667 | 2018-09-22 01:00 | 2019-06-29 | 35% | 0.80539 | 0.28189 | Avoid | 15% | 0.80539 | 0.12081 | H2 | 2 | Stable | TRUE | 279.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-200 | Project_039_Risk-200 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | SWAP of SubSystem Modules | Person_531 | 2016-07-21 | 2016-10-19 01:00 | 20% | 2.4183 | 0.48366 | Reduce | 10% | 1.2092 | 0.12092 | H3 | 3 | -- | TRUE | 90.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-200 | Project_039_Risk-200 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | SWAP of SubSystem Modules | Person_531 | 2016-07-21 | 2016-11-19 01:00 | 20% | 2.4183 | 0.48366 | Reduce | 10% | 1.2092 | 0.12092 | H3 | 3 | -- | TRUE | 121.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-200 | Project_039_Risk-200 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | SWAP of SubSystem Modules | Person_531 | 2016-07-21 | 2016-11-19 01:00 | 20% | 2.4183 | 0.48366 | Reduce | 10% | 1.2092 | 0.12092 | H3 | 3 | -- | TRUE | 121.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-200 | Project_039_Risk-200 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | SWAP of SubSystem Modules | Person_531 | 2016-07-21 | 2016-11-19 01:00 | 20% | 2.4183 | 0.48366 | Reduce | 10% | 1.2092 | 0.12092 | H3 | 3 | -- | TRUE | 121.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-200 | Project_039_Risk-200 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | SWAP of SubSystem Modules | Person_531 | 2016-07-21 | 2016-11-19 | 20% | 2.4183 | 0.48366 | Reduce | 10% | 1.2092 | 0.12092 | H3 | 3 | -- | TRUE | 121 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-200 | Project_039_Risk-200 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | SWAP of SubSystem Modules | Person_531 | 2016-07-21 | 2016-11-19 01:00 | 20% | 2.4183 | 0.48366 | Reduce | 10% | 1.2092 | 0.12092 | H3 | 3 | -- | TRUE | 121.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-200 | Project_039_Risk-200 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | SWAP of SubSystem Modules | Person_531 | 2016-07-21 | 2016-11-19 01:00 | 20% | 2.4183 | 0.48366 | Reduce | 10% | 1.2092 | 0.12092 | H3 | 3 | -- | TRUE | 121.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK034 | Project_042_RISK034 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) 1st July to 30 September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 20% | 1.0334 | 0.20667 | Accept | 15% | 0.80789 | 0.12118 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2017-10-05 01:00 | 2018-07-19 | 60% | 20.4355 | 12.2613 | Reduce | 10% | 1.217 | 0.1217 | H3 | 3 | -- | FALSE | 286.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2017-10-05 01:00 | 2018-07-19 | 60% | 20.4355 | 12.2613 | Reduce | 10% | 1.217 | 0.1217 | H3 | 3 | -- | FALSE | 286.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2017-10-05 | 2018-07-19 | 60% | 20.4355 | 12.2613 | Reduce | 10% | 1.217 | 0.1217 | H3 | 3 | -- | FALSE | 287 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2017-10-05 01:00 | 2018-07-19 | 60% | 20.4355 | 12.2613 | Reduce | 10% | 1.217 | 0.1217 | H3 | 3 | -- | FALSE | 286.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2017-10-04 23:00 | 2018-07-19 | 60% | 20.4355 | 12.2613 | Reduce | 10% | 1.217 | 0.1217 | H3 | 3 | -- | FALSE | 287.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2017-10-04 22:00 | 2018-07-19 | 60% | 20.4355 | 12.2613 | Reduce | 10% | 1.217 | 0.1217 | H3 | 3 | -- | FALSE | 287.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2017-10-04 23:00 | 2018-07-19 | 60% | 20.4355 | 12.2613 | Reduce | 10% | 1.217 | 0.1217 | H3 | 3 | -- | FALSE | 287.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-07 22:00 | 2017-11-25 22:00 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK465 | Project_065_RISK465 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement on new requirements with Customer cannot be reached for heat and power consumption | Person_661 | 2017-10-04 22:00 | 2018-07-19 | 60% | 20.4355 | 12.2613 | Reduce | 10% | 1.217 | 0.1217 | H3 | 3 | -- | FALSE | 287.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-07 23:00 | 2017-11-25 23:00 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-08 01:00 | 2017-11-26 01:00 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-08 | 2017-11-26 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-08 01:00 | 2017-11-26 01:00 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK042 | Project_065_RISK042 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal management can’t dissipate required heat load | Person_661 | 2016-09-07 23:00 | 2017-11-25 23:00 | 10% | 1.9523 | 0.19523 | Reduce | 10% | 0.9736 | 0.09736 | H2 | 2 | -- | TRUE | 444 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 2 |  | Re-imaging of PC's - additional material | Person_515 | 2016-11-20 01:00 | 2017-10-21 01:00 | 50% | 0.21008 | 0.10504 | Avoid | 50% | 0.21008 | 0.10504 | H2 | 2 | -- | TRUE | 335 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 2 |  | Re-imaging of PC's - additional material | Person_515 | 2016-11-20 01:00 | 2017-10-21 01:00 | 50% | 0.21008 | 0.10504 | Avoid | 50% | 0.21008 | 0.10504 | H2 | 2 | Stable | TRUE | 335 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 2 |  | Re-imaging of PC's - additional material | Person_515 | 2016-11-20 | 2017-10-21 | 50% | 0.21008 | 0.10504 | Avoid | 50% | 0.21008 | 0.10504 | H2 | 2 | Stable | TRUE | 335 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 2 |  | Re-imaging of PC's - additional material | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 50% | 0.21008 | 0.10504 | Avoid | 50% | 0.21008 | 0.10504 | H2 | 2 | Stable | TRUE | 335 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 2 |  | Re-imaging of PC's - additional material | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 50% | 0.21008 | 0.10504 | Avoid | 50% | 0.21008 | 0.10504 | H2 | 2 | Stable | TRUE | 335 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 2 |  | Re-imaging of PC's - additional material | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 50% | 0.21008 | 0.10504 | Avoid | 50% | 0.21008 | 0.10504 | H2 | 2 | Stable | TRUE | 335 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R81 | Project_041_R81 | Threat | Project Contingency | Open | H2 | 2 |  | Re-imaging of PC's - additional material | Person_515 | 2016-11-19 22:00 | 2017-10-20 22:00 | 50% | 0.21008 | 0.10504 | Avoid | 50% | 0.21008 | 0.10504 | H2 | 2 | Stable | TRUE | 335 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R039 | Project_021_Risk-R039 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to build standard issue | Person_174 | 2016-07-27 | 2016-08-21 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 25.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R039 | Project_021_Risk-R039 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to build standard issue | Person_174 | 2016-07-27 | 2016-08-21 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 25 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 25% | 0.49834 | 0.12459 | Accept | 25% | 0.49834 | 0.12459 | H3 | 3 | Stable | TRUE | 852 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 25% | 0.49834 | 0.12459 | Accept | 25% | 0.49834 | 0.12459 | H3 | 3 | Stable | TRUE | 852 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 25% | 0.49834 | 0.12459 | Accept | 25% | 0.49834 | 0.12459 | H3 | 3 | Stable | TRUE | 852 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 25% | 0.49834 | 0.12459 | Accept | 25% | 0.49834 | 0.12459 | H3 | 3 | Stable | TRUE | 852 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 25% | 0.49834 | 0.12459 | Accept | 25% | 0.49834 | 0.12459 | H3 | 3 | Stable | TRUE | 852 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-095 | Project_011_Risk-095 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Issues found during integration of Customer sub-system resulting in PO uplift or contract change | Person_230 | 2016-04-21 | 2018-08-21 | 25% | 0.49834 | 0.12459 | Accept | 25% | 0.49834 | 0.12459 | H3 | 3 | Stable | TRUE | 852 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2017-01-20 01:00 | 50% | 16.3745 | 8.1873 | Accept | 5% | 2.5077 | 0.12538 | H3 | 3 | Stable | FALSE | 1876 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2017-01-20 01:00 | 50% | 16.3745 | 8.1873 | Accept | 5% | 2.5077 | 0.12538 | H3 | 3 | Stable | FALSE | 1876 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-012 | Project_062_Risk-012 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Integration Rig Move | Person_253 | 2018-05-23 | 2019-05-23 | 30% | 0.4183 | 0.12549 | Avoid | 30% | 0.4183 | 0.12549 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK015 | Project_062_RISK015 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Absence of evidence underpinning the supporting CoDs and thus the Safety Case. | Person_253 | 2018-09-21 01:00 | 2019-02-21 01:00 | 80% | 0.62744 | 0.50196 | Avoid | 20% | 0.62744 | 0.12549 | H3 | 3 | Stable | FALSE | 153 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK014 | Project_062_RISK014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rework to kits following Factory Acceptance Test | Person_253 | 2018-11-21 01:00 | 2019-04-22 | 20% | 0.62744 | 0.12549 | Avoid | 20% | 0.62744 | 0.12549 | H3 | 3 | Stable | FALSE | 151.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK085 | Project_049_RISK085 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Maintenance | Person_282 | 2018-09-15 01:00 | 2020-08-24 01:00 | 25% | 2.5203 | 0.63008 | Reduce | 5% | 2.5203 | 0.12602 | H3 | 3 | -- | TRUE | 709 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 20% | 0.63074 | 0.12615 | -- | 20% | 0.63074 | 0.12615 | H2 | 2 | Stable | TRUE | 58.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 | 20% | 0.63074 | 0.12615 | -- | 20% | 0.63074 | 0.12615 | H2 | 2 | Stable | TRUE | 58 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 | 20% | 0.63074 | 0.12615 | -- | 20% | 0.63074 | 0.12615 | H2 | 2 | Stable | TRUE | 58 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 20% | 0.63074 | 0.12615 | -- | 20% | 0.63074 | 0.12615 | H2 | 2 | Stable | TRUE | 58.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 20% | 0.63074 | 0.12615 | -- | 20% | 0.63074 | 0.12615 | H2 | 2 | Stable | TRUE | 58.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-123 | Project_011_Risk-123 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | No Requirement for Delta acceptance | Person_187 | 2017-06-23 | 2017-08-20 01:00 | 20% | 0.63074 | 0.12615 | -- | 20% | 0.63074 | 0.12615 | H2 | 2 | Stable | TRUE | 58.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R039 | Project_021_Risk-R039 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to build standard issue | Person_174 | 2016-07-27 | 2016-08-21 01:00 | 10% | 2.2183 | 0.22183 | Reduce | 5% | 2.2183 | 0.11091 | H2 | 2 | -- | TRUE | 25.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK019 | Project_058_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Licenses (Legacy) | Person_511 | 2018-01-21 01:00 | 2018-11-07 01:00 | 60% | 1.9574 | 1.1744 | Reduce | 30% | 0.39148 | 0.11744 | H2 | 2 | -- | TRUE | 290 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK019 | Project_058_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Licenses (Legacy) | Person_511 | 2018-01-21 01:00 | 2018-11-07 01:00 | 60% | 1.9574 | 1.1744 | Reduce | 30% | 0.39148 | 0.11744 | H2 | 2 | -- | TRUE | 290 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK019 | Project_058_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Licenses (Legacy) | Person_109 | 2018-01-21 01:00 | 2018-11-07 01:00 | 60% | 1.9574 | 1.1744 | Reduce | 30% | 0.39148 | 0.11744 | H2 | 2 | -- | TRUE | 290 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK019 | Project_058_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Licenses (Legacy) | Person_109 | 2018-01-21 01:00 | 2018-11-07 01:00 | 60% | 1.9574 | 1.1744 | Reduce | 30% | 0.39148 | 0.11744 | H2 | 2 | -- | TRUE | 290 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK019 | Project_058_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Licenses (Legacy) | Person_109 | 2018-01-21 01:00 | 2018-11-07 01:00 | 60% | 1.9574 | 1.1744 | Reduce | 30% | 0.39148 | 0.11744 | H2 | 2 | -- | TRUE | 290 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK019 | Project_058_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Licenses (Legacy) | Person_109 | 2018-01-21 01:00 | 2018-11-07 01:00 | 60% | 1.9574 | 1.1744 | Reduce | 30% | 0.39148 | 0.11744 | H2 | 2 | -- | TRUE | 290 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK019 | Project_058_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Licenses (Legacy) | Person_109 | 2018-01-21 01:00 | 2018-11-07 01:00 | 60% | 1.9574 | 1.1744 | Reduce | 30% | 0.39148 | 0.11744 | H2 | 2 | -- | TRUE | 290 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK005 | Project_074_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence of the boards | Person_595 | 2017-09-20 01:00 | 2019-11-21 01:00 | 30% | 0.39983 | 0.11995 | Accept | 30% | 0.39983 | 0.11995 | H2 | 2 | -- | TRUE | 792 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK538 | Project_065_RISK538 | Threat | Project Contingency | Open | H2 | 2 |  | Information provided to the connector supplier ahead of CDR is immature and leads to redesign | Person_661 | 2018-04-22 | 2018-09-17 01:00 | 30% | 1.217 | 0.3651 | Reduce | 10% | 1.217 | 0.1217 | H2 | 2 | -- | TRUE | 148.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK538 | Project_065_RISK538 | Threat | Project Contingency | Open | H2 | 2 |  | Information provided to the connector supplier ahead of CDR is immature and leads to redesign | Person_661 | 2018-04-22 | 2018-09-17 | 30% | 1.217 | 0.3651 | Reduce | 10% | 1.217 | 0.1217 | H2 | 2 | -- | TRUE | 148 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK538 | Project_065_RISK538 | Threat | Project Contingency | Open | H2 | 2 |  | Information provided to the connector supplier ahead of CDR is immature and leads to redesign | Person_661 | 2018-04-22 | 2018-09-17 01:00 | 30% | 1.217 | 0.3651 | Reduce | 10% | 1.217 | 0.1217 | H2 | 2 | -- | TRUE | 148.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK538 | Project_065_RISK538 | Threat | Project Contingency | Open | H2 | 2 |  | Information provided to the connector supplier ahead of CDR is immature and leads to redesign | Person_661 | 2018-04-22 | 2018-09-16 23:00 | 30% | 1.217 | 0.3651 | Reduce | 10% | 1.217 | 0.1217 | H2 | 2 | -- | TRUE | 147.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK044 | Project_043_RISK044 | Threat | Project Contingency | Open | H2 | 2 |  | T&E - Additional Support / data is required | Person_367 | 2014-09-13 | 2018-03-21 | 40% | 0.32336 | 0.12935 | -- | 40% | 0.32336 | 0.12935 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK112 | Project_066_RISK112 | Threat | Project Contingency | Open | H2 | 2 |  | SW vulnerability issues | Person_507 | 2018-10-22 01:00 | 2019-06-24 | 30% | 1.345 | 0.4035 | -- | 10% | 1.345 | 0.1345 | H2 | 2 | -- | TRUE | 244.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-084 | Project_043_Risk-084 | Threat | Project Contingency | Open | H2 | 2 |  | complex repair ( over and above the forecast average) | Person_693 | 2017-12-20 22:00 | 2020-12-20 22:00 | 20% | 0.71859 | 0.14372 | Reduce | 20% | 0.71859 | 0.14372 | H2 | 2 | Stable | TRUE | 1096 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 70% | 0.84985 | 0.5949 | -- | 18% | 0.84985 | 0.15297 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 70% | 0.84985 | 0.5949 | -- | 18% | 0.84985 | 0.15297 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 70% | 0.84985 | 0.5949 | -- | 18% | 0.84985 | 0.15297 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 70% | 0.84985 | 0.5949 | -- | 18% | 0.84985 | 0.15297 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK024 | Project_012_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Component Repair & test costs | Person_359 | 2015-04-04 | 2016-04-12 | 70% | 0.84985 | 0.5949 | -- | 18% | 0.84985 | 0.15297 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK027 | Project_058_RISK027 | Threat | Project Contingency | Open | H2 | 2 |  | Damage to repair parts | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 0.39148 | 0.15659 | Reduce | 40% | 0.39148 | 0.15659 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK019 | Project_058_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Licenses (Legacy) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 0.39148 | 0.15659 | Reduce | 40% | 0.39148 | 0.15659 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK014 | Project_092_RISK014 | Threat | Project Contingency | Open | H2 | 2 |  | Unit EMC or Environmental Failure | Person_169 | 2019-11-01 01:00 | 2020-04-22 | 30% | 0.5476 | 0.16428 | Accept | 30% | 0.5476 | 0.16428 | H2 | 2 | -- | TRUE | 172.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK040 | Project_042_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | STTE 1st May to 30 Oct | Person_455 | 2019-09-21 01:00 | 2020-03-21 | 10% | 1.8788 | 0.18788 | Accept | 7% | 1.8225 | 0.12757 | H2 | 2 | Stable | TRUE | 181.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_703 | 2011-05-24 | 2018-11-20 01:00 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 1.2807 | 0.12807 | H3 | 3 | -- | TRUE | 2737.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2016-07-20 | 61% | 0.25667 | 0.15657 | Reduce | 50% | 0.25667 | 0.12834 | H2 | 2 | Stable | TRUE | 576.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 61% | 0.25667 | 0.15657 | Reduce | 50% | 0.25667 | 0.12834 | H2 | 2 | Stable | TRUE | 2037.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 61% | 0.25667 | 0.15657 | Reduce | 50% | 0.25667 | 0.12834 | H2 | 2 | Stable | TRUE | 2037.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 61% | 0.25667 | 0.15657 | Reduce | 50% | 0.25667 | 0.12834 | H2 | 2 | Stable | TRUE | 2037.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 61% | 0.25667 | 0.15657 | Reduce | 50% | 0.25667 | 0.12834 | H2 | 2 | Stable | TRUE | 2037.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 61% | 0.25667 | 0.15657 | Reduce | 50% | 0.25667 | 0.12834 | H2 | 2 | Stable | TRUE | 2037.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 61% | 0.25667 | 0.15657 | Reduce | 50% | 0.25667 | 0.12834 | H2 | 2 | Stable | TRUE | 2037.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-091 | Project_029_Risk-091 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Lack of accreditation for Rig Equipment | Person_102 | 2014-12-21 01:00 | 2020-07-20 | 61% | 0.25667 | 0.15657 | Reduce | 50% | 0.25667 | 0.12834 | H2 | 2 | Stable | TRUE | 2037.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-102 | Project_039_Risk-102 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Component Structural Failure | Person_176 | 2015-11-21 01:00 | 2016-05-22 | 15% | 2.5686 | 0.38529 | Reduce | 5% | 2.5686 | 0.12843 | H3 | 3 | Stable | TRUE | 182.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK005 | Project_073_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence of the boards | Person_595 | 2017-09-20 01:00 | 2019-08-01 | 70% | 0.41801 | 0.29261 | Accept | 40% | 0.41801 | 0.1672 | H2 | 2 | -- | TRUE | 679.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK257 | Project_024_RISK257 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet complex Mission requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 1.2983 | 1.0386 | Reduce | 10% | 1.2983 | 0.12983 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK257 | Project_024_RISK257 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet complex Mission requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 1.2983 | 1.0386 | Reduce | 10% | 1.2983 | 0.12983 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK257 | Project_024_RISK257 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet complex Mission requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 1.2983 | 1.0386 | Reduce | 10% | 1.2983 | 0.12983 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK257 | Project_024_RISK257 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet complex Mission requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 1.2983 | 1.0386 | Reduce | 10% | 1.2983 | 0.12983 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK257 | Project_024_RISK257 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet complex Mission requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 1.2983 | 1.0386 | Reduce | 10% | 1.2983 | 0.12983 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK257 | Project_024_RISK257 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet complex Mission requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 1.2983 | 1.0386 | Reduce | 10% | 1.2983 | 0.12983 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK257 | Project_024_RISK257 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unable to meet complex Mission requirement | Person_318 | 2016-07-21 | 2017-05-23 | 80% | 1.2983 | 1.0386 | Reduce | 10% | 1.2983 | 0.12983 | H3 | 3 | -- | FALSE | 306 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_080 | RISK011 | Project_080_RISK011 | Threat | Project Contingency | Open | H2 | 2 |  | Working outside of contract | Person_493 | 2018-08-22 01:00 | 2018-12-21 01:00 | 70% | 0.46186 | 0.3233 | Reduce | 40% | 0.46186 | 0.18474 | H2 | 2 | -- | TRUE | 121 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-047 | Project_043_Risk-047 | Threat | Project Contingency | Open | H2 | 2 |  | Inability/Lack of Resource capability | Person_135 | 2014-09-13 | 2018-03-21 | 40% | 1.9162 | 0.76649 | Reduce | 10% | 1.9162 | 0.19162 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_080 | RISK008 | Project_080_RISK008 | Threat | Project Contingency | Open | H2 | 2 |  | TTE Supplier | Person_493 | 2012-09-20 01:00 | 2018-12-21 01:00 | 80% | 0.38488 | 0.3079 | Reduce | 50% | 0.38488 | 0.19244 | H2 | 2 | -- | TRUE | 2283 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK154 | Project_092_RISK154 | Threat | Project Contingency | Open | H2 | 2 |  | Signal Losses in Path | Person_002 | 2020-08-22 01:00 | 2021-12-04 01:00 | 50% | 1.9353 | 0.96767 | Reduce | 10% | 1.9353 | 0.19353 | H2 | 2 | -- | TRUE | 469 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-025 | Project_062_Risk-025 | Threat | Project Contingency | Open | H2 | 2 |  | System Obsolescence Risk | Person_543 | 2017-07-21 | 2019-03-22 | 30% | 2.0915 | 0.62744 | Avoid | 10% | 2.0915 | 0.20915 | H2 | 2 | Stable | TRUE | 609 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK026 | Project_075_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Desiccant Solution required needs to be resolved | Person_636 | 2017-09-20 01:00 | 2018-06-22 | 50% | 0.84371 | 0.42185 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 274.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK027 | Project_075_RISK027 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal impact from Chassis | Person_636 | 2017-04-22 | 2018-09-20 01:00 | 50% | 0.84371 | 0.42185 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 516.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK041 | Project_075_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Reliability does not meet requirement | Person_449 | 2018-05-23 | 2018-10-21 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 151.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK027 | Project_075_RISK027 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal impact from Chassis | Person_636 | 2017-04-22 | 2018-08-04 | 50% | 0.84371 | 0.42185 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 469 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK041 | Project_075_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Reliability does not meet requirement | Person_449 | 2018-05-23 | 2018-10-21 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 151.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK027 | Project_075_RISK027 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal impact from Chassis | Person_636 | 2017-04-22 | 2018-08-20 | 50% | 0.84371 | 0.42185 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 485 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-106 | Project_039_Risk-106 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Deliverables - Report Rework | Person_185 | 2014-12-22 01:00 | 2015-05-23 | 50% | 0.53661 | 0.2683 | Reduce | 25% | 0.53661 | 0.13415 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-036 | Project_026_Risk-036 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Greater number of defects identified at than anticipated | Person_607 | 2018-12-27 01:00 | 2022-10-28 01:00 | 15% | 1.343 | 0.20146 | Reduce | 10% | 1.343 | 0.1343 | H2 | 2 | -- | TRUE | 1401 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK041 | Project_075_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Reliability does not meet requirement | Person_449 | 2018-05-23 | 2018-10-21 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 151.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-020 | Project_077_T-020 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Cybersecurity | Person_544 | 2018-02-20 01:00 | 2020-02-21 01:00 | 10% | 1.3478 | 0.13478 | Reduce | 10% | 1.3478 | 0.13478 | H3 | 3 | Stable | FALSE | 731 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Mode Specific | Person_448 | 2016-07-20 | 2017-02-19 01:00 | 20% | 0.67512 | 0.13502 | Accept | 20% | 0.67512 | 0.13502 | H3 | 3 | Stable | TRUE | 214.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Mode Specific | Person_448 | 2015-09-04 01:00 | 2017-02-19 01:00 | 20% | 0.67512 | 0.13502 | Accept | 20% | 0.67512 | 0.13502 | H3 | 3 | Stable | TRUE | 534 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Mode Specific | Person_448 | 2015-09-04 01:00 | 2017-02-19 01:00 | 20% | 0.67512 | 0.13502 | Accept | 20% | 0.67512 | 0.13502 | H3 | 3 | Stable | TRUE | 534 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Mode Specific | Person_448 | 2015-09-04 01:00 | 2017-02-19 01:00 | 20% | 0.67512 | 0.13502 | Accept | 20% | 0.67512 | 0.13502 | H3 | 3 | Stable | TRUE | 534 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK202 | Project_024_RISK202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Mode Specific | Person_448 | 2015-09-04 01:00 | 2017-02-19 01:00 | 20% | 0.67512 | 0.13502 | Accept | 20% | 0.67512 | 0.13502 | H3 | 3 | Stable | TRUE | 534 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-041 | Project_028_Risk-041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Role Test Equipment Team Deliver Late | Person_542 | 2015-04-08 | 2016-11-19 | 40% | 0.681 | 0.2724 | Accept | 20% | 0.681 | 0.1362 | H2 | 2 | Stable | TRUE | 591 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-041 | Project_028_Risk-041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Role Test Equipment Team Deliver Late | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 40% | 0.681 | 0.2724 | Accept | 20% | 0.681 | 0.1362 | H2 | 2 | Stable | TRUE | 591.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-041 | Project_028_Risk-041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Role Test Equipment Team Deliver Late | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 40% | 0.681 | 0.2724 | Accept | 20% | 0.681 | 0.1362 | H2 | 2 | Stable | TRUE | 591.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-041 | Project_028_Risk-041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Role Test Equipment Team Deliver Late | Person_542 | 2015-04-08 | 2017-02-19 01:00 | 40% | 0.681 | 0.2724 | Accept | 20% | 0.681 | 0.1362 | H2 | 2 | Stable | TRUE | 683.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-103 | Project_039_Risk-103 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Performance when integrated not sufficient. | Person_176 | 2016-01-22 01:00 | 2016-06-20 | 20% | 0.68686 | 0.13737 | Accept | 20% | 0.68686 | 0.13737 | H3 | 3 | Stable | TRUE | 149.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 60% | 1.1089 | 0.66536 | Reduce | 30% | 0.46206 | 0.13862 | H2 | 2 | Worsening | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 60% | 1.1089 | 0.66536 | Reduce | 30% | 0.46206 | 0.13862 | H2 | 2 | Improving | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 60% | 1.1089 | 0.66536 | Reduce | 30% | 0.46206 | 0.13862 | H2 | 2 | Improving | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 60% | 1.1089 | 0.66536 | Reduce | 30% | 0.46206 | 0.13862 | H2 | 2 | Improving | TRUE | 1906 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 1906 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 60% | 1.1089 | 0.66536 | Reduce | 30% | 0.46206 | 0.13862 | H2 | 2 | Improving | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 60% | 1.1089 | 0.66536 | Reduce | 30% | 0.46206 | 0.13862 | H2 | 2 | Improving | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 60% | 1.1089 | 0.66536 | Reduce | 30% | 0.46206 | 0.13862 | H2 | 2 | Improving | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2017-08-20 | 60% | 1.1089 | 0.66536 | Reduce | 30% | 0.46206 | 0.13862 | H2 | 2 | Improving | TRUE | 1906 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2017-08-20 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 1906 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk27 | Project_010_Risk27 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Significant numbers of NoFaultFound returns during warranty period which affect production | Person_359 | 2012-06-01 | 2018-05-22 | 20% | 0.92411 | 0.18482 | Reduce | 15% | 0.92411 | 0.13862 | H3 | 3 | Stable | TRUE | 2181 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-081 | Project_011_Risk-081 | Threat | Project Contingency | Open | H2 | 2 | Customers | Incur LDs on Release 3 | Person_147 | 2014-08-22 01:00 | 2018-08-21 | 30% | 0.93077 | 0.27923 | Reduce | 15% | 0.93077 | 0.13962 | H2 | 2 | -- | TRUE | 1459.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-081 | Project_011_Risk-081 | Threat | Project Contingency | Open | H2 | 2 | Customers | Incur LDs on Release 3 | Person_147 | 2014-08-22 | 2018-08-21 | 30% | 0.93077 | 0.27923 | Reduce | 15% | 0.93077 | 0.13962 | H2 | 2 | -- | TRUE | 1460 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-081 | Project_011_Risk-081 | Threat | Project Contingency | Open | H2 | 2 | Customers | Incur LDs on Release 3 | Person_147 | 2014-08-22 | 2018-08-21 | 30% | 0.93077 | 0.27923 | Reduce | 15% | 0.93077 | 0.13962 | H2 | 2 | -- | TRUE | 1460 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-081 | Project_011_Risk-081 | Threat | Project Contingency | Open | H2 | 2 | Customers | Incur LDs on final Release | Person_147 | 2014-08-22 01:00 | 2018-08-21 | 30% | 0.93077 | 0.27923 | Reduce | 15% | 0.93077 | 0.13962 | H2 | 2 | -- | TRUE | 1459.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-081 | Project_011_Risk-081 | Threat | Project Contingency | Open | H2 | 2 | Customers | Incur LDs on final Release | Person_147 | 2014-08-22 01:00 | 2018-08-21 | 30% | 0.93077 | 0.27923 | Reduce | 15% | 0.93077 | 0.13962 | H2 | 2 | -- | TRUE | 1459.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-081 | Project_011_Risk-081 | Threat | Project Contingency | Open | H2 | 2 | Customers | Incur LDs on final Release | Person_147 | 2014-08-22 01:00 | 2018-08-21 | 30% | 0.93077 | 0.27923 | Reduce | 15% | 0.93077 | 0.13962 | H2 | 2 | -- | TRUE | 1459.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 2 | Customers | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.93941 | 0.14091 | Accept | 15% | 0.93941 | 0.14091 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 2 | Customers | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.93941 | 0.14091 | Accept | 15% | 0.93941 | 0.14091 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 2 | Customers | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.93941 | 0.14091 | Accept | 15% | 0.93941 | 0.14091 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 2 | Customers | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.93941 | 0.14091 | Accept | 15% | 0.93941 | 0.14091 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 2 | Customers | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.93941 | 0.14091 | Accept | 15% | 0.93941 | 0.14091 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 2 | Customers | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.93941 | 0.14091 | Accept | 15% | 0.93941 | 0.14091 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk014 | Project_042_Risk014 | Threat | Project Contingency | Open | H2 | 2 | Customers | Transport Routes | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 0.93941 | 0.14091 | Accept | 15% | 0.93941 | 0.14091 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--37 | Project_021_Risk--37 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay to delivery of Customer dependencies for Tech Pubs | Person_436 | 2018-08-22 01:00 | 2019-03-23 | 40% | 1.4347 | 0.57388 | Reduce | 20% | 0.71735 | 0.14347 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--37 | Project_021_Risk--37 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay to delivery of Customer dependencies for Tech Pubs | Person_436 | 2018-08-22 01:00 | 2019-03-23 | 40% | 1.4347 | 0.57388 | Reduce | 20% | 0.71735 | 0.14347 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--37 | Project_021_Risk--37 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay to delivery of Customer dependencies for Tech Pubs | Person_436 | 2018-08-22 01:00 | 2019-03-23 | 40% | 1.4347 | 0.57388 | Reduce | 20% | 0.71735 | 0.14347 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--37 | Project_021_Risk--37 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay to delivery of Customer dependencies for Tech Pubs | Person_436 | 2018-08-22 01:00 | 2019-03-23 | 40% | 1.4347 | 0.57388 | Reduce | 20% | 0.71735 | 0.14347 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--37 | Project_021_Risk--37 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay to delivery of Customer dependencies for Tech Pubs | Person_436 | 2018-08-22 01:00 | 2019-03-23 | 40% | 1.4347 | 0.57388 | Reduce | 20% | 0.71735 | 0.14347 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--37 | Project_021_Risk--37 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay to delivery of Customer dependencies for Tech Pubs | Person_436 | 2018-08-22 01:00 | 2019-03-23 | 40% | 1.4347 | 0.57388 | Reduce | 20% | 0.71735 | 0.14347 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--37 | Project_021_Risk--37 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay to delivery of Customer dependencies for Tech Pubs | Person_436 | 2018-08-22 01:00 | 2019-03-23 | 40% | 1.4347 | 0.57388 | Reduce | 20% | 0.71735 | 0.14347 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--37 | Project_021_Risk--37 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay to delivery of Customer dependencies for Tech Pubs | Person_436 | 2018-08-22 01:00 | 2019-03-23 | 40% | 1.4347 | 0.57388 | Reduce | 20% | 0.71735 | 0.14347 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK027 | Project_075_RISK027 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal impact from Chassis | Person_636 | 2017-04-22 | 2018-08-20 | 50% | 0.84371 | 0.42185 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 485 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK041 | Project_075_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Reliability does not meet requirement | Person_449 | 2018-05-23 | 2018-10-21 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 151.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK027 | Project_075_RISK027 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal impact from Chassis | Person_636 | 2017-04-22 | 2018-08-20 | 50% | 0.84371 | 0.42185 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 485 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK041 | Project_075_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Reliability does not meet requirement | Person_449 | 2018-05-23 | 2018-10-21 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 25% | 0.84371 | 0.21093 | H2 | 2 | -- | TRUE | 151.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK008 | Project_012_RISK008 | Threat | Project Contingency | Open | H2 | 2 |  | Critical Resource leave the project | Person_359 | 2015-04-04 | 2016-03-22 01:00 | 25% | 0.84985 | 0.21246 | Accept | 25% | 0.84985 | 0.21246 | H2 | 2 | Stable | TRUE | 353.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK002 | Project_092_RISK002 | Threat | Project Contingency | Open | H2 | 2 |  | Mass and/or CoG of assembly cannot be maintained. | Person_169 | 2019-10-12 01:00 | 2020-05-08 | 70% | 0.45083 | 0.31558 | Reduce | 50% | 0.45083 | 0.22542 | H2 | 2 | -- | TRUE | 208.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK038 | Project_043_RISK038 | Threat | Project Contingency | Open | H2 | 2 |  | Spares pool is limited | Person_307 | 2014-09-13 01:00 | 2018-03-21 | 25% | 0.95811 | 0.23953 | -- | 25% | 0.95811 | 0.23953 | H2 | 2 | -- | TRUE | 1284.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK038 | Project_043_RISK038 | Threat | Project Contingency | Open | H2 | 2 |  | Spares pool is limited | Person_307 | 2014-09-13 | 2018-03-21 | 25% | 0.95811 | 0.23953 | -- | 25% | 0.95811 | 0.23953 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK045 | Project_075_RISK045 | Threat | Project Contingency | Open | H2 | 2 |  | Any electronic redesign is not captured in schedule or costs | Person_314 | 2017-08-30 01:00 | 2018-10-03 01:00 | 80% | 2.5902 | 2.0721 | Reduce | 40% | 0.60747 | 0.24299 | H2 | 2 | -- | TRUE | 399 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK045 | Project_075_RISK045 | Threat | Project Contingency | Open | H2 | 2 |  | Any electronic redesign is not captured in schedule or costs | Person_314 | 2017-08-30 01:00 | 2018-10-03 01:00 | 80% | 2.5902 | 2.0721 | Reduce | 40% | 0.60747 | 0.24299 | H2 | 2 | -- | TRUE | 399 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-105 | Project_039_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | PMO Loading | Person_185 | 2014-12-22 01:00 | 2015-05-23 | 50% | 0.98021 | 0.4901 | Reduce | 15% | 0.98021 | 0.14703 | H3 | 3 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK045 | Project_075_RISK045 | Threat | Project Contingency | Open | H2 | 2 |  | Any electronic redesign is not captured in schedule or costs | Person_314 | 2017-08-30 01:00 | 2018-10-03 01:00 | 80% | 2.5902 | 2.0721 | Reduce | 40% | 0.60747 | 0.24299 | H2 | 2 | -- | TRUE | 399 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK032 | Project_075_RISK032 | Threat | Project Contingency | Open | H2 | 2 |  | If the requirement we have specified isnt achieved, the product becomes unsellable. | Person_449 | 2018-02-20 01:00 | 2018-08-21 | 30% | 0.84371 | 0.25311 | Avoid | 30% | 0.84371 | 0.25311 | H2 | 2 | -- | TRUE | 181.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 2 |  | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-10-21 01:00 | 30% | 1.5935 | 0.47805 | Reduce | 30% | 0.84455 | 0.25337 | H2 | 2 | Stable | TRUE | 304 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 2 |  | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-10-21 01:00 | 30% | 1.5935 | 0.47805 | Reduce | 30% | 0.84455 | 0.25337 | H2 | 2 | Stable | TRUE | 304 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 2 |  | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-10-21 01:00 | 30% | 1.5935 | 0.47805 | Reduce | 30% | 0.84455 | 0.25337 | H2 | 2 | Stable | TRUE | 304 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 2 |  | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 30% | 1.5935 | 0.47805 | Reduce | 30% | 0.84455 | 0.25337 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 2 |  | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 30% | 1.5935 | 0.47805 | Reduce | 30% | 0.84455 | 0.25337 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 2 |  | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 30% | 1.5935 | 0.47805 | Reduce | 30% | 0.84455 | 0.25337 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-085 | Project_011_Risk-085 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Automatic Testing | Person_230 | 2013-08-21 01:00 | 2018-08-21 | 50% | 0.29776 | 0.14888 | -- | 50% | 0.29776 | 0.14888 | H3 | 3 | -- | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-085 | Project_011_Risk-085 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Automatic Testing | Person_230 | 2013-08-21 01:00 | 2018-08-21 | 50% | 0.29776 | 0.14888 | -- | 50% | 0.29776 | 0.14888 | H3 | 3 | -- | FALSE | 1825.9583 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-034 | Project_011_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | INterface incompatibility | Person_230 | 2013-09-20 01:00 | 2017-01-19 01:00 | 45% | 0.33412 | 0.15036 | Accept | 45% | 0.33412 | 0.15036 | H2 | 2 | -- | TRUE | 1217 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-034 | Project_011_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | INterface incompatibility | Person_230 | 2013-09-20 | 2017-01-19 | 45% | 0.33412 | 0.15036 | Accept | 45% | 0.33412 | 0.15036 | H2 | 2 | -- | TRUE | 1217 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-034 | Project_011_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | INterface incompatibility | Person_230 | 2013-09-20 | 2017-01-19 | 45% | 0.33412 | 0.15036 | Accept | 45% | 0.33412 | 0.15036 | H2 | 2 | -- | TRUE | 1217 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-034 | Project_011_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | INterface incompatibility | Person_230 | 2013-09-20 01:00 | 2017-04-21 | 45% | 0.33412 | 0.15036 | Accept | 45% | 0.33412 | 0.15036 | H2 | 2 | -- | TRUE | 1308.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-034 | Project_011_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | INterface incompatibility | Person_230 | 2013-09-20 01:00 | 2017-04-21 | 45% | 0.33412 | 0.15036 | Accept | 45% | 0.33412 | 0.15036 | H2 | 2 | -- | TRUE | 1308.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-034 | Project_011_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | INterface incompatibility | Person_230 | 2013-09-20 01:00 | 2017-04-21 | 45% | 0.33412 | 0.15036 | Accept | 45% | 0.33412 | 0.15036 | H2 | 2 | -- | TRUE | 1308.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 | 2019-11-20 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-09-30 23:00 | 2019-11-19 23:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-09-30 22:00 | 2019-11-19 22:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-09-30 22:00 | 2019-11-19 22:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 | 2019-11-20 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-10-01 01:00 | 2019-11-20 01:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK226 | Project_065_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SubSystem System Design | Person_038 | 2017-09-30 23:00 | 2019-11-19 23:00 | 20% | 1.5213 | 0.30425 | Reduce | 10% | 1.5213 | 0.15213 | H3 | 3 | Stable | FALSE | 780 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-20 01:00 | 2017-09-19 01:00 | 25% | 0.6088 | 0.1522 | Accept | 25% | 0.6088 | 0.1522 | H3 | 3 | -- | TRUE | 303 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-20 01:00 | 2017-09-19 01:00 | 25% | 0.6088 | 0.1522 | Accept | 25% | 0.6088 | 0.1522 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-20 | 2017-09-19 | 25% | 0.6088 | 0.1522 | Accept | 25% | 0.6088 | 0.1522 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-19 23:00 | 2017-09-18 23:00 | 25% | 0.6088 | 0.1522 | Accept | 25% | 0.6088 | 0.1522 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-19 23:00 | 2017-09-18 23:00 | 25% | 0.6088 | 0.1522 | Accept | 25% | 0.6088 | 0.1522 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-19 23:00 | 2017-09-18 23:00 | 25% | 0.6088 | 0.1522 | Accept | 25% | 0.6088 | 0.1522 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R06 | Project_041_R06 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional PM time to support the supply chain | Person_359 | 2016-11-19 22:00 | 2017-09-18 22:00 | 25% | 0.6088 | 0.1522 | Accept | 25% | 0.6088 | 0.1522 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 2 |  | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 30% | 1.5935 | 0.47805 | Reduce | 30% | 0.84455 | 0.25337 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK341 | Project_037_RISK341 | Threat | Project Contingency | Open | H2 | 2 |  | Data throughput of solution exceeds Customer budget | Person_334 | 2015-12-22 01:00 | 2016-12-21 01:00 | 30% | 1.5935 | 0.47805 | Reduce | 30% | 0.84455 | 0.25337 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK016 | Project_012_RISK016 | Threat | Project Contingency | Open | H2 | 2 |  | Cable reliability improvement not ready for follow on units | Person_368 | 2015-04-25 | 2016-04-12 | 61% | 0.42493 | 0.25921 | Accept | 61% | 0.42493 | 0.25921 | H2 | 2 | -- | TRUE | 353 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK016 | Project_012_RISK016 | Threat | Project Contingency | Open | H2 | 2 |  | Cable reliability improvement not ready for follow on units | Person_368 | 2015-04-25 | 2016-04-12 | 61% | 0.42493 | 0.25921 | Accept | 61% | 0.42493 | 0.25921 | H2 | 2 | -- | TRUE | 353 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-034 | Project_028_Risk-034 | Threat | Project Contingency | Open | H2 | 2 |  | Network Migration | Person_542 | 2015-04-08 | 2017-05-22 | 50% | 0.52384 | 0.26192 | Accept | 50% | 0.52384 | 0.26192 | H2 | 2 | Stable | TRUE | 775 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.0534 | 0.61601 | Transfer | 10% | 1.54 | 0.154 | H3 | 3 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-105 | Project_029_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Changes to CE markings | Person_692 | 2015-05-24 | 2020-11-19 01:00 | 80% | 0.51334 | 0.41067 | Reduce | 30% | 0.51334 | 0.154 | H3 | 3 | Stable | TRUE | 2006.0417 |  | 1 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 1.0648 | 0.53241 | Reduce | 25% | 1.0648 | 0.2662 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.0534 | 0.61601 | Transfer | 10% | 1.54 | 0.154 | H3 | 3 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-105 | Project_029_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Changes to CE markings | Person_692 | 2015-05-24 | 2020-11-19 01:00 | 80% | 0.51334 | 0.41067 | Reduce | 30% | 0.51334 | 0.154 | H3 | 3 | Stable | TRUE | 2006.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 1.0648 | 0.53241 | Reduce | 25% | 1.0648 | 0.2662 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.0534 | 0.61601 | Transfer | 10% | 1.54 | 0.154 | H3 | 3 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-105 | Project_029_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Changes to CE markings | Person_692 | 2015-05-24 | 2020-11-19 01:00 | 80% | 0.51334 | 0.41067 | Reduce | 30% | 0.51334 | 0.154 | H3 | 3 | Stable | TRUE | 2006.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-072 | Project_007_R-072 | Threat | Project Contingency | Open | H2 | 2 |  | Software Issues | Person_245 | 2013-12-03 19:00 | 2016-03-23 | 50% | 0.58546 | 0.29273 | Accept | 50% | 0.58546 | 0.29273 | H2 | 2 | Stable | TRUE | 840.2083 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.0534 | 0.61601 | Transfer | 10% | 1.54 | 0.154 | H3 | 3 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-105 | Project_029_Risk-105 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Changes to CE markings | Person_692 | 2015-05-24 | 2020-11-19 01:00 | 80% | 0.51334 | 0.41067 | Reduce | 30% | 0.51334 | 0.154 | H3 | 3 | Stable | TRUE | 2006.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK020 | Project_031_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Product compatibility | Person_498 | 2013-08-20 19:00 | 2014-08-19 19:00 | 10% | 0.84608 | 0.084608 | Avoid | 99% | 0.29613 | 0.29317 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.0534 | 0.61601 | Transfer | 10% | 1.54 | 0.154 | H3 | 3 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK020 | Project_031_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Product compatibility | Person_498 | 2013-08-20 18:00 | 2014-08-19 18:00 | 10% | 0.84608 | 0.084608 | Avoid | 99% | 0.29613 | 0.29317 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.0534 | 0.61601 | Transfer | 10% | 1.54 | 0.154 | H3 | 3 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK020 | Project_031_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Product compatibility | Person_498 | 2013-08-20 17:00 | 2014-08-19 17:00 | 10% | 0.84608 | 0.084608 | Avoid | 99% | 0.29613 | 0.29317 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.0534 | 0.61601 | Transfer | 10% | 1.54 | 0.154 | H3 | 3 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK020 | Project_031_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Product compatibility | Person_498 | 2013-08-20 17:00 | 2014-08-19 17:00 | 10% | 0.84608 | 0.084608 | Avoid | 99% | 0.29613 | 0.29317 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-114 | Project_029_Risk-114 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Additional SW effort post acceptance start due to systems not available | Person_692 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.0534 | 0.61601 | Transfer | 10% | 1.54 | 0.154 | H3 | 3 | Stable | TRUE | 180.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK020 | Project_031_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Product compatibility | Person_498 | 2013-08-20 17:00 | 2014-08-19 17:00 | 10% | 0.84608 | 0.084608 | Avoid | 99% | 0.29613 | 0.29317 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK020 | Project_031_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Product compatibility | Person_498 | 2013-08-20 17:00 | 2014-08-19 17:00 | 10% | 0.84608 | 0.084608 | Avoid | 99% | 0.29613 | 0.29317 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK008 | Project_041_RISK008 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Unforseen and substantial increase in Repairs workload during new build production period. | Person_547 | 2017-10-23 01:00 | 2019-08-21 01:00 | 30% | 1.5434 | 0.46303 | Reduce | 10% | 1.5434 | 0.15434 | H3 | 3 | Stable | FALSE | 667 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK020 | Project_031_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Product compatibility | Person_498 | 2013-08-20 16:00 | 2014-08-19 16:00 | 10% | 0.84608 | 0.084608 | Avoid | 99% | 0.29613 | 0.29317 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK020 | Project_031_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Product compatibility | Person_498 | 2013-08-20 16:00 | 2014-08-19 16:00 | 10% | 0.84608 | 0.084608 | Avoid | 99% | 0.29613 | 0.29317 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 2 |  | Equipment Delivery | Person_368 | 2014-09-13 01:00 | 2018-03-21 | 25% | 1.1976 | 0.29941 | -- | 25% | 1.1976 | 0.29941 | H2 | 2 | -- | TRUE | 1284.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-026 | Project_043_Risk-026 | Threat | Project Contingency | Open | H2 | 2 |  | Equipment Delivery | Person_368 | 2014-09-13 | 2018-03-21 | 25% | 1.1976 | 0.29941 | -- | 25% | 1.1976 | 0.29941 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK350 | Project_035_RISK350 | Threat | Project Contingency | Open | H2 | 2 |  | Sub-System Performance against Bid Scenario | Person_303 | 2015-06-24 | 2017-01-19 01:00 | 50% | 2.0423 | 1.0211 | -- | 30% | 1.0168 | 0.30503 | H2 | 2 | Stable | TRUE | 575.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK350 | Project_035_RISK350 | Threat | Project Contingency | Open | H2 | 2 |  | Sub-System Performance against Bid Scenario | Person_303 | 2015-06-24 | 2017-01-19 01:00 | 50% | 2.0423 | 1.0211 | -- | 30% | 1.0168 | 0.30503 | H2 | 2 | Stable | TRUE | 575.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK350 | Project_035_RISK350 | Threat | Project Contingency | Open | H2 | 2 |  | Sub-System Performance against Bid Scenario | Person_303 | 2015-06-24 | 2017-04-21 | 50% | 2.0423 | 1.0211 | -- | 30% | 1.0168 | 0.30503 | H2 | 2 | Stable | TRUE | 667 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK007 | Project_012_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Materials failure/shortages | Person_515 | 2015-04-04 | 2016-04-12 | 61% | 0.87818 | 0.53569 | Accept | 35% | 0.87818 | 0.30736 | H2 | 2 | Worsening | TRUE | 374 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-074 | Project_026_Risk-074 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Risk Balance Case | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 40% | 0.53162 | 0.21265 | Reduce | 30% | 0.53162 | 0.15949 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R049 | Project_085_R049 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Telemetry test equipment modification | Person_539 | 2018-12-22 | 2019-11-20 | 50% | 0.53311 | 0.26655 | Reduce | 30% | 0.53311 | 0.15993 | H3 | 3 | -- | TRUE | 333 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-034 | Project_011_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | INterface incompatibility | Person_230 | 2013-09-20 01:00 | 2016-10-19 01:00 | 35% | 0.45743 | 0.1601 | Accept | 35% | 0.45743 | 0.1601 | H2 | 2 | -- | TRUE | 1125 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-034 | Project_011_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | INterface incompatibility | Person_230 | 2013-09-20 01:00 | 2016-10-19 01:00 | 35% | 0.45743 | 0.1601 | Accept | 35% | 0.45743 | 0.1601 | H2 | 2 | -- | TRUE | 1125 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 35% | 3.2401 | 1.134 | Transfer | 5% | 3.2401 | 0.16201 | H3 | 3 | Improving | FALSE | 546.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 35% | 3.2401 | 1.134 | Transfer | 5% | 3.2401 | 0.16201 | H3 | 3 | Improving | FALSE | 546.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 35% | 3.2401 | 1.134 | Transfer | 5% | 3.2401 | 0.16201 | H3 | 3 | Improving | FALSE | 546.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1001 | Project_091_RISK1001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Test Equipment | Person_557 | 2018-08-22 01:00 | 2026-03-22 | 50% | 0.3251 | 0.16255 | Reduce | 50% | 0.3251 | 0.16255 | H2 | 2 | -- | TRUE | 2768.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1001 | Project_091_RISK1001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Test Equipment | Person_557 | 2018-09-21 01:00 | 2026-03-22 | 50% | 0.3251 | 0.16255 | Reduce | 50% | 0.3251 | 0.16255 | H2 | 2 | -- | TRUE | 2738.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK006 | Project_041_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Change of Component material | Person_468 | 2016-11-20 01:00 | 2018-11-20 01:00 | 40% | 0.77172 | 0.30869 | Accept | 40% | 0.77172 | 0.30869 | H2 | 2 | -- | TRUE | 730 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Rotatory System | Person_403 | 2013-03-14 20:00 | 2019-08-20 20:00 | 90% | 9.9244 | 8.932 | Reduce | 10% | 1.6541 | 0.16541 | H3 | 3 | Stable | FALSE | 2350 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Rotatory System | Person_403 | 2013-03-14 20:00 | 2019-08-20 20:00 | 90% | 9.9244 | 8.932 | Reduce | 10% | 1.6541 | 0.16541 | H3 | 3 | Stable | FALSE | 2350 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Rotatory System | Person_403 | 2013-03-14 20:00 | 2019-08-20 20:00 | 90% | 9.9244 | 8.932 | Reduce | 10% | 1.6541 | 0.16541 | H3 | 3 | Stable | FALSE | 2350 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Rotatory System | Person_403 | 2013-03-14 20:00 | 2019-08-20 20:00 | 90% | 9.9244 | 8.932 | Reduce | 10% | 1.6541 | 0.16541 | H3 | 3 | Stable | FALSE | 2350 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 90% | 9.9244 | 8.932 | Reduce | 10% | 1.6541 | 0.16541 | H3 | 3 | Stable | FALSE | 2350 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 90% | 9.9244 | 8.932 | Reduce | 10% | 1.6541 | 0.16541 | H3 | 3 | Stable | FALSE | 2350 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 90% | 9.9244 | 8.932 | Reduce | 10% | 1.6541 | 0.16541 | H3 | 3 | Stable | FALSE | 2350 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS001 | Project_025_RS001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Rotatory System | Person_403 | 2013-03-14 19:00 | 2019-08-20 19:00 | 90% | 9.9244 | 8.932 | Reduce | 10% | 1.6541 | 0.16541 | H3 | 3 | Stable | FALSE | 2350 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--104 | Project_100_Risk--104 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Customer BERs | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 40% | 0.41625 | 0.1665 | -- | 40% | 0.41625 | 0.1665 | H3 | 3 | -- | TRUE | 1094 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-20 | 2020-11-20 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK075 | Project_076_RISK075 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delay in SW completion due to safety workload | Person_152 | 2018-07-05 | 2019-05-16 | 50% | 1.6723 | 0.83613 | Reduce | 10% | 1.6723 | 0.16723 | H3 | 3 | Stable | FALSE | 315 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK004 | Project_062_RISK004 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Carry out Console & Cabinet mod kit reviews in parallel | Person_019 | 2017-10-21 01:00 | 2019-02-21 01:00 | 50% | 0.33464 | 0.16732 | Exploit | 50% | 0.33464 | 0.16732 | H3 | 3 | Stable | TRUE | 488 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation for each platform | Person_298 | 2017-08-21 01:00 | 2022-10-28 01:00 | 50% | 0.67152 | 0.33576 | Reduce | 25% | 0.67152 | 0.16788 | H2 | 2 | -- | TRUE | 1894 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation for each platform | Person_298 | 2017-08-21 01:00 | 2022-10-28 01:00 | 50% | 0.67152 | 0.33576 | Reduce | 25% | 0.67152 | 0.16788 | H2 | 2 | -- | TRUE | 1894 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation for each platform | Person_298 | 2017-08-21 01:00 | 2022-10-28 01:00 | 50% | 0.67152 | 0.33576 | Reduce | 25% | 0.67152 | 0.16788 | H2 | 2 | -- | TRUE | 1894 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation for each platform | Person_298 | 2017-08-21 01:00 | 2022-10-28 01:00 | 50% | 0.67152 | 0.33576 | Reduce | 25% | 0.67152 | 0.16788 | H2 | 2 | -- | TRUE | 1894 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation for each platform | Person_298 | 2017-08-21 01:00 | 2022-10-28 01:00 | 50% | 0.67152 | 0.33576 | Reduce | 25% | 0.67152 | 0.16788 | H2 | 2 | -- | TRUE | 1894 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation for each platform | Person_298 | 2017-08-21 01:00 | 2022-10-28 01:00 | 50% | 0.67152 | 0.33576 | Reduce | 25% | 0.67152 | 0.16788 | H2 | 2 | -- | TRUE | 1894 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation for each platform | Person_298 | 2017-08-21 01:00 | 2022-10-28 01:00 | 50% | 0.67152 | 0.33576 | Reduce | 25% | 0.67152 | 0.16788 | H2 | 2 | -- | TRUE | 1894 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation for each platform | Person_298 | 2017-08-21 01:00 | 2022-10-28 01:00 | 50% | 0.67152 | 0.33576 | Reduce | 25% | 0.67152 | 0.16788 | H2 | 2 | -- | TRUE | 1894 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK043 | Project_097_RISK043 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence - Suppliers unable to provide extended validity on prices | Person_659 | 2018-09-21 01:00 | 2019-01-22 01:00 | 40% | 0.88593 | 0.35437 | Reduce | 20% | 0.84566 | 0.16913 | H2 | 2 | Stable | TRUE | 123 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_661 | 2016-09-08 01:00 | 2019-11-15 01:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_661 | 2016-09-08 01:00 | 2019-11-15 01:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_661 | 2016-09-08 | 2019-11-15 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_661 | 2016-09-07 23:00 | 2019-11-14 23:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_661 | 2016-09-07 22:00 | 2019-11-14 22:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_661 | 2016-09-07 23:00 | 2019-11-14 23:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_020 | 2016-09-08 01:00 | 2019-11-15 01:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_661 | 2016-09-07 22:00 | 2019-11-14 22:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_020 | 2016-09-08 | 2019-11-15 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_020 | 2016-09-08 01:00 | 2019-11-15 01:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK078 | Project_065_RISK078 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Component Shock test failure | Person_020 | 2016-09-07 23:00 | 2019-11-14 23:00 | 40% | 0.8467 | 0.33868 | Reduce | 20% | 0.8467 | 0.16934 | H3 | 3 | Stable | TRUE | 1163 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK010 | Project_099_RISK010 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Material fails porosity testing | Person_605 | 2018-05-06 | 2018-12-16 01:00 | 10% | 1.7331 | 0.17331 | Accept | 10% | 1.7331 | 0.17331 | H3 | 3 | -- | FALSE | 224.0417 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-009 | Project_026_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Security Controls | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 60% | 0.58198 | 0.34919 | Reduce | 30% | 0.58198 | 0.17459 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-009 | Project_026_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Security Controls | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 60% | 0.58198 | 0.34919 | Reduce | 30% | 0.58198 | 0.17459 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-009 | Project_026_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Security Controls | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 60% | 0.58198 | 0.34919 | Reduce | 30% | 0.58198 | 0.17459 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-009 | Project_026_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Security Controls | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 60% | 0.58198 | 0.34919 | Reduce | 30% | 0.58198 | 0.17459 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-009 | Project_026_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Security Controls | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 60% | 0.58198 | 0.34919 | Reduce | 30% | 0.58198 | 0.17459 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-009 | Project_026_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Security Controls | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 60% | 0.58198 | 0.34919 | Reduce | 30% | 0.58198 | 0.17459 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-009 | Project_026_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Security Controls | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 60% | 0.58198 | 0.34919 | Reduce | 30% | 0.58198 | 0.17459 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-009 | Project_026_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Security Controls | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 60% | 0.58198 | 0.34919 | Reduce | 30% | 0.58198 | 0.17459 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R78 | Project_041_R78 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Availability of key resource within Engineering | Person_693 | 2018-01-21 01:00 | 2019-05-23 | 10% | 1.7492 | 0.17492 | Accept | 10% | 1.7492 | 0.17492 | H3 | 3 | Improving | FALSE | 486.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-128 | Project_043_Risk-128 | Threat | Project Contingency | Open | H2 | 2 | Customers | Reliance of Customer Avaliability | Person_135 | 2017-04-19 | 2018-08-21 | 50% | 1.7665 | 0.88326 | Reduce | 10% | 1.7665 | 0.17665 | H2 | 2 | Stable | TRUE | 489 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-19 01:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1370.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-19 01:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1370.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-19 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1371 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-19 01:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1370.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-18 23:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1371.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-18 22:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1371.0833 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-19 01:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1370.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-18 22:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1371.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-19 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1371 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-19 01:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1370.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK103 | Project_065_RISK103 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Stabilisation Facility Availability Inhibits Ability to complete Workpackages | Person_404 | 2016-08-18 23:00 | 2020-05-21 | 25% | 3.58 | 0.89501 | Reduce | 10% | 1.79 | 0.179 | H3 | 3 | -- | TRUE | 1371.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-19 22:00 | 2020-11-19 22:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_703 | 2015-05-24 | 2019-05-22 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 1.1996 | 0.17994 | H3 | 3 | Stable | FALSE | 1459 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 10% | 3.6014 | 0.36014 | Reduce | 5% | 3.6014 | 0.18007 | H3 | 3 | -- | FALSE | 547.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 10% | 3.6014 | 0.36014 | Reduce | 5% | 3.6014 | 0.18007 | H3 | 3 | Stable | FALSE | 547.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-20 | 2018-05-22 | 10% | 3.6014 | 0.36014 | Reduce | 5% | 3.6014 | 0.18007 | H3 | 3 | Stable | FALSE | 548 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 10% | 3.6014 | 0.36014 | Reduce | 5% | 3.6014 | 0.18007 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 10% | 3.6014 | 0.36014 | Reduce | 5% | 3.6014 | 0.18007 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 10% | 3.6014 | 0.36014 | Reduce | 5% | 3.6014 | 0.18007 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R29 | Project_041_R29 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Attrition | Person_515 | 2016-11-19 22:00 | 2018-05-22 | 10% | 3.6014 | 0.36014 | Reduce | 5% | 3.6014 | 0.18007 | H3 | 3 | Stable | FALSE | 548.0833 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK006 | Project_086_RISK006 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delivery Risk from Lack of Tool and Process Knowledge | Person_048 | 2018-09-21 01:00 | 2018-11-20 01:00 | 30% | 0.60436 | 0.18131 | Accept | 30% | 0.60436 | 0.18131 | H2 | 2 | Improving | TRUE | 60 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_021 | Project_086 | RISK002 | Project_086_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Factory Acceptance Test Rejected/ Accepted with Corrective Action | Person_048 | 2018-11-14 01:00 | 2018-11-22 01:00 | 30% | 0.60436 | 0.18131 | Accept | 30% | 0.60436 | 0.18131 | H2 | 2 | -- | TRUE | 8 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-19 22:00 | 2020-11-19 22:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-20 | 2020-11-20 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK029 | Project_065_RISK029 | Threat | Management Contingency | Open | H2 | 2 |  | Manufacturing labour estimate is too low | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 30% | 1.0497 | 0.3149 | Accept | 30% | 1.0497 | 0.3149 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-089 | Project_043_Risk-089 | Threat | Project Contingency | Open | H2 | 2 |  | Spares pool is limited | Person_307 | 2018-12-21 22:00 | 2020-12-20 22:00 | 25% | 1.5969 | 0.39921 | Reduce | 25% | 1.2775 | 0.31937 | H2 | 2 | Stable | TRUE | 730 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | Programme Extended during Development - Increase in level of effort resources | Person_147 | 2013-11-20 01:00 | 2018-08-21 | 25% | 1.3217 | 0.33043 | Reduce | 25% | 1.3217 | 0.33043 | H2 | 2 | -- | TRUE | 1734.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | Programme Extended during Development - Increase in level of effort resources | Person_147 | 2013-11-20 | 2018-08-21 | 25% | 1.3217 | 0.33043 | Reduce | 25% | 1.3217 | 0.33043 | H2 | 2 | -- | TRUE | 1735 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2018-11-20 01:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 0.45943 | 0.18377 | H2 | 2 | Stable | TRUE | 4625.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-011 | Project_077_T-011 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Bus Scheduling table changes affecting proven interface | Person_544 | 2019-05-24 | 2020-02-21 01:00 | 20% | 0.92103 | 0.18421 | Reduce | 20% | 0.92103 | 0.18421 | H3 | 3 | Stable | FALSE | 273.0417 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | Programme Extended during Development - Increase in level of effort resources | Person_147 | 2013-11-20 | 2018-08-21 | 25% | 1.3217 | 0.33043 | Reduce | 25% | 1.3217 | 0.33043 | H2 | 2 | -- | TRUE | 1735 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Improving | FALSE | 1539.0417 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Improving | FALSE | 1539.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Improving | FALSE | 1539.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Improving | FALSE | 1539 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Improving | FALSE | 1539.0417 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Improving | FALSE | 1539.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 01:00 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Improving | FALSE | 1539.0417 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2016-08-19 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Improving | FALSE | 1539 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-26 17:00 | 2018-05-22 | 10% | 3.6965 | 0.36965 | Accept | 5% | 3.6965 | 0.18482 | H2 | 2 | Stable | TRUE | 1272.2917 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK74 | Project_010_RISK74 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change Notes / Requests and concessions being delayed | Person_359 | 2012-06-02 | 2018-05-21 | 20% | 0.92411 | 0.18482 | Accept | 20% | 0.92411 | 0.18482 | H3 | 3 | Worsening | FALSE | 2179 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK6 | Project_010_RISK6 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Loss of design knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 60% | 0.92411 | 0.55447 | Reduce | 50% | 0.36965 | 0.18482 | H2 | 2 | Stable | TRUE | 2181 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | Programme Extended during Development - Increase in level of effort resources | Person_147 | 2013-11-20 01:00 | 2018-08-21 | 25% | 1.3217 | 0.33043 | Reduce | 25% | 1.3217 | 0.33043 | H2 | 2 | -- | TRUE | 1734.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | Programme Extended during Development - Increase in level of effort resources | Person_147 | 2013-11-20 01:00 | 2018-08-21 | 25% | 1.3217 | 0.33043 | Reduce | 25% | 1.3217 | 0.33043 | H2 | 2 | -- | TRUE | 1734.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-020 | Project_011_Risk-020 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | There is a risk that Windows XP Obsolescence will require SW work arounds to overcome major issues | Person_141 | 2013-08-21 01:00 | 2018-08-21 | 45% | 0.41709 | 0.18769 | Accept | 45% | 0.41709 | 0.18769 | H1 | 1 | -- | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-020 | Project_011_Risk-020 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | There is a risk that Windows XP Obsolescence will require SW work arounds to overcome major issues | Person_141 | 2013-08-21 01:00 | 2018-08-21 | 45% | 0.41709 | 0.18769 | Accept | 45% | 0.41709 | 0.18769 | H1 | 1 | -- | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 1.8788 | 0.18788 | Accept | 10% | 1.8788 | 0.18788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 1.8788 | 0.18788 | Accept | 10% | 1.8788 | 0.18788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 1.8788 | 0.18788 | Accept | 10% | 1.8788 | 0.18788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 1.8788 | 0.18788 | Accept | 10% | 1.8788 | 0.18788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 1.8788 | 0.18788 | Accept | 10% | 1.8788 | 0.18788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 1.8788 | 0.18788 | Accept | 10% | 1.8788 | 0.18788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk013 | Project_042_Risk013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Local customer Engineers in country | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 1.8788 | 0.18788 | Accept | 10% | 1.8788 | 0.18788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK058 | Project_042_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Special to type Test Equipment availability | Person_129 | 2018-09-23 01:00 | 2019-10-22 01:00 | 10% | 1.8788 | 0.18788 | Accept | 10% | 1.8788 | 0.18788 | H3 | 3 | Stable | FALSE | 394 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | Programme Extended during Development - Increase in level of effort resources | Person_147 | 2013-11-20 01:00 | 2018-08-21 | 25% | 1.3217 | 0.33043 | Reduce | 25% | 1.3217 | 0.33043 | H2 | 2 | -- | TRUE | 1734.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2017-11-19 01:00 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 851.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2017-11-19 01:00 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 851.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2017-11-19 01:00 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 851.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2017-11-19 01:00 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 851.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2019-07-21 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 1460 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2019-07-21 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 1460 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2015-07-22 | 2019-07-21 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 1460 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-02-20 01:00 | 2019-07-21 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 880.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | System: Validation of In-environment performance. | Person_102 | 2017-05-23 | 2020-10-26 01:00 | 30% | 0.94968 | 0.28491 | Accept | 20% | 0.94968 | 0.18994 | H3 | 3 | Stable | FALSE | 1252.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_160 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_160 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_160 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_160 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_160 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_160 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_160 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_572 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_160 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_572 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_572 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK456 | Project_065_RISK456 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Testing repetition | Person_572 | 2019-05-24 | 2024-05-21 | 25% | 0.76063 | 0.19016 | Accept | 25% | 0.76063 | 0.19016 | H3 | 3 | -- | TRUE | 1824 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 30% | 0.95209 | 0.28563 | Reduce | 20% | 0.95209 | 0.19042 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 30% | 0.95209 | 0.28563 | Reduce | 20% | 0.95209 | 0.19042 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 30% | 0.95209 | 0.28563 | Reduce | 20% | 0.95209 | 0.19042 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 30% | 0.95209 | 0.28563 | Reduce | 20% | 0.95209 | 0.19042 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 30% | 0.95209 | 0.28563 | Reduce | 20% | 0.95209 | 0.19042 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK196 | Project_024_RISK196 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional Trials - Cost of Labour | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 30% | 0.95209 | 0.28563 | Reduce | 20% | 0.95209 | 0.19042 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 10% | 1.9128 | 0.19128 | Accept | 10% | 1.9128 | 0.19128 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 10% | 1.9128 | 0.19128 | Accept | 10% | 1.9128 | 0.19128 | H3 | 3 | Improving | FALSE | 121 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 10% | 1.9128 | 0.19128 | Accept | 10% | 1.9128 | 0.19128 | H3 | 3 | Improving | FALSE | 121 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 10% | 1.9128 | 0.19128 | Accept | 10% | 1.9128 | 0.19128 | H3 | 3 | Improving | FALSE | 121 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK203 | Project_024_RISK203 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Detection/Tracking modifications | Person_448 | 2016-10-21 01:00 | 2017-02-19 01:00 | 10% | 1.9128 | 0.19128 | Accept | 10% | 1.9128 | 0.19128 | H3 | 3 | Stable | FALSE | 121 |  | 1 | 1 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--29 | Project_021_Risk--29 | Threat | Project Contingency | Open | H2 | 2 |  | Operational hours not sufficient | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 1.6952 | 0.84758 | Reduce | 20% | 1.6969 | 0.33938 | H2 | 2 | -- | TRUE | 151.0417 |  | 0 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--29 | Project_021_Risk--29 | Threat | Project Contingency | Open | H2 | 2 |  | Operational hours not sufficient | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 1.6952 | 0.84758 | Reduce | 20% | 1.6969 | 0.33938 | H2 | 2 | -- | TRUE | 151.0417 |  | 0 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--29 | Project_021_Risk--29 | Threat | Project Contingency | Open | H2 | 2 |  | Operational hours not sufficient | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 1.6952 | 0.84758 | Reduce | 20% | 1.6969 | 0.33938 | H2 | 2 | -- | TRUE | 151.0417 |  | 0 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--29 | Project_021_Risk--29 | Threat | Project Contingency | Open | H2 | 2 |  | Operational hours not sufficient | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 1.6952 | 0.84758 | Reduce | 20% | 1.6969 | 0.33938 | H2 | 2 | -- | TRUE | 151.0417 |  | 0 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--29 | Project_021_Risk--29 | Threat | Project Contingency | Open | H2 | 2 |  | Operational hours not sufficient | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 1.6952 | 0.84758 | Reduce | 20% | 1.6969 | 0.33938 | H2 | 2 | -- | TRUE | 151.0417 |  | 0 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--29 | Project_021_Risk--29 | Threat | Project Contingency | Open | H2 | 2 |  | Operational hours not sufficient | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 1.6952 | 0.84758 | Reduce | 20% | 1.6969 | 0.33938 | H2 | 2 | -- | TRUE | 151.0417 |  | 0 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--29 | Project_021_Risk--29 | Threat | Project Contingency | Open | H2 | 2 |  | Operational hours not sufficient | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 1.6952 | 0.84758 | Reduce | 20% | 1.6969 | 0.33938 | H2 | 2 | -- | TRUE | 151.0417 |  | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--29 | Project_021_Risk--29 | Threat | Project Contingency | Open | H2 | 2 |  | Operational hours not sufficient | Person_080 | 2018-06-22 | 2018-11-20 01:00 | 50% | 1.6952 | 0.84758 | Reduce | 20% | 1.6969 | 0.33938 | H2 | 2 | -- | TRUE | 151.0417 |  | 0 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_020 | 2020-04-19 | 2020-07-17 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H2 | 2 | -- | TRUE | 89 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_470 | 2016-11-19 | 2017-11-19 | 40% | 0.48559 | 0.19424 | Reduce | 40% | 0.48559 | 0.19424 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_470 | 2016-11-18 23:00 | 2017-11-18 23:00 | 40% | 0.48559 | 0.19424 | Reduce | 40% | 0.48559 | 0.19424 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_174 | 2001-05-23 | 2018-02-19 01:00 | 40% | 0.48559 | 0.19424 | Reduce | 40% | 0.48559 | 0.19424 | H2 | 2 | Stable | TRUE | 6116.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_174 | 2001-05-23 | 2018-02-19 | 40% | 0.48559 | 0.19424 | Reduce | 40% | 0.48559 | 0.19424 | H2 | 2 | Stable | TRUE | 6116 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO22 | Project_021_Risk-RO22 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Engineering support is not available to support introduction of changes in the Tech Pubs | Person_174 | 2001-05-23 | 2018-02-19 01:00 | 40% | 0.48559 | 0.19424 | Reduce | 40% | 0.48559 | 0.19424 | H2 | 2 | Stable | TRUE | 6116.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_020 | 2020-04-19 | 2020-07-17 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H2 | 2 | -- | TRUE | 89 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_020 | 2020-04-19 | 2020-07-17 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H2 | 2 | -- | TRUE | 89 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_020 | 2020-04-19 | 2020-07-17 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H2 | 2 | -- | TRUE | 89 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R87 | Project_041_R87 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Reduction of Programme Manager hours by full transfer of product into Industry | Person_359 | 2016-11-20 01:00 | 2018-05-22 | 30% | 0.77172 | 0.23152 | Exploit | 50% | 0.77172 | 0.38586 | H2 | 2 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence and missing info | Person_727 | 2015-11-25 | 2016-08-20 | 30% | 1.3215 | 0.39644 | Accept | 30% | 1.3215 | 0.39644 | H2 | 2 | Stable | TRUE | 269 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-09-19 01:00 | 30% | 1.3215 | 0.39644 | Accept | 30% | 1.3215 | 0.39644 | H2 | 2 | Stable | TRUE | 299 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-09-19 01:00 | 30% | 1.3215 | 0.39644 | Accept | 30% | 1.3215 | 0.39644 | H2 | 2 | Stable | TRUE | 299 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-11-19 01:00 | 30% | 1.3215 | 0.39644 | Accept | 30% | 1.3215 | 0.39644 | H2 | 2 | Stable | TRUE | 360 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-11-19 01:00 | 30% | 1.3215 | 0.39644 | Accept | 30% | 1.3215 | 0.39644 | H2 | 2 | Stable | TRUE | 360 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2016-11-19 01:00 | 30% | 1.3215 | 0.39644 | Accept | 30% | 1.3215 | 0.39644 | H2 | 2 | Stable | TRUE | 360 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2017-02-19 01:00 | 30% | 1.3215 | 0.39644 | Accept | 30% | 1.3215 | 0.39644 | H2 | 2 | Stable | TRUE | 452 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-030 | Project_028_Risk-030 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence and missing info | Person_727 | 2015-11-25 01:00 | 2017-02-19 01:00 | 30% | 1.3215 | 0.39644 | Accept | 30% | 1.3215 | 0.39644 | H2 | 2 | Stable | TRUE | 452 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 1216.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 1216.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 1216.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 1216.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 1216.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 1216.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 1216.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2014-07-22 | 2017-11-19 01:00 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 1216.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-101 | Project_029_Risk-101 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Security Accreditation not obtained for Equipment and System. | Person_465 | 2018-03-22 | 2019-07-21 | 25% | 0.7914 | 0.19785 | Reduce | 25% | 0.7914 | 0.19785 | H2 | 2 | Improving | TRUE | 486 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Regulatory standards changes misunderstood | Person_693 | 2018-03-23 | 2018-11-18 01:00 | 30% | 1.3377 | 0.4013 | Reduce | 15% | 1.3377 | 0.20065 | H3 | 3 | Stable | FALSE | 240.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 25% | 7.4225 | 1.8556 | Reduce | 10% | 2.0081 | 0.20081 | H3 | 3 | Stable | TRUE | 3772.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 25% | 7.4225 | 1.8556 | Reduce | 10% | 2.0081 | 0.20081 | H3 | 3 | Stable | TRUE | 3772.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 25% | 7.4225 | 1.8556 | Reduce | 10% | 2.0081 | 0.20081 | H3 | 3 | Stable | TRUE | 3772.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-039 | Project_026_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | OEM Documentation | Person_250 | 2015-09-30 01:00 | 2018-12-27 01:00 | 30% | 2.0146 | 0.60437 | Transfer | 10% | 2.0146 | 0.20146 | H3 | 3 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-039 | Project_026_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | OEM Documentation | Person_250 | 2015-09-30 01:00 | 2018-12-27 01:00 | 30% | 2.0146 | 0.60437 | Transfer | 10% | 2.0146 | 0.20146 | H3 | 3 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-039 | Project_026_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | OEM Documentation | Person_250 | 2015-09-30 01:00 | 2018-12-27 01:00 | 30% | 2.0146 | 0.60437 | Transfer | 10% | 2.0146 | 0.20146 | H3 | 3 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-039 | Project_026_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | OEM Documentation | Person_250 | 2015-09-30 01:00 | 2018-12-27 01:00 | 30% | 2.0146 | 0.60437 | Transfer | 10% | 2.0146 | 0.20146 | H3 | 3 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Maintenance Schedules | Person_250 | 2015-02-21 01:00 | 2019-01-18 01:00 | 10% | 4.0291 | 0.40291 | Reduce | 5% | 4.0291 | 0.20146 | H3 | 3 | -- | TRUE | 1427 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Maintenance Schedules | Person_250 | 2015-02-21 01:00 | 2019-01-18 01:00 | 10% | 4.0291 | 0.40291 | Reduce | 5% | 4.0291 | 0.20146 | H3 | 3 | -- | TRUE | 1427 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-039 | Project_026_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | OEM Documentation | Person_250 | 2015-09-30 01:00 | 2018-12-27 01:00 | 30% | 2.0146 | 0.60437 | Transfer | 10% | 2.0146 | 0.20146 | H3 | 3 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Maintenance Schedules | Person_250 | 2015-02-21 01:00 | 2019-01-18 01:00 | 10% | 4.0291 | 0.40291 | Reduce | 5% | 4.0291 | 0.20146 | H3 | 3 | -- | TRUE | 1427 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-039 | Project_026_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | OEM Documentation | Person_250 | 2015-09-30 01:00 | 2018-12-27 01:00 | 30% | 2.0146 | 0.60437 | Transfer | 10% | 2.0146 | 0.20146 | H3 | 3 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Maintenance Schedules | Person_250 | 2015-02-21 01:00 | 2019-01-18 01:00 | 10% | 4.0291 | 0.40291 | Reduce | 5% | 4.0291 | 0.20146 | H3 | 3 | -- | TRUE | 1427 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-039 | Project_026_Risk-039 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | OEM Documentation | Person_250 | 2015-09-30 01:00 | 2018-12-27 01:00 | 30% | 2.0146 | 0.60437 | Transfer | 10% | 2.0146 | 0.20146 | H3 | 3 | -- | TRUE | 1184 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK045 | Project_075_RISK045 | Threat | Project Contingency | Open | H2 | 2 |  | Any electronic redesign is not captured in schedule or costs | Person_314 | 2017-08-30 01:00 | 2018-07-20 | 80% | 4.2185 | 3.3748 | Reduce | 10% | 4.2185 | 0.42185 | H2 | 2 | -- | TRUE | 323.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 2 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2018-03-22 | 2020-11-25 01:00 | 40% | 1.4673 | 0.58692 | Accept | 30% | 1.4673 | 0.44019 | H2 | 2 | Improving | TRUE | 979.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK027 | Project_079_RISK027 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Trials | Person_002 | 2018-07-22 | 2018-08-21 | 50% | 0.88388 | 0.44194 | -- | 50% | 0.88388 | 0.44194 | H2 | 2 | -- | TRUE | 30 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK027 | Project_079_RISK027 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Trials | Person_002 | 2018-07-22 | 2018-08-21 | 50% | 0.88388 | 0.44194 | -- | 50% | 0.88388 | 0.44194 | H2 | 2 | -- | TRUE | 30 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK027 | Project_079_RISK027 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Trials | Person_002 | 2018-07-22 | 2018-08-21 | 50% | 0.88388 | 0.44194 | -- | 50% | 0.88388 | 0.44194 | H2 | 2 | Stable | TRUE | 30 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK324 | Project_037_RISK324 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to integration | Person_330 | 2015-05-24 | 2016-05-15 | 50% | 1.4926 | 0.74629 | Reduce | 30% | 1.4926 | 0.44777 | H2 | 2 | Stable | TRUE | 357 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK113 | Project_065_RISK113 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Equipment Space Volume | Person_201 | 2016-04-24 | 2017-12-19 01:00 | 30% | 1.0142 | 0.30425 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | Stable | TRUE | 604.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK324 | Project_037_RISK324 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to integration | Person_330 | 2015-05-24 | 2016-05-15 | 50% | 1.4926 | 0.74629 | Reduce | 30% | 1.4926 | 0.44777 | H2 | 2 | Stable | TRUE | 357 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-113 | Project_043_Risk-113 | Threat | Project Contingency | Open | H2 | 2 |  | No Gen 1 products available, transition cost to Gen 2 | Person_769 | 2017-04-19 | 2020-12-20 22:00 | 30% | 1.4971 | 0.44912 | Reduce | 30% | 1.4971 | 0.44912 | H2 | 2 | Stable | TRUE | 1341.9167 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK040 | Project_043_RISK040 | Threat | Project Contingency | Open | H2 | 2 |  | Movements of equipment and the exporter of record | Person_204 | 2014-09-13 01:00 | 2018-03-21 | 10% | 8.9823 | 0.89823 | Avoid | 5% | 8.9823 | 0.44912 | H2 | 2 | -- | TRUE | 1284.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK040 | Project_043_RISK040 | Threat | Project Contingency | Open | H2 | 2 |  | Movements of equipment and the exporter of record | Person_204 | 2014-09-13 | 2018-03-21 | 10% | 8.9823 | 0.89823 | Avoid | 5% | 8.9823 | 0.44912 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK070 | Project_058_RISK070 | Threat | Project Contingency | Open | H2 | 2 |  | Subsystem Fails EMC Testing | Person_414 | 2017-06-23 | 2018-05-22 | 80% | 3.1318 | 2.5054 | Reduce | 30% | 1.5659 | 0.46977 | H2 | 2 | -- | TRUE | 333 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK070 | Project_058_RISK070 | Threat | Project Contingency | Open | H2 | 2 |  | Subsystem Fails EMC Testing | Person_414 | 2017-06-23 | 2018-05-22 | 80% | 3.1318 | 2.5054 | Reduce | 30% | 1.5659 | 0.46977 | H2 | 2 | -- | TRUE | 333 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK048 | Project_058_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance overheads (Legacy) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK046 | Project_058_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Quality Control Plan | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK018 | Project_058_RISK018 | Threat | Project Contingency | Open | H2 | 2 |  | Doc Pack Contents | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK048 | Project_058_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance overheads (Legacy) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK046 | Project_058_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Quality Control Plan | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK048 | Project_058_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance overheads (Legacy) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK046 | Project_058_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Quality Control Plan | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK048 | Project_058_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance overheads (Legacy) | Person_072 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK046 | Project_058_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Quality Control Plan | Person_639 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK048 | Project_058_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance overheads (Legacy) | Person_072 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK046 | Project_058_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Quality Control Plan | Person_639 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Reduce | 40% | 1.1744 | 0.46977 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK398 | Project_037_RISK398 | Threat | Project Contingency | Open | H2 | 2 |  | BIT Updates | Person_330 | 2016-07-27 | 2016-12-21 01:00 | 30% | 1.5669 | 0.47008 | -- | 30% | 1.5669 | 0.47008 | H2 | 2 | -- | TRUE | 147.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK398 | Project_037_RISK398 | Threat | Project Contingency | Open | H2 | 2 |  | BIT Updates | Person_330 | 2016-07-27 | 2016-12-21 01:00 | 30% | 1.5669 | 0.47008 | -- | 30% | 1.5669 | 0.47008 | H2 | 2 | -- | TRUE | 147.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_418 | 2019-05-24 | 2021-10-03 01:00 | 60% | 1.9776 | 1.1866 | Reduce | 25% | 1.9776 | 0.49441 | H2 | 2 | -- | TRUE | 863.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_418 | 2019-05-24 | 2021-10-03 | 60% | 1.9776 | 1.1866 | Reduce | 25% | 1.9776 | 0.49441 | H2 | 2 | -- | TRUE | 863 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_418 | 2019-05-24 | 2021-10-03 01:00 | 60% | 1.9776 | 1.1866 | Reduce | 25% | 1.9776 | 0.49441 | H2 | 2 | -- | TRUE | 863.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_418 | 2019-05-24 | 2021-10-02 23:00 | 60% | 1.9776 | 1.1866 | Reduce | 25% | 1.9776 | 0.49441 | H2 | 2 | -- | TRUE | 862.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK561 | Project_065_RISK561 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2018-08-17 | 60% | 5.0709 | 3.0425 | Reduce | 10% | 5.0709 | 0.50709 | H2 | 2 | -- | TRUE | 119 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK560 | Project_065_RISK560 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2018-10-17 01:00 | 60% | 5.0709 | 3.0425 | Reduce | 10% | 5.0709 | 0.50709 | H2 | 2 | -- | TRUE | 180.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK561 | Project_065_RISK561 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2018-08-17 | 60% | 5.0709 | 3.0425 | Reduce | 10% | 5.0709 | 0.50709 | H2 | 2 | -- | TRUE | 119 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK560 | Project_065_RISK560 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2018-10-17 | 60% | 5.0709 | 3.0425 | Reduce | 10% | 5.0709 | 0.50709 | H2 | 2 | -- | TRUE | 180 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK561 | Project_065_RISK561 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2018-08-17 | 60% | 5.0709 | 3.0425 | Reduce | 10% | 5.0709 | 0.50709 | H2 | 2 | -- | TRUE | 119 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK560 | Project_065_RISK560 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2018-10-17 01:00 | 60% | 5.0709 | 3.0425 | Reduce | 10% | 5.0709 | 0.50709 | H2 | 2 | -- | TRUE | 180.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK561 | Project_065_RISK561 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2018-08-17 | 60% | 5.0709 | 3.0425 | Reduce | 10% | 5.0709 | 0.50709 | H2 | 2 | -- | TRUE | 119 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK560 | Project_065_RISK560 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2018-10-16 23:00 | 60% | 5.0709 | 3.0425 | Reduce | 10% | 5.0709 | 0.50709 | H2 | 2 | -- | TRUE | 179.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK294 | Project_024_RISK294 | Threat | Project Contingency | Open | H2 | 2 |  | Scope Increase | Person_318 | 2016-11-05 01:00 | 2017-04-22 | 20% | 2.5966 | 0.51932 | Accept | 20% | 2.5966 | 0.51932 | H2 | 2 | -- | TRUE | 167.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H2 | 2 |  | Scope Increase | Person_318 | 2016-11-05 01:00 | 2017-04-22 | 20% | 2.5966 | 0.51932 | Accept | 20% | 2.5966 | 0.51932 | H2 | 2 | Worsening | TRUE | 167.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H2 | 2 |  | Scope Increase | Person_318 | 2016-11-05 01:00 | 2017-04-22 | 20% | 2.5966 | 0.51932 | Accept | 20% | 2.5966 | 0.51932 | H2 | 2 | -- | TRUE | 167.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Bank Guarantees | Person_703 | 2012-04-19 | 2017-04-21 | 80% | 3.3531 | 2.6825 | Exploit | 80% | 0.65554 | 0.52443 | H2 | 2 | Stable | TRUE | 1828 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK031 | Project_058_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Witnessing | Person_215 | 2017-05-23 | 2018-08-19 | 60% | 1.9574 | 1.1744 | Reduce | 40% | 1.3702 | 0.54807 | H2 | 2 | -- | TRUE | 453 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | OPP001 | Project_042_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Risk Savings | Person_455 | 2020-05-23 | 2021-05-22 | 5% | 3.7576 | 0.18788 | Accept | 15% | 3.7576 | 0.56365 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK046 | Project_058_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Quality Control Plan | Person_639 | 2018-07-22 | 2019-07-21 | 40% | 1.8791 | 0.75163 | Reduce | 30% | 1.8791 | 0.56373 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 1 | Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 40% | 0.51141 | 0.20457 | Avoid | 40% | 0.51141 | 0.20457 | H1 | 1 | Stable | TRUE | 30 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 1 | Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 40% | 0.51141 | 0.20457 | Avoid | 40% | 0.51141 | 0.20457 | H1 | 1 | Stable | TRUE | 30 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 1 | Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 40% | 0.51141 | 0.20457 | Avoid | 40% | 0.51141 | 0.20457 | H1 | 1 | Stable | TRUE | 30 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 1 | Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 40% | 0.51141 | 0.20457 | Avoid | 40% | 0.51141 | 0.20457 | H1 | 1 | Stable | TRUE | 30 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 1 | Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 40% | 0.51141 | 0.20457 | Avoid | 40% | 0.51141 | 0.20457 | H1 | 1 | Stable | TRUE | 30 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-096 | Project_011_Risk-096 | Threat | Project Contingency | Open | H1 | 1 | Customers | Additional Technical Support for Customer Acceptance not funded | Person_147 | 2018-07-22 | 2018-08-21 | 40% | 0.51141 | 0.20457 | Avoid | 40% | 0.51141 | 0.20457 | H1 | 1 | Stable | TRUE | 30 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 50% | 0.41055 | 0.20527 | Reduce | 50% | 0.41055 | 0.20527 | H1 | 1 | -- | TRUE | 99 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R034 | Project_021_Risk-R034 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-08-10 | 2016-09-19 01:00 | 50% | 0.41055 | 0.20527 | Reduce | 50% | 0.41055 | 0.20527 | H1 | 1 | -- | TRUE | 40.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 | 2017-01-19 | 50% | 0.41055 | 0.20527 | Reduce | 50% | 0.41055 | 0.20527 | H1 | 1 | -- | TRUE | 130 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R034 | Project_021_Risk-R034 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-08-10 | 2016-10-19 | 50% | 0.41055 | 0.20527 | Reduce | 50% | 0.41055 | 0.20527 | H1 | 1 | -- | TRUE | 70 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-009 | Project_021_Risk-009 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Config Qualification delays due to insufficient resource | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 50% | 0.41055 | 0.20527 | Reduce | 50% | 0.41055 | 0.20527 | H1 | 1 | -- | TRUE | 130 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 2.0816 | 0.20816 | Accept | 10% | 2.0816 | 0.20816 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 2.0816 | 0.20816 | Accept | 10% | 2.0816 | 0.20816 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 2.0816 | 0.20816 | Accept | 10% | 2.0816 | 0.20816 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 2.0816 | 0.20816 | Accept | 10% | 2.0816 | 0.20816 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 2.0816 | 0.20816 | Accept | 10% | 2.0816 | 0.20816 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK195 | Project_024_RISK195 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Perfomance Validation document not accepted | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 10% | 2.0816 | 0.20816 | Accept | 10% | 2.0816 | 0.20816 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK046 | Project_058_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Quality Control Plan | Person_639 | 2018-07-22 | 2019-07-21 | 40% | 1.8791 | 0.75163 | Reduce | 30% | 1.8791 | 0.56373 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-09 01:00 | 2017-12-15 01:00 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 6 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-09 01:00 | 2018-05-21 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 162.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-09 | 2018-05-21 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 163 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-09 01:00 | 2018-05-21 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 162.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-08 23:00 | 2018-05-21 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 163.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-08 22:00 | 2018-05-21 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 163.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-08 23:00 | 2018-05-21 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 163.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-09 01:00 | 2018-11-16 01:00 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 342 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-08 22:00 | 2018-05-21 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 163.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-09 | 2018-11-16 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 342 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-09 01:00 | 2018-11-16 01:00 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 342 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK484 | Project_065_RISK484 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | The COTS microphone may fail environmental testing such as shock, vibration and EMC | Person_661 | 2017-12-08 23:00 | 2018-11-15 23:00 | 50% | 7.3718 | 3.6859 | Reduce | 10% | 2.0939 | 0.20939 | H3 | 3 | -- | TRUE | 342 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK046 | Project_058_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Quality Control Plan | Person_639 | 2018-07-22 | 2019-07-21 | 40% | 1.8791 | 0.75163 | Reduce | 30% | 1.8791 | 0.56373 | H2 | 2 | -- | TRUE | 364 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK011 | Project_074_RISK011 | Threat | Project Contingency | Open | H2 | 2 |  | Low attrition | Person_263 | 2017-09-20 01:00 | 2019-11-21 01:00 | 50% | 1.8992 | 0.94959 | Reduce | 30% | 1.8992 | 0.56976 | H2 | 2 | -- | TRUE | 792 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-031 | Project_043_Risk-031 | Threat | Project Contingency | Open | H2 | 2 |  | Compliant Solution not meeting Customer expectations | Person_084 | 2014-09-13 | 2018-03-21 | 40% | 2.8743 | 1.1497 | -- | 20% | 2.8743 | 0.57487 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK004 | Project_095_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Field visits greater than anticipated | Person_490 | 2018-11-21 01:00 | 2023-07-22 | 30% | 1.9428 | 0.58285 | -- | 30% | 1.9428 | 0.58285 | H2 | 2 | -- | TRUE | 1703.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 2 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 40% | 1.078 | 0.43121 | Reduce | 40% | 1.4673 | 0.58692 | H2 | 2 | Stable | TRUE | 1399 |  | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 2 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 40% | 1.078 | 0.43121 | Reduce | 40% | 1.4673 | 0.58692 | H2 | 2 | Stable | TRUE | 1399 |  | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 2 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 40% | 1.078 | 0.43121 | Reduce | 40% | 1.4673 | 0.58692 | H2 | 2 | Stable | TRUE | 1399 |  | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H2 | 2 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 40% | 1.078 | 0.43121 | Reduce | 40% | 1.4673 | 0.58692 | H2 | 2 | Improving | TRUE | 1399 |  | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK030 | Project_058_RISK030 | Threat | Project Contingency | Open | H2 | 2 |  | Source Inspection Q1 | Person_236 | 2018-03-14 01:00 | 2018-08-21 | 80% | 2.9361 | 2.3489 | Reduce | 50% | 1.1744 | 0.58721 | H2 | 2 | -- | TRUE | 159.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK018 | Project_012_RISK018 | Threat | Project Contingency | Open | H2 | 2 |  | No Additional material available due to attrition | Person_359 | 2015-04-04 | 2016-04-21 | 80% | 0.9915 | 0.7932 | Avoid | 70% | 0.84985 | 0.5949 | H2 | 2 | Stable | TRUE | 383 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK554 | Project_065_RISK554 | Threat | Project Contingency | Open | H2 | 2 |  | Rejection on new non-compliances (display related) as part of bid. | Person_022 | 2018-04-18 | 2018-11-20 01:00 | 50% | 2.4027 | 1.2014 | Reduce | 25% | 2.4027 | 0.60068 | H2 | 2 | -- | TRUE | 216.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK554 | Project_065_RISK554 | Threat | Project Contingency | Open | H2 | 2 |  | Rejection on new non-compliances (display related) as part of bid. | Person_022 | 2018-04-18 | 2018-11-20 | 50% | 2.4027 | 1.2014 | Reduce | 25% | 2.4027 | 0.60068 | H2 | 2 | -- | TRUE | 216 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 10% | 2.1388 | 0.21388 | Accept | 10% | 2.1388 | 0.21388 | H2 | 2 | Stable | TRUE | 90.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 10% | 2.1388 | 0.21388 | Accept | 10% | 2.1388 | 0.21388 | H2 | 2 | Stable | TRUE | 90.9583 |  | 1 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 10% | 2.1388 | 0.21388 | Accept | 10% | 2.1388 | 0.21388 | H2 | 2 | Stable | TRUE | 90.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 10% | 2.1388 | 0.21388 | Accept | 10% | 2.1388 | 0.21388 | H2 | 2 | Stable | TRUE | 90.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PR rectification | Person_615 | 2018-02-20 01:00 | 2018-05-22 | 10% | 2.1388 | 0.21388 | Accept | 10% | 2.1388 | 0.21388 | H2 | 2 | Stable | TRUE | 90.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PR rectification | Person_207 | 2018-02-20 01:00 | 2018-11-05 01:00 | 10% | 2.1388 | 0.21388 | Accept | 10% | 2.1388 | 0.21388 | H2 | 2 | Stable | TRUE | 258 |  | 1 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PR rectification | Person_207 | 2018-02-20 01:00 | 2018-11-05 01:00 | 10% | 2.1388 | 0.21388 | Accept | 10% | 2.1388 | 0.21388 | H2 | 2 | Stable | TRUE | 258 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--27 | Project_021_Risk--27 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PR rectification | Person_207 | 2018-02-20 01:00 | 2018-11-05 01:00 | 10% | 2.1388 | 0.21388 | Accept | 10% | 2.1388 | 0.21388 | H2 | 2 | Stable | TRUE | 258 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-011 | Project_062_Risk-011 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Variant deviations between SW | Person_479 | 2017-07-21 | 2018-11-20 01:00 | 40% | 0.71808 | 0.28723 | Reduce | 30% | 0.71808 | 0.21542 | H2 | 2 | Stable | TRUE | 487.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK554 | Project_065_RISK554 | Threat | Project Contingency | Open | H2 | 2 |  | Rejection on new non-compliances (display related) as part of bid. | Person_022 | 2018-04-18 | 2018-11-20 01:00 | 50% | 2.4027 | 1.2014 | Reduce | 25% | 2.4027 | 0.60068 | H2 | 2 | -- | TRUE | 216.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK554 | Project_065_RISK554 | Threat | Project Contingency | Open | H2 | 2 |  | Rejection on new non-compliances (display related) as part of bid. | Person_022 | 2018-04-18 | 2018-11-19 23:00 | 50% | 2.4027 | 1.2014 | Reduce | 25% | 2.4027 | 0.60068 | H2 | 2 | -- | TRUE | 215.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK048 | Project_017_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Warranty | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 20% | 3.0903 | 0.61807 | Accept | 20% | 3.0903 | 0.61807 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK048 | Project_017_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Warranty | Person_374 | 2016-01-22 01:00 | 2023-02-20 01:00 | 20% | 3.0903 | 0.61807 | Accept | 20% | 3.0903 | 0.61807 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK151 | Project_038_RISK151 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | ILS Data | Person_671 | 2015-05-24 | 2016-05-22 | 20% | 5.3935 | 1.0787 | Accept | 4% | 5.3935 | 0.21574 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK151 | Project_038_RISK151 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | ILS Data | Person_671 | 2015-05-24 | 2016-05-22 | 20% | 5.3935 | 1.0787 | Accept | 4% | 5.3935 | 0.21574 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162- | Project_065_RISK162- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 10% | 2.1974 | 0.21974 | Accept | 10% | 2.1974 | 0.21974 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK039 | Project_042_RISK039 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Quality Issues 16th August to 15th August | Person_540 | 2020-01-06 01:00 | 2021-01-04 01:00 | 10% | 2.8182 | 0.28182 | Accept | 8% | 2.7619 | 0.22095 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK270- | Project_065_RISK270- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Compliant connector interface | Person_038 | 2017-10-01 01:00 | 2019-10-22 01:00 | 10% | 2.216 | 0.2216 | Accept | 10% | 2.216 | 0.2216 | H3 | 3 | -- | TRUE | 751 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK270- | Project_065_RISK270- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Compliant connector interface | Person_038 | 2017-10-01 01:00 | 2019-10-22 01:00 | 10% | 2.216 | 0.2216 | Accept | 10% | 2.216 | 0.2216 | H3 | 3 | -- | TRUE | 751 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK270- | Project_065_RISK270- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Compliant connector interface | Person_038 | 2017-10-01 | 2019-10-22 | 10% | 2.216 | 0.2216 | Accept | 10% | 2.216 | 0.2216 | H3 | 3 | -- | TRUE | 751 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK270- | Project_065_RISK270- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Compliant connector interface | Person_038 | 2017-10-01 01:00 | 2019-10-22 01:00 | 10% | 2.216 | 0.2216 | Accept | 10% | 2.216 | 0.2216 | H3 | 3 | -- | TRUE | 751 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK270- | Project_065_RISK270- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Compliant connector interface | Person_038 | 2017-09-30 23:00 | 2019-10-21 23:00 | 10% | 2.216 | 0.2216 | Accept | 10% | 2.216 | 0.2216 | H3 | 3 | -- | TRUE | 751 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK270- | Project_065_RISK270- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Compliant connector interface | Person_038 | 2017-09-30 22:00 | 2019-10-21 22:00 | 10% | 2.216 | 0.2216 | Accept | 10% | 2.216 | 0.2216 | H3 | 3 | -- | TRUE | 751 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK270- | Project_065_RISK270- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Compliant connector interface | Person_038 | 2017-09-30 22:00 | 2019-10-21 22:00 | 10% | 2.216 | 0.2216 | Accept | 10% | 2.216 | 0.2216 | H3 | 3 | -- | TRUE | 751 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK048 | Project_017_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Warranty | Person_374 | 2016-01-22 | 2023-02-20 | 20% | 3.0903 | 0.61807 | Accept | 20% | 3.0903 | 0.61807 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK335 | Project_033_RISK335 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 2.2311 | 0.44622 | Avoid | 10% | 2.2311 | 0.22311 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK335 | Project_033_RISK335 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 2.2311 | 0.44622 | Avoid | 10% | 2.2311 | 0.22311 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK335 | Project_033_RISK335 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 2.2311 | 0.44622 | Avoid | 10% | 2.2311 | 0.22311 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK335 | Project_033_RISK335 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 2.2311 | 0.44622 | Avoid | 10% | 2.2311 | 0.22311 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK335 | Project_033_RISK335 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Scope creep | Person_330 | 2015-02-20 18:00 | 2016-04-22 | 20% | 2.2311 | 0.44622 | Avoid | 10% | 2.2311 | 0.22311 | H3 | 3 | -- | TRUE | 426.25 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-08-20 | 10% | 4.4727 | 0.44727 | Accept | 5% | 4.4727 | 0.22363 | H2 | 2 | Stable | TRUE | 881 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-09-19 01:00 | 10% | 4.4727 | 0.44727 | Accept | 5% | 4.4727 | 0.22363 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-10-20 01:00 | 10% | 4.4727 | 0.44727 | Accept | 5% | 4.4727 | 0.22363 | H2 | 2 | Stable | TRUE | 942.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-11-19 01:00 | 10% | 4.4727 | 0.44727 | Accept | 5% | 4.4727 | 0.22363 | H2 | 2 | Stable | TRUE | 972.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-12-18 01:00 | 10% | 4.4727 | 0.44727 | Accept | 5% | 4.4727 | 0.22363 | H2 | 2 | Stable | TRUE | 1001.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2016-12-18 01:00 | 10% | 4.4727 | 0.44727 | Accept | 5% | 4.4727 | 0.22363 | H2 | 2 | Stable | TRUE | 1001.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2017-03-21 01:00 | 10% | 4.4727 | 0.44727 | Accept | 5% | 4.4727 | 0.22363 | H2 | 2 | Stable | TRUE | 1094.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-002 | Project_028_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Record / Replay feature | Person_499 | 2014-03-23 | 2017-03-21 01:00 | 10% | 4.4727 | 0.44727 | Accept | 5% | 4.4727 | 0.22363 | H2 | 2 | Stable | TRUE | 1094.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-016 | Project_026_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Responsibility for Defective Custeomr Furnished Equipment disputed | Person_091 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 13.99 | 3.4975 | Reduce | 10% | 2.2384 | 0.22384 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-016 | Project_026_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Responsibility for Defective Custeomr Furnished Equipment disputed | Person_091 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 13.99 | 3.4975 | Reduce | 10% | 2.2384 | 0.22384 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-016 | Project_026_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Responsibility for Defective Custeomr Furnished Equipment disputed | Person_091 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 13.99 | 3.4975 | Reduce | 10% | 2.2384 | 0.22384 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-016 | Project_026_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Responsibility for Defective Custeomr Furnished Equipment disputed | Person_091 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 13.99 | 3.4975 | Reduce | 10% | 2.2384 | 0.22384 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-016 | Project_026_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Responsibility for Defective Custeomr Furnished Equipment disputed | Person_091 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 13.99 | 3.4975 | Reduce | 10% | 2.2384 | 0.22384 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-016 | Project_026_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Responsibility for Defective Custeomr Furnished Equipment disputed | Person_091 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 13.99 | 3.4975 | Reduce | 10% | 2.2384 | 0.22384 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-016 | Project_026_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Responsibility for Defective Custeomr Furnished Equipment disputed | Person_091 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 13.99 | 3.4975 | Reduce | 10% | 2.2384 | 0.22384 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-016 | Project_026_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Consequential impact of Defective Custeomr Furnished Equipment | Person_091 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 13.99 | 3.4975 | Reduce | 10% | 2.2384 | 0.22384 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK048 | Project_017_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Warranty | Person_374 | 2016-01-22 | 2023-02-20 | 20% | 3.0903 | 0.61807 | Accept | 20% | 3.0903 | 0.61807 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 1.1273 | 0.22546 | Accept | 20% | 1.1273 | 0.22546 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 1.1273 | 0.22546 | Accept | 20% | 1.1273 | 0.22546 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 1.1273 | 0.22546 | Accept | 20% | 1.1273 | 0.22546 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 1.1273 | 0.22546 | Accept | 20% | 1.1273 | 0.22546 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 1.1273 | 0.22546 | Accept | 20% | 1.1273 | 0.22546 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 1.1273 | 0.22546 | Accept | 20% | 1.1273 | 0.22546 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk012 | Project_042_Risk012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Consumables | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 1.1273 | 0.22546 | Accept | 20% | 1.1273 | 0.22546 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK033 | Project_042_RISK033 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) 1st April to 30 June | Person_455 | 2019-08-22 01:00 | 2019-11-20 01:00 | 20% | 1.8788 | 0.37576 | Accept | 15% | 1.5031 | 0.22546 | H2 | 2 | Stable | TRUE | 90 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK035 | Project_042_RISK035 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) 1st October to 31st December | Person_455 | 2021-02-20 01:00 | 2021-05-22 | 20% | 1.8788 | 0.37576 | Accept | 15% | 1.5031 | 0.22546 | H2 | 2 | Stable | TRUE | 90.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK026 | Project_042_RISK026 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares1st Jan to 31st March | Person_455 | 2020-05-23 | 2020-08-20 01:00 | 25% | 1.8788 | 0.46971 | Accept | 15% | 1.5031 | 0.22546 | H2 | 2 | Stable | TRUE | 89.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK028 | Project_042_RISK028 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares 1st July to 30th September | Person_455 | 2020-11-20 01:00 | 2021-02-19 01:00 | 25% | 1.8788 | 0.46971 | Accept | 15% | 1.5031 | 0.22546 | H2 | 2 | Stable | TRUE | 91 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK027 | Project_042_RISK027 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares1st April to 30th June | Person_455 | 2020-08-21 01:00 | 2020-09-19 01:00 | 25% | 1.8788 | 0.46971 | Accept | 15% | 1.5031 | 0.22546 | H2 | 2 | Stable | TRUE | 29 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2018-05-22 | 40% | 0.77001 | 0.30801 | Accept | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 729 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2018-05-22 | 40% | 0.77001 | 0.30801 | Accept | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 729 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2018-05-22 | 40% | 0.77001 | 0.30801 | Accept | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 729 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2018-05-22 | 40% | 0.77001 | 0.30801 | Accept | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 729 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2019-07-21 | 40% | 0.77001 | 0.30801 | Accept | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 1154 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2019-07-21 | 40% | 0.77001 | 0.30801 | Accept | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 1154 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2016-05-23 | 2019-07-21 | 40% | 0.77001 | 0.30801 | Accept | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 1154 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2017-02-20 01:00 | 2019-07-21 | 40% | 0.77001 | 0.30801 | Accept | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 880.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-009 | Project_029_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Functionality Test of system with a Test Box | Person_102 | 2018-03-22 | 2020-04-26 | 40% | 0.77001 | 0.30801 | Reduce | 30% | 0.77001 | 0.231 | H2 | 2 | Stable | TRUE | 766 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 30% | 1.54 | 0.46201 | Accept | 20% | 1.155 | 0.231 | H3 | 3 | Stable | FALSE | 1186.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 30% | 1.54 | 0.46201 | Accept | 20% | 1.155 | 0.231 | H3 | 3 | Stable | FALSE | 1186.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 30% | 1.54 | 0.46201 | Accept | 20% | 1.155 | 0.231 | H3 | 3 | Stable | FALSE | 1186.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 30% | 1.54 | 0.46201 | Reduce | 20% | 1.155 | 0.231 | H3 | 3 | Stable | FALSE | 1186.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 30% | 1.54 | 0.46201 | Reduce | 20% | 1.155 | 0.231 | H3 | 3 | Stable | FALSE | 1186.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK84 | Project_010_RISK84 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Quality issues (for the future) | Person_359 | 2012-09-20 01:00 | 2017-08-20 01:00 | 60% | 2.033 | 1.2198 | Reduce | 25% | 0.92411 | 0.23103 | H2 | 2 | Stable | TRUE | 1795 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK84 | Project_010_RISK84 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Quality issues (for the future) | Person_359 | 2012-09-20 01:00 | 2017-08-20 01:00 | 60% | 2.033 | 1.2198 | Reduce | 25% | 0.92411 | 0.23103 | H2 | 2 | Stable | TRUE | 1795 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK84 | Project_010_RISK84 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Quality issues (for the future) | Person_359 | 2012-09-20 01:00 | 2017-08-20 01:00 | 60% | 2.033 | 1.2198 | Reduce | 25% | 0.92411 | 0.23103 | H2 | 2 | Stable | TRUE | 1795 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK84 | Project_010_RISK84 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Quality issues (for the future) | Person_359 | 2012-09-20 | 2017-08-20 | 60% | 2.033 | 1.2198 | Reduce | 25% | 0.92411 | 0.23103 | H2 | 2 | Stable | TRUE | 1795 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK5 | Project_010_RISK5 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Loss of system knowledge | Person_359 | 2012-06-01 | 2018-05-22 | 60% | 1.1089 | 0.66536 | Reduce | 50% | 0.46206 | 0.23103 | H1 | 1 | Stable | TRUE | 2181 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R52 | Project_041_R52 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Outstanding CRs | Person_693 | 2017-05-23 | 2019-02-21 01:00 | 70% | 0.77172 | 0.54021 | Accept | 30% | 0.77172 | 0.23152 | H3 | 3 | Stable | TRUE | 639.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK013 | Project_041_RISK013 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional components validation | Person_693 | 2017-07-15 | 2018-10-21 01:00 | 40% | 1.6721 | 0.66883 | Accept | 13.9% | 1.6721 | 0.23242 | H3 | 3 | Stable | FALSE | 463.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 20% | 1.1685 | 0.23369 | Accept | 20% | 1.1685 | 0.23369 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 20% | 1.1685 | 0.23369 | Accept | 20% | 1.1685 | 0.23369 | H2 | 2 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 20% | 1.1685 | 0.23369 | Accept | 20% | 1.1685 | 0.23369 | H2 | 2 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 20% | 1.1685 | 0.23369 | Accept | 20% | 1.1685 | 0.23369 | H2 | 2 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 20% | 1.1685 | 0.23369 | Accept | 20% | 1.1685 | 0.23369 | H2 | 2 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 20% | 1.1685 | 0.23369 | Accept | 20% | 1.1685 | 0.23369 | H2 | 2 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 20% | 1.1685 | 0.23369 | Accept | 20% | 1.1685 | 0.23369 | H2 | 2 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK197 | Project_024_RISK197 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Fitness for purpose | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 20% | 1.1685 | 0.23369 | Accept | 20% | 1.1685 | 0.23369 | H2 | 2 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 0.93941 | 0.23485 | Transfer | 25% | 0.93941 | 0.23485 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 0.93941 | 0.23485 | Transfer | 25% | 0.93941 | 0.23485 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 0.93941 | 0.23485 | Transfer | 25% | 0.93941 | 0.23485 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 0.93941 | 0.23485 | Transfer | 25% | 0.93941 | 0.23485 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 0.93941 | 0.23485 | Transfer | 25% | 0.93941 | 0.23485 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 0.93941 | 0.23485 | Transfer | 25% | 0.93941 | 0.23485 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk018 | Project_042_Risk018 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Governance and Export Rules | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 0.93941 | 0.23485 | Transfer | 25% | 0.93941 | 0.23485 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK048 | Project_017_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Warranty | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 20% | 3.0903 | 0.61807 | Accept | 20% | 3.0903 | 0.61807 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK048 | Project_017_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Warranty | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 20% | 3.0903 | 0.61807 | Accept | 20% | 3.0903 | 0.61807 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK048 | Project_017_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Warranty | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 20% | 3.0903 | 0.61807 | Accept | 20% | 3.0903 | 0.61807 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK048 | Project_017_RISK048 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Warranty | Person_374 | 2016-01-21 21:00 | 2023-02-19 21:00 | 20% | 3.0903 | 0.61807 | Accept | 20% | 3.0903 | 0.61807 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK008 | Project_073_RISK008 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in material cost | Person_263 | 2017-09-20 01:00 | 2019-08-01 | 80% | 2.0901 | 1.672 | Reduce | 30% | 2.0901 | 0.62702 | H2 | 2 | -- | TRUE | 679.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Environmental test failure | Person_020 | 2020-07-21 | 2020-09-24 01:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 65.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Environmental test failure | Person_020 | 2020-07-21 | 2020-09-24 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 65 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Environmental test failure | Person_020 | 2020-07-21 | 2020-09-24 01:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 65.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Environmental test failure | Person_020 | 2020-07-21 | 2020-09-23 23:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 64.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Environmental test failure | Person_020 | 2020-07-21 | 2020-09-23 22:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 64.9167 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Environmental test failure | Person_020 | 2020-07-21 | 2020-09-23 23:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 64.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | The Customer supplied carcass causes issues during the vibration testing | Person_020 | 2018-05-23 | 2019-11-09 01:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 535.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Environmental test failure | Person_020 | 2020-07-21 | 2020-09-23 22:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 64.9167 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_097 | RISK011 | Project_097_RISK011 | Opportunitity | Project Contingency | Open | H1 | 1 | Project Management | SW Uplift Core - Price Reduction | Person_667 | 2018-09-15 01:00 | 2019-01-21 01:00 | 5% | 0.46981 | 0.023491 | Exploit | 50% | 0.46981 | 0.23491 | H1 | 1 | Stable | TRUE | 128 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 25% | 2.358 | 0.58951 | Reduce | 10% | 2.358 | 0.2358 | H3 | 3 | -- | TRUE | 547.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 25% | 2.358 | 0.58951 | Reduce | 10% | 2.358 | 0.2358 | H3 | 3 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-20 | 2018-05-22 | 25% | 2.358 | 0.58951 | Reduce | 10% | 2.358 | 0.2358 | H3 | 3 | Stable | TRUE | 548 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 2.358 | 0.58951 | Reduce | 10% | 2.358 | 0.2358 | H3 | 3 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 2.358 | 0.58951 | Reduce | 10% | 2.358 | 0.2358 | H3 | 3 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 2.358 | 0.58951 | Reduce | 10% | 2.358 | 0.2358 | H3 | 3 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Production - Supplier Quality | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 25% | 2.358 | 0.58951 | Reduce | 10% | 2.358 | 0.2358 | H3 | 3 | Stable | TRUE | 548.0833 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R28 | Project_041_R28 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Production - Supplier Quality | Person_468 | 2017-05-23 | 2019-02-17 01:00 | 25% | 2.358 | 0.58951 | Reduce | 10% | 2.358 | 0.2358 | H3 | 3 | Improving | TRUE | 635.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | The Customer supplied carcass causes issues during the vibration testing | Person_020 | 2018-05-23 | 2019-11-09 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 535 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | The Customer supplied carcass causes issues during the vibration testing | Person_020 | 2018-05-23 | 2019-11-09 01:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 535.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK017 | Project_001_RISK017 | Threat | Project Contingency | Open | H3 | 3 | Bid Management | Field Service deployment | Person_674 | 2016-08-04 | 2016-08-04 | 20% | 1.2004 | 0.24009 | Accept | 20% | 1.2004 | 0.24009 | H3 | 3 | -- | TRUE | 0 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK017 | Project_001_RISK017 | Threat | Project Contingency | Open | H3 | 3 | Bid Management | Field Service deployment | Person_674 | 2016-08-04 | 2016-08-04 | 20% | 1.2004 | 0.24009 | Accept | 20% | 1.2004 | 0.24009 | H3 | 3 | -- | TRUE | 0 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-115 | Project_039_Risk-115 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Physical Integration of subsystem in to system | Person_343 | 2015-12-22 01:00 | 2016-05-15 | 50% | 2.4184 | 1.2092 | Reduce | 10% | 2.4184 | 0.24184 | H3 | 3 | Stable | FALSE | 144.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | The Customer supplied carcass causes issues during the vibration testing | Person_020 | 2018-05-23 | 2019-11-08 23:00 | 60% | 1.5694 | 0.94166 | Reduce | 40% | 1.5694 | 0.62777 | H2 | 2 | -- | TRUE | 534.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK014 | Project_074_RISK014 | Threat | Project Contingency | Open | H2 | 2 |  | Components | Person_595 | 2017-09-20 01:00 | 2018-09-20 01:00 | 25% | 2.5322 | 0.63306 | Accept | 25% | 2.5322 | 0.63306 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-04-27 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 704 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-04-27 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 704 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-04-27 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 704 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 40% | 0.68188 | 0.27275 | Reduce | 40% | 0.6137 | 0.24548 | H2 | 2 | Stable | TRUE | 730.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 40% | 0.68188 | 0.27275 | Reduce | 40% | 0.6137 | 0.24548 | H2 | 2 | Stable | TRUE | 730.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-111 | Project_029_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unplanned courier cost and T&S for any transportation of hardware during Integration phase | Person_692 | 2015-07-22 | 2017-04-22 | 80% | 0.12834 | 0.10267 | Accept | 80% | 0.30801 | 0.2464 | H2 | 2 | Stable | TRUE | 640 |  | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK166 | Project_024_RISK166 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Requirements Acceptance Criteria | Person_288 | 2016-04-10 | 2017-03-06 01:00 | 40% | 3.843 | 1.5372 | Reduce | 20% | 1.2464 | 0.24927 | H2 | 2 | Improving | TRUE | 330.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK166 | Project_024_RISK166 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Requirements Acceptance Criteria | Person_288 | 2016-04-10 | 2017-03-06 01:00 | 40% | 3.843 | 1.5372 | Reduce | 20% | 1.2464 | 0.24927 | H2 | 2 | Improving | TRUE | 330.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK166 | Project_024_RISK166 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Requirements Acceptance Criteria | Person_288 | 2016-04-10 | 2017-03-06 01:00 | 40% | 3.843 | 1.5372 | Reduce | 20% | 1.2464 | 0.24927 | H2 | 2 | Improving | TRUE | 330.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK166 | Project_024_RISK166 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Requirements Acceptance Criteria | Person_288 | 2016-04-10 | 2017-03-06 01:00 | 40% | 3.843 | 1.5372 | Reduce | 20% | 1.2464 | 0.24927 | H2 | 2 | Improving | TRUE | 330.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supply Chain Delays - Component and sus-system | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 30% | 3.2554 | 0.97663 | Reduce | 15% | 1.6635 | 0.24952 | H3 | 3 | -- | TRUE | 182 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK012 | Project_081_RISK012 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier unable to deliver course without our input | Person_419 | 2017-09-27 01:00 | 2021-09-27 01:00 | 50% | 0.50038 | 0.25019 | Reduce | 50% | 0.50038 | 0.25019 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-10-30 01:00 | 50% | 16.3745 | 8.1873 | Reduce | 10% | 2.5077 | 0.25077 | H3 | 3 | Stable | FALSE | 1794 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-10-30 01:00 | 50% | 16.3745 | 8.1873 | Reduce | 10% | 2.5077 | 0.25077 | H3 | 3 | Stable | FALSE | 1794 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-10-30 01:00 | 50% | 16.3745 | 8.1873 | Reduce | 10% | 2.5077 | 0.25077 | H3 | 3 | Stable | FALSE | 1794 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-054 | Project_062_Risk-054 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | sub-system rework to reviised standard | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 40% | 0.62744 | 0.25098 | Transfer | 40% | 0.62744 | 0.25098 | H2 | 2 | Stable | TRUE | 488.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-008 | Project_062_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Paperwork for Legacy & New Items | Person_459 | 2018-09-21 01:00 | 2019-04-23 | 30% | 0.83659 | 0.25098 | Avoid | 30% | 0.83659 | 0.25098 | H2 | 2 | Stable | TRUE | 213.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-04-27 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 704 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-04-27 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 704 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-04-27 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 704 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-04-27 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 704 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-05-12 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 719 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-04-27 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 704 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-05-12 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 719 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-05-12 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 719 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK036 | Project_065_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | Free-issued component is delivered with faults | Person_661 | 2016-05-23 | 2018-05-12 | 60% | 2.1805 | 1.3083 | Reduce | 30% | 2.1805 | 0.65414 | H2 | 2 | -- | TRUE | 719 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-27 | Project_022_RISK-27 | Threat | Project Contingency | Open | H2 | 2 |  | Provision for future emerging risks | Person_703 | 2015-02-21 01:00 | 2016-11-19 01:00 | 100% | 2.3975 | 2.3975 | Accept | 100% | 0.66364 | 0.66364 | H2 | 2 | -- | TRUE | 637 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-27 | Project_022_RISK-27 | Threat | Project Contingency | Open | H2 | 2 |  | Provision for future emerging risks | Person_703 | 2015-02-21 01:00 | 2016-11-19 01:00 | 100% | 2.3975 | 2.3975 | Accept | 100% | 0.66364 | 0.66364 | H2 | 2 | -- | TRUE | 637 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-27 | Project_022_RISK-27 | Threat | Project Contingency | Open | H2 | 2 |  | Provision for future emerging risks | Person_703 | 2015-02-21 01:00 | 2016-11-19 01:00 | 100% | 2.3975 | 2.3975 | Accept | 100% | 0.66364 | 0.66364 | H2 | 2 | -- | TRUE | 637 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK001 | Project_092_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Unit requires independant EMC and environmental Testing | Person_169 | 2018-10-31 01:00 | 2019-11-14 01:00 | 70% | 1.7103 | 1.1972 | Reduce | 40% | 1.7103 | 0.68412 | H2 | 2 | -- | TRUE | 379 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK110 | Project_066_RISK110 | Threat | Project Contingency | Open | H2 | 2 |  | No float in SW schedule | Person_507 | 2018-08-23 01:00 | 2019-10-03 01:00 | 60% | 1.729 | 1.0374 | Reduce | 40% | 1.729 | 0.6916 | H2 | 2 | -- | TRUE | 406 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-20 01:00 | 2018-11-20 01:00 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-20 01:00 | 2018-11-20 01:00 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-20 | 2018-11-20 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-20 01:00 | 2018-11-20 01:00 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-19 23:00 | 2018-11-19 23:00 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-20 | 2018-11-20 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-19 22:00 | 2018-11-19 22:00 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-19 23:00 | 2018-11-19 23:00 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2017-09-19 22:00 | 2018-11-19 22:00 | 20% | 2.5354 | 0.50709 | Reduce | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 426 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139- | Project_065_RISK139- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2018-05-23 | 2024-04-22 | 10% | 8.0289 | 0.80289 | Accept | 10% | 2.5354 | 0.25354 | H3 | 3 | -- | TRUE | 2161 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-117 | Project_029_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework costs | Person_216 | 2015-09-21 01:00 | 2016-12-19 01:00 | 33% | 0.77001 | 0.2541 | Accept | 33% | 0.77001 | 0.2541 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-117 | Project_029_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework costs | Person_216 | 2015-09-21 01:00 | 2016-12-19 01:00 | 33% | 0.77001 | 0.2541 | Accept | 33% | 0.77001 | 0.2541 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-117 | Project_029_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Rework costs | Person_216 | 2015-09-21 01:00 | 2016-12-19 01:00 | 33% | 0.77001 | 0.2541 | Accept | 33% | 0.77001 | 0.2541 | H3 | 3 | Stable | TRUE | 455 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--108 | Project_100_Risk--108 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Insufficient LOE to manage the supply chain with reducing number of spares | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 40% | 0.6385 | 0.2554 | Accept | 40% | 0.6385 | 0.2554 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK011 | Project_041_RISK011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Supplier Development support | Person_693 | 2018-04-11 | 2019-01-19 01:00 | 50% | 0.77172 | 0.38586 | Accept | 33.2% | 0.77172 | 0.25621 | H2 | 2 | Stable | TRUE | 283.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_102 | 2016-05-23 | 2018-04-22 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_102 | 2017-05-23 | 2018-04-22 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_102 | 2018-02-20 01:00 | 2018-04-22 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 60.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-007 | Project_029_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | system - Integration - platform Installation Activities | Person_694 | 2018-02-20 01:00 | 2019-08-04 | 35% | 1.0267 | 0.35934 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | Stable | TRUE | 529.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK022 | Project_029_RISK022 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | platform Build 4 | Person_150 | 2019-02-21 01:00 | 2019-10-21 01:00 | 50% | 1.0267 | 0.51334 | Reduce | 25% | 1.0267 | 0.25667 | H2 | 2 | -- | TRUE | 242 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-113 | Project_029_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | SW Delivery to INtegration (including bug fixes post delivery) | Person_199 | 2014-07-22 | 2016-09-19 01:00 | 40% | 0.64168 | 0.25667 | Avoid | 40% | 0.64168 | 0.25667 | H2 | 2 | Worsening | TRUE | 790.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-08 01:00 | 2019-11-20 01:00 | 45% | 1.9776 | 0.88993 | Reduce | 35% | 1.9776 | 0.69217 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-113 | Project_029_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | SW Delivery to INtegration (including bug fixes post delivery) | Person_199 | 2014-07-22 | 2016-11-19 01:00 | 40% | 0.64168 | 0.25667 | Avoid | 40% | 0.64168 | 0.25667 | H2 | 2 | Worsening | TRUE | 851.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-08 01:00 | 2019-11-20 01:00 | 45% | 1.9776 | 0.88993 | Reduce | 35% | 1.9776 | 0.69217 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-08 | 2019-11-20 | 45% | 1.9776 | 0.88993 | Reduce | 35% | 1.9776 | 0.69217 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-07 23:00 | 2019-11-19 23:00 | 45% | 1.9776 | 0.88993 | Reduce | 35% | 1.9776 | 0.69217 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-003 | Project_098_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Continuation of in service support | Person_464 | 2018-05-24 | 2027-05-16 | 50% | 51.6624 | 25.8312 | Reduce | 10% | 2.5831 | 0.25831 | H2 | 2 | Stable | TRUE | 3279 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-07 22:00 | 2019-11-19 22:00 | 45% | 1.9776 | 0.88993 | Reduce | 35% | 1.9776 | 0.69217 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012- | Project_065_RISK012- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-07 23:00 | 2019-11-19 23:00 | 45% | 1.9776 | 0.88993 | Reduce | 35% | 1.9776 | 0.69217 | H2 | 2 | -- | TRUE | 1168 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK076 | Project_076_RISK076 | Threat | Project Contingency | Open | H2 | 2 |  | SW Core Estimate | Person_152 | 2018-06-23 | 2018-09-23 01:00 | 90% | 0.82922 | 0.7463 | Accept | 90% | 0.82922 | 0.7463 | H2 | 2 | -- | TRUE | 92.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK076 | Project_076_RISK076 | Threat | Project Contingency | Open | H2 | 2 |  | SW Core Estimate | Person_152 | 2018-06-23 | 2018-09-23 01:00 | 90% | 0.82922 | 0.7463 | Accept | 90% | 0.82922 | 0.7463 | H2 | 2 | -- | TRUE | 92.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-11-20 01:00 | 50% | 4.7805 | 2.3902 | Avoid | 20% | 1.3279 | 0.26558 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 50% | 4.7805 | 2.3902 | Avoid | 20% | 1.3279 | 0.26558 | H3 | 3 | Stable | FALSE | 334 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 50% | 4.7805 | 2.3902 | Avoid | 20% | 1.3279 | 0.26558 | H3 | 3 | Stable | FALSE | 334 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 50% | 4.7805 | 2.3902 | Avoid | 20% | 1.3279 | 0.26558 | H3 | 3 | Stable | FALSE | 334 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 50% | 4.7805 | 2.3902 | Avoid | 20% | 1.3279 | 0.26558 | H3 | 3 | Stable | FALSE | 334 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-12-21 01:00 | 50% | 4.7805 | 2.3902 | Avoid | 20% | 1.3279 | 0.26558 | H3 | 3 | Stable | FALSE | 334 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-009 | Project_062_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Unresolved technical debt (excluding ILS) | Person_253 | 2017-07-21 | 2019-03-23 | 50% | 2.5098 | 1.2549 | Reduce | 30% | 2.5098 | 0.75293 | H2 | 2 | Stable | TRUE | 610 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK537 | Project_065_RISK537 | Threat | Project Contingency | Open | H2 | 2 |  | Assembly Technical Specification release ahead of engineering process | Person_661 | 2018-04-21 | 2018-09-17 01:00 | 60% | 5.0709 | 3.0425 | Reduce | 15% | 5.0709 | 0.76063 | H2 | 2 | -- | TRUE | 149.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK562 | Project_065_RISK562 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2023-03-22 | 60% | 5.0709 | 3.0425 | Reduce | 15% | 5.0709 | 0.76063 | H2 | 2 | -- | TRUE | 1797 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-01-20 01:00 | 40% | 0.66881 | 0.26753 | Reduce | 40% | 0.66881 | 0.26753 | H2 | 2 | Stable | TRUE | 1248 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 | 2017-01-20 | 40% | 0.66881 | 0.26753 | Reduce | 40% | 0.66881 | 0.26753 | H2 | 2 | Stable | TRUE | 1248 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 | 2017-01-20 | 40% | 0.66881 | 0.26753 | Reduce | 40% | 0.66881 | 0.26753 | H2 | 2 | Stable | TRUE | 1248 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-04-21 | 40% | 0.66881 | 0.26753 | Reduce | 40% | 0.66881 | 0.26753 | H2 | 2 | Stable | TRUE | 1338.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-04-21 | 40% | 0.66881 | 0.26753 | Reduce | 40% | 0.66881 | 0.26753 | H2 | 2 | Stable | TRUE | 1338.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rework required following integration of Customer System | Person_142 | 2013-08-21 01:00 | 2017-04-21 | 40% | 0.66881 | 0.26753 | Reduce | 40% | 0.66881 | 0.26753 | H2 | 2 | Stable | TRUE | 1338.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK537 | Project_065_RISK537 | Threat | Project Contingency | Open | H2 | 2 |  | Assembly Technical Specification release ahead of engineering process | Person_661 | 2018-04-21 | 2018-09-17 | 60% | 5.0709 | 3.0425 | Reduce | 15% | 5.0709 | 0.76063 | H2 | 2 | -- | TRUE | 149 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK562 | Project_065_RISK562 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2023-03-22 | 60% | 5.0709 | 3.0425 | Reduce | 15% | 5.0709 | 0.76063 | H2 | 2 | -- | TRUE | 1797 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-120 | Project_026_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Standards evidence | Person_385 | 2015-09-30 01:00 | 2018-12-27 01:00 | 40% | 1.343 | 0.53721 | Reduce | 20% | 1.343 | 0.26861 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-120 | Project_026_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Standards evidence | Person_385 | 2015-09-30 01:00 | 2018-12-27 01:00 | 40% | 1.343 | 0.53721 | Reduce | 20% | 1.343 | 0.26861 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-120 | Project_026_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Standards evidence | Person_385 | 2015-09-30 01:00 | 2018-12-27 01:00 | 40% | 1.343 | 0.53721 | Reduce | 20% | 1.343 | 0.26861 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-120 | Project_026_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Standards evidence | Person_385 | 2015-09-30 01:00 | 2018-12-27 01:00 | 40% | 1.343 | 0.53721 | Reduce | 20% | 1.343 | 0.26861 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-120 | Project_026_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Standards evidence | Person_385 | 2015-09-30 01:00 | 2018-12-27 01:00 | 40% | 1.343 | 0.53721 | Reduce | 20% | 1.343 | 0.26861 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-120 | Project_026_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Standards evidence | Person_385 | 2015-09-30 01:00 | 2018-12-27 01:00 | 40% | 1.343 | 0.53721 | Reduce | 20% | 1.343 | 0.26861 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-120 | Project_026_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Standards evidence | Person_385 | 2015-09-30 01:00 | 2018-12-27 01:00 | 40% | 1.343 | 0.53721 | Reduce | 20% | 1.343 | 0.26861 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-120 | Project_026_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Standards evidence | Person_385 | 2015-09-30 01:00 | 2018-12-27 01:00 | 40% | 1.343 | 0.53721 | Reduce | 20% | 1.343 | 0.26861 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 20% | 1.3502 | 0.27005 | Accept | 20% | 1.3502 | 0.27005 | H3 | 3 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 20% | 1.3502 | 0.27005 | Accept | 20% | 1.3502 | 0.27005 | H3 | 3 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 20% | 1.3502 | 0.27005 | Accept | 20% | 1.3502 | 0.27005 | H3 | 3 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 20% | 1.3502 | 0.27005 | Accept | 20% | 1.3502 | 0.27005 | H3 | 3 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 20% | 1.3502 | 0.27005 | Accept | 20% | 1.3502 | 0.27005 | H3 | 3 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1032 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1032 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1032 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1032 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1032 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1032 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1032 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-07-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1123 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-04-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1032 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-07-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1123 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-07-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1123 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK033 | Project_065_RISK033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Procurement of Power Supply prior to CDR | Person_047 | 2015-06-24 | 2018-07-21 | 30% | 2.723 | 0.81691 | Reduce | 10% | 2.723 | 0.2723 | H3 | 3 | Improving | FALSE | 1123 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-050 | Project_011_Risk-050 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Indications associated with each agreed fault have been underestimated | Person_187 | 2013-08-21 01:00 | 2017-08-04 | 40% | 0.68188 | 0.27275 | Accept | 40% | 0.68188 | 0.27275 | H1 | 1 | -- | TRUE | 1443.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-050 | Project_011_Risk-050 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Indications associated with each agreed fault have been underestimated | Person_187 | 2013-08-21 01:00 | 2017-08-04 | 40% | 0.68188 | 0.27275 | Accept | 40% | 0.68188 | 0.27275 | H1 | 1 | -- | TRUE | 1443.9583 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK537 | Project_065_RISK537 | Threat | Project Contingency | Open | H2 | 2 |  | Assembly Technical Specification release ahead of engineering process | Person_661 | 2018-04-21 | 2018-09-17 01:00 | 60% | 5.0709 | 3.0425 | Reduce | 15% | 5.0709 | 0.76063 | H2 | 2 | -- | TRUE | 149.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK013 | Project_012_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional improvementactivities have to be costed | Person_515 | 2015-04-04 | 2016-02-20 01:00 | 15% | 2.762 | 0.4143 | Avoid | 10% | 2.762 | 0.2762 | H3 | 3 | -- | TRUE | 322.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-024 | Project_026_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Support Product Acceptability | Person_250 | 2014-11-21 01:00 | 2018-12-27 01:00 | 5% | 5.596 | 0.2798 | Reduce | 5% | 5.596 | 0.2798 | H3 | 3 | -- | FALSE | 1497 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-042 | Project_026_Risk-042 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Paper work | Person_607 | 2018-09-18 01:00 | 2022-10-28 01:00 | 30% | 2.798 | 0.8394 | Reduce | 10% | 2.798 | 0.2798 | H2 | 2 | -- | TRUE | 1501 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-024 | Project_026_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Support Product Acceptability | Person_250 | 2014-11-21 01:00 | 2018-12-27 01:00 | 5% | 5.596 | 0.2798 | Reduce | 5% | 5.596 | 0.2798 | H3 | 3 | -- | FALSE | 1497 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-024 | Project_026_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Support Product Acceptability | Person_250 | 2014-11-21 01:00 | 2018-12-27 01:00 | 5% | 5.596 | 0.2798 | Reduce | 5% | 5.596 | 0.2798 | H3 | 3 | -- | FALSE | 1497 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-024 | Project_026_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Support Product Acceptability | Person_250 | 2014-11-21 01:00 | 2018-12-27 01:00 | 5% | 5.596 | 0.2798 | Reduce | 5% | 5.596 | 0.2798 | H3 | 3 | -- | FALSE | 1497 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-024 | Project_026_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Support Product Acceptability | Person_250 | 2014-11-21 01:00 | 2018-12-27 01:00 | 5% | 5.596 | 0.2798 | Reduce | 5% | 5.596 | 0.2798 | H3 | 3 | -- | FALSE | 1497 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-024 | Project_026_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Support Product Acceptability | Person_250 | 2014-11-21 01:00 | 2018-12-27 01:00 | 5% | 5.596 | 0.2798 | Reduce | 5% | 5.596 | 0.2798 | H3 | 3 | -- | FALSE | 1497 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-024 | Project_026_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Support Product Acceptability | Person_250 | 2014-11-21 01:00 | 2018-12-27 01:00 | 5% | 5.596 | 0.2798 | Reduce | 5% | 5.596 | 0.2798 | H3 | 3 | -- | FALSE | 1497 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-024 | Project_026_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Support Product Acceptability | Person_250 | 2014-11-21 01:00 | 2018-12-27 01:00 | 5% | 5.596 | 0.2798 | Reduce | 5% | 5.596 | 0.2798 | H3 | 3 | -- | FALSE | 1497 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 1.8788 | 0.28182 | Accept | 15% | 1.8788 | 0.28182 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 1.8788 | 0.28182 | Accept | 15% | 1.8788 | 0.28182 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 1.8788 | 0.28182 | Accept | 15% | 1.8788 | 0.28182 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 1.8788 | 0.28182 | Accept | 15% | 1.8788 | 0.28182 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 1.8788 | 0.28182 | Accept | 15% | 1.8788 | 0.28182 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 1.8788 | 0.28182 | Accept | 15% | 1.8788 | 0.28182 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk010 | Project_042_Risk010 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Suppliers | Person_455 | 2016-05-23 | 2020-05-23 | 15% | 1.8788 | 0.28182 | Accept | 15% | 1.8788 | 0.28182 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1276.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1276.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1276 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1276.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 23:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1275.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 22:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1275.9167 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 23:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1275.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1276.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 22:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1275.9167 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1276 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-20 01:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1276.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK056 | Project_065_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | New interface fails during integration | Person_047 | 2016-03-23 | 2019-09-19 23:00 | 40% | 2.8643 | 1.1457 | Reduce | 10% | 2.8643 | 0.28643 | H3 | 3 | Stable | FALSE | 1275.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-037 | Project_026_Risk-037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient time and resources to support programme closure | Person_362 | 2022-10-28 01:00 | 2023-10-28 01:00 | 15% | 2.9099 | 0.43649 | Reduce | 10% | 2.9099 | 0.29099 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-037 | Project_026_Risk-037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient time and resources to support programme closure | Person_362 | 2022-10-28 01:00 | 2023-10-28 01:00 | 15% | 2.9099 | 0.43649 | Reduce | 10% | 2.9099 | 0.29099 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-037 | Project_026_Risk-037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient time and resources to support programme closure | Person_362 | 2022-10-28 01:00 | 2023-10-28 01:00 | 15% | 2.9099 | 0.43649 | Reduce | 10% | 2.9099 | 0.29099 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-037 | Project_026_Risk-037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient time and resources to support programme closure | Person_362 | 2022-10-28 01:00 | 2023-10-28 01:00 | 15% | 2.9099 | 0.43649 | Reduce | 10% | 2.9099 | 0.29099 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-037 | Project_026_Risk-037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient time and resources to support programme closure | Person_362 | 2022-10-28 01:00 | 2023-10-28 01:00 | 15% | 2.9099 | 0.43649 | Reduce | 10% | 2.9099 | 0.29099 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-037 | Project_026_Risk-037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient time and resources to support programme closure | Person_362 | 2022-10-28 01:00 | 2023-10-28 01:00 | 15% | 2.9099 | 0.43649 | Reduce | 10% | 2.9099 | 0.29099 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-037 | Project_026_Risk-037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient time and resources to support programme closure | Person_362 | 2022-10-28 01:00 | 2023-10-28 01:00 | 15% | 2.9099 | 0.43649 | Reduce | 10% | 2.9099 | 0.29099 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-037 | Project_026_Risk-037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient time and resources to support programme closure | Person_362 | 2022-10-28 01:00 | 2023-10-28 01:00 | 15% | 2.9099 | 0.43649 | Reduce | 10% | 2.9099 | 0.29099 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 5% | 5.8286 | 0.29143 | Accept | 5% | 5.8286 | 0.29143 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 5% | 5.8286 | 0.29143 | Accept | 5% | 5.8286 | 0.29143 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 5% | 5.8286 | 0.29143 | Accept | 5% | 5.8286 | 0.29143 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 5% | 5.8286 | 0.29143 | Accept | 5% | 5.8286 | 0.29143 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK562 | Project_065_RISK562 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2023-03-22 | 60% | 5.0709 | 3.0425 | Reduce | 15% | 5.0709 | 0.76063 | H2 | 2 | -- | TRUE | 1797 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK537 | Project_065_RISK537 | Threat | Project Contingency | Open | H2 | 2 |  | Assembly Technical Specification release ahead of engineering process | Person_661 | 2018-04-21 | 2018-09-16 23:00 | 60% | 5.0709 | 3.0425 | Reduce | 15% | 5.0709 | 0.76063 | H2 | 2 | -- | TRUE | 148.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK562 | Project_065_RISK562 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Specification release ahead of engineering process | Person_661 | 2018-04-20 | 2023-03-22 | 60% | 5.0709 | 3.0425 | Reduce | 15% | 5.0709 | 0.76063 | H2 | 2 | -- | TRUE | 1797 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK043 | Project_017_RISK043 | Threat | Project Contingency | Open | H2 | 2 |  | Effectiveness of user training resources | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 40% | 3.8114 | 1.5246 | Accept | 20% | 3.8114 | 0.76228 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-61 | Project_022_RISK-61 | Threat | Project Contingency | Open | H2 | 2 |  | Extended programme | Person_703 | 2016-11-20 01:00 | 2017-01-20 01:00 | 60% | 1.2976 | 0.77853 | Reduce | 60% | 1.2976 | 0.77853 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-61 | Project_022_RISK-61 | Threat | Project Contingency | Open | H2 | 2 |  | Extended programme | Person_703 | 2016-11-20 01:00 | 2017-01-20 01:00 | 60% | 1.2976 | 0.77853 | Reduce | 60% | 1.2976 | 0.77853 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-61 | Project_022_RISK-61 | Threat | Project Contingency | Open | H2 | 2 |  | Extended programme | Person_703 | 2016-11-20 01:00 | 2017-01-20 01:00 | 60% | 1.2976 | 0.77853 | Reduce | 60% | 1.2976 | 0.77853 | H2 | 2 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Reduce touch labour if get-well programme successful | Person_515 | 2016-11-20 01:00 | 2017-10-21 01:00 | 30% | 1.5606 | 0.46818 | Exploit | 50% | 1.5606 | 0.7803 | H2 | 2 | -- | TRUE | 335 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK031 | Project_058_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Witnessing | Person_215 | 2017-05-23 | 2018-07-21 | 60% | 2.9361 | 1.7616 | Reduce | 40% | 1.9574 | 0.78295 | H2 | 2 | -- | TRUE | 424 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK031 | Project_058_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Witnessing | Person_215 | 2017-05-23 | 2018-07-21 | 60% | 2.9361 | 1.7616 | Reduce | 40% | 1.9574 | 0.78295 | H2 | 2 | -- | TRUE | 424 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK031 | Project_058_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Witnessing | Person_215 | 2017-05-23 | 2018-07-21 | 60% | 2.9361 | 1.7616 | Reduce | 40% | 1.9574 | 0.78295 | H2 | 2 | -- | TRUE | 424 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK070 | Project_058_RISK070 | Threat | Project Contingency | Open | H2 | 2 |  | Subsystem Fails EMC Testing | Person_414 | 2017-06-23 | 2018-07-20 | 50% | 3.1318 | 1.5659 | Reduce | 50% | 1.5659 | 0.78295 | H2 | 2 | -- | TRUE | 392 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK031 | Project_058_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Witnessing | Person_215 | 2017-05-23 | 2018-08-19 | 60% | 2.9361 | 1.7616 | Reduce | 40% | 1.9574 | 0.78295 | H2 | 2 | -- | TRUE | 453 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK070 | Project_058_RISK070 | Threat | Project Contingency | Open | H2 | 2 |  | Subsystem Fails EMC Testing | Person_414 | 2017-06-23 | 2018-07-20 | 50% | 3.1318 | 1.5659 | Reduce | 50% | 1.5659 | 0.78295 | H2 | 2 | -- | TRUE | 392 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK031 | Project_058_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Witnessing | Person_215 | 2017-05-23 | 2018-08-19 | 60% | 2.9361 | 1.7616 | Reduce | 40% | 1.9574 | 0.78295 | H2 | 2 | -- | TRUE | 453 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-020 | Project_062_Risk-020 | Threat | Project Contingency | Open | H2 | 2 |  | Security Encryption Solution | Person_245 | 2017-07-21 | 2018-10-22 01:00 | 25% | 4.183 | 1.0457 | Reduce | 20% | 4.183 | 0.83659 | H2 | 2 | Improving | TRUE | 458.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 15% | 5.8725 | 0.88088 | Accept | 5% | 5.8725 | 0.29363 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 15% | 5.8725 | 0.88088 | Reduce | 5% | 5.8725 | 0.29363 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-08 | 2020-09-21 | 15% | 5.8725 | 0.88088 | Reduce | 5% | 5.8725 | 0.29363 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 15% | 5.8725 | 0.88088 | Reduce | 5% | 5.8725 | 0.29363 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-07 23:00 | 2020-09-20 23:00 | 15% | 5.8725 | 0.88088 | Reduce | 5% | 5.8725 | 0.29363 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-07 22:00 | 2020-09-20 22:00 | 15% | 5.8725 | 0.88088 | Reduce | 5% | 5.8725 | 0.29363 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-07 23:00 | 2020-09-20 23:00 | 15% | 5.8725 | 0.88088 | Reduce | 5% | 5.8725 | 0.29363 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-07 22:00 | 2020-09-20 22:00 | 15% | 5.8725 | 0.88088 | Reduce | 5% | 5.8725 | 0.29363 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R040 | Project_085_R040 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Telemetry interconnectiion of the Sub-assemblies | Person_539 | 2017-12-21 | 2018-12-21 | 20% | 2.9617 | 0.59234 | Reduce | 10% | 2.9617 | 0.29617 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK050 | Project_031_RISK050 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to Security accrediation | Person_246 | 2015-05-13 | 2015-07-21 | 20% | 4.2304 | 0.84608 | -- | 20% | 4.2304 | 0.84608 | H2 | 2 | -- | TRUE | 69 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK050 | Project_031_RISK050 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to Security accrediation | Person_246 | 2015-05-13 | 2015-07-21 | 20% | 4.2304 | 0.84608 | -- | 20% | 4.2304 | 0.84608 | H2 | 2 | -- | TRUE | 69 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-07-20 | 10% | 3.005 | 0.3005 | Reduce | 10% | 3.005 | 0.3005 | H3 | 3 | Stable | TRUE | 545.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2017-02-19 01:00 | 10% | 3.005 | 0.3005 | Reduce | 10% | 3.005 | 0.3005 | H3 | 3 | Stable | TRUE | 760 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-10-20 01:00 | 10% | 3.005 | 0.3005 | Reduce | 10% | 3.005 | 0.3005 | H3 | 3 | Stable | TRUE | 638 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 10% | 3.005 | 0.3005 | Reduce | 10% | 3.005 | 0.3005 | H3 | 3 | Stable | TRUE | 698 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 10% | 3.005 | 0.3005 | Reduce | 10% | 3.005 | 0.3005 | H3 | 3 | Stable | TRUE | 698 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_185 | 2015-01-21 | 2016-12-19 | 10% | 3.005 | 0.3005 | Reduce | 10% | 3.005 | 0.3005 | H3 | 3 | Stable | TRUE | 698 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 10% | 3.005 | 0.3005 | Reduce | 10% | 3.005 | 0.3005 | H3 | 3 | Stable | TRUE | 698 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_185 | 2015-01-21 01:00 | 2016-12-19 01:00 | 10% | 3.005 | 0.3005 | Reduce | 10% | 3.005 | 0.3005 | H3 | 3 | Stable | TRUE | 698 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 729 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 729 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 729 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 729 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 729 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_594 | 2016-03-23 | 2018-03-22 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 729 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_418 | 2016-03-23 | 2018-06-06 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 805 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_418 | 2016-03-23 | 2018-06-06 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 805 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_418 | 2016-03-23 | 2018-06-06 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 805 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK071 | Project_065_RISK071 | Threat | Management Contingency | Open | H3 | 3 | Project Management | In-house development of sub-system estimate is low | Person_418 | 2016-03-23 | 2018-06-06 | 50% | 6.5118 | 3.2559 | Reduce | 20% | 1.506 | 0.30121 | H3 | 3 | Stable | TRUE | 805 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-034 | Project_026_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Training capacity on Operator Courses | Person_525 | 2017-08-13 | 2018-12-27 01:00 | 70% | 3.0218 | 2.1153 | Reduce | 10% | 3.0218 | 0.30218 | H3 | 3 | -- | TRUE | 501.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-034 | Project_026_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Training capacity on Operator Courses | Person_525 | 2017-08-13 | 2018-12-27 01:00 | 70% | 3.0218 | 2.1153 | Reduce | 10% | 3.0218 | 0.30218 | H3 | 3 | -- | TRUE | 501.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-034 | Project_026_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Training capacity on Operator Courses | Person_525 | 2017-08-13 | 2018-12-27 01:00 | 70% | 3.0218 | 2.1153 | Reduce | 10% | 3.0218 | 0.30218 | H3 | 3 | -- | TRUE | 501.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-034 | Project_026_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Training capacity on Operator Courses | Person_525 | 2017-08-13 | 2018-12-27 01:00 | 70% | 3.0218 | 2.1153 | Reduce | 10% | 3.0218 | 0.30218 | H3 | 3 | -- | TRUE | 501.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-034 | Project_026_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Training capacity on Operator Courses | Person_525 | 2017-08-13 | 2018-12-27 01:00 | 70% | 3.0218 | 2.1153 | Reduce | 10% | 3.0218 | 0.30218 | H3 | 3 | -- | TRUE | 501.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-034 | Project_026_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Training capacity on Operator Courses | Person_525 | 2017-08-13 | 2018-12-27 01:00 | 70% | 3.0218 | 2.1153 | Reduce | 10% | 3.0218 | 0.30218 | H3 | 3 | -- | TRUE | 501.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-034 | Project_026_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Training capacity on Operator Courses | Person_525 | 2017-08-13 | 2018-12-27 01:00 | 70% | 3.0218 | 2.1153 | Reduce | 10% | 3.0218 | 0.30218 | H3 | 3 | -- | TRUE | 501.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-034 | Project_026_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Training capacity on Operator Courses | Person_525 | 2017-08-13 | 2018-12-27 01:00 | 70% | 3.0218 | 2.1153 | Reduce | 10% | 3.0218 | 0.30218 | H3 | 3 | -- | TRUE | 501.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-014 | Project_096_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Hosting issues | Person_259 | 2018-06-23 | 2018-12-16 01:00 | 15% | 3.0354 | 0.45532 | Reduce | 10% | 3.0354 | 0.30354 | H3 | 3 | Stable | FALSE | 176.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.38121 | 0.30497 | Exploit | 80% | 0.38121 | 0.30497 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.38121 | 0.30497 | Exploit | 80% | 0.38121 | 0.30497 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.38121 | 0.30497 | Exploit | 80% | 0.38121 | 0.30497 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.38121 | 0.30497 | Exploit | 80% | 0.38121 | 0.30497 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK050 | Project_031_RISK050 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to Security accrediation | Person_246 | 2015-05-13 | 2015-07-21 | 20% | 4.2304 | 0.84608 | -- | 20% | 4.2304 | 0.84608 | H2 | 2 | -- | TRUE | 69 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK050 | Project_031_RISK050 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to Security accrediation | Person_246 | 2015-05-13 | 2015-07-21 | 20% | 4.2304 | 0.84608 | -- | 20% | 4.2304 | 0.84608 | H2 | 2 | -- | TRUE | 69 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK050 | Project_031_RISK050 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to Security accrediation | Person_246 | 2015-05-13 | 2015-07-21 | 20% | 4.2304 | 0.84608 | -- | 20% | 4.2304 | 0.84608 | H2 | 2 | -- | TRUE | 69 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK003 | Project_081_RISK003 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Export control issues taking longer to resolve | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 20% | 1.5256 | 0.30511 | Reduce | 20% | 1.5256 | 0.30511 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-092 | Project_011_Risk-092 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Merge Release 4 and 5 | Person_230 | 2016-07-21 | 2018-07-22 | 50% | 0.6137 | 0.30685 | -- | 50% | 0.6137 | 0.30685 | H3 | 3 | -- | FALSE | 731 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-092 | Project_011_Risk-092 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Merge Release 4 and 5 | Person_230 | 2016-07-21 | 2018-07-22 | 50% | 0.6137 | 0.30685 | -- | 50% | 0.6137 | 0.30685 | H3 | 3 | -- | FALSE | 731 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK050 | Project_031_RISK050 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to Security accrediation | Person_246 | 2015-05-13 | 2015-07-21 | 20% | 4.2304 | 0.84608 | -- | 20% | 4.2304 | 0.84608 | H2 | 2 | -- | TRUE | 69 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK050 | Project_031_RISK050 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to Security accrediation | Person_246 | 2015-05-13 | 2015-07-21 | 20% | 4.2304 | 0.84608 | -- | 20% | 4.2304 | 0.84608 | H2 | 2 | -- | TRUE | 69 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2016-08-21 01:00 | 55% | 0.56468 | 0.31057 | Reduce | 55% | 0.56468 | 0.31057 | H2 | 2 | Stable | TRUE | 243 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2016-08-21 01:00 | 55% | 0.56468 | 0.31057 | Reduce | 55% | 0.56468 | 0.31057 | H2 | 2 | Stable | TRUE | 243 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2016-12-21 01:00 | 55% | 0.56468 | 0.31057 | Reduce | 55% | 0.56468 | 0.31057 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2016-12-21 01:00 | 55% | 0.56468 | 0.31057 | Reduce | 55% | 0.56468 | 0.31057 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Acceptance Schedule is longer in duration/delayed | Person_102 | 2015-12-22 01:00 | 2017-05-23 | 55% | 0.56468 | 0.31057 | Reduce | 55% | 0.56468 | 0.31057 | H2 | 2 | Stable | TRUE | 517.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2015-12-22 01:00 | 2017-05-23 | 55% | 0.56468 | 0.31057 | Reduce | 55% | 0.56468 | 0.31057 | H2 | 2 | Stable | TRUE | 517.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2017-03-21 01:00 | 40% | 1.1257 | 0.45028 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Improving | TRUE | 191 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 284 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2017-03-21 01:00 | 40% | 1.1257 | 0.45028 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Improving | TRUE | 191 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 284 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2017-03-21 01:00 | 40% | 1.1257 | 0.45028 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Improving | TRUE | 191 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 284 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-08-20 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 375.0417 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-08-20 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 375.0417 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-08-20 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 375.0417 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-08-20 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 375 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-09-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 405.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--11 | Project_021_Risk--11 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional documentation required for final build certification | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 30% | 1.0374 | 0.31122 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_031 | RISK050 | Project_031_RISK050 | Threat | Project Contingency | Open | H2 | 2 |  | Delay to Security accrediation | Person_246 | 2015-05-13 | 2015-07-21 | 20% | 4.2304 | 0.84608 | -- | 20% | 4.2304 | 0.84608 | H2 | 2 | -- | TRUE | 69 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK013 | Project_074_RISK013 | Threat | Project Contingency | Open | H2 | 2 |  | Legacy material | Person_493 | 2017-09-20 01:00 | 2019-11-21 01:00 | 70% | 2.1324 | 1.4927 | Reduce | 40% | 2.1324 | 0.85297 | H2 | 2 | -- | TRUE | 792 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.3531 | 2.6825 | Exploit | 80% | 1.0687 | 0.85496 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.3531 | 2.6825 | Exploit | 80% | 1.0687 | 0.85496 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK559 | Project_065_RISK559 | Threat | Project Contingency | Open | H2 | 2 |  | COTS item grounding | Person_022 | 2018-04-14 | 2019-05-14 | 80% | 2.9326 | 2.3461 | Reduce | 30% | 2.9326 | 0.87979 | H2 | 2 | -- | TRUE | 395 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK559 | Project_065_RISK559 | Threat | Project Contingency | Open | H2 | 2 |  | COTS item grounding | Person_022 | 2018-04-14 | 2019-05-14 | 80% | 2.9326 | 2.3461 | Reduce | 30% | 2.9326 | 0.87979 | H2 | 2 | -- | TRUE | 395 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK559 | Project_065_RISK559 | Threat | Project Contingency | Open | H2 | 2 |  | COTS item grounding | Person_022 | 2018-04-14 | 2019-05-14 | 80% | 2.9326 | 2.3461 | Reduce | 30% | 2.9326 | 0.87979 | H2 | 2 | -- | TRUE | 395 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK559 | Project_065_RISK559 | Threat | Project Contingency | Open | H2 | 2 |  | COTS item grounding | Person_022 | 2018-04-14 | 2019-05-14 | 80% | 2.9326 | 2.3461 | Reduce | 30% | 2.9326 | 0.87979 | H2 | 2 | -- | TRUE | 395 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK055 | Project_058_RISK055 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Source Inspection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 30% | 2.9361 | 0.88082 | -- | 30% | 2.9361 | 0.88082 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK025 | Project_058_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Material / Supply chain delays (generic) | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 70% | 2.9361 | 2.0552 | Reduce | 30% | 2.9361 | 0.88082 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK025 | Project_058_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Material / Supply chain delays (generic) | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 70% | 2.9361 | 2.0552 | Reduce | 30% | 2.9361 | 0.88082 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK025 | Project_058_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Material / Supply chain delays (generic) | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 70% | 2.9361 | 2.0552 | Reduce | 30% | 2.9361 | 0.88082 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK025 | Project_058_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Material / Supply chain delays (generic) | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 70% | 2.9361 | 2.0552 | Reduce | 30% | 2.9361 | 0.88082 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK025 | Project_058_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Material / Supply chain delays (generic) | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 70% | 2.9361 | 2.0552 | Reduce | 30% | 2.9361 | 0.88082 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK025 | Project_058_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Material / Supply chain delays (generic) | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 70% | 2.9361 | 2.0552 | Reduce | 30% | 2.9361 | 0.88082 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK025 | Project_058_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Material / Supply chain delays (generic) | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 70% | 2.9361 | 2.0552 | Reduce | 30% | 2.9361 | 0.88082 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK006 | Project_092_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Mounting of Ruggedised Converters not possible | Person_169 | 2019-09-06 01:00 | 2019-12-26 01:00 | 30% | 9.1502 | 2.745 | Avoid | 10% | 9.1502 | 0.91502 | H2 | 2 | -- | TRUE | 111 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK070 | Project_058_RISK070 | Threat | Project Contingency | Open | H2 | 2 |  | Subsystem Fails EMC Testing | Person_108 | 2017-06-23 | 2018-01-19 01:00 | 30% | 3.1318 | 0.93954 | Reduce | 30% | 3.1318 | 0.93954 | H2 | 2 | -- | TRUE | 210.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK070 | Project_058_RISK070 | Threat | Project Contingency | Open | H2 | 2 |  | Subsystem Fails EMC Testing | Person_108 | 2017-06-23 | 2018-01-19 01:00 | 30% | 3.1318 | 0.93954 | Reduce | 30% | 3.1318 | 0.93954 | H2 | 2 | -- | TRUE | 210.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK113 | Project_066_RISK113 | Threat | Project Contingency | Open | H2 | 2 |  | Required Level of SME support not Available | Person_507 | 2018-08-23 01:00 | 2019-10-21 01:00 | 50% | 3.1538 | 1.5769 | Reduce | 30% | 3.1538 | 0.94613 | H2 | 2 | -- | TRUE | 424 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-20 01:00 | 2017-09-19 01:00 | 25% | 1.2519 | 0.31298 | Accept | 25% | 1.2519 | 0.31298 | H3 | 3 | -- | TRUE | 303 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-20 01:00 | 2017-09-19 01:00 | 25% | 1.2519 | 0.31298 | Accept | 25% | 1.2519 | 0.31298 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-20 | 2017-09-19 | 25% | 1.2519 | 0.31298 | Accept | 25% | 1.2519 | 0.31298 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-19 23:00 | 2017-09-18 23:00 | 25% | 1.2519 | 0.31298 | Accept | 25% | 1.2519 | 0.31298 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-19 23:00 | 2017-09-18 23:00 | 25% | 1.2519 | 0.31298 | Accept | 25% | 1.2519 | 0.31298 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-19 23:00 | 2017-09-18 23:00 | 25% | 1.2519 | 0.31298 | Accept | 25% | 1.2519 | 0.31298 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R05 | Project_041_R05 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Additional Engineering time to support the supply chain | Person_368 | 2016-11-19 22:00 | 2017-09-18 22:00 | 25% | 1.2519 | 0.31298 | Accept | 25% | 1.2519 | 0.31298 | H3 | 3 | Stable | TRUE | 303 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2016-11-20 01:00 | 2019-05-23 | 50% | 2.5081 | 1.2541 | Reduce | 25% | 1.2541 | 0.31351 | H3 | 3 | -- | TRUE | 913.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in Installation time in country | Person_330 | 2016-03-23 | 2016-08-19 01:00 | 40% | 3.187 | 1.2748 | Reduce | 30% | 3.187 | 0.9561 | H2 | 2 | Stable | TRUE | 149.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 40% | 3.187 | 1.2748 | Reduce | 30% | 3.187 | 0.9561 | H2 | 2 | Stable | TRUE | 302.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 40% | 3.187 | 1.2748 | Reduce | 30% | 3.187 | 0.9561 | H2 | 2 | Stable | TRUE | 302.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 2 |  | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-12-21 01:00 | 30% | 3.2155 | 0.96464 | Accept | 30% | 3.2155 | 0.96464 | H2 | 2 | Stable | TRUE | 577.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 2 |  | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-12-21 01:00 | 30% | 3.2155 | 0.96464 | Accept | 30% | 3.2155 | 0.96464 | H2 | 2 | Stable | TRUE | 577.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 2 |  | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-12-21 01:00 | 30% | 3.2155 | 0.96464 | Accept | 30% | 3.2155 | 0.96464 | H2 | 2 | Stable | TRUE | 577.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 2 |  | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 30% | 3.2155 | 0.96464 | Accept | 30% | 3.2155 | 0.96464 | H2 | 2 | Improving | TRUE | 516.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 2 |  | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 30% | 3.2155 | 0.96464 | Accept | 30% | 3.2155 | 0.96464 | H2 | 2 | Improving | TRUE | 516.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 2 |  | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 30% | 3.2155 | 0.96464 | Accept | 30% | 3.2155 | 0.96464 | H2 | 2 | Improving | TRUE | 516.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H2 | 2 |  | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 30% | 3.2155 | 0.96464 | Accept | 30% | 3.2155 | 0.96464 | H2 | 2 | Improving | TRUE | 516.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Reduce | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Reduce | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_332 | 2017-01-21 01:00 | 2019-05-16 | 40% | 1.5914 | 0.63655 | Reduce | 20% | 1.5914 | 0.31827 | H3 | 3 | Stable | FALSE | 844.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Transfer | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Transfer | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Transfer | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK037 | Project_042_RISK037 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs 1st Jan to 31 December Year 1 | Person_455 | 2020-05-23 | 2021-05-22 | 14% | 2.2828 | 0.31959 | Accept | 14% | 2.2828 | 0.31959 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1003 | Project_091_RISK1003 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integration issues arise with Controller | Person_557 | 2018-08-22 01:00 | 2020-05-22 | 20% | 1.5989 | 0.31977 | Accept | 20% | 1.5989 | 0.31977 | H3 | 3 | -- | TRUE | 638.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1003 | Project_091_RISK1003 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integration issues arise with Controller | Person_557 | 2018-09-21 01:00 | 2020-05-22 | 20% | 1.5989 | 0.31977 | Accept | 20% | 1.5989 | 0.31977 | H3 | 3 | -- | TRUE | 608.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Transfer | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK061 | Project_076_RISK061 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hazard Analysis Delay - SRS | Person_771 | 2018-05-23 | 2019-10-22 01:00 | 40% | 6.4264 | 2.5706 | Reduce | 5% | 6.4264 | 0.32132 | H3 | 3 | -- | FALSE | 517.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Transfer | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK061 | Project_076_RISK061 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hazard Analysis Delay - SRS | Person_771 | 2018-05-23 | 2019-10-22 01:00 | 40% | 6.4264 | 2.5706 | Reduce | 5% | 6.4264 | 0.32132 | H3 | 3 | -- | FALSE | 517.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Transfer | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK061 | Project_076_RISK061 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Hazard Analysis Delay - SRS | Person_771 | 2018-05-23 | 2019-10-22 01:00 | 40% | 6.4264 | 2.5706 | Reduce | 5% | 6.4264 | 0.32132 | H3 | 3 | -- | FALSE | 517.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 35% | 0.85557 | 0.29945 | Reduce | 35% | 0.92402 | 0.32341 | H2 | 2 | Stable | TRUE | 654 |  | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 35% | 0.85557 | 0.29945 | Reduce | 35% | 0.92402 | 0.32341 | H2 | 2 | Stable | TRUE | 654 |  | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 35% | 0.85557 | 0.29945 | Reduce | 35% | 0.92402 | 0.32341 | H2 | 2 | Stable | TRUE | 654 |  | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 35% | 0.85557 | 0.29945 | Reduce | 35% | 0.92402 | 0.32341 | H2 | 2 | Stable | TRUE | 654 |  | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 35% | 0.85557 | 0.29945 | Reduce | 35% | 0.92402 | 0.32341 | H2 | 2 | Stable | TRUE | 654 |  | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 35% | 3.2401 | 1.134 | Transfer | 10% | 3.2401 | 0.32401 | H3 | 3 | Stable | FALSE | 546.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 35% | 3.2401 | 1.134 | Transfer | 10% | 3.2401 | 0.32401 | H3 | 3 | Stable | FALSE | 546.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 35% | 3.2401 | 1.134 | Transfer | 10% | 3.2401 | 0.32401 | H3 | 3 | Stable | FALSE | 546.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 35% | 3.2401 | 1.134 | Transfer | 10% | 3.2401 | 0.32401 | H3 | 3 | Improving | FALSE | 546.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK117 | Project_037_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Data Comms Availability or Performance | Person_334 | 2015-05-24 | 2016-11-20 01:00 | 35% | 3.2401 | 1.134 | Transfer | 10% | 3.2401 | 0.32401 | H3 | 3 | Improving | FALSE | 546.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK084 | Project_049_RISK084 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Outsourcing (Quality) | Person_282 | 2017-08-23 01:00 | 2020-08-24 01:00 | 30% | 1.6274 | 0.48821 | Reduce | 20% | 1.6274 | 0.32547 | H3 | 3 | -- | TRUE | 1097 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-012 | Project_077_T-012 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Management cost increases for BMN | Person_202 | 2018-03-01 01:00 | 2020-02-21 01:00 | 21% | 1.5725 | 0.33022 | Avoid | 21% | 1.5725 | 0.33022 | H3 | 3 | Stable | TRUE | 722 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK007 | Project_058_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Project workload within Systems Engineering | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 50% | 3.9148 | 1.9574 | Transfer | 25% | 3.9148 | 0.97869 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 2 |  | Risk of repeat component Tests | Person_515 | 2016-11-20 01:00 | 2019-05-23 | 50% | 1.9722 | 0.98609 | Accept | 50% | 1.9722 | 0.98609 | H2 | 2 | -- | TRUE | 913.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 2 |  | Risk of repeat component Tests | Person_515 | 2017-12-21 01:00 | 2019-01-21 01:00 | 50% | 1.9722 | 0.98609 | Accept | 50% | 1.9722 | 0.98609 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 2 |  | Risk of repeat component Tests | Person_515 | 2017-12-21 | 2019-01-21 | 50% | 1.9722 | 0.98609 | Accept | 50% | 1.9722 | 0.98609 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 2 |  | Risk of repeat component Tests | Person_515 | 2017-12-20 23:00 | 2019-01-20 23:00 | 50% | 1.9722 | 0.98609 | Accept | 50% | 1.9722 | 0.98609 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 2 |  | Risk of repeat component Tests | Person_515 | 2017-12-20 23:00 | 2019-01-20 23:00 | 50% | 1.9722 | 0.98609 | Accept | 50% | 1.9722 | 0.98609 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 0.55181 | 0.44144 | Reduce | 60% | 0.55181 | 0.33108 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK070 | Project_076_RISK070 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Component needs to refigured | Person_484 | 2018-05-23 | 2019-09-26 01:00 | 20% | 1.6584 | 0.33169 | Accept | 20% | 1.6584 | 0.33169 | H3 | 3 | -- | FALSE | 491.0417 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK070 | Project_076_RISK070 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Component needs to be refigured | Person_484 | 2018-05-23 | 2019-09-26 01:00 | 20% | 1.6584 | 0.33169 | Accept | 20% | 1.6584 | 0.33169 | H3 | 3 | -- | FALSE | 491.0417 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK070 | Project_076_RISK070 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Component needs to be refigured | Person_484 | 2018-05-23 | 2019-09-26 01:00 | 20% | 1.6584 | 0.33169 | Accept | 20% | 1.6584 | 0.33169 | H3 | 3 | Stable | FALSE | 491.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 2 |  | Risk of repeat component Tests | Person_515 | 2017-12-20 23:00 | 2019-01-20 23:00 | 50% | 1.9722 | 0.98609 | Accept | 50% | 1.9722 | 0.98609 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 20% | 1.661 | 0.33219 | Reduce | 20% | 1.661 | 0.33219 | H2 | 2 | Stable | TRUE | 730.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 | 2018-08-21 | 20% | 1.661 | 0.33219 | Reduce | 20% | 1.661 | 0.33219 | H2 | 2 | Stable | TRUE | 731 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 | 2018-08-21 | 20% | 1.661 | 0.33219 | Reduce | 20% | 1.661 | 0.33219 | H2 | 2 | Stable | TRUE | 731 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 20% | 1.661 | 0.33219 | Reduce | 20% | 1.661 | 0.33219 | H2 | 2 | Stable | TRUE | 730.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 20% | 1.661 | 0.33219 | Reduce | 20% | 1.661 | 0.33219 | H2 | 2 | Stable | TRUE | 730.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-066 | Project_011_Risk-066 | Threat | Project Contingency | Open | H2 | 2 | Customers | Issue with Customer Acceptance of Customer Model (Hybrid vs. Live) | Person_187 | 2016-08-20 01:00 | 2018-08-21 | 20% | 1.661 | 0.33219 | Reduce | 20% | 1.661 | 0.33219 | H2 | 2 | Stable | TRUE | 730.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-19 17:00 | 5% | 11.0894 | 0.55447 | Accept | 3% | 11.0894 | 0.33268 | H2 | 2 | Stable | TRUE | 1905.7083 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK013 | Project_001_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Heavy reliance on contractors | Person_674 | 2016-08-21 01:00 | 2016-08-04 | 30% | 0.95502 | 0.2865 | Reduce | 35% | 0.95502 | 0.33426 | H3 | 3 | -- | TRUE | -17.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK013 | Project_001_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Heavy reliance on contractors | Person_674 | 2016-08-21 01:00 | 2016-08-04 | 30% | 0.95502 | 0.2865 | Reduce | 35% | 0.95502 | 0.33426 | H3 | 3 | -- | TRUE | -17.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-20 01:00 | 2018-05-22 | 50% | 1.3377 | 0.66883 | Reduce | 25% | 1.3377 | 0.33441 | H2 | 2 | -- | TRUE | 547.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-20 01:00 | 2018-05-22 | 50% | 1.3377 | 0.66883 | Reduce | 25% | 1.3377 | 0.33441 | H2 | 2 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-20 | 2018-05-22 | 50% | 1.3377 | 0.66883 | Reduce | 25% | 1.3377 | 0.33441 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-19 23:00 | 2018-05-22 | 50% | 1.3377 | 0.66883 | Reduce | 25% | 1.3377 | 0.33441 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-19 23:00 | 2018-05-22 | 50% | 1.3377 | 0.66883 | Reduce | 25% | 1.3377 | 0.33441 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-19 23:00 | 2018-05-22 | 50% | 1.3377 | 0.66883 | Reduce | 25% | 1.3377 | 0.33441 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R21 | Project_041_R21 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Regulatory standards changes misunderstood | Person_368 | 2016-11-19 22:00 | 2018-05-22 | 50% | 1.3377 | 0.66883 | Reduce | 25% | 1.3377 | 0.33441 | H2 | 2 | Stable | TRUE | 548.0833 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R89 | Project_041_R89 | Threat | Project Contingency | Open | H2 | 2 |  | Risk of repeat component Tests | Person_515 | 2017-12-20 22:00 | 2019-01-20 22:00 | 50% | 1.9722 | 0.98609 | Accept | 50% | 1.9722 | 0.98609 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 2 |  | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-09-19 01:00 | 80% | 3.6791 | 2.9433 | Reduce | 34.7% | 2.9061 | 1.0084 | H2 | 2 | Worsening | TRUE | 1614.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 2 |  | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-10-19 01:00 | 80% | 3.6791 | 2.9433 | Reduce | 34.7% | 2.9061 | 1.0084 | H2 | 2 | Worsening | TRUE | 1644.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 2 |  | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.6791 | 2.9433 | Reduce | 34.7% | 2.9061 | 1.0084 | H2 | 2 | Worsening | TRUE | 1675.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 40% | 2.5311 | 1.0124 | H2 | 2 | Stable | TRUE | 488 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-021 | Project_026_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Customer may reject acceptance evidence | Person_607 | 2015-09-30 01:00 | 2018-12-27 01:00 | 50% | 1.343 | 0.67152 | Reduce | 25% | 1.343 | 0.33576 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2016-05-23 | 2019-08-21 01:00 | 10% | 6.7334 | 0.67334 | Reduce | 5% | 6.7334 | 0.33667 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.6835 | 0.42087 | Reduce | 20% | 1.6835 | 0.33669 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.6835 | 0.42087 | Reduce | 20% | 1.6835 | 0.33669 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.6835 | 0.42087 | Reduce | 20% | 1.6835 | 0.33669 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.6835 | 0.42087 | Reduce | 20% | 1.6835 | 0.33669 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.6835 | 0.42087 | Reduce | 20% | 1.6835 | 0.33669 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.6835 | 0.42087 | Reduce | 20% | 1.6835 | 0.33669 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK201 | Project_024_RISK201 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Indication mode failure | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.6835 | 0.42087 | Reduce | 20% | 1.6835 | 0.33669 | H3 | 3 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-032 | Project_077_T-032 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Requirement Updated from Issue 4 to 6 | Person_092 | 2018-02-20 01:00 | 2020-02-21 01:00 | 50% | 3.3696 | 1.6848 | Avoid | 10% | 3.3696 | 0.33696 | H3 | 3 | Stable | FALSE | 731 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 40% | 2.5311 | 1.0124 | H2 | 2 | Stable | TRUE | 488 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 40% | 2.5311 | 1.0124 | H2 | 2 | Stable | TRUE | 488 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 40% | 2.5311 | 1.0124 | H2 | 2 | Stable | TRUE | 488 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK024 | Project_075_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Failure to meet promised delivery dates | Person_627 | 2017-09-20 01:00 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 40% | 2.5311 | 1.0124 | H2 | 2 | Stable | TRUE | 488 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 2 |  | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.6791 | 2.9433 | Reduce | 35% | 2.9061 | 1.0171 | H2 | 2 | Worsening | TRUE | 1675.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.3502 | 0.33756 | Accept | 25% | 1.3502 | 0.33756 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.3502 | 0.33756 | Accept | 25% | 1.3502 | 0.33756 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.3502 | 0.33756 | Accept | 25% | 1.3502 | 0.33756 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.3502 | 0.33756 | Accept | 25% | 1.3502 | 0.33756 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.3502 | 0.33756 | Accept | 25% | 1.3502 | 0.33756 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.3502 | 0.33756 | Accept | 25% | 1.3502 | 0.33756 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.3502 | 0.33756 | Accept | 25% | 1.3502 | 0.33756 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK194 | Project_024_RISK194 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Performance Models require additional effort | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 25% | 1.3502 | 0.33756 | Accept | 25% | 1.3502 | 0.33756 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-113 | Project_029_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | SW Delivery to INtegration (including bug fixes post delivery) | Person_199 | 2014-07-22 | 2016-11-19 01:00 | 40% | 0.64168 | 0.25667 | Avoid | 40% | 0.84702 | 0.33881 | H2 | 2 | Worsening | TRUE | 851.0417 |  | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-113 | Project_029_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | Project Management | SW Delivery to INtegration (including bug fixes post delivery) | Person_199 | 2014-07-22 | 2016-11-19 01:00 | 40% | 0.64168 | 0.25667 | Avoid | 40% | 0.84702 | 0.33881 | H2 | 2 | Worsening | TRUE | 851.0417 |  | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK045 | Project_049_RISK045 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Failure to Meet Safety Legislation - Supplier evidence does not meet requirements | Person_714 | 2017-08-23 01:00 | 2019-11-18 01:00 | 20% | 1.6962 | 0.33923 | Accept | 20% | 1.6962 | 0.33923 | H3 | 3 | -- | TRUE | 817 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 2 |  | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.6791 | 2.9433 | Reduce | 35% | 2.9061 | 1.0171 | H2 | 2 | Worsening | TRUE | 1675.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 2 |  | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.6791 | 2.9433 | Reduce | 35% | 2.9061 | 1.0171 | H2 | 2 | Worsening | TRUE | 1675.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 2 |  | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-02-19 01:00 | 80% | 3.6791 | 2.9433 | Reduce | 35% | 2.9061 | 1.0171 | H2 | 2 | Stable | TRUE | 1767.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-02 | Project_022_RISK-02 | Threat | Project Contingency | Open | H2 | 2 |  | Customer dependencies on completing contract | Person_703 | 2012-04-19 | 2017-04-21 | 80% | 3.6791 | 2.9433 | Reduce | 35% | 2.9061 | 1.0171 | H2 | 2 | Stable | TRUE | 1828 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK002 | Project_043_RISK002 | Threat | Project Contingency | Open | H2 | 2 |  | Replacement of Gen-1 products by Gen-2 products | Person_368 | 2014-09-13 | 2018-03-21 | 10% | 10.683 | 1.0683 | -- | 10% | 10.18 | 1.018 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | OOP003 | Project_042_OOP003 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Cost Base Savings. | Person_455 | 2021-01-21 01:00 | 2021-05-22 | 10% | 10.3335 | 1.0334 | Accept | 10% | 10.3335 | 1.0334 | H2 | 2 | -- | TRUE | 120.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK533-Risk- | Project_065_RISK533-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Late Deliveries Between internal organisations | Person_038 | 2020-05-23 | 2023-04-23 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK533- | Project_065_RISK533- | Threat | Project Contingency | Open | H2 | 2 |  | Late Deliveries Between internal organisations | Person_038 | 2020-05-23 | 2021-11-20 01:00 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 546.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK533-Risk- | Project_065_RISK533-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Late Deliveries Between internal organisations | Person_038 | 2020-05-23 | 2023-04-23 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK533- | Project_065_RISK533- | Threat | Project Contingency | Open | H2 | 2 |  | Late Deliveries Between internal organisations | Person_038 | 2020-05-23 | 2021-11-20 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 546 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2019-05-24 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Reduce | 10% | 3.4651 | 0.34651 | H3 | 3 | -- | TRUE | 699 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2019-05-24 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Reduce | 10% | 3.4651 | 0.34651 | H3 | 3 | -- | TRUE | 699 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2019-05-24 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Reduce | 10% | 3.4651 | 0.34651 | H3 | 3 | -- | TRUE | 699 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H3 | 3 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2019-05-24 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Reduce | 10% | 3.4651 | 0.34651 | H3 | 3 | -- | TRUE | 699 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 50% | 0.87268 | 0.43634 | Accept | 40% | 0.87268 | 0.34907 | H3 | 3 | Stable | TRUE | 1117 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 50% | 0.87268 | 0.43634 | Accept | 40% | 0.87268 | 0.34907 | H3 | 3 | Stable | TRUE | 1117 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 50% | 0.87268 | 0.43634 | Accept | 40% | 0.87268 | 0.34907 | H3 | 3 | Stable | TRUE | 1117 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 50% | 0.87268 | 0.43634 | Accept | 40% | 0.87268 | 0.34907 | H3 | 3 | Stable | TRUE | 1117 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-026 | Project_029_Risk-026 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | platform Integration - SW support | Person_102 | 2016-09-02 01:00 | 2019-09-24 01:00 | 50% | 0.87268 | 0.43634 | Accept | 40% | 0.87268 | 0.34907 | H3 | 3 | Stable | TRUE | 1117 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-26 01:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 958.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-26 01:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 958.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-26 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 958 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-26 01:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 958.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-25 23:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 957.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-25 22:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 957.9167 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-25 23:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 957.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-26 01:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 958.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-25 22:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 957.9167 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-26 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 958 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-26 01:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 958.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK478 | Project_065_RISK478 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient hardware to support all SW verification testing required for deliveries | Person_661 | 2018-04-13 | 2020-11-25 23:00 | 80% | 6.4907 | 5.1926 | Reduce | 15% | 2.3326 | 0.34989 | H3 | 3 | -- | FALSE | 957.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 10% | 1.6835 | 0.16835 | Reduce | 10% | 3.5011 | 0.35011 | H3 | 3 | Improving | FALSE | 332 |  | 0 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 10% | 1.6835 | 0.16835 | Reduce | 10% | 3.5011 | 0.35011 | H3 | 3 | Improving | FALSE | 332 |  | 0 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK533-Risk- | Project_065_RISK533-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Late Deliveries Between internal organisations | Person_038 | 2020-05-23 | 2023-04-23 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 35% | 1.0052 | 0.35182 | Accept | 35% | 1.0052 | 0.35182 | H1 | 1 | Stable | TRUE | 196.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 | 35% | 1.0052 | 0.35182 | Accept | 35% | 1.0052 | 0.35182 | H1 | 1 | Stable | TRUE | 196 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 | 35% | 1.0052 | 0.35182 | Accept | 35% | 1.0052 | 0.35182 | H1 | 1 | Stable | TRUE | 196 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 35% | 1.0052 | 0.35182 | Accept | 35% | 1.0052 | 0.35182 | H1 | 1 | Stable | TRUE | 196.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 35% | 1.0052 | 0.35182 | Accept | 35% | 1.0052 | 0.35182 | H1 | 1 | Stable | TRUE | 196.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-119 | Project_011_Risk-119 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | More issues than expected during Qualification | Person_147 | 2017-04-22 | 2017-11-04 01:00 | 35% | 1.0052 | 0.35182 | Accept | 35% | 1.0052 | 0.35182 | H1 | 1 | Stable | TRUE | 196.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK533- | Project_065_RISK533- | Threat | Project Contingency | Open | H2 | 2 |  | Late Deliveries Between internal organisations | Person_038 | 2020-05-23 | 2021-11-20 01:00 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 546.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK533-Risk- | Project_065_RISK533-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Late Deliveries Between internal organisations | Person_038 | 2020-05-23 | 2023-04-23 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK533- | Project_065_RISK533- | Threat | Project Contingency | Open | H2 | 2 |  | Late Deliveries Between internal organisations | Person_038 | 2020-05-23 | 2021-11-19 23:00 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 545.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK211 | Project_024_RISK211 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer drives scope change | Person_351 | 2017-01-21 01:00 | 2017-06-22 | 30% | 1.7657 | 0.52971 | Reduce | 20% | 1.7657 | 0.35314 | H3 | 3 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2019-05-24 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Reduce | 10% | 3.5496 | 0.35496 | H3 | 3 | -- | TRUE | 729 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2019-05-24 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Reduce | 10% | 3.5496 | 0.35496 | H3 | 3 | -- | TRUE | 729 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2019-05-24 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Reduce | 10% | 3.5496 | 0.35496 | H3 | 3 | -- | TRUE | 729 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2019-05-24 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Reduce | 10% | 3.5496 | 0.35496 | H3 | 3 | -- | TRUE | 729 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2019-05-24 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Reduce | 10% | 3.5496 | 0.35496 | H3 | 3 | -- | TRUE | 729 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2019-05-24 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Reduce | 10% | 3.5496 | 0.35496 | H3 | 3 | -- | TRUE | 729 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2019-05-24 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Reduce | 10% | 3.5496 | 0.35496 | H3 | 3 | -- | TRUE | 729 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-048 | Project_062_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software lockdown features | Person_245 | 2017-07-21 | 2018-11-21 01:00 | 50% | 0.71808 | 0.35904 | Reduce | 50% | 0.71808 | 0.35904 | H2 | 2 | Stable | TRUE | 488.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK024 | Project_029_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Design Changes | Person_332 | 2019-02-21 01:00 | 2020-03-21 | 70% | 1.0267 | 0.71868 | Reduce | 35% | 1.0267 | 0.35934 | H2 | 2 | -- | TRUE | 393.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk001 | Project_009_Risk001 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Work to complete sus-system | Person_459 | 2016-08-03 | 2016-09-19 01:00 | 100% | 1.2105 | 1.2105 | Accept | 30% | 1.2105 | 0.36316 | H2 | 2 | -- | TRUE | 47.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK317 | Project_035_RISK317 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test Equipment Failure | Person_570 | 2014-10-22 01:00 | 2016-08-19 01:00 | 10% | 3.65 | 0.365 | Accept | 10% | 3.65 | 0.365 | H3 | 3 | Stable | TRUE | 667 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 70% | 24.1887 | 16.9321 | Reduce | 25% | 4.3567 | 1.0892 | H2 | 2 | Stable | TRUE | 1146 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 70% | 24.1887 | 16.9321 | Reduce | 25% | 4.3567 | 1.0892 | H2 | 2 | Stable | TRUE | 1146 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 70% | 24.1887 | 16.9321 | Reduce | 25% | 4.3567 | 1.0892 | H2 | 2 | Stable | TRUE | 1146 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 70% | 24.1887 | 16.9321 | Reduce | 25% | 4.3567 | 1.0892 | H2 | 2 | Stable | TRUE | 1146 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 70% | 24.1887 | 16.9321 | Reduce | 25% | 4.3567 | 1.0892 | H2 | 2 | Stable | TRUE | 1146 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2016-11-17 01:00 | 70% | 24.1887 | 16.9321 | Reduce | 25% | 4.3567 | 1.0892 | H2 | 2 | Stable | TRUE | 1146 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-03-22 | 70% | 24.1887 | 16.9321 | Reduce | 25% | 4.3567 | 1.0892 | H2 | 2 | Stable | TRUE | 1270.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-009 | Project_023_Risk-009 | Threat | Project Contingency | Open | H2 | 2 |  | Test & Acceptance | Person_277 | 2013-09-28 01:00 | 2017-03-22 | 70% | 24.1887 | 16.9321 | Reduce | 25% | 4.3567 | 1.0892 | H2 | 2 | Stable | TRUE | 1270.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK056 | Project_058_RISK056 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Doc Pack Content | Person_294 | 2018-02-20 01:00 | 2018-11-20 01:00 | 70% | 1.5659 | 1.0961 | -- | 70% | 1.5659 | 1.0961 | H2 | 2 | -- | TRUE | 273 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK056 | Project_058_RISK056 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Doc Pack Content | Person_294 | 2018-02-20 01:00 | 2018-11-20 01:00 | 70% | 1.5659 | 1.0961 | -- | 70% | 1.5659 | 1.0961 | H2 | 2 | -- | TRUE | 273 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK022 | Project_058_RISK022 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | Reduce | 40% | 2.9361 | 1.1744 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK031 | Project_058_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Witnessing | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | -- | 40% | 2.9361 | 1.1744 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK030 | Project_058_RISK030 | Threat | Project Contingency | Open | H2 | 2 |  | Source Inspection Q1 | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | Reduce | 40% | 2.9361 | 1.1744 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK022 | Project_058_RISK022 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2018-05-22 | 80% | 5.8721 | 4.6977 | Reduce | 40% | 2.9361 | 1.1744 | H2 | 2 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK022 | Project_058_RISK022 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2018-05-22 | 80% | 5.8721 | 4.6977 | Reduce | 40% | 2.9361 | 1.1744 | H2 | 2 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-21 01:00 | 2018-08-19 | 50% | 3.9172 | 1.9586 | Reduce | 30% | 3.9172 | 1.1752 | H2 | 2 | -- | TRUE | 666.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-21 | 2018-08-19 | 50% | 3.9172 | 1.9586 | Reduce | 30% | 3.9172 | 1.1752 | H2 | 2 | -- | TRUE | 667 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-21 01:00 | 2018-08-19 | 50% | 3.9172 | 1.9586 | Reduce | 30% | 3.9172 | 1.1752 | H2 | 2 | -- | TRUE | 666.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-20 23:00 | 2018-08-19 | 50% | 3.9172 | 1.9586 | Reduce | 30% | 3.9172 | 1.1752 | H2 | 2 | -- | TRUE | 667.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-033 | Project_043_Risk-033 | Threat | Project Contingency | Open | H2 | 2 |  | Customer - Increased Scope | Person_184 | 2015-04-06 | 2016-04-05 | 30% | 11.3776 | 3.4133 | -- | 20% | 5.9882 | 1.1976 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK031 | Project_075_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Unit Production Cost | Person_627 | 2017-05-23 | 2018-09-20 01:00 | 60% | 4.0498 | 2.4299 | Reduce | 30% | 4.0498 | 1.2149 | H2 | 2 | -- | TRUE | 485.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 20% | 7.3175 | 1.4635 | Reduce | 5% | 7.3175 | 0.36588 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 20% | 7.3175 | 1.4635 | Reduce | 5% | 7.3175 | 0.36588 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 20% | 7.3175 | 1.4635 | Reduce | 5% | 7.3175 | 0.36588 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 20% | 7.3175 | 1.4635 | Reduce | 5% | 7.3175 | 0.36588 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 20% | 7.3175 | 1.4635 | Reduce | 5% | 7.3175 | 0.36588 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 20% | 7.3175 | 1.4635 | Reduce | 5% | 7.3175 | 0.36588 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 20% | 7.3175 | 1.4635 | Reduce | 5% | 7.3175 | 0.36588 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-200 | Project_027_Risk-200 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Sucession Planning for key team members | Person_060 | 2014-01-04 01:00 | 2017-08-20 01:00 | 20% | 7.3175 | 1.4635 | Reduce | 5% | 7.3175 | 0.36588 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-089 | Project_011_Risk-089 | Opportunitity | Project Contingency | Open | H2 | 2 | Finance | Protect 10% of the current risk budget to contribute to current EAC challenge | Person_522 | 2015-01-22 01:00 | 2018-07-22 | 60% | 0.6137 | 0.36822 | -- | 60% | 0.6137 | 0.36822 | H3 | 3 | -- | FALSE | 1276.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-089 | Project_011_Risk-089 | Opportunitity | Project Contingency | Open | H2 | 2 | Finance | Protect 10% of the current risk budget to contribute to current EAC challenge | Person_522 | 2015-01-22 01:00 | 2018-07-22 | 60% | 0.6137 | 0.36822 | -- | 60% | 0.6137 | 0.36822 | H3 | 3 | -- | FALSE | 1276.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-050 | Project_026_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Post CDR Supply | Person_396 | 2014-11-21 01:00 | 2018-01-21 01:00 | 5% | 7.3867 | 0.36934 | Reduce | 5% | 7.3867 | 0.36934 | H2 | 2 | -- | TRUE | 1157 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-050 | Project_026_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Post CDR Supply | Person_396 | 2014-11-21 01:00 | 2018-01-21 01:00 | 5% | 7.3867 | 0.36934 | Reduce | 5% | 7.3867 | 0.36934 | H2 | 2 | -- | TRUE | 1157 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-050 | Project_026_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Post CDR Supply | Person_396 | 2014-11-21 01:00 | 2018-01-21 01:00 | 5% | 7.3867 | 0.36934 | Reduce | 5% | 7.3867 | 0.36934 | H2 | 2 | -- | TRUE | 1157 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-050 | Project_026_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Post CDR Supply | Person_396 | 2014-11-21 01:00 | 2018-01-21 01:00 | 5% | 7.3867 | 0.36934 | Reduce | 5% | 7.3867 | 0.36934 | H2 | 2 | -- | TRUE | 1157 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-050 | Project_026_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Supply of components to the subsystem team | Person_690 | 2014-11-21 01:00 | 2018-01-21 01:00 | 5% | 7.3867 | 0.36934 | Reduce | 5% | 7.3867 | 0.36934 | H2 | 2 | -- | TRUE | 1157 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 10% | 3.6965 | 0.36965 | Accept | 10% | 3.6965 | 0.36965 | H2 | 2 | Stable | TRUE | 632 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 30% | 1.8482 | 0.55447 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 976 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 1368.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 10% | 3.6965 | 0.36965 | Accept | 10% | 3.6965 | 0.36965 | H2 | 2 | Stable | TRUE | 632 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 30% | 1.8482 | 0.55447 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 976 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 1368.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 10% | 3.6965 | 0.36965 | Accept | 10% | 3.6965 | 0.36965 | H2 | 2 | Stable | TRUE | 632 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 30% | 1.8482 | 0.55447 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 976 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 1368.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 | 2016-08-20 | 10% | 3.6965 | 0.36965 | Accept | 10% | 3.6965 | 0.36965 | H2 | 2 | Stable | TRUE | 632 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 30% | 1.8482 | 0.55447 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 976 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 1368 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 10% | 3.6965 | 0.36965 | Accept | 10% | 3.6965 | 0.36965 | H2 | 2 | Stable | TRUE | 632 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 30% | 1.8482 | 0.55447 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 976 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 1368.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 10% | 3.6965 | 0.36965 | Accept | 10% | 3.6965 | 0.36965 | H2 | 2 | Stable | TRUE | 632 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 30% | 1.8482 | 0.55447 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 976 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 1368.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 01:00 | 2016-08-20 01:00 | 10% | 3.6965 | 0.36965 | Accept | 10% | 3.6965 | 0.36965 | H2 | 2 | Stable | TRUE | 632 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 30% | 1.8482 | 0.55447 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 976 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 01:00 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 1368.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK71 | Project_010_RISK71 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Wiring Loom may cause issues during warranty period of the Export systems | Person_359 | 2014-11-27 | 2016-08-20 | 10% | 3.6965 | 0.36965 | Accept | 10% | 3.6965 | 0.36965 | H2 | 2 | Stable | TRUE | 632 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2016-04-22 | 30% | 1.8482 | 0.55447 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 976 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2016-02-20 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 1368 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK86 | Project_010_RISK86 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Tariff charges & extended processes | Person_359 | 2013-08-20 | 2018-04-22 | 30% | 1.8482 | 0.55447 | Accept | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | TRUE | 1706 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK80 | Project_010_RISK80 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | FPGA Test Spec | Person_359 | 2012-05-23 | 2018-02-18 17:00 | 80% | 18.4823 | 14.7858 | Reduce | 20% | 1.8482 | 0.36965 | H3 | 3 | Stable | FALSE | 2097.7083 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--111 | Project_100_Risk--111 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Failure to achieve KPIs | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 10% | 3.7 | 0.37 | -- | 10% | 3.7 | 0.37 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-018 | Project_077_T-018 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Config system changes | Person_092 | 2018-02-20 01:00 | 2020-02-21 01:00 | 15% | 2.4711 | 0.37066 | Accept | 15% | 2.4711 | 0.37066 | H3 | 3 | Stable | FALSE | 731 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-07-12 | 61% | 1.2358 | 0.75383 | Reduce | 30% | 1.2358 | 0.37073 | H2 | 2 | Stable | TRUE | 294.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-07-12 | 61% | 1.2358 | 0.75383 | Reduce | 30% | 1.2358 | 0.37073 | H2 | 2 | Stable | TRUE | 294.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 61% | 1.2358 | 0.75383 | Reduce | 30% | 1.2358 | 0.37073 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 61% | 1.2358 | 0.75383 | Reduce | 30% | 1.2358 | 0.37073 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 61% | 1.2358 | 0.75383 | Reduce | 30% | 1.2358 | 0.37073 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 61% | 1.2358 | 0.75383 | Reduce | 30% | 1.2358 | 0.37073 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK114 | Project_035_RISK114 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Qualification Facilities Availability. | Person_570 | 2015-09-21 01:00 | 2016-08-20 01:00 | 61% | 1.2358 | 0.75383 | Reduce | 30% | 1.2358 | 0.37073 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-21 23:00 | 2017-05-22 | 25% | 7.4225 | 1.8556 | Reduce | 10% | 3.7113 | 0.37113 | H3 | 3 | Stable | TRUE | 3773.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-21 22:00 | 2017-05-22 | 25% | 7.4225 | 1.8556 | Reduce | 10% | 3.7113 | 0.37113 | H3 | 3 | Stable | TRUE | 3773.0833 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-21 21:00 | 2017-05-22 | 25% | 7.4225 | 1.8556 | Reduce | 10% | 3.7113 | 0.37113 | H3 | 3 | Stable | TRUE | 3773.125 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 25% | 7.4225 | 1.8556 | Reduce | 10% | 3.7113 | 0.37113 | H3 | 3 | Stable | TRUE | 3772.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-6 | Project_020_Risk-6 | Threat | Project Contingency | Open | H3 | 3 | Acquisition and offsets | Supplier Performance | Person_575 | 2007-01-22 01:00 | 2017-05-22 | 25% | 7.4225 | 1.8556 | Reduce | 10% | 3.7113 | 0.37113 | H3 | 3 | Stable | TRUE | 3772.9583 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 01:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1251.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 01:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1251.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1251 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 01:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1251.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-25 23:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1250.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-26 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1251 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-25 22:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1250.9167 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-25 23:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1250.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_572 | 2020-05-23 | 2023-10-26 01:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1251.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_038 | 2020-05-23 | 2023-10-25 22:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1250.9167 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_572 | 2020-05-23 | 2023-10-26 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1251 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_572 | 2020-05-23 | 2023-10-26 01:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1251.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK057 | Project_065_RISK057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Penetration testing could lead to follow up changes | Person_572 | 2020-05-23 | 2023-10-25 23:00 | 20% | 7.4599 | 1.492 | Reduce | 5% | 7.4599 | 0.37299 | H2 | 2 | Stable | TRUE | 1250.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-034 | Project_077_T-034 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Simulator update not viable if needed | Person_203 | 2018-10-22 01:00 | 2020-02-21 01:00 | 50% | 0.74806 | 0.37403 | Avoid | 50% | 0.74806 | 0.37403 | H2 | 2 | Stable | TRUE | 487 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 10% | 3.7514 | 0.37514 | Accept | 10% | 3.7514 | 0.37514 | H3 | 3 | -- | FALSE | 547.9583 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 10% | 3.7514 | 0.37514 | Accept | 10% | 3.7514 | 0.37514 | H3 | 3 | Stable | FALSE | 547.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-20 | 2018-05-22 | 10% | 3.7514 | 0.37514 | Accept | 10% | 3.7514 | 0.37514 | H3 | 3 | Stable | FALSE | 548 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 10% | 3.7514 | 0.37514 | Accept | 10% | 3.7514 | 0.37514 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 10% | 3.7514 | 0.37514 | Accept | 10% | 3.7514 | 0.37514 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 10% | 3.7514 | 0.37514 | Accept | 10% | 3.7514 | 0.37514 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R26 | Project_041_R26 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production - Design Changes | Person_515 | 2016-11-19 22:00 | 2018-05-22 | 10% | 3.7514 | 0.37514 | Accept | 10% | 3.7514 | 0.37514 | H3 | 3 | Stable | FALSE | 548.0833 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK023 | Project_042_RISK023 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence May to April | Person_455 | 2018-09-21 01:00 | 2019-09-20 01:00 | 20% | 4.6971 | 0.93941 | Accept | 10% | 3.7576 | 0.37576 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 20:00 | 2019-08-20 20:00 | 61% | 2.2054 | 1.3453 | Reduce | 61% | 0.61752 | 0.37669 | H1 | 1 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 20:00 | 2019-08-20 20:00 | 61% | 2.2054 | 1.3453 | Reduce | 61% | 0.61752 | 0.37669 | H1 | 1 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 20:00 | 2019-08-20 20:00 | 61% | 2.2054 | 1.3453 | Reduce | 61% | 0.61752 | 0.37669 | H1 | 1 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 20:00 | 2019-08-20 20:00 | 61% | 2.2054 | 1.3453 | Reduce | 61% | 0.61752 | 0.37669 | H1 | 1 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 61% | 2.2054 | 1.3453 | Reduce | 61% | 0.61752 | 0.37669 | H1 | 1 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 61% | 2.2054 | 1.3453 | Reduce | 61% | 0.61752 | 0.37669 | H1 | 1 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 61% | 2.2054 | 1.3453 | Reduce | 61% | 0.61752 | 0.37669 | H1 | 1 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS013 | Project_025_RS013 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Unsupported Software | Person_335 | 2012-08-20 19:00 | 2019-08-20 19:00 | 61% | 2.2054 | 1.3453 | Reduce | 61% | 0.61752 | 0.37669 | H1 | 1 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-045 | Project_028_Risk-045 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Subcontractor Delays to Software | Person_542 | 2015-11-21 | 2016-06-22 | 30% | 1.2572 | 0.37717 | Accept | 30% | 1.2572 | 0.37717 | H2 | 2 | Stable | TRUE | 214 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 45% | 0.83883 | 0.37747 | Reduce | 45% | 0.83883 | 0.37747 | H2 | 2 | Stable | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 | 2018-08-21 | 45% | 0.83883 | 0.37747 | Reduce | 45% | 0.83883 | 0.37747 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 | 2018-08-21 | 45% | 0.83883 | 0.37747 | Reduce | 45% | 0.83883 | 0.37747 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 45% | 0.83883 | 0.37747 | Reduce | 45% | 0.83883 | 0.37747 | H2 | 2 | Stable | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 45% | 0.83883 | 0.37747 | Reduce | 45% | 0.83883 | 0.37747 | H2 | 2 | Stable | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional PRs raised during development cannot be absorbed into current WPs | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 45% | 0.83883 | 0.37747 | Reduce | 45% | 0.83883 | 0.37747 | H2 | 2 | Stable | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-081 | Project_011_Risk-081 | Threat | Project Contingency | Open | H2 | 2 | Customers | Incur LDs on final Release | Person_147 | 2014-08-22 01:00 | 2018-08-21 | 40% | 0.94441 | 0.37776 | Reduce | 40% | 0.94441 | 0.37776 | H2 | 2 | -- | TRUE | 1459.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-081 | Project_011_Risk-081 | Threat | Project Contingency | Open | H2 | 2 | Customers | Incur LDs on final Release | Person_147 | 2014-08-22 01:00 | 2018-08-21 | 40% | 0.94441 | 0.37776 | Reduce | 40% | 0.94441 | 0.37776 | H2 | 2 | -- | TRUE | 1459.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H1 | 1 | Project Management | PRs per release cannot be absorbed within each WP and require a dedicated PR budget | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 80% | 0.47334 | 0.37867 | Reduce | 80% | 0.47334 | 0.37867 | H1 | 1 | Stable | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-048 | Project_011_Risk-048 | Threat | Project Contingency | Open | H1 | 1 | Project Management | PRs per release cannot be absorbed within each WP and require a dedicated PR budget | Person_147 | 2013-08-21 01:00 | 2018-08-21 | 80% | 0.47334 | 0.37867 | Reduce | 80% | 0.47334 | 0.37867 | H1 | 1 | Stable | TRUE | 1825.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.38121 | 0.30497 | Exploit | 80% | 0.47651 | 0.38121 | H2 | 2 | Stable | TRUE | 1464 |  | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-019 | Project_023_Risk-019 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.38121 | 0.30497 | Exploit | 80% | 0.47651 | 0.38121 | H2 | 2 | Stable | TRUE | 1464 |  | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-015 | Project_096_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Ssub-system Accreditation | Person_623 | 2018-11-21 01:00 | 2019-03-22 | 15% | 7.6685 | 1.1503 | Reduce | 5% | 7.6685 | 0.38342 | H3 | 3 | Stable | FALSE | 120.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-007 | Project_096_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Dependency | Person_623 | 2018-03-23 | 2018-11-07 01:00 | 40% | 0.95856 | 0.38342 | Reduce | 40% | 0.95856 | 0.38342 | H2 | 2 | Worsening | TRUE | 229.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK031 | Project_075_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Unit Production Cost | Person_627 | 2017-05-23 | 2018-09-20 01:00 | 60% | 4.0498 | 2.4299 | Reduce | 30% | 4.0498 | 1.2149 | H2 | 2 | -- | TRUE | 485.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK033 | Project_029_Risk-RISK033 | Opportunitity | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Minimum Order Quantities | Person_403 | 2017-11-20 01:00 | 2019-05-16 | 20% | 1.925 | 0.38501 | Exploit | 20% | 1.925 | 0.38501 | H3 | 3 | Stable | FALSE | 541.9583 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK031 | Project_075_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Unit Production Cost | Person_627 | 2017-05-23 | 2018-09-20 01:00 | 60% | 4.0498 | 2.4299 | Reduce | 30% | 4.0498 | 1.2149 | H2 | 2 | -- | TRUE | 485.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK007 | Project_041_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Advanced production of products using a Qual. standard component rather than a Prod. standard | Person_547 | 2018-09-21 01:00 | 2019-02-20 01:00 | 49% | 1.2862 | 0.63024 | Reduce | 25% | 1.5434 | 0.38586 | H2 | 2 | Stable | TRUE | 152 |  | 0 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-005 | Project_098_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Failure | Person_360 | 2018-05-24 | 2019-11-20 01:00 | 20% | 3.8747 | 0.77494 | Reduce | 10% | 3.8747 | 0.38747 | H2 | 2 | Stable | TRUE | 545.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK016 | Project_079_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 80% | 1.9552 | 1.5642 | Avoid | 20% | 1.9552 | 0.39105 | H3 | 3 | Worsening | TRUE | 600.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK016 | Project_079_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Test Equipment | Person_683 | 2017-09-29 01:00 | 2019-05-23 | 80% | 1.9552 | 1.5642 | Avoid | 20% | 1.9552 | 0.39105 | H3 | 3 | Stable | TRUE | 600.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_009 | Project_051 | RISK001 | Project_051_RISK001 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Generic Labour or Material Overspend | Person_577 | 2012-05-23 | 2021-05-22 | 50% | 0.78901 | 0.3945 | Accept | 50% | 0.78901 | 0.3945 | H3 | 3 | Stable | TRUE | 3286 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-071 | Project_030_Risk-071 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Laptops on board platform | Person_561 | 2013-09-20 01:00 | 2013-11-20 01:00 | 30% | 1.3176 | 0.39529 | Exploit | 30% | 1.3176 | 0.39529 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-071 | Project_030_Risk-071 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Laptops on board platform | Person_561 | 2013-09-20 01:00 | 2013-11-20 01:00 | 30% | 1.3176 | 0.39529 | Exploit | 30% | 1.3176 | 0.39529 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-071 | Project_030_Risk-071 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Laptops on board platform | Person_561 | 2013-09-20 01:00 | 2013-11-20 01:00 | 30% | 1.3176 | 0.39529 | Exploit | 30% | 1.3176 | 0.39529 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-071 | Project_030_Risk-071 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Laptops on board platform | Person_561 | 2013-09-20 | 2013-11-20 | 30% | 1.3176 | 0.39529 | Exploit | 30% | 1.3176 | 0.39529 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-071 | Project_030_Risk-071 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Laptops on board platform | Person_561 | 2013-09-20 01:00 | 2013-11-20 01:00 | 30% | 1.3176 | 0.39529 | Exploit | 30% | 1.3176 | 0.39529 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-071 | Project_030_Risk-071 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Laptops on board platform | Person_561 | 2013-09-20 01:00 | 2013-11-20 01:00 | 30% | 1.3176 | 0.39529 | Exploit | 30% | 1.3176 | 0.39529 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-071 | Project_030_Risk-071 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Laptops on board platform | Person_561 | 2013-09-20 01:00 | 2013-11-20 01:00 | 30% | 1.3176 | 0.39529 | Exploit | 30% | 1.3176 | 0.39529 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-071 | Project_030_Risk-071 | Opportunitity | Project Contingency | Open | H3 | 3 | Hardware/Software development | Laptops on board platform | Person_561 | 2013-09-20 | 2013-11-20 | 30% | 1.3176 | 0.39529 | Exploit | 30% | 1.3176 | 0.39529 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK031 | Project_075_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Unit Production Cost | Person_627 | 2017-05-23 | 2018-09-20 01:00 | 60% | 4.0498 | 2.4299 | Reduce | 30% | 4.0498 | 1.2149 | H2 | 2 | -- | TRUE | 485.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK031 | Project_075_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Unit Production Cost | Person_627 | 2017-05-23 | 2018-09-20 01:00 | 60% | 4.0498 | 2.4299 | Reduce | 30% | 4.0498 | 1.2149 | H2 | 2 | -- | TRUE | 485.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK007 | Project_088_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Updated Filter Design | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 25% | 6.1105 | 1.5276 | Reduce | 20% | 6.1105 | 1.2221 | H2 | 2 | -- | TRUE | 1389.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_088 | RISK007 | Project_088_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Updated Filter Design | Person_627 | 2015-05-27 | 2019-03-16 01:00 | 25% | 6.1105 | 1.5276 | Reduce | 20% | 6.1105 | 1.2221 | H2 | 2 | -- | TRUE | 1389.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK034 | Project_076_RISK034 | Threat | Project Contingency | Open | H2 | 2 |  | Representative Hardware for testing | Person_152 | 2016-03-23 | 2019-04-23 | 80% | 12.4383 | 9.9506 | Reduce | 10% | 12.4383 | 1.2438 | H2 | 2 | -- | TRUE | 1126 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK056 | Project_058_RISK056 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Doc Pack Content | Person_294 | 2018-02-20 01:00 | 2018-11-20 01:00 | 70% | 1.5659 | 1.0961 | -- | 80% | 1.5659 | 1.2527 | H2 | 2 | -- | TRUE | 273 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK056 | Project_058_RISK056 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Doc Pack Content | Person_294 | 2018-02-20 01:00 | 2018-11-20 01:00 | 70% | 1.5659 | 1.0961 | -- | 80% | 1.5659 | 1.2527 | H2 | 2 | -- | TRUE | 273 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK056 | Project_058_RISK056 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Doc Pack Content | Person_294 | 2018-02-20 01:00 | 2018-11-20 01:00 | 70% | 1.5659 | 1.0961 | -- | 80% | 1.5659 | 1.2527 | H2 | 2 | -- | TRUE | 273 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP260 | Project_024_OPP260 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Additional release not required | Person_534 | 2016-05-23 | 2017-01-15 01:00 | 10% | 2.5187 | 0.25187 | Exploit | 50% | 2.5187 | 1.2594 | H2 | 2 | -- | TRUE | 237.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 2 |  | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 50% | 2.5311 | 1.2656 | Accept | 50% | 2.5311 | 1.2656 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 2 |  | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 50% | 2.5311 | 1.2656 | Accept | 50% | 2.5311 | 1.2656 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 2 |  | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 50% | 2.5311 | 1.2656 | Accept | 50% | 2.5311 | 1.2656 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 2 |  | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 50% | 2.5311 | 1.2656 | Accept | 50% | 2.5311 | 1.2656 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK018 | Project_075_RISK018 | Threat | Project Contingency | Open | H2 | 2 |  | Crystal switch | Person_627 | 2017-03-21 01:00 | 2018-09-20 01:00 | 50% | 2.5311 | 1.2656 | Accept | 50% | 2.5311 | 1.2656 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in Installation time in country | Person_330 | 2016-03-23 | 2016-08-19 01:00 | 40% | 3.187 | 1.2748 | Reduce | 40% | 3.187 | 1.2748 | H2 | 2 | Stable | TRUE | 149.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in Installation time in country | Person_330 | 2016-03-23 | 2016-08-19 01:00 | 40% | 3.187 | 1.2748 | Reduce | 40% | 3.187 | 1.2748 | H2 | 2 | Stable | TRUE | 149.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 3% | 27.1644 | 0.81493 | Accept | 10% | 12.8336 | 1.2834 | H2 | 2 | Stable | TRUE | 28 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 70% | 1.3243 | 0.92704 | Reduce | 30% | 1.3243 | 0.3973 | H2 | 2 | Stable | TRUE | 172.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R030 | Project_021_Risk-R030 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-08-03 | 2016-10-19 | 10% | 3.973 | 0.3973 | Reduce | 10% | 3.973 | 0.3973 | H2 | 2 | Improving | TRUE | 77 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK001 | Project_044_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Non-compliance with regs | Person_044 | 2018-07-14 | 2019-02-10 01:00 | 50% | 2.0403 | 1.0202 | Reduce | 20% | 1.992 | 0.39841 | H3 | 3 | Stable | FALSE | 211.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-07-20 | 25% | 3.9852 | 0.9963 | Reduce | 10% | 3.9852 | 0.39852 | H3 | 3 | Stable | FALSE | 1712.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-07-20 | 25% | 3.9852 | 0.9963 | Reduce | 10% | 3.9852 | 0.39852 | H3 | 3 | Stable | FALSE | 1712.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-010 | Project_005_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Risk that required resources (people and rigs) will not be available as required due to other projects/bids (Customer & Internal) | Person_470 | 2011-11-11 01:00 | 2016-07-20 | 25% | 3.9852 | 0.9963 | Reduce | 10% | 3.9852 | 0.39852 | H3 | 3 | Stable | FALSE | 1712.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 20% | 1.9998 | 0.39995 | Accept | 20% | 1.9998 | 0.39995 | H2 | 2 | Improving | TRUE | 119.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 20% | 1.9998 | 0.39995 | Accept | 20% | 1.9998 | 0.39995 | H2 | 2 | Improving | TRUE | 119.9583 |  | 1 | 1 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 20% | 1.9998 | 0.39995 | Accept | 20% | 1.9998 | 0.39995 | H2 | 2 | Improving | TRUE | 119.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 20% | 1.9998 | 0.39995 | Accept | 20% | 1.9998 | 0.39995 | H2 | 2 | Improving | TRUE | 119.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--26 | Project_021_Risk--26 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional design effort required to satisfy SME feedback/input | Person_615 | 2018-01-21 01:00 | 2018-05-21 | 20% | 1.9998 | 0.39995 | Accept | 20% | 1.9998 | 0.39995 | H2 | 2 | Improving | TRUE | 119.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 30% | 1.3502 | 0.40507 | Accept | 30% | 1.3502 | 0.40507 | H2 | 2 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 30% | 1.3502 | 0.40507 | Accept | 30% | 1.3502 | 0.40507 | H2 | 2 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 30% | 1.3502 | 0.40507 | Accept | 30% | 1.3502 | 0.40507 | H2 | 2 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 30% | 1.3502 | 0.40507 | Accept | 30% | 1.3502 | 0.40507 | H2 | 2 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 30% | 1.3502 | 0.40507 | Accept | 30% | 1.3502 | 0.40507 | H2 | 2 | Stable | TRUE | 241.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 3% | 27.1644 | 0.81493 | Accept | 10% | 12.8336 | 1.2834 | H2 | 2 | Stable | TRUE | 28 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 3% | 27.1644 | 0.81493 | Accept | 10% | 12.8336 | 1.2834 | H2 | 2 | Stable | TRUE | 28 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK002 | Project_081_RISK002 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supplier costs to be covered by us | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 20% | 2.0381 | 0.40763 | Reduce | 20% | 2.0381 | 0.40763 | H3 | 3 | Stable | TRUE | 1454 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK036 | Project_042_RISK036 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs 1st Jan to 31 December Year 2 | Person_455 | 2019-05-24 | 2020-05-22 | 25% | 2.1419 | 0.53546 | Accept | 20% | 2.0479 | 0.40958 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 3% | 27.1644 | 0.81493 | Accept | 10% | 12.8336 | 1.2834 | H2 | 2 | Stable | TRUE | 28 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2017-10-20 01:00 | 3% | 27.1644 | 0.81493 | Accept | 10% | 12.8336 | 1.2834 | H2 | 2 | Stable | TRUE | 28 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 3% | 27.1644 | 0.81493 | Accept | 10% | 12.8336 | 1.2834 | H2 | 2 | Stable | TRUE | 698 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 3% | 27.1644 | 0.81493 | Accept | 10% | 12.8336 | 1.2834 | H2 | 2 | Stable | TRUE | 698 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_692 | 2017-09-22 01:00 | 2019-08-21 01:00 | 3% | 27.1644 | 0.81493 | Accept | 10% | 12.8336 | 1.2834 | H2 | 2 | Stable | TRUE | 698 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 2 |  | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-09-13 01:00 | 30% | 6.3266 | 1.898 | Accept | 20.5% | 6.3266 | 1.297 | H2 | 2 | Improving | TRUE | 478.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 2 |  | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 30% | 6.3266 | 1.898 | Accept | 20.5% | 6.3266 | 1.297 | H2 | 2 | Improving | TRUE | 516.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 2 |  | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 30% | 6.3266 | 1.898 | Accept | 20.5% | 6.3266 | 1.297 | H2 | 2 | Improving | TRUE | 516.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-057 | Project_062_Risk-057 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Supplier Application Encryption / Protection | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 30% | 4.183 | 1.2549 | Reduce | 10% | 4.183 | 0.4183 | H3 | 3 | Stable | FALSE | 580.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-317 | Project_027_Risk-317 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Modifications | Person_443 | 2015-04-15 | 2016-05-22 | 10% | 8.3972 | 0.83972 | Accept | 5% | 8.3972 | 0.41986 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-317 | Project_027_Risk-317 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Modifications | Person_443 | 2015-04-15 | 2016-05-22 | 10% | 8.3972 | 0.83972 | Accept | 5% | 8.3972 | 0.41986 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-317 | Project_027_Risk-317 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Modifications | Person_443 | 2015-04-15 | 2016-05-22 | 10% | 8.3972 | 0.83972 | Accept | 5% | 8.3972 | 0.41986 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-317 | Project_027_Risk-317 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Modifications | Person_443 | 2015-04-15 | 2016-05-22 | 10% | 8.3972 | 0.83972 | Accept | 5% | 8.3972 | 0.41986 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-317 | Project_027_Risk-317 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Modifications | Person_443 | 2015-04-15 | 2016-05-22 | 10% | 8.3972 | 0.83972 | Accept | 5% | 8.3972 | 0.41986 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-317 | Project_027_Risk-317 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Modifications | Person_443 | 2015-04-15 | 2016-05-22 | 10% | 8.3972 | 0.83972 | Accept | 5% | 8.3972 | 0.41986 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-317 | Project_027_Risk-317 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Modifications | Person_443 | 2015-04-15 | 2016-05-22 | 10% | 8.3972 | 0.83972 | Accept | 5% | 8.3972 | 0.41986 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-317 | Project_027_Risk-317 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Modifications | Person_443 | 2015-04-15 | 2016-05-22 | 10% | 8.3972 | 0.83972 | Accept | 5% | 8.3972 | 0.41986 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 25% | 1.6835 | 0.42087 | Accept | 25% | 1.6835 | 0.42087 | H2 | 2 | Stable | TRUE | 332 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 25% | 1.6835 | 0.42087 | Accept | 25% | 1.6835 | 0.42087 | H2 | 2 | Improving | TRUE | 332 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 25% | 1.6835 | 0.42087 | Accept | 25% | 1.6835 | 0.42087 | H2 | 2 | Improving | TRUE | 332 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 25% | 1.6835 | 0.42087 | Accept | 25% | 1.6835 | 0.42087 | H2 | 2 | Improving | TRUE | 332 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK205 | Project_024_RISK205 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Overland performance | Person_448 | 2016-06-23 | 2017-05-21 | 25% | 1.6835 | 0.42087 | Accept | 25% | 1.6835 | 0.42087 | H2 | 2 | Improving | TRUE | 332 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 2 |  | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 30% | 6.3266 | 1.898 | Accept | 20.5% | 6.3266 | 1.297 | H2 | 2 | Improving | TRUE | 516.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK023 | Project_083_RISK023 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Customer Deliverables - Read Across from product | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 25% | 4.279 | 1.0697 | Reduce | 15% | 2.8267 | 0.42401 | H3 | 3 | Improving | TRUE | 309 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK096 | Project_035_RISK096 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Product Real World Performance | Person_699 | 2015-05-24 | 2017-01-20 01:00 | 15% | 3.5631 | 0.53446 | Accept | 12% | 3.5631 | 0.42757 | H3 | 3 | Improving | FALSE | 607.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1006 | Project_091_RISK1006 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Safety Argument | Person_557 | 2018-08-22 01:00 | 2019-05-23 | 40% | 1.0726 | 0.42903 | Accept | 40% | 1.0726 | 0.42903 | H3 | 3 | -- | TRUE | 273.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1006 | Project_091_RISK1006 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Safety Argument | Person_557 | 2018-09-21 01:00 | 2019-05-23 | 40% | 1.0726 | 0.42903 | Accept | 40% | 1.0726 | 0.42903 | H3 | 3 | -- | TRUE | 243.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 2 |  | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-10-21 01:00 | 30% | 6.3266 | 1.898 | Accept | 20.5% | 6.3266 | 1.297 | H2 | 2 | Improving | TRUE | 516.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK009 | Project_092_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Length of cable run requires fibre conversion | Person_169 | 2019-01-27 01:00 | 2019-05-26 | 50% | 4.4333 | 2.2167 | Reduce | 30% | 4.4333 | 1.33 | H2 | 2 | -- | TRUE | 118.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-073 | Project_030_Risk-073 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Rapid Prototyping | Person_639 | 2013-07-21 | 2017-05-15 | 30% | 4.6117 | 1.3835 | -- | 30% | 4.6117 | 1.3835 | H2 | 2 | -- | TRUE | 1394 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-073 | Project_030_Risk-073 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Rapid Prototyping | Person_639 | 2013-07-21 | 2017-05-15 | 30% | 4.6117 | 1.3835 | -- | 30% | 4.6117 | 1.3835 | H2 | 2 | -- | TRUE | 1394 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-073 | Project_030_Risk-073 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Rapid Prototyping | Person_639 | 2013-07-21 | 2017-05-15 | 30% | 4.6117 | 1.3835 | -- | 30% | 4.6117 | 1.3835 | H2 | 2 | -- | TRUE | 1394 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-073 | Project_030_Risk-073 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Rapid Prototyping | Person_639 | 2013-07-21 | 2017-05-15 | 30% | 4.6117 | 1.3835 | -- | 30% | 4.6117 | 1.3835 | H2 | 2 | -- | TRUE | 1394 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-004 | Project_077_T-004 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Technical Debt | Person_202 | 2018-10-20 01:00 | 2020-02-21 01:00 | 20% | 2.1566 | 0.43131 | Reduce | 20% | 2.1566 | 0.43131 | H3 | 3 | Stable | FALSE | 489 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--109 | Project_100_Risk--109 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Increased repairs and spares | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 20% | 2.1583 | 0.43166 | Accept | 20% | 2.1583 | 0.43166 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.1606 | 0.43213 | Accept | 20% | 2.1606 | 0.43213 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.1606 | 0.43213 | Accept | 20% | 2.1606 | 0.43213 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.1606 | 0.43213 | Accept | 20% | 2.1606 | 0.43213 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.1606 | 0.43213 | Accept | 20% | 2.1606 | 0.43213 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.1606 | 0.43213 | Accept | 20% | 2.1606 | 0.43213 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.1606 | 0.43213 | Accept | 20% | 2.1606 | 0.43213 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk009 | Project_042_Risk009 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Engineering Queries | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.1606 | 0.43213 | Accept | 20% | 2.1606 | 0.43213 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-073 | Project_030_Risk-073 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Rapid Prototyping | Person_639 | 2013-07-21 | 2017-05-15 | 30% | 4.6117 | 1.3835 | -- | 30% | 4.6117 | 1.3835 | H2 | 2 | -- | TRUE | 1394 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-073 | Project_030_Risk-073 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Rapid Prototyping | Person_639 | 2013-07-21 | 2017-05-15 | 30% | 4.6117 | 1.3835 | -- | 30% | 4.6117 | 1.3835 | H2 | 2 | -- | TRUE | 1394 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-073 | Project_030_Risk-073 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Rapid Prototyping | Person_639 | 2013-07-21 | 2017-05-15 | 30% | 4.6117 | 1.3835 | -- | 30% | 4.6117 | 1.3835 | H2 | 2 | -- | TRUE | 1394 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-073 | Project_030_Risk-073 | Opportunitity | Project Contingency | Open | H2 | 2 |  | System Rapid Prototyping | Person_639 | 2013-07-21 | 2017-05-15 | 30% | 4.6117 | 1.3835 | -- | 30% | 4.6117 | 1.3835 | H2 | 2 | -- | TRUE | 1394 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 25% | 1.7297 | 0.43243 | -- | 25% | 1.7297 | 0.43243 | H2 | 2 | Stable | TRUE | 119.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 | 25% | 1.7297 | 0.43243 | -- | 25% | 1.7297 | 0.43243 | H2 | 2 | Stable | TRUE | 119 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 | 25% | 1.7297 | 0.43243 | -- | 25% | 1.7297 | 0.43243 | H2 | 2 | Stable | TRUE | 119 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 25% | 1.7297 | 0.43243 | -- | 25% | 1.7297 | 0.43243 | H2 | 2 | Stable | TRUE | 119.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 25% | 1.7297 | 0.43243 | -- | 25% | 1.7297 | 0.43243 | H2 | 2 | Stable | TRUE | 119.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-116 | Project_011_Risk-116 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delays to Qualification | Person_147 | 2017-04-22 | 2017-08-19 01:00 | 25% | 1.7297 | 0.43243 | -- | 25% | 1.7297 | 0.43243 | H2 | 2 | Stable | TRUE | 119.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK152 | Project_038_RISK152 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test Equipment Costs | Person_640 | 2015-06-24 | 2016-05-22 | 20% | 5.4834 | 1.0967 | Accept | 8% | 5.4834 | 0.43867 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK152 | Project_038_RISK152 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test Equipment Costs | Person_640 | 2015-06-24 | 2016-05-22 | 20% | 5.4834 | 1.0967 | Accept | 8% | 5.4834 | 0.43867 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-039 | Project_043_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | System fails to achieve required performance | Person_051 | 2017-04-19 | 2018-11-19 22:00 | 30% | 4.7906 | 1.4372 | Reduce | 30% | 4.7906 | 1.4372 | H2 | 2 | Stable | TRUE | 579.9167 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK022 | Project_058_RISK022 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2019-05-23 | 60% | 2.9361 | 1.7616 | Reduce | 50% | 2.9361 | 1.468 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK022 | Project_058_RISK022 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2019-05-23 | 60% | 2.9361 | 1.7616 | Reduce | 50% | 2.9361 | 1.468 | H2 | 2 | -- | TRUE | 427 |  | 1 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Items damaged in transit | Person_387 | 2017-04-22 | 2018-11-20 01:00 | 30% | 29.3607 | 8.8082 | Reduce | 5% | 29.3607 | 1.468 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Items damaged in transit | Person_387 | 2017-04-22 | 2018-11-20 01:00 | 30% | 29.3607 | 8.8082 | Reduce | 5% | 29.3607 | 1.468 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-021 | Project_062_Risk-021 | Threat | Project Contingency | Open | H2 | 2 |  | Hardware CoSupplierng | Person_664 | 2017-07-21 | 2018-11-20 01:00 | 30% | 7.5293 | 2.2588 | Reduce | 20% | 7.5293 | 1.5059 | H2 | 2 | Stable | TRUE | 487.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 2 |  | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 50% | 3.0417 | 1.5208 | -- | 50% | 3.0417 | 1.5208 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 2 |  | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 50% | 3.0417 | 1.5208 | -- | 50% | 3.0417 | 1.5208 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-050 | Project_028_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Compatibility | Person_542 | 2015-10-22 | 2016-08-20 | 15% | 4.4003 | 0.66004 | Accept | 10% | 4.4003 | 0.44003 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-050 | Project_028_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Compatibility | Person_542 | 2015-10-22 01:00 | 2016-09-19 01:00 | 15% | 4.4003 | 0.66004 | Accept | 10% | 4.4003 | 0.44003 | H3 | 3 | Stable | FALSE | 333 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 2 |  | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 50% | 3.0417 | 1.5208 | -- | 50% | 3.0417 | 1.5208 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2016-03-23 | 2018-02-19 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 698 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2016-03-23 | 2018-02-18 23:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 697.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R020 | Project_021_Risk-R020 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Manual rewrite will affect estimate | Person_279 | 2001-05-23 | 2018-02-19 01:00 | 30% | 1.4678 | 0.44034 | Reduce | 30% | 1.4678 | 0.44034 | H2 | 2 | -- | TRUE | 6116.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 2 |  | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 50% | 3.0417 | 1.5208 | -- | 50% | 3.0417 | 1.5208 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 2 |  | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 50% | 3.0417 | 1.5208 | -- | 50% | 3.0417 | 1.5208 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 2 |  | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 50% | 3.0417 | 1.5208 | -- | 50% | 3.0417 | 1.5208 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--105 | Project_100_Risk--105 | Threat | Project Contingency | Open | H3 | 3 | Project Management | FFF replacement costs | Person_433 | 2018-08-22 01:00 | 2021-08-20 01:00 | 40% | 1.1049 | 0.44194 | -- | 40% | 1.1049 | 0.44194 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 2 |  | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 50% | 3.0417 | 1.5208 | -- | 50% | 3.0417 | 1.5208 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK395 | Project_035_RISK395 | Threat | Project Contingency | Open | H2 | 2 |  | Test area Site Availability | Person_691 | 2016-05-23 | 2016-11-19 01:00 | 50% | 3.0417 | 1.5208 | -- | 50% | 3.0417 | 1.5208 | H2 | 2 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK046 | Project_075_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Over temperature causing damage due to misalignment | Person_449 | 2017-12-20 01:00 | 2018-08-20 | 50% | 7.7621 | 3.8811 | Reduce | 20% | 7.7621 | 1.5524 | H2 | 2 | -- | TRUE | 242.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK046 | Project_075_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Over temperature causing damage due to misalignment | Person_449 | 2017-12-20 01:00 | 2018-08-20 | 50% | 7.7621 | 3.8811 | Reduce | 20% | 7.7621 | 1.5524 | H2 | 2 | -- | TRUE | 242.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK046 | Project_075_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Over temperature causing damage due to misalignment | Person_449 | 2017-12-20 01:00 | 2018-08-20 | 50% | 7.7621 | 3.8811 | Reduce | 20% | 7.7621 | 1.5524 | H2 | 2 | -- | TRUE | 242.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-20 01:00 | 2018-05-22 | 50% | 3.1083 | 1.5542 | Exploit | 50% | 3.1083 | 1.5542 | H2 | 2 | Stable | TRUE | 547.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-20 | 2018-05-22 | 50% | 3.1083 | 1.5542 | Exploit | 50% | 3.1083 | 1.5542 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-19 23:00 | 2018-05-22 | 50% | 3.1083 | 1.5542 | Exploit | 50% | 3.1083 | 1.5542 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-19 23:00 | 2018-05-22 | 50% | 3.1083 | 1.5542 | Exploit | 50% | 3.1083 | 1.5542 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_594 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_594 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_594 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_594 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_594 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_594 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_594 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_418 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_594 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_418 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_418 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK485 | Project_065_RISK485 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | The supplier provided PTS are not suitable for use. | Person_418 | 2019-03-22 | 2019-05-03 | 25% | 1.7748 | 0.4437 | Accept | 25% | 1.7748 | 0.4437 | H2 | 2 | -- | TRUE | 42 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-202 | Project_039_Risk-202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Sensitivity | Person_247 | 2016-07-21 | 2016-11-19 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 121.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-199 | Project_039_Risk-199 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Technical Challenges | Person_612 | 2016-07-21 | 2016-12-19 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 151.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-202 | Project_039_Risk-202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Sensitivity | Person_247 | 2016-07-21 | 2016-11-19 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 121.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-199 | Project_039_Risk-199 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Technical Challenges | Person_612 | 2016-07-21 | 2016-12-19 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 151.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-202 | Project_039_Risk-202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Sensitivity | Person_247 | 2016-07-21 | 2017-01-19 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 182.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-199 | Project_039_Risk-199 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Technical Challenges | Person_612 | 2016-07-21 | 2017-01-20 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 183.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-202 | Project_039_Risk-202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Sensitivity | Person_247 | 2016-07-21 | 2017-01-19 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 182.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-199 | Project_039_Risk-199 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Technical Challenges | Person_612 | 2016-07-21 | 2017-01-20 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 183.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-202 | Project_039_Risk-202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Sensitivity | Person_247 | 2016-07-21 | 2017-01-19 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 182 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-199 | Project_039_Risk-199 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Technical Challenges | Person_612 | 2016-07-21 | 2017-01-20 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 183 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-202 | Project_039_Risk-202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Sensitivity | Person_247 | 2016-07-21 | 2017-01-19 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 182.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-199 | Project_039_Risk-199 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Technical Challenges | Person_612 | 2016-07-21 | 2017-01-20 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 183.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-202 | Project_039_Risk-202 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Sensitivity | Person_247 | 2016-07-21 | 2017-01-19 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 182.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-199 | Project_039_Risk-199 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Technical Challenges | Person_612 | 2016-07-21 | 2017-01-20 01:00 | 30% | 1.4882 | 0.44646 | Accept | 30% | 1.4882 | 0.44646 | H3 | 3 | -- | TRUE | 183.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-032 | Project_026_Risk-032 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Data sharing may be more complex than anticipated | Person_362 | 2014-05-09 | 2017-08-20 01:00 | 10% | 4.4768 | 0.44768 | Reduce | 10% | 4.4768 | 0.44768 | H3 | 3 | -- | TRUE | 1199.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-19 23:00 | 2018-05-22 | 50% | 3.1083 | 1.5542 | Exploit | 50% | 3.1083 | 1.5542 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R86 | Project_041_R86 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Sharing Attrition Stock with Warranty Spares pool | Person_501 | 2016-11-19 22:00 | 2018-05-22 | 50% | 3.1083 | 1.5542 | Exploit | 50% | 3.1083 | 1.5542 | H2 | 2 | Stable | TRUE | 548.0833 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK060 | Project_058_RISK060 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Obsolescence (address via LTB only) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 3.9148 | 1.5659 | -- | 40% | 3.9148 | 1.5659 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_294 | 2018-03-22 | 2018-10-22 01:00 | 80% | 3.9148 | 3.1318 | Reduce | 40% | 3.9148 | 1.5659 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_294 | 2018-03-22 | 2018-10-22 01:00 | 80% | 3.9148 | 3.1318 | Reduce | 40% | 3.9148 | 1.5659 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 25% | 4.4946 | 1.1236 | Accept | 10% | 4.4946 | 0.44946 | H3 | 3 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 25% | 4.4946 | 1.1236 | Accept | 10% | 4.4946 | 0.44946 | H3 | 3 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 25% | 4.4946 | 1.1236 | Accept | 10% | 4.4946 | 0.44946 | H3 | 3 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 25% | 4.4946 | 1.1236 | Accept | 10% | 4.4946 | 0.44946 | H3 | 3 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 25% | 4.4946 | 1.1236 | Accept | 10% | 4.4946 | 0.44946 | H3 | 3 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-11-20 01:00 | 25% | 4.4946 | 1.1236 | Accept | 10% | 4.4946 | 0.44946 | H3 | 3 | Stable | TRUE | 334 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 80% | 3.9148 | 3.1318 | Reduce | 40% | 3.9148 | 1.5659 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 80% | 3.9148 | 3.1318 | Reduce | 40% | 3.9148 | 1.5659 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 80% | 3.9148 | 3.1318 | Reduce | 40% | 3.9148 | 1.5659 | H2 | 2 | -- | TRUE | 214.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 80% | 3.9148 | 3.1318 | Reduce | 40% | 3.9148 | 1.5659 | H2 | 2 | Improving | TRUE | 214.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK020 | Project_058_RISK020 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Delay | Person_511 | 2018-03-22 | 2018-10-22 01:00 | 80% | 3.9148 | 3.1318 | Reduce | 40% | 3.9148 | 1.5659 | H2 | 2 | Improving | TRUE | 214.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK032 | Project_079_RISK032 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Procurement Opportunity - Supplier | Person_261 | 2018-08-04 | 2021-05-22 | 80% | 1.9999 | 1.5999 | -- | 80% | 1.9999 | 1.5999 | H2 | 2 | -- | TRUE | 1022 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK032 | Project_079_RISK032 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Procurement Opportunity - Supplier | Person_261 | 2018-08-04 | 2021-05-22 | 80% | 1.9999 | 1.5999 | -- | 80% | 1.9999 | 1.5999 | H2 | 2 | -- | TRUE | 1022 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK032 | Project_079_RISK032 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Procurement Opportunity - Supplier | Person_261 | 2018-08-04 | 2021-05-22 | 80% | 1.9999 | 1.5999 | -- | 80% | 1.9999 | 1.5999 | H2 | 2 | -- | TRUE | 1022 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 1.1273 | 0.45092 | Accept | 40% | 1.1273 | 0.45092 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 1.1273 | 0.45092 | Accept | 40% | 1.1273 | 0.45092 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 1.1273 | 0.45092 | Accept | 40% | 1.1273 | 0.45092 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 1.1273 | 0.45092 | Accept | 40% | 1.1273 | 0.45092 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 1.1273 | 0.45092 | Accept | 40% | 1.1273 | 0.45092 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 1.1273 | 0.45092 | Accept | 40% | 1.1273 | 0.45092 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk008 | Project_042_Risk008 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Country Stability | Person_455 | 2016-05-23 | 2020-05-23 | 40% | 1.1273 | 0.45092 | Accept | 40% | 1.1273 | 0.45092 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Mission System not compatible with platform systems | Person_585 | 2016-07-21 | 2017-02-19 01:00 | 10% | 4.5441 | 0.45441 | Accept | 10% | 4.5441 | 0.45441 | H3 | 3 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 10% | 4.5441 | 0.45441 | Accept | 10% | 4.5441 | 0.45441 | H3 | 3 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 10% | 4.5441 | 0.45441 | Accept | 10% | 4.5441 | 0.45441 | H3 | 3 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 10% | 4.5441 | 0.45441 | Accept | 10% | 4.5441 | 0.45441 | H3 | 3 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 10% | 4.5441 | 0.45441 | Accept | 10% | 4.5441 | 0.45441 | H3 | 3 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 10% | 4.5441 | 0.45441 | Accept | 10% | 4.5441 | 0.45441 | H3 | 3 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Mission System not compatible with platform systems | Person_289 | 2016-07-21 | 2017-02-19 01:00 | 10% | 4.5441 | 0.45441 | Accept | 10% | 4.5441 | 0.45441 | H3 | 3 | Stable | TRUE | 213.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK087 | Project_024_RISK087 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Mission System not compatible with platform systems | Person_710 | 2016-07-21 | 2017-04-21 | 10% | 4.5441 | 0.45441 | Accept | 10% | 4.5441 | 0.45441 | H3 | 3 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK160 | Project_038_RISK160 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Low noise Requirement | Person_017 | 2016-02-21 01:00 | 2016-07-21 | 10% | 4.5695 | 0.45695 | Accept | 10% | 4.5695 | 0.45695 | H3 | 3 | Stable | TRUE | 150.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK160 | Project_038_RISK160 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Low noise Requirement | Person_017 | 2016-02-21 01:00 | 2016-07-21 | 10% | 4.5695 | 0.45695 | Accept | 10% | 4.5695 | 0.45695 | H3 | 3 | Stable | TRUE | 150.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK036 | Project_075_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | NRE causing increase to project budget | Person_627 | 2017-05-23 | 2019-01-21 01:00 | 70% | 4.0498 | 2.8349 | Reduce | 40% | 4.0498 | 1.6199 | H2 | 2 | -- | TRUE | 608.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK036 | Project_075_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | NRE causing increase to project budget | Person_627 | 2017-05-23 | 2019-01-21 01:00 | 70% | 4.0498 | 2.8349 | Reduce | 40% | 4.0498 | 1.6199 | H2 | 2 | -- | TRUE | 608.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK036 | Project_075_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | NRE causing increase to project budget | Person_627 | 2017-05-23 | 2019-01-21 01:00 | 70% | 4.0498 | 2.8349 | Reduce | 40% | 4.0498 | 1.6199 | H2 | 2 | -- | TRUE | 608.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK036 | Project_075_RISK036 | Threat | Project Contingency | Open | H2 | 2 |  | NRE causing increase to project budget | Person_627 | 2017-05-23 | 2019-01-21 01:00 | 70% | 4.0498 | 2.8349 | Reduce | 40% | 4.0498 | 1.6199 | H2 | 2 | -- | TRUE | 608.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK019 | Project_092_RISK019 | Threat | Project Contingency | Open | H2 | 2 |  | Component Isolation Specification | Person_169 | 2019-07-05 | 2019-11-14 01:00 | 50% | 8.3115 | 4.1558 | Accept | 20% | 8.3115 | 1.6623 | H2 | 2 | -- | TRUE | 132.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK053 | Project_017_RISK053 | Threat | Project Contingency | Open | H2 | 2 |  | VOP Under- Recovery | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 33.3% | 5.0063 | 1.6671 | -- | 33.3% | 5.0063 | 1.6671 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-143 | Project_030_Risk-143 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Shock Testing Re-inbursement from Customer | Person_518 | 2014-12-02 01:00 | 2015-02-20 01:00 | 30% | 5.7097 | 1.7129 | -- | 30% | 5.7097 | 1.7129 | H2 | 2 | -- | TRUE | 80 |  | 1 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 80% | 1.1522 | 0.92174 | Reduce | 40% | 1.1522 | 0.46087 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 80% | 1.1522 | 0.92174 | Reduce | 40% | 1.1522 | 0.46087 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 80% | 1.1522 | 0.92174 | Reduce | 40% | 1.1522 | 0.46087 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 80% | 1.1522 | 0.92174 | Reduce | 40% | 1.1522 | 0.46087 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 80% | 1.1522 | 0.92174 | Reduce | 40% | 1.1522 | 0.46087 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 80% | 1.1522 | 0.92174 | Reduce | 40% | 1.1522 | 0.46087 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_766 | 2018-03-23 | 2019-03-23 | 80% | 1.1522 | 0.92174 | Reduce | 40% | 1.1522 | 0.46087 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--28 | Project_021_Risk--28 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort required to agree protocl for Client Server | Person_615 | 2018-03-23 | 2019-02-20 01:00 | 80% | 1.1522 | 0.92174 | Reduce | 40% | 1.1522 | 0.46087 | H2 | 2 | Stable | TRUE | 334.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK025 | Project_029_RISK025 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Test Equipment for Integration and System Acceptance | Person_102 | 2018-10-22 01:00 | 2021-01-19 01:00 | 60% | 0.77001 | 0.46201 | Accept | 60% | 0.77001 | 0.46201 | H1 | 1 | -- | TRUE | 820 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--106 | Project_100_Risk--106 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Higher Repairs Cost than Modelled | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 30% | 1.5417 | 0.4625 | Reduce | 30% | 1.5417 | 0.4625 | H3 | 3 | -- | TRUE | 1094 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK055 | Project_042_RISK055 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | PR Forecasting | Person_134 | 2018-09-23 01:00 | 2019-10-22 01:00 | 25% | 1.86 | 0.46501 | Accept | 25% | 1.86 | 0.46501 | H2 | 2 | -- | TRUE | 394 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-143 | Project_030_Risk-143 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Shock Testing Re-inbursement from Customer | Person_518 | 2014-12-02 01:00 | 2015-02-20 01:00 | 30% | 5.7097 | 1.7129 | -- | 30% | 5.7097 | 1.7129 | H2 | 2 | -- | TRUE | 80 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-143 | Project_030_Risk-143 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Shock Testing Re-inbursement from Customer | Person_518 | 2014-12-02 01:00 | 2015-02-20 01:00 | 30% | 5.7097 | 1.7129 | -- | 30% | 5.7097 | 1.7129 | H2 | 2 | -- | TRUE | 80 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-143 | Project_030_Risk-143 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Shock Testing Re-inbursement from Customer | Person_518 | 2014-12-02 | 2015-02-20 | 30% | 5.7097 | 1.7129 | -- | 30% | 5.7097 | 1.7129 | H2 | 2 | -- | TRUE | 80 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-143 | Project_030_Risk-143 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Shock Testing Re-inbursement from Customer | Person_518 | 2014-12-02 01:00 | 2015-02-20 01:00 | 30% | 5.7097 | 1.7129 | -- | 30% | 5.7097 | 1.7129 | H2 | 2 | -- | TRUE | 80 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-143 | Project_030_Risk-143 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Shock Testing Re-inbursement from Customer | Person_518 | 2014-12-02 01:00 | 2015-02-20 01:00 | 30% | 5.7097 | 1.7129 | -- | 30% | 5.7097 | 1.7129 | H2 | 2 | -- | TRUE | 80 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-143 | Project_030_Risk-143 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Shock Testing Re-inbursement from Customer | Person_518 | 2014-12-02 01:00 | 2015-02-20 01:00 | 30% | 5.7097 | 1.7129 | -- | 30% | 5.7097 | 1.7129 | H2 | 2 | -- | TRUE | 80 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-143 | Project_030_Risk-143 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Shock Testing Re-inbursement from Customer | Person_518 | 2014-12-02 | 2015-02-20 | 30% | 5.7097 | 1.7129 | -- | 30% | 5.7097 | 1.7129 | H2 | 2 | -- | TRUE | 80 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-152 | Project_030_Risk-152 | Threat | Project Contingency | Open | H2 | 2 |  | Delays to Install | Person_123 | 2015-07-22 | 2018-05-13 | 50% | 3.5137 | 1.7568 | -- | 50% | 3.5137 | 1.7568 | H2 | 2 | -- | TRUE | 1026 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-152 | Project_030_Risk-152 | Threat | Project Contingency | Open | H2 | 2 |  | Delays to Install | Person_123 | 2015-07-22 | 2018-05-13 | 50% | 3.5137 | 1.7568 | -- | 50% | 3.5137 | 1.7568 | H2 | 2 | -- | TRUE | 1026 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-152 | Project_030_Risk-152 | Threat | Project Contingency | Open | H2 | 2 |  | Delays to Install | Person_123 | 2015-07-22 | 2018-05-13 | 50% | 3.5137 | 1.7568 | -- | 50% | 3.5137 | 1.7568 | H2 | 2 | -- | TRUE | 1026 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-152 | Project_030_Risk-152 | Threat | Project Contingency | Open | H2 | 2 |  | Delays to Install | Person_123 | 2015-07-22 | 2018-05-13 | 50% | 3.5137 | 1.7568 | -- | 50% | 3.5137 | 1.7568 | H2 | 2 | -- | TRUE | 1026 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-152 | Project_030_Risk-152 | Threat | Project Contingency | Open | H2 | 2 |  | Delays to Install | Person_123 | 2015-07-22 | 2018-05-13 | 50% | 3.5137 | 1.7568 | -- | 50% | 3.5137 | 1.7568 | H2 | 2 | -- | TRUE | 1026 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-152 | Project_030_Risk-152 | Threat | Project Contingency | Open | H2 | 2 |  | Delays to Install | Person_123 | 2015-07-22 | 2018-05-13 | 50% | 3.5137 | 1.7568 | -- | 50% | 3.5137 | 1.7568 | H2 | 2 | -- | TRUE | 1026 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-152 | Project_030_Risk-152 | Threat | Project Contingency | Open | H2 | 2 |  | Delays to Install | Person_123 | 2015-07-22 | 2018-05-13 | 50% | 3.5137 | 1.7568 | -- | 50% | 3.5137 | 1.7568 | H2 | 2 | -- | TRUE | 1026 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-152 | Project_030_Risk-152 | Threat | Project Contingency | Open | H2 | 2 |  | Delays to Install | Person_123 | 2015-07-22 | 2018-05-13 | 50% | 3.5137 | 1.7568 | -- | 50% | 3.5137 | 1.7568 | H2 | 2 | -- | TRUE | 1026 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK026 | Project_065_RISK026 | Threat | Project Contingency | Open | H2 | 2 |  | Environmental test failure | Person_020 | 2020-07-21 | 2020-09-24 01:00 | 60% | 4.4345 | 2.6607 | Reduce | 40% | 4.4345 | 1.7738 | H2 | 2 | -- | TRUE | 65.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK115 | Project_066_RISK115 | Threat | Project Contingency | Open | H2 | 2 |  | Qualification scope | Person_068 | 2019-03-24 | 2019-11-21 01:00 | 40% | 4.4524 | 1.781 | Reduce | 40% | 4.4524 | 1.781 | H2 | 2 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK074 | Project_043_RISK074 | Threat | Project Contingency | Open | H2 | 2 |  | Milestone Delayed due to a number of factors | Person_084 | 2014-09-13 | 2018-03-21 | 50% | 5.9882 | 2.9941 | -- | 30% | 5.9882 | 1.7965 | H2 | 2 | -- | TRUE | 1285 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-21 01:00 | 2017-12-19 01:00 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 667 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-21 01:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 819.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-21 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-045 | Project_026_Risk-045 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Certification - evidence presented will be in insufficient for approval | Person_385 | 2018-10-28 01:00 | 2019-01-26 01:00 | 20% | 2.3503 | 0.47006 | Accept | 20% | 2.3503 | 0.47006 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-045 | Project_026_Risk-045 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Certification - evidence presented will be in insufficient for approval | Person_385 | 2018-10-28 01:00 | 2019-01-26 01:00 | 20% | 2.3503 | 0.47006 | Accept | 20% | 2.3503 | 0.47006 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-045 | Project_026_Risk-045 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Certification - evidence presented will be in insufficient for approval | Person_385 | 2018-10-28 01:00 | 2019-01-26 01:00 | 20% | 2.3503 | 0.47006 | Accept | 20% | 2.3503 | 0.47006 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-045 | Project_026_Risk-045 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Certification - evidence presented will be in insufficient for approval | Person_385 | 2018-10-28 01:00 | 2019-01-26 01:00 | 20% | 2.3503 | 0.47006 | Accept | 20% | 2.3503 | 0.47006 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-045 | Project_026_Risk-045 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Certification - evidence presented will be in insufficient for approval | Person_385 | 2018-10-28 01:00 | 2019-01-26 01:00 | 20% | 2.3503 | 0.47006 | Accept | 20% | 2.3503 | 0.47006 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-045 | Project_026_Risk-045 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Certification - evidence presented will be in insufficient for approval | Person_385 | 2018-10-28 01:00 | 2019-01-26 01:00 | 20% | 2.3503 | 0.47006 | Accept | 20% | 2.3503 | 0.47006 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-045 | Project_026_Risk-045 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Certification - evidence presented will be in insufficient for approval | Person_385 | 2018-10-28 01:00 | 2019-01-26 01:00 | 20% | 2.3503 | 0.47006 | Accept | 20% | 2.3503 | 0.47006 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-045 | Project_026_Risk-045 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Certification - evidence presented will be in insufficient for approval | Person_385 | 2018-10-28 01:00 | 2019-01-26 01:00 | 20% | 2.3503 | 0.47006 | Accept | 20% | 2.3503 | 0.47006 | H1 | 1 | -- | TRUE | 90 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-21 01:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 819.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-20 23:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 820.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-109 | Project_039_Risk-109 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Component Reselection | Person_224 | 2015-06-24 | 2016-05-15 | 30% | 2.218 | 0.6654 | Reduce | 20% | 2.3611 | 0.47222 | H3 | 3 | Stable | TRUE | 326 |  | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 35% | 1.3502 | 0.47258 | Accept | 35% | 1.3502 | 0.47258 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 35% | 1.3502 | 0.47258 | Accept | 35% | 1.3502 | 0.47258 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 35% | 1.3502 | 0.47258 | Accept | 35% | 1.3502 | 0.47258 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 35% | 1.3502 | 0.47258 | Accept | 35% | 1.3502 | 0.47258 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 35% | 1.3502 | 0.47258 | Accept | 35% | 1.3502 | 0.47258 | H2 | 2 | Worsening | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK053 | Project_035_RISK053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Assembly Use of Glass Reinforced Plastics | Person_570 | 2015-03-24 | 2016-08-20 01:00 | 20% | 8.4297 | 1.6859 | Accept | 10% | 4.745 | 0.4745 | H3 | 3 | Stable | FALSE | 515.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-20 22:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 820.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-20 23:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 820.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-21 01:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 819.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-20 22:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 820.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-21 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2020-04-26 | 35% | 1.9208 | 0.67227 | Accept | 25% | 1.9208 | 0.48019 | H2 | 2 | Stable | TRUE | 1010 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-21 01:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 819.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK123 | Project_065_RISK123 | Threat | Management Contingency | Open | H2 | 2 |  | Video Chain Performance Issues | Person_661 | 2016-02-20 23:00 | 2018-05-21 | 50% | 6.265 | 3.1325 | Reduce | 30% | 6.2617 | 1.8785 | H2 | 2 | -- | TRUE | 820.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 2 |  | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-08-13 | 30% | 6.3266 | 1.898 | Accept | 30% | 6.3266 | 1.898 | H2 | 2 | Stable | TRUE | 447 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 2 |  | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-08-13 | 30% | 6.3266 | 1.898 | Accept | 30% | 6.3266 | 1.898 | H2 | 2 | Stable | TRUE | 447 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-053 | Project_026_Risk-053 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Code of Conections Requirements | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 25% | 2.4249 | 0.60623 | Reduce | 20% | 2.4249 | 0.48499 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-053 | Project_026_Risk-053 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Code of Conections Requirements | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 25% | 2.4249 | 0.60623 | Reduce | 20% | 2.4249 | 0.48499 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-053 | Project_026_Risk-053 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Code of Conections Requirements | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 25% | 2.4249 | 0.60623 | Reduce | 20% | 2.4249 | 0.48499 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-053 | Project_026_Risk-053 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Code of Conections Requirements | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 25% | 2.4249 | 0.60623 | Reduce | 20% | 2.4249 | 0.48499 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-053 | Project_026_Risk-053 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Code of Conections Requirements | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 25% | 2.4249 | 0.60623 | Reduce | 20% | 2.4249 | 0.48499 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-053 | Project_026_Risk-053 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Code of Conections Requirements | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 25% | 2.4249 | 0.60623 | Reduce | 20% | 2.4249 | 0.48499 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-053 | Project_026_Risk-053 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Code of Conections Requirements | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 25% | 2.4249 | 0.60623 | Reduce | 20% | 2.4249 | 0.48499 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-053 | Project_026_Risk-053 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Code of Conections Requirements | Person_298 | 2015-02-21 01:00 | 2018-12-27 01:00 | 25% | 2.4249 | 0.60623 | Reduce | 20% | 2.4249 | 0.48499 | H2 | 2 | -- | TRUE | 1405 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-11-20 01:00 | 50% | 2.4768 | 1.2384 | -- | 40% | 1.2167 | 0.48666 | H3 | 3 | Improving | TRUE | 273 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK031 | Project_079_RISK031 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Line Closure Savings | Person_683 | 2020-12-21 01:00 | 2021-04-22 | 80% | 2.3927 | 1.9142 | -- | 80% | 2.3927 | 1.9142 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK031 | Project_079_RISK031 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Line Closure Savings | Person_683 | 2020-12-21 01:00 | 2021-04-22 | 80% | 2.3927 | 1.9142 | -- | 80% | 2.3927 | 1.9142 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK031 | Project_079_RISK031 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Line Closure Savings | Person_683 | 2020-12-21 01:00 | 2021-04-22 | 80% | 2.3927 | 1.9142 | -- | 80% | 2.3927 | 1.9142 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-03 01:00 | 2018-04-22 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 595.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-03 01:00 | 2018-04-22 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 595.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-03 | 2018-04-22 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 596 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-03 01:00 | 2018-04-22 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 595.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-02 23:00 | 2018-04-22 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 596.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-02 22:00 | 2018-04-22 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 596.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-02 23:00 | 2018-04-22 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 596.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-03 01:00 | 2019-04-23 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 961.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-02 22:00 | 2018-04-22 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 596.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-03 | 2019-04-23 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 962 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-03 01:00 | 2019-04-23 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 961.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-07-20 | 50% | 1.6266 | 0.8133 | Reduce | 30% | 1.6266 | 0.48798 | H3 | 3 | Stable | TRUE | 770 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-07-20 | 50% | 1.6266 | 0.8133 | Reduce | 30% | 1.6266 | 0.48798 | H3 | 3 | Stable | TRUE | 770 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-060 | Project_005_Risk-060 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Technical Acceptance may be more difficult than anticipated | Person_470 | 2014-06-11 | 2016-07-20 | 50% | 1.6266 | 0.8133 | Reduce | 30% | 1.6266 | 0.48798 | H3 | 3 | Stable | TRUE | 770 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK025 | Project_065_RISK025 | Threat | Project Contingency | Open | H2 | 2 |  | Mechanical model used for analysis during bid was incorrect | Person_022 | 2016-09-02 23:00 | 2019-04-23 | 60% | 6.4907 | 3.8944 | Reduce | 30% | 6.4907 | 1.9472 | H2 | 2 | -- | TRUE | 962.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-099 | Project_030_Risk-099 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Spares from suppliers | Person_251 | 2014-02-19 01:00 | 2018-02-19 01:00 | 20% | 4.4799 | 0.89598 | Reduce | 11% | 4.4799 | 0.49279 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-099 | Project_030_Risk-099 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Spares from suppliers | Person_251 | 2014-02-19 01:00 | 2018-02-19 01:00 | 20% | 4.4799 | 0.89598 | Reduce | 11% | 4.4799 | 0.49279 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-099 | Project_030_Risk-099 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Spares from suppliers | Person_251 | 2014-02-19 01:00 | 2018-02-19 01:00 | 20% | 4.4799 | 0.89598 | Reduce | 11% | 4.4799 | 0.49279 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-099 | Project_030_Risk-099 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Spares from suppliers | Person_251 | 2014-02-19 | 2018-02-19 | 20% | 4.4799 | 0.89598 | Reduce | 11% | 4.4799 | 0.49279 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-099 | Project_030_Risk-099 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Spares from suppliers | Person_251 | 2014-02-19 01:00 | 2018-02-19 01:00 | 20% | 4.4799 | 0.89598 | Reduce | 11% | 4.4799 | 0.49279 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-099 | Project_030_Risk-099 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Spares from suppliers | Person_251 | 2014-02-19 01:00 | 2018-02-19 01:00 | 20% | 4.4799 | 0.89598 | Reduce | 11% | 4.4799 | 0.49279 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-099 | Project_030_Risk-099 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Spares from suppliers | Person_251 | 2014-02-19 01:00 | 2018-02-19 01:00 | 20% | 4.4799 | 0.89598 | Reduce | 11% | 4.4799 | 0.49279 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-099 | Project_030_Risk-099 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Spares from suppliers | Person_251 | 2014-02-19 | 2018-02-19 | 20% | 4.4799 | 0.89598 | Reduce | 11% | 4.4799 | 0.49279 | H2 | 2 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK020 | Project_029_RISK020 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Setting to Work Resource | Person_694 | 2018-10-22 01:00 | 2021-07-20 | 50% | 1.4117 | 0.70585 | Reduce | 35% | 1.4117 | 0.49409 | H2 | 2 | -- | TRUE | 1001.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-08-20 01:00 | 50% | 4.6444 | 2.3222 | Avoid | 30% | 1.648 | 0.4944 | H2 | 2 | Worsening | TRUE | 395.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-12-20 01:00 | 50% | 4.6444 | 2.3222 | Avoid | 30% | 1.648 | 0.4944 | H2 | 2 | Worsening | TRUE | 517.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-12-20 01:00 | 50% | 4.6444 | 2.3222 | Avoid | 30% | 1.648 | 0.4944 | H2 | 2 | Worsening | TRUE | 517.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 2 |  | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 20% | 9.8671 | 1.9734 | Accept | 20% | 9.8671 | 1.9734 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 2 |  | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 20% | 9.8671 | 1.9734 | Accept | 20% | 9.8671 | 1.9734 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 2 |  | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 20% | 9.8671 | 1.9734 | Accept | 20% | 9.8671 | 1.9734 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 2 |  | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 20% | 9.8671 | 1.9734 | Accept | 20% | 9.8671 | 1.9734 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK222 | Project_024_RISK222 | Threat | Project Contingency | Open | H2 | 2 |  | Testing Extends beyond target completion | Person_351 | 2017-07-21 | 2018-08-21 | 20% | 9.8671 | 1.9734 | Accept | 20% | 9.8671 | 1.9734 | H2 | 2 | Stable | TRUE | 396 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 50% | 4.0228 | 2.0114 | Accept | 50% | 4.0228 | 2.0114 | H2 | 2 | Stable | TRUE | 810 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 50% | 4.1802 | 2.0901 | Accept | 50% | 4.1802 | 2.0901 | H2 | 2 | Stable | TRUE | 810 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-08-20 01:00 | 80% | 8.6133 | 6.8907 | Exploit | 80% | 2.6904 | 2.1524 | H2 | 2 | Stable | TRUE | 1584.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 8.6133 | 6.8907 | Exploit | 80% | 2.6904 | 2.1524 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2015-04-23 | 2018-08-21 | 40% | 1.2444 | 0.49778 | Reduce | 40% | 1.2444 | 0.49778 | H2 | 2 | Stable | TRUE | 1216 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2015-04-23 | 2018-08-21 | 40% | 1.2444 | 0.49778 | Reduce | 40% | 1.2444 | 0.49778 | H2 | 2 | Stable | TRUE | 1216 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2015-04-23 | 2018-08-21 | 40% | 1.2444 | 0.49778 | Reduce | 40% | 1.2444 | 0.49778 | H2 | 2 | Stable | TRUE | 1216 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 40% | 1.2444 | 0.49778 | Reduce | 40% | 1.2444 | 0.49778 | H2 | 2 | Stable | TRUE | 303.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 40% | 1.2444 | 0.49778 | Reduce | 40% | 1.2444 | 0.49778 | H2 | 2 | Stable | TRUE | 303.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer Acceptance -Residual PRs or post Factory Acceptance Test/SAT software updates after each release | Person_147 | 2017-10-21 01:00 | 2018-08-21 | 40% | 1.2444 | 0.49778 | Reduce | 40% | 1.2444 | 0.49778 | H2 | 2 | Stable | TRUE | 303.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change at Elevation | Person_701 | 2016-09-20 01:00 | 2016-11-20 01:00 | 41% | 1.2271 | 0.50311 | Accept | 41% | 1.2271 | 0.50311 | H2 | 2 | Stable | TRUE | 61 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change at Elevation | Person_701 | 2016-09-20 01:00 | 2016-11-20 01:00 | 41% | 1.2271 | 0.50311 | Accept | 41% | 1.2271 | 0.50311 | H2 | 2 | Stable | TRUE | 61 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change at Elevation | Person_570 | 2016-09-20 01:00 | 2017-01-20 01:00 | 41% | 1.2271 | 0.50311 | Accept | 41% | 1.2271 | 0.50311 | H2 | 2 | Stable | TRUE | 122 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 41% | 1.2271 | 0.50311 | Accept | 41% | 1.2271 | 0.50311 | H2 | 2 | Stable | TRUE | 122 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 41% | 1.2271 | 0.50311 | Accept | 41% | 1.2271 | 0.50311 | H2 | 2 | Stable | TRUE | 122 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 41% | 1.2271 | 0.50311 | Accept | 41% | 1.2271 | 0.50311 | H2 | 2 | Stable | TRUE | 122 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 41% | 1.2271 | 0.50311 | Accept | 41% | 1.2271 | 0.50311 | H2 | 2 | Stable | TRUE | 122 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK304 | Project_035_RISK304 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Change at Elevation | Person_425 | 2016-09-20 01:00 | 2017-01-20 01:00 | 41% | 1.2271 | 0.50311 | Accept | 41% | 1.2271 | 0.50311 | H2 | 2 | Stable | TRUE | 122 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 8.6133 | 6.8907 | Exploit | 80% | 2.6904 | 2.1524 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 8.6133 | 6.8907 | Exploit | 80% | 2.6904 | 2.1524 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-30 | Project_022_RISK-30 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Setting to work and acceptance issues | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 8.6133 | 6.8907 | Exploit | 80% | 2.6904 | 2.1524 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-145 | Project_030_Risk-145 | Threat | Project Contingency | Open | H2 | 2 |  | ILS Handbook Costs | Person_251 | 2015-03-24 | 2016-01-20 01:00 | 50% | 6.2982 | 3.1491 | -- | 50% | 4.3657 | 2.1829 | H2 | 2 | -- | TRUE | 302.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-145 | Project_030_Risk-145 | Threat | Project Contingency | Open | H2 | 2 |  | ILS Handbook Costs | Person_251 | 2015-03-24 | 2016-01-20 01:00 | 50% | 6.2982 | 3.1491 | -- | 50% | 4.3657 | 2.1829 | H2 | 2 | -- | TRUE | 302.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-145 | Project_030_Risk-145 | Threat | Project Contingency | Open | H2 | 2 |  | ILS Handbook Costs | Person_251 | 2015-03-24 | 2016-01-20 01:00 | 50% | 6.2982 | 3.1491 | -- | 50% | 4.3657 | 2.1829 | H2 | 2 | -- | TRUE | 302.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-145 | Project_030_Risk-145 | Threat | Project Contingency | Open | H2 | 2 |  | ILS Handbook Costs | Person_251 | 2015-03-24 | 2016-01-20 | 50% | 6.2982 | 3.1491 | -- | 50% | 4.3657 | 2.1829 | H2 | 2 | -- | TRUE | 302 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2018-04-14 | 2020-01-21 01:00 | 20% | 2.5354 | 0.50709 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | FALSE | 647.0417 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-145 | Project_030_Risk-145 | Threat | Project Contingency | Open | H2 | 2 |  | ILS Handbook Costs | Person_251 | 2015-03-24 | 2016-01-20 01:00 | 50% | 6.2982 | 3.1491 | -- | 50% | 4.3657 | 2.1829 | H2 | 2 | -- | TRUE | 302.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-145 | Project_030_Risk-145 | Threat | Project Contingency | Open | H2 | 2 |  | ILS Handbook Costs | Person_251 | 2015-03-24 | 2016-01-20 01:00 | 50% | 6.2982 | 3.1491 | -- | 50% | 4.3657 | 2.1829 | H2 | 2 | -- | TRUE | 302.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2018-04-14 | 2020-01-21 | 20% | 2.5354 | 0.50709 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | FALSE | 647 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-145 | Project_030_Risk-145 | Threat | Project Contingency | Open | H2 | 2 |  | ILS Handbook Costs | Person_251 | 2015-03-24 | 2016-01-20 01:00 | 50% | 6.2982 | 3.1491 | -- | 50% | 4.3657 | 2.1829 | H2 | 2 | -- | TRUE | 302.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-145 | Project_030_Risk-145 | Threat | Project Contingency | Open | H2 | 2 |  | ILS Handbook Costs | Person_251 | 2015-03-24 | 2016-01-20 | 50% | 6.2982 | 3.1491 | -- | 50% | 4.3657 | 2.1829 | H2 | 2 | -- | TRUE | 302 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2018-04-14 | 2020-01-21 01:00 | 20% | 2.5354 | 0.50709 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | FALSE | 647.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK007 | Project_095_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Freight cost increase. | Person_286 | 2018-07-22 | 2023-07-22 | 20% | 1.8322 | 0.36643 | -- | 20% | 10.9929 | 2.1986 | H2 | 2 | -- | TRUE | 1826 |  | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 50% | 4.4091 | 2.2045 | Accept | 50% | 4.4091 | 2.2045 | H2 | 2 | Stable | TRUE | 810 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK139-Risk- | Project_065_RISK139-Risk- | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional EMC Design / Testing from Risk Assessment | Person_160 | 2021-04-22 | 2024-04-22 | 20% | 8.0289 | 1.6058 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK460 | Project_065_RISK460 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Limited margin in connector space to accommodate design changes, without significant redesign | Person_038 | 2018-04-14 | 2020-01-20 23:00 | 20% | 2.5354 | 0.50709 | Accept | 20% | 2.5354 | 0.50709 | H3 | 3 | -- | FALSE | 646.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 50% | 4.4091 | 2.2045 | Accept | 50% | 4.4091 | 2.2045 | H2 | 2 | Stable | TRUE | 810 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 50% | 4.4221 | 2.2111 | Accept | 50% | 4.4221 | 2.2111 | H2 | 2 | Stable | TRUE | 810 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 50% | 4.4221 | 2.2111 | Accept | 50% | 4.4221 | 2.2111 | H2 | 2 | Stable | TRUE | 810 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 50% | 4.4221 | 2.2111 | Accept | 50% | 4.4221 | 2.2111 | H2 | 2 | Stable | TRUE | 810 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_014 | RISK001 | Project_014_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Generic Labour Risk Provision | Person_662 | 2015-11-02 01:00 | 2018-01-20 01:00 | 50% | 4.4221 | 2.2111 | Accept | 50% | 4.4221 | 2.2111 | H2 | 2 | Stable | TRUE | 810 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK005 | Project_095_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Travel costs increase | Person_286 | 2018-11-21 01:00 | 2023-07-22 | 30% | 7.3778 | 2.2133 | -- | 30% | 7.3778 | 2.2133 | H2 | 2 | -- | TRUE | 1703.9583 |  | 1 | 1 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts | Person_387 | 2016-05-23 | 2019-08-20 | 80% | 9.0039 | 7.2032 | Reduce | 25% | 9.0039 | 2.251 | H2 | 2 | Improving | TRUE | 1184 |  | 1 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts | Person_387 | 2016-05-23 | 2019-08-20 | 80% | 9.0039 | 7.2032 | Reduce | 25% | 9.0039 | 2.251 | H2 | 2 | Improving | TRUE | 1184 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK081 | Project_065_RISK081 | Threat | Management Contingency | Open | H3 | 3 | System Engineering | Qualification Equipment Does Not Allow Close Off | Person_704 | 2015-05-24 | 2018-03-21 | 40% | 5.1004 | 2.0402 | Reduce | 20% | 2.5506 | 0.51013 | H3 | 3 | Stable | TRUE | 1032 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-088 | Project_011_Risk-088 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Increased Opportunties in year 2 to 5 | Person_522 | 2015-01-22 01:00 | 2018-07-22 | 50% | 1.0228 | 0.51141 | -- | 50% | 1.0228 | 0.51141 | H3 | 3 | -- | FALSE | 1276.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-088 | Project_011_Risk-088 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Increased Opportunties in year 2 to 5 | Person_522 | 2015-01-22 01:00 | 2018-07-22 | 50% | 1.0228 | 0.51141 | -- | 50% | 1.0228 | 0.51141 | H3 | 3 | -- | FALSE | 1276.9583 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1005 | Project_091_RISK1005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | COTS design is not acceptable | Person_557 | 2018-08-22 01:00 | 2019-05-23 | 40% | 1.2791 | 0.51164 | Reduce | 40% | 1.2791 | 0.51164 | H2 | 2 | -- | TRUE | 273.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1005 | Project_091_RISK1005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | COTS design is not acceptable | Person_557 | 2018-09-21 01:00 | 2019-05-23 | 40% | 1.2791 | 0.51164 | Reduce | 40% | 1.2791 | 0.51164 | H2 | 2 | -- | TRUE | 243.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional effort for System HW/SW- System upgrade. | Person_199 | 2017-05-23 | 2019-09-18 01:00 | 30% | 2.5667 | 0.77001 | Reduce | 20% | 2.5667 | 0.51334 | H3 | 3 | Stable | FALSE | 848.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen changes to SW interfaces as a result of design. | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Accept | 20% | 2.5667 | 0.51334 | H3 | 3 | Stable | FALSE | 881.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK015 | Project_041_RISK015 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Conponent on product #1 having to be returned to Supplier (qualification temperature failure) | Person_693 | 2018-10-22 01:00 | 2018-12-22 01:00 | 50% | 1.029 | 0.51448 | -- | 50% | 1.029 | 0.51448 | H2 | 2 | Stable | TRUE | 61 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | RISK003 | Project_044_RISK003 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Unavailability / failure of Range | Person_553 | 2018-08-14 | 2019-10-21 01:00 | 70% | 21.7314 | 15.212 | Reduce | 20% | 2.5957 | 0.51914 | H3 | 3 | Worsening | TRUE | 433.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_387 | 2016-05-23 | 2019-08-20 | 40% | 9.0039 | 3.6016 | Reduce | 25% | 9.0039 | 2.251 | H2 | 2 | Improving | TRUE | 1184 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_294 | 2016-05-23 | 2019-08-20 | 40% | 9.0039 | 3.6016 | Reduce | 25% | 9.0039 | 2.251 | H2 | 2 | Improving | TRUE | 1184 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 40% | 9.0039 | 3.6016 | Reduce | 25% | 9.0039 | 2.251 | H2 | 2 | Improving | TRUE | 819 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 40% | 9.0039 | 3.6016 | Reduce | 25% | 9.0039 | 2.251 | H2 | 2 | Improving | TRUE | 819 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 40% | 9.0039 | 3.6016 | Reduce | 25% | 9.0039 | 2.251 | H2 | 2 | Improving | TRUE | 819 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 40% | 9.0039 | 3.6016 | Reduce | 25% | 9.0039 | 2.251 | H2 | 2 | Improving | TRUE | 819 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-015 | Project_062_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Re-work | Person_253 | 2018-03-01 01:00 | 2019-05-22 | 50% | 1.0457 | 0.52287 | Avoid | 50% | 1.0457 | 0.52287 | H2 | 2 | Stable | TRUE | 446.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 50% | 1.3243 | 0.66217 | Reduce | 40% | 1.3243 | 0.52974 | H2 | 2 | -- | TRUE | 99 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R033 | Project_021_Risk-R033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config 1c Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-08-10 | 2016-11-19 01:00 | 50% | 1.3243 | 0.66217 | Reduce | 40% | 1.3243 | 0.52974 | H2 | 2 | -- | TRUE | 101.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 | 2016-12-19 | 50% | 1.3243 | 0.66217 | Reduce | 40% | 1.3243 | 0.52974 | H2 | 2 | Stable | TRUE | 99 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R033 | Project_021_Risk-R033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config 1c Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-08-10 | 2016-11-19 | 50% | 1.3243 | 0.66217 | Reduce | 40% | 1.3243 | 0.52974 | H2 | 2 | Improving | TRUE | 101 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 50% | 1.3243 | 0.66217 | Reduce | 40% | 1.3243 | 0.52974 | H2 | 2 | Stable | TRUE | 99 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 50% | 1.3243 | 0.66217 | Reduce | 40% | 1.3243 | 0.52974 | H2 | 2 | Stable | TRUE | 133 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-008 | Project_021_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 50% | 1.3243 | 0.66217 | Reduce | 40% | 1.3243 | 0.52974 | H2 | 2 | Stable | TRUE | 133 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-024 | Project_062_Risk-024 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional SW Build post-Factory Acceptance Test | Person_479 | 2018-08-22 01:00 | 2019-04-22 | 30% | 1.7778 | 0.53333 | Avoid | 30% | 1.7778 | 0.53333 | H2 | 2 | Stable | TRUE | 242.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK096 | Project_035_RISK096 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Product Real World Performance | Person_699 | 2015-05-24 | 2016-10-20 01:00 | 15% | 3.5631 | 0.53446 | Accept | 15% | 3.5631 | 0.53446 | H3 | 3 | Stable | FALSE | 515.0417 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK096 | Project_035_RISK096 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Product Real World Performance | Person_699 | 2015-05-24 | 2016-10-20 01:00 | 15% | 3.5631 | 0.53446 | Accept | 15% | 3.5631 | 0.53446 | H3 | 3 | Stable | FALSE | 515.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK003 | Project_060_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Misalignment of Critical Resource | Person_312 | 2017-12-19 01:00 | 2018-11-06 01:00 | 70% | 1.0769 | 0.75381 | Reduce | 50% | 1.0769 | 0.53844 | H2 | 2 | Improving | TRUE | 322 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2016-06-21 | 60% | 0.89835 | 0.53901 | Transfer | 60% | 0.89835 | 0.53901 | H1 | 1 | Stable | TRUE | 302.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2016-09-19 01:00 | 60% | 0.89835 | 0.53901 | Transfer | 60% | 0.89835 | 0.53901 | H1 | 1 | Stable | TRUE | 393 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2016-10-21 01:00 | 60% | 0.89835 | 0.53901 | Transfer | 60% | 0.89835 | 0.53901 | H1 | 1 | Stable | TRUE | 425 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2016-10-21 01:00 | 60% | 0.89835 | 0.53901 | Transfer | 60% | 0.89835 | 0.53901 | H1 | 1 | Stable | TRUE | 425 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2020-10-20 01:00 | 20% | 2.6951 | 0.53901 | Reduce | 20% | 2.6951 | 0.53901 | H3 | 3 | Stable | FALSE | 1611.0417 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-05-23 | 60% | 0.89835 | 0.53901 | Transfer | 60% | 0.89835 | 0.53901 | H1 | 1 | Stable | TRUE | 638.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2020-10-20 01:00 | 20% | 2.6951 | 0.53901 | Reduce | 20% | 2.6951 | 0.53901 | H3 | 3 | Stable | FALSE | 1611.0417 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-05-23 | 60% | 0.89835 | 0.53901 | Transfer | 60% | 0.89835 | 0.53901 | H1 | 1 | Stable | TRUE | 638.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2020-10-20 01:00 | 20% | 2.6951 | 0.53901 | Reduce | 20% | 2.6951 | 0.53901 | H3 | 3 | Stable | FALSE | 1611.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-05-23 | 60% | 0.89835 | 0.53901 | Transfer | 60% | 0.89835 | 0.53901 | H1 | 1 | Stable | TRUE | 638.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2020-10-20 01:00 | 20% | 2.6951 | 0.53901 | Reduce | 20% | 2.6951 | 0.53901 | H3 | 3 | Stable | FALSE | 1611.0417 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-112 | Project_029_Risk-112 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Safety Customer Deliverables - Additional Effort | Person_102 | 2015-08-23 01:00 | 2017-05-23 | 60% | 0.89835 | 0.53901 | Transfer | 60% | 0.89835 | 0.53901 | H1 | 1 | Stable | TRUE | 638.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK017 | Project_029_Risk-RISK017 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen Component Rack Re-Design | Person_216 | 2016-05-23 | 2017-07-20 | 20% | 2.6951 | 0.53901 | Reduce | 20% | 2.6951 | 0.53901 | H3 | 3 | Improving | FALSE | 423 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 40% | 1.3502 | 0.54009 | Accept | 40% | 1.3502 | 0.54009 | H1 | 1 | Worsening | TRUE | 272.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 40% | 1.3502 | 0.54009 | Accept | 40% | 1.3502 | 0.54009 | H1 | 1 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 40% | 1.3502 | 0.54009 | Accept | 40% | 1.3502 | 0.54009 | H1 | 1 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 40% | 1.3502 | 0.54009 | Accept | 40% | 1.3502 | 0.54009 | H1 | 1 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 40% | 1.3502 | 0.54009 | Accept | 40% | 1.3502 | 0.54009 | H1 | 1 | Improving | TRUE | 272.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK152 | Project_024_RISK152 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Component Damage | Person_674 | 2016-04-06 | 2016-07-21 | 10% | 5.4096 | 0.54096 | Accept | 10% | 5.4096 | 0.54096 | H3 | 3 | Stable | FALSE | 106 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK152 | Project_024_RISK152 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Component Damage | Person_674 | 2016-04-06 | 2016-10-21 01:00 | 10% | 5.4096 | 0.54096 | Accept | 10% | 5.4096 | 0.54096 | H3 | 3 | Stable | FALSE | 198.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK152 | Project_024_RISK152 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Component Damage | Person_674 | 2016-04-06 | 2016-10-21 01:00 | 10% | 5.4096 | 0.54096 | Accept | 10% | 5.4096 | 0.54096 | H3 | 3 | Stable | FALSE | 198.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK152 | Project_024_RISK152 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Component Damage | Person_674 | 2016-04-06 | 2016-10-21 01:00 | 10% | 5.4096 | 0.54096 | Accept | 10% | 5.4096 | 0.54096 | H3 | 3 | Stable | FALSE | 198.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--117 | Project_100_Risk--117 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Offset of Management costs | Person_565 | 2018-08-22 01:00 | 2021-08-20 01:00 | 80% | 0.67704 | 0.54163 | Exploit | 80% | 0.67704 | 0.54163 | H2 | 2 | -- | TRUE | 1094 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Workshop ability | Person_039 | 2012-08-20 20:00 | 2019-08-20 20:00 | 41% | 2.5362 | 1.0399 | Reduce | 41% | 1.3255 | 0.54344 | H3 | 3 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Workshop ability | Person_039 | 2012-08-20 20:00 | 2019-08-20 20:00 | 41% | 2.5362 | 1.0399 | Reduce | 41% | 1.3255 | 0.54344 | H3 | 3 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Workshop ability | Person_039 | 2012-08-20 20:00 | 2019-08-20 20:00 | 41% | 2.5362 | 1.0399 | Reduce | 41% | 1.3255 | 0.54344 | H3 | 3 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Workshop ability | Person_039 | 2012-08-20 20:00 | 2019-08-20 20:00 | 41% | 2.5362 | 1.0399 | Reduce | 41% | 1.3255 | 0.54344 | H3 | 3 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 41% | 2.5362 | 1.0399 | Reduce | 41% | 1.3255 | 0.54344 | H3 | 3 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 41% | 2.5362 | 1.0399 | Reduce | 41% | 1.3255 | 0.54344 | H3 | 3 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 41% | 2.5362 | 1.0399 | Reduce | 41% | 1.3255 | 0.54344 | H3 | 3 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS011 | Project_025_RS011 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Workshop ability | Person_039 | 2012-08-20 19:00 | 2019-08-20 19:00 | 41% | 2.5362 | 1.0399 | Reduce | 41% | 1.3255 | 0.54344 | H3 | 3 | Stable | TRUE | 2556 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 41% | 3.8666 | 1.5853 | Accept | 41% | 1.3288 | 0.5448 | H2 | 2 | Stable | TRUE | 176.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 41% | 3.8666 | 1.5853 | Accept | 41% | 1.3288 | 0.5448 | H2 | 2 | Stable | TRUE | 176.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 41% | 3.8666 | 1.5853 | Accept | 41% | 1.3288 | 0.5448 | H2 | 2 | Stable | TRUE | 176.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 41% | 3.8666 | 1.5853 | Accept | 41% | 1.3288 | 0.5448 | H2 | 2 | Stable | TRUE | 176.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 41% | 3.8666 | 1.5853 | Accept | 41% | 1.3288 | 0.5448 | H2 | 2 | Stable | TRUE | 176.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2016-12-08 01:00 | 41% | 3.8666 | 1.5853 | Accept | 41% | 1.3288 | 0.5448 | H2 | 2 | Stable | TRUE | 176.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-03-22 | 41% | 3.8666 | 1.5853 | Accept | 41% | 1.3288 | 0.5448 | H2 | 2 | Stable | TRUE | 280 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-014 | Project_023_Risk-014 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Weather during acceptance | Person_703 | 2016-06-15 | 2017-03-22 | 41% | 3.8666 | 1.5853 | Accept | 41% | 1.3288 | 0.5448 | H2 | 2 | Stable | TRUE | 280 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-048 | Project_028_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Compatibility | Person_542 | 2015-04-08 | 2016-08-20 | 5% | 11.0007 | 0.55004 | Accept | 5% | 11.0007 | 0.55004 | H2 | 2 | Stable | TRUE | 500 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-048 | Project_028_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Compatibility | Person_542 | 2015-04-08 | 2016-09-19 01:00 | 5% | 11.0007 | 0.55004 | Accept | 5% | 11.0007 | 0.55004 | H2 | 2 | Stable | TRUE | 530.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-048 | Project_028_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Compatibility | Person_542 | 2015-04-08 | 2016-09-19 01:00 | 5% | 11.0007 | 0.55004 | Accept | 5% | 11.0007 | 0.55004 | H2 | 2 | Stable | TRUE | 530.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK052 | Project_042_RISK052 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Additional Engineering Support to Industry | Person_134 | 2018-09-23 01:00 | 2019-10-22 01:00 | 50% | 1.1011 | 0.55057 | Accept | 50% | 1.1011 | 0.55057 | H2 | 2 | Stable | TRUE | 394 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-004 | Project_026_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Resource Project Impacts | Person_264 | 2015-05-24 | 2017-08-20 01:00 | 5% | 11.0427 | 0.55214 | Reduce | 5% | 11.0427 | 0.55214 | H2 | 2 | -- | TRUE | 819.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-004 | Project_026_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Resource Project Impacts | Person_264 | 2015-05-24 | 2017-08-20 01:00 | 5% | 11.0427 | 0.55214 | Reduce | 5% | 11.0427 | 0.55214 | H2 | 2 | -- | TRUE | 819.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_418 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_418 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_418 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_418 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_418 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_418 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_418 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013-Risk- | Project_065_RISK013-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_418 | 2017-03-23 | 2018-06-09 | 50% | 13.3921 | 6.6961 | Reduce | 30% | 7.6883 | 2.3065 | H2 | 2 | -- | TRUE | 443 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2016-09-02 01:00 | 2018-07-21 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 686.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2016-09-02 01:00 | 2018-07-21 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 686.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-09-20 01:00 | 30% | 5.5433 | 1.663 | Reduce | 10% | 5.5433 | 0.55433 | H3 | 3 | Improving | TRUE | 89.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-10-21 01:00 | 30% | 5.5433 | 1.663 | Reduce | 10% | 5.5433 | 0.55433 | H3 | 3 | Improving | TRUE | 120.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 30% | 5.5433 | 1.663 | Reduce | 10% | 5.5433 | 0.55433 | H3 | 3 | Improving | TRUE | 150.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 30% | 5.5433 | 1.663 | Reduce | 10% | 5.5433 | 0.55433 | H3 | 3 | Improving | TRUE | 150.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 30% | 5.5433 | 1.663 | Reduce | 10% | 5.5433 | 0.55433 | H3 | 3 | Improving | TRUE | 150.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 30% | 5.5433 | 1.663 | Reduce | 10% | 5.5433 | 0.55433 | H3 | 3 | Improving | TRUE | 150.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 5% | 11.0894 | 0.55447 | Accept | 5% | 11.0894 | 0.55447 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 5% | 11.0894 | 0.55447 | Accept | 5% | 11.0894 | 0.55447 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 5% | 11.0894 | 0.55447 | Accept | 5% | 11.0894 | 0.55447 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 | 5% | 11.0894 | 0.55447 | Accept | 5% | 11.0894 | 0.55447 | H2 | 2 | Stable | TRUE | 1906 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 5% | 11.0894 | 0.55447 | Accept | 5% | 11.0894 | 0.55447 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 5% | 11.0894 | 0.55447 | Accept | 5% | 11.0894 | 0.55447 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 01:00 | 5% | 11.0894 | 0.55447 | Accept | 5% | 11.0894 | 0.55447 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk10 | Project_010_Risk10 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Furnished Equipment (Rig) becomes commercially unavailable | Person_359 | 2012-06-01 | 2017-08-20 | 5% | 11.0894 | 0.55447 | Accept | 5% | 11.0894 | 0.55447 | H2 | 2 | Stable | TRUE | 1906 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 30% | 1.8602 | 0.55807 | Accept | 30% | 1.8602 | 0.55807 | H3 | 3 | -- | TRUE | 182 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-197 | Project_039_Risk-197 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Key Test facilities Availability | Person_185 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 1.8602 | 0.93012 | Reduce | 30% | 1.8602 | 0.55807 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 30% | 1.8602 | 0.55807 | Accept | 30% | 1.8602 | 0.55807 | H3 | 3 | Worsening | TRUE | 182 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-197 | Project_039_Risk-197 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Key Test facilities Availability | Person_185 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 1.8602 | 0.93012 | Reduce | 30% | 1.8602 | 0.55807 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 30% | 1.8602 | 0.55807 | Accept | 30% | 1.8602 | 0.55807 | H3 | 3 | Worsening | TRUE | 182 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-197 | Project_039_Risk-197 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Key Test facilities Availability | Person_185 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 1.8602 | 0.93012 | Reduce | 30% | 1.8602 | 0.55807 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 30% | 1.8602 | 0.55807 | Accept | 30% | 1.8602 | 0.55807 | H3 | 3 | Worsening | TRUE | 182 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-197 | Project_039_Risk-197 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Key Test facilities Availability | Person_185 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 1.8602 | 0.93012 | Reduce | 30% | 1.8602 | 0.55807 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 | 2017-02-19 | 30% | 1.8602 | 0.55807 | Accept | 30% | 1.8602 | 0.55807 | H3 | 3 | Worsening | TRUE | 182 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-197 | Project_039_Risk-197 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Key Test facilities Availability | Person_185 | 2016-09-20 | 2017-02-19 | 50% | 1.8602 | 0.93012 | Reduce | 30% | 1.8602 | 0.55807 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 30% | 1.8602 | 0.55807 | Accept | 30% | 1.8602 | 0.55807 | H3 | 3 | Worsening | TRUE | 182 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-197 | Project_039_Risk-197 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Key Test facilities Availability | Person_185 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 1.8602 | 0.93012 | Reduce | 30% | 1.8602 | 0.55807 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-195 | Project_039_Risk-195 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supply Chain Delays - System Comms, Component, and subsystem | Person_083 | 2016-08-21 01:00 | 2017-02-19 01:00 | 30% | 1.8602 | 0.55807 | Accept | 30% | 1.8602 | 0.55807 | H3 | 3 | Worsening | TRUE | 182 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-197 | Project_039_Risk-197 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Key Test facilities Availability | Person_185 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 1.8602 | 0.93012 | Reduce | 30% | 1.8602 | 0.55807 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2016-09-02 | 2018-07-21 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 687 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2016-09-02 01:00 | 2018-07-21 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 686.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Environmental Conditions | Person_393 | 2012-04-19 | 2016-11-19 01:00 | 20% | 2.7943 | 0.55886 | Accept | 20% | 2.7943 | 0.55886 | H3 | 3 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Environmental Conditions | Person_393 | 2012-04-19 | 2016-11-19 01:00 | 20% | 2.7943 | 0.55886 | Accept | 20% | 2.7943 | 0.55886 | H3 | 3 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Environmental Conditions | Person_393 | 2012-04-19 | 2016-11-19 01:00 | 20% | 2.7943 | 0.55886 | Accept | 20% | 2.7943 | 0.55886 | H3 | 3 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Environmental Conditions | Person_393 | 2012-04-19 | 2016-11-19 01:00 | 20% | 2.7943 | 0.55886 | Accept | 20% | 2.7943 | 0.55886 | H3 | 3 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-132 | Project_020_Risk-132 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Outstanding Customer Loaned Stock | Person_575 | 2007-05-24 | 2016-05-22 | 50% | 3.1564 | 1.5782 | Reduce | 25% | 2.2492 | 0.56231 | H3 | 3 | -- | TRUE | 3286 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-132 | Project_020_Risk-132 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Outstanding Customer Loaned Stock | Person_575 | 2007-05-24 | 2016-05-22 | 50% | 3.1564 | 1.5782 | Reduce | 25% | 2.2492 | 0.56231 | H3 | 3 | -- | TRUE | 3286 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-132 | Project_020_Risk-132 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Outstanding Customer Loaned Stock | Person_575 | 2007-05-24 | 2016-05-22 | 50% | 3.1564 | 1.5782 | Reduce | 25% | 2.2492 | 0.56231 | H3 | 3 | -- | TRUE | 3286 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-132 | Project_020_Risk-132 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Outstanding Customer Loaned Stock | Person_575 | 2007-05-24 | 2016-05-22 | 50% | 3.1564 | 1.5782 | Reduce | 25% | 2.2492 | 0.56231 | H3 | 3 | -- | TRUE | 3286 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-132 | Project_020_Risk-132 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Outstanding Customer Loaned Stock | Person_575 | 2007-05-24 | 2016-05-22 | 50% | 3.1564 | 1.5782 | Reduce | 25% | 2.2492 | 0.56231 | H3 | 3 | -- | TRUE | 3286 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-132 | Project_020_Risk-132 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Outstanding Customer Loaned Stock | Person_575 | 2007-05-24 | 2016-05-22 | 50% | 3.1564 | 1.5782 | Reduce | 25% | 2.2492 | 0.56231 | H3 | 3 | -- | TRUE | 3286 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-132 | Project_020_Risk-132 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Outstanding Customer Loaned Stock | Person_575 | 2007-05-24 | 2016-05-22 | 50% | 3.1564 | 1.5782 | Reduce | 25% | 2.2492 | 0.56231 | H3 | 3 | -- | TRUE | 3286 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-132 | Project_020_Risk-132 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Outstanding Customer Loaned Stock | Person_575 | 2007-05-24 | 2016-05-22 | 50% | 3.1564 | 1.5782 | Reduce | 25% | 2.2492 | 0.56231 | H3 | 3 | -- | TRUE | 3286 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2016-10-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 50% | 1.1257 | 0.56284 | H1 | 1 | -- | TRUE | 38 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 50% | 1.1257 | 0.56284 | Reduce | 50% | 1.1257 | 0.56284 | H1 | 1 | -- | TRUE | 284 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 | 2017-01-19 | 50% | 1.1257 | 0.56284 | Reduce | 50% | 1.1257 | 0.56284 | H1 | 1 | Stable | TRUE | 130 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 50% | 1.1257 | 0.56284 | Reduce | 50% | 1.1257 | 0.56284 | H1 | 1 | -- | TRUE | 284 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-011 | Project_021_Risk-011 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-09-11 01:00 | 2017-01-19 01:00 | 50% | 1.1257 | 0.56284 | Reduce | 50% | 1.1257 | 0.56284 | H1 | 1 | Stable | TRUE | 130 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R038 | Project_021_Risk-R038 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional documentation required for final build certification | Person_207 | 2016-08-10 | 2017-05-21 | 50% | 1.1257 | 0.56284 | Reduce | 50% | 1.1257 | 0.56284 | H1 | 1 | Stable | TRUE | 284 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.8182 | 0.56365 | Accept | 20% | 2.8182 | 0.56365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.8182 | 0.56365 | Accept | 20% | 2.8182 | 0.56365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.8182 | 0.56365 | Accept | 20% | 2.8182 | 0.56365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.8182 | 0.56365 | Accept | 20% | 2.8182 | 0.56365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.8182 | 0.56365 | Accept | 20% | 2.8182 | 0.56365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.8182 | 0.56365 | Accept | 20% | 2.8182 | 0.56365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk006 | Project_042_Risk006 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Internal Quality Issues | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 2.8182 | 0.56365 | Accept | 20% | 2.8182 | 0.56365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2016-09-01 23:00 | 2018-07-21 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 687.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK025 | Project_042_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence May to 31 Dec | Person_455 | 2020-09-20 01:00 | 2021-05-22 | 20% | 4.6971 | 0.93941 | Accept | 15% | 3.7576 | 0.56365 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2016-09-01 22:00 | 2018-07-21 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 687.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2016-09-01 23:00 | 2018-07-21 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 687.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2018-05-23 | 2024-05-22 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 2191 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-056 | Project_062_Risk-056 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Supplier integration acceptance by end Customer | Person_031 | 2017-07-21 | 2018-11-21 01:00 | 30% | 1.8823 | 0.5647 | Reduce | 30% | 1.8823 | 0.5647 | H3 | 3 | Stable | TRUE | 488.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 951.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 951.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 951 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 951.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 23:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 950.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 22:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 950.9167 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 23:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 950.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 951.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 22:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 950.9167 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 951 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 951.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031- | Project_065_RISK031- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2020-04-22 | 2021-04-22 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK031-Risk- | Project_065_RISK031-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | General - EMC Performance | Person_160 | 2021-04-22 | 2023-11-28 23:00 | 60% | 5.7098 | 3.4259 | Reduce | 25% | 2.263 | 0.56574 | H2 | 2 | Stable | TRUE | 950.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 5% | 11.3437 | 0.56718 | Reduce | 5% | 11.3437 | 0.56718 | H3 | 3 | Stable | FALSE | 1232.0417 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 5% | 11.3437 | 0.56718 | Reduce | 5% | 11.3437 | 0.56718 | H3 | 3 | Stable | FALSE | 1232 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 5% | 11.3437 | 0.56718 | Reduce | 5% | 11.3437 | 0.56718 | H3 | 3 | Stable | FALSE | 1232 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 | 5% | 11.3437 | 0.56718 | Reduce | 5% | 11.3437 | 0.56718 | H3 | 3 | Stable | FALSE | 1232 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 5% | 11.3437 | 0.56718 | Reduce | 5% | 11.3437 | 0.56718 | H3 | 3 | Stable | FALSE | 1232.0417 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 5% | 11.3437 | 0.56718 | Reduce | 5% | 11.3437 | 0.56718 | H3 | 3 | Stable | FALSE | 1232.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 5% | 11.3437 | 0.56718 | Reduce | 5% | 11.3437 | 0.56718 | H3 | 3 | Stable | FALSE | 1232.0417 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-153 | Project_032_Risk-153 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Sub-contractor STTE failure | Person_487 | 2014-04-06 | 2017-08-20 01:00 | 5% | 11.3437 | 0.56718 | Reduce | 5% | 11.3437 | 0.56718 | H3 | 3 | Stable | FALSE | 1232.0417 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2016-09-01 22:00 | 2018-07-21 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 687.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2018-05-23 | 2024-05-22 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 2191 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK116 | Project_065_RISK116 | Threat | Management Contingency | Open | H3 | 3 | Hardware/Software development | Software Release 3 implementation | Person_550 | 2017-05-23 | 2018-04-21 | 80% | 19.1678 | 15.3343 | Reduce | 20% | 2.8752 | 0.57503 | H3 | 3 | Stable | TRUE | 333 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R018 | Project_044_Risk-R018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC (susceptibility) | Person_763 | 2016-03-23 | 2019-11-20 01:00 | 50% | 5.795 | 2.8975 | Reduce | 10% | 5.795 | 0.5795 | H3 | 3 | Stable | FALSE | 1337.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2018-05-23 | 2024-05-22 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 2191 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 10% | 5.8286 | 0.58286 | Accept | 10% | 5.8286 | 0.58286 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 10% | 5.8286 | 0.58286 | Accept | 10% | 5.8286 | 0.58286 | H2 | 2 | Stable | TRUE | 1794 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 10% | 5.8286 | 0.58286 | Accept | 10% | 5.8286 | 0.58286 | H2 | 2 | Stable | TRUE | 1794 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-135 | Project_032_Risk-135 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Significant failure | Person_360 | 2012-08-21 | 2017-07-20 | 10% | 5.8286 | 0.58286 | Accept | 10% | 5.8286 | 0.58286 | H2 | 2 | Stable | TRUE | 1794 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK016 | Project_079_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Test Equipment | Person_104 | 2017-09-29 01:00 | 2019-05-23 | 80% | 1.9552 | 1.5642 | Avoid | 30% | 1.9552 | 0.58657 | H3 | 3 | Stable | TRUE | 600.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK016 | Project_079_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Test Equipment | Person_104 | 2017-09-29 01:00 | 2019-05-23 | 80% | 1.9552 | 1.5642 | Avoid | 30% | 1.9552 | 0.58657 | H3 | 3 | Worsening | TRUE | 600.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK038 | Project_065_RISK038 | Threat | Management Contingency | Open | H2 | 2 |  | Verification strategy changes post bid leads to cost and schedule impact | Person_160 | 2018-05-23 | 2024-05-22 | 40% | 13.0118 | 5.2047 | Reduce | 30% | 7.804 | 2.3412 | H2 | 2 | -- | TRUE | 2191 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK059 | Project_058_RISK059 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Manufacturing (Batching) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 50% | 4.6977 | 2.3489 | -- | 50% | 4.6977 | 2.3489 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK017 | Project_075_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | New Materials not tested for Out Gassing | Person_451 | 2017-07-21 | 2018-06-22 | 35% | 12.3041 | 4.3064 | Reduce | 20% | 12.3041 | 2.4608 | H2 | 2 | Stable | TRUE | 336 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK017 | Project_075_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | New Materials not tested for Out Gassing | Person_451 | 2017-07-21 | 2018-08-20 | 35% | 12.3041 | 4.3064 | Reduce | 20% | 12.3041 | 2.4608 | H2 | 2 | Stable | TRUE | 395 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK017 | Project_075_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | New Materials not tested for Out Gassing | Person_451 | 2017-07-21 | 2018-08-20 | 35% | 12.3041 | 4.3064 | Reduce | 20% | 12.3041 | 2.4608 | H2 | 2 | Stable | TRUE | 395 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK017 | Project_075_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | New Materials not tested for Out Gassing | Person_451 | 2017-07-21 | 2018-08-20 | 35% | 12.3041 | 4.3064 | Reduce | 20% | 12.3041 | 2.4608 | H2 | 2 | Stable | TRUE | 395 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 2 |  | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-05-22 | 35% | 4.2355 | 1.4824 | Reduce | 30% | 8.471 | 2.5413 | H2 | 2 | Stable | TRUE | 547.9583 |  | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 2 |  | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-05-22 | 35% | 4.2355 | 1.4824 | Reduce | 30% | 8.471 | 2.5413 | H2 | 2 | Stable | TRUE | 547.9583 |  | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-141 | Project_030_Risk-141 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity for cost savings on Cabinet | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 8.872 | 2.3067 | -- | 30% | 8.4914 | 2.5474 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-141 | Project_030_Risk-141 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity for cost savings on Cabinet | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 8.872 | 2.3067 | -- | 30% | 8.4914 | 2.5474 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-141 | Project_030_Risk-141 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity for cost savings on Cabinet | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 8.872 | 2.3067 | -- | 30% | 8.4914 | 2.5474 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-141 | Project_030_Risk-141 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity for cost savings on Cabinet | Person_518 | 2014-10-22 | 2015-05-23 | 26% | 8.872 | 2.3067 | -- | 30% | 8.4914 | 2.5474 | H2 | 2 | -- | TRUE | 213 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-141 | Project_030_Risk-141 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity for cost savings on Cabinet | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 8.872 | 2.3067 | -- | 30% | 8.4914 | 2.5474 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-141 | Project_030_Risk-141 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity for cost savings on Cabinet | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 8.872 | 2.3067 | -- | 30% | 8.4914 | 2.5474 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-141 | Project_030_Risk-141 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity for cost savings on Cabinet | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 8.872 | 2.3067 | -- | 30% | 8.4914 | 2.5474 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-141 | Project_030_Risk-141 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity for cost savings on Cabinet | Person_518 | 2014-10-22 | 2015-05-23 | 26% | 8.872 | 2.3067 | -- | 30% | 8.4914 | 2.5474 | H2 | 2 | -- | TRUE | 213 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK278 | Project_024_RISK278 | Threat | Project Contingency | Open | H2 | 2 |  | Operating systems haven't had security patches | Person_237 | 2017-01-21 01:00 | 2019-05-23 | 20% | 12.983 | 2.5966 | Accept | 20% | 12.983 | 2.5966 | H2 | 2 | -- | TRUE | 851.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK278 | Project_024_RISK278 | Threat | Project Contingency | Open | H2 | 2 |  | Operating systems haven't had security patches | Person_237 | 2017-01-21 01:00 | 2019-05-23 | 20% | 12.983 | 2.5966 | Accept | 20% | 12.983 | 2.5966 | H2 | 2 | -- | TRUE | 851.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK278 | Project_024_RISK278 | Threat | Project Contingency | Open | H2 | 2 |  | Operating systems haven't had security patches | Person_237 | 2017-01-21 01:00 | 2018-05-22 | 20% | 12.983 | 2.5966 | Accept | 20% | 12.983 | 2.5966 | H2 | 2 | -- | TRUE | 485.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Bank Guarantees | Person_703 | 2012-04-19 | 2016-08-20 01:00 | 80% | 3.3531 | 2.6825 | Exploit | 80% | 3.3531 | 2.6825 | H2 | 2 | Stable | TRUE | 1584.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.3531 | 2.6825 | Exploit | 80% | 3.3531 | 2.6825 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.3531 | 2.6825 | Exploit | 80% | 3.3531 | 2.6825 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.3531 | 2.6825 | Exploit | 80% | 3.3531 | 2.6825 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-54 | Project_022_RISK-54 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Bank Guarantees | Person_703 | 2012-04-19 | 2016-11-19 01:00 | 80% | 3.3531 | 2.6825 | Exploit | 80% | 3.3531 | 2.6825 | H2 | 2 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK292 | Project_024_RISK292 | Threat | Project Contingency | Open | H2 | 2 |  | Renewal of Annual Licenses | Person_318 | 2016-04-22 | 2019-05-15 | 100% | 2.7146 | 2.7146 | Accept | 100% | 2.7146 | 2.7146 | H2 | 2 | -- | TRUE | 1118 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK292 | Project_024_RISK292 | Threat | Project Contingency | Open | H2 | 2 |  | Renewal of Annual Licenses | Person_318 | 2016-04-22 | 2019-05-15 | 100% | 2.7146 | 2.7146 | Accept | 100% | 2.7146 | 2.7146 | H2 | 2 | -- | TRUE | 1118 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK292 | Project_024_RISK292 | Threat | Project Contingency | Open | H2 | 2 |  | Renewal of Annual Licenses | Person_318 | 2016-04-22 | 2019-05-15 | 100% | 2.7146 | 2.7146 | Accept | 100% | 2.7146 | 2.7146 | H2 | 2 | -- | TRUE | 1118 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK292 | Project_024_RISK292 | Threat | Project Contingency | Open | H2 | 2 |  | Renewal of Annual Licenses | Person_318 | 2016-04-22 | 2019-05-15 | 100% | 2.7146 | 2.7146 | Accept | 100% | 2.7146 | 2.7146 | H2 | 2 | -- | TRUE | 1118 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK292 | Project_024_RISK292 | Threat | Project Contingency | Open | H2 | 2 |  | Renewal of Annual Licenses | Person_318 | 2016-04-22 | 2019-05-15 | 100% | 2.7146 | 2.7146 | Accept | 100% | 2.7146 | 2.7146 | H2 | 2 | -- | TRUE | 1118 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK028 | Project_058_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | RFIs | Person_294 | 2017-05-24 | 2019-11-15 01:00 | 60% | 9.7869 | 5.8721 | Reduce | 30% | 9.7869 | 2.9361 | H2 | 2 | -- | TRUE | 905.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK028 | Project_058_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | RFIs | Person_294 | 2017-05-24 | 2019-11-15 01:00 | 60% | 9.7869 | 5.8721 | Reduce | 30% | 9.7869 | 2.9361 | H2 | 2 | -- | TRUE | 905.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK028 | Project_058_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | RFIs | Person_294 | 2017-05-24 | 2019-11-15 01:00 | 60% | 9.7869 | 5.8721 | Reduce | 30% | 9.7869 | 2.9361 | H2 | 2 | -- | TRUE | 905.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK028 | Project_058_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | RFIs | Person_294 | 2017-05-24 | 2019-11-15 01:00 | 60% | 9.7869 | 5.8721 | Reduce | 30% | 9.7869 | 2.9361 | H2 | 2 | -- | TRUE | 905.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 30% | 5.8725 | 1.7618 | Reduce | 10% | 5.8725 | 0.58725 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-08 | 2020-09-21 | 30% | 5.8725 | 1.7618 | Reduce | 10% | 5.8725 | 0.58725 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-08 01:00 | 2020-09-21 01:00 | 30% | 5.8725 | 1.7618 | Reduce | 10% | 5.8725 | 0.58725 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK058 | Project_065_RISK058 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance | Person_305 | 2016-09-07 23:00 | 2020-09-20 23:00 | 30% | 5.8725 | 1.7618 | Reduce | 10% | 5.8725 | 0.58725 | H2 | 2 | Stable | TRUE | 1474 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK028 | Project_058_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | RFIs | Person_294 | 2017-05-24 | 2019-11-15 01:00 | 60% | 9.7869 | 5.8721 | Reduce | 30% | 9.7869 | 2.9361 | H2 | 2 | -- | TRUE | 905.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK028 | Project_058_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | RFIs | Person_215 | 2017-05-24 | 2019-11-15 01:00 | 60% | 9.7869 | 5.8721 | Reduce | 30% | 9.7869 | 2.9361 | H2 | 2 | -- | TRUE | 905.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-001 | Project_028_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Porting software | Person_542 | 2014-03-23 | 2016-12-20 | 50% | 8.8098 | 4.4049 | Reduce | 8% | 7.4545 | 0.59636 | H2 | 2 | Stable | TRUE | 1003 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-001 | Project_028_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Porting software | Person_542 | 2014-03-23 | 2016-12-20 01:00 | 50% | 8.8098 | 4.4049 | Reduce | 8% | 7.4545 | 0.59636 | H2 | 2 | Stable | TRUE | 1003.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-001 | Project_028_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Porting software | Person_542 | 2014-03-23 | 2016-12-20 01:00 | 50% | 8.8098 | 4.4049 | Reduce | 8% | 7.4545 | 0.59636 | H2 | 2 | Stable | TRUE | 1003.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-001 | Project_028_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Porting software | Person_542 | 2014-03-23 | 2016-12-20 01:00 | 50% | 8.8098 | 4.4049 | Reduce | 8% | 7.4545 | 0.59636 | H2 | 2 | Stable | TRUE | 1003.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-048 | Project_026_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Maintainer Training | Person_525 | 2018-12-27 01:00 | 2018-12-27 01:00 | 90% | 2.9845 | 2.6861 | Reduce | 20% | 2.9845 | 0.59691 | H2 | 2 | -- | TRUE | 0 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-048 | Project_026_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Maintainer Training | Person_525 | 2018-12-27 01:00 | 2018-12-27 01:00 | 90% | 2.9845 | 2.6861 | Reduce | 20% | 2.9845 | 0.59691 | H2 | 2 | -- | TRUE | 0 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-048 | Project_026_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Maintainer Training | Person_525 | 2018-12-27 01:00 | 2018-12-27 01:00 | 90% | 2.9845 | 2.6861 | Reduce | 20% | 2.9845 | 0.59691 | H2 | 2 | -- | TRUE | 0 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-048 | Project_026_Risk-048 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Maintainer Training | Person_525 | 2018-12-27 01:00 | 2018-12-27 01:00 | 90% | 2.9845 | 2.6861 | Reduce | 20% | 2.9845 | 0.59691 | H2 | 2 | -- | TRUE | 0 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK272 | Project_024_RISK272 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Function implementation | Person_318 | 2016-03-23 | 2016-11-20 01:00 | 20% | 7.2921 | 1.4584 | Reduce | 20% | 2.9861 | 0.59722 | H2 | 2 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK028 | Project_058_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | RFIs | Person_215 | 2017-05-24 | 2019-11-15 01:00 | 60% | 9.7869 | 5.8721 | Reduce | 30% | 9.7869 | 2.9361 | H2 | 2 | -- | TRUE | 905.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Items damaged in transit | Person_387 | 2017-04-22 | 2018-11-20 01:00 | 30% | 29.3607 | 8.8082 | Reduce | 10% | 29.3607 | 2.9361 | H2 | 2 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK056 | Project_058_RISK056 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Doc Pack Content | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 70% | 4.6977 | 3.2884 | -- | 70% | 4.6977 | 3.2884 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK056 | Project_058_RISK056 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Doc Pack Content | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 70% | 4.6977 | 3.2884 | -- | 70% | 4.6977 | 3.2884 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK056 | Project_058_RISK056 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Doc Pack Content | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 70% | 4.6977 | 3.2884 | -- | 70% | 4.6977 | 3.2884 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK278 | Project_024_RISK278 | Threat | Project Contingency | Open | H2 | 2 |  | Operating systems haven't had security patches | Person_237 | 2017-01-21 01:00 | 2019-05-23 | 20% | 12.983 | 2.5966 | Accept | 20% | 16.8779 | 3.3756 | H2 | 2 | -- | TRUE | 851.9583 |  | 0 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK073 | Project_076_RISK073 | Threat | Project Contingency | Open | H2 | 2 |  | Competence Centre Level of effort | Person_152 | 2018-05-23 | 2019-10-22 01:00 | 80% | 4.3949 | 3.5159 | Accept | 80% | 4.3949 | 3.5159 | H2 | 2 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK073 | Project_076_RISK073 | Threat | Project Contingency | Open | H2 | 2 |  | Competence Centre Level of effort | Person_152 | 2018-05-23 | 2019-10-22 01:00 | 80% | 4.3949 | 3.5159 | Accept | 80% | 4.3949 | 3.5159 | H2 | 2 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK073 | Project_076_RISK073 | Threat | Project Contingency | Open | H2 | 2 |  | Competence Centre Level of effort | Person_152 | 2018-05-23 | 2019-10-22 01:00 | 80% | 4.3949 | 3.5159 | Accept | 80% | 4.3949 | 3.5159 | H2 | 2 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK073 | Project_076_RISK073 | Threat | Project Contingency | Open | H2 | 2 |  | Competence Centre Level of effort | Person_152 | 2018-05-23 | 2019-10-22 01:00 | 80% | 4.3949 | 3.5159 | Accept | 80% | 4.3949 | 3.5159 | H2 | 2 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-117 | Project_039_Risk-117 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Filters | Person_380 | 2015-01-21 01:00 | 2016-07-20 | 40% | 3.005 | 1.202 | Reduce | 20% | 3.005 | 0.601 | H3 | 3 | Stable | TRUE | 545.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-198 | Project_039_Risk-198 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | subsystems Testing | Person_224 | 2016-09-20 01:00 | 2017-02-19 01:00 | 40% | 6.01 | 2.404 | Reduce | 20% | 3.005 | 0.601 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-196 | Project_039_Risk-196 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integrated Assembly | Person_185 | 2016-12-21 01:00 | 2017-02-19 01:00 | 40% | 6.01 | 2.404 | Reduce | 20% | 3.005 | 0.601 | H3 | 3 | -- | TRUE | 60 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-12 01:00 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1025.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-12 01:00 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1025.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-12 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1025 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-11 23:00 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1024.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-11 22:00 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1024.9167 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-11 23:00 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1024.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-04-22 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1125 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-01-11 22:00 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1024.9167 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-04-22 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1125 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-04-22 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1125 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK083 | Project_065_RISK083 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power unit Control | Person_047 | 2016-03-23 | 2019-04-22 | 80% | 18.0459 | 14.4367 | Reduce | 20% | 3.0076 | 0.60153 | H3 | 3 | Stable | FALSE | 1125 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 20% | 18.6688 | 3.7338 | Accept | 20% | 18.6688 | 3.7338 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--116 | Project_100_Risk--116 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Reduction in T&S | Person_565 | 2018-08-22 01:00 | 2021-08-20 01:00 | 50% | 1.2076 | 0.60381 | Exploit | 50% | 1.2076 | 0.60381 | H3 | 3 | -- | FALSE | 1094 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 20% | 4.0291 | 0.80582 | Reduce | 15% | 4.0291 | 0.60437 | H2 | 2 | Improving | TRUE | 1537 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Mitigation of security vulnerabilities | Person_298 | 2016-05-23 | 2022-10-28 01:00 | 60% | 2.0146 | 1.2087 | Reduce | 30% | 2.0146 | 0.60437 | H1 | 1 | -- | TRUE | 2349.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 20% | 4.0291 | 0.80582 | Reduce | 15% | 4.0291 | 0.60437 | H2 | 2 | Improving | TRUE | 1537 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Mitigation of security vulnerabilities | Person_298 | 2016-05-23 | 2022-10-28 01:00 | 60% | 2.0146 | 1.2087 | Reduce | 30% | 2.0146 | 0.60437 | H1 | 1 | -- | TRUE | 2349.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 20% | 4.0291 | 0.80582 | Reduce | 15% | 4.0291 | 0.60437 | H2 | 2 | Improving | TRUE | 1537 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Mitigation of security vulnerabilities | Person_298 | 2016-05-23 | 2022-10-28 01:00 | 60% | 2.0146 | 1.2087 | Reduce | 30% | 2.0146 | 0.60437 | H1 | 1 | -- | TRUE | 2349.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 20% | 4.0291 | 0.80582 | Reduce | 15% | 4.0291 | 0.60437 | H2 | 2 | Improving | TRUE | 1537 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Mitigation of security vulnerabilities | Person_298 | 2016-05-23 | 2022-10-28 01:00 | 60% | 2.0146 | 1.2087 | Reduce | 30% | 2.0146 | 0.60437 | H1 | 1 | -- | TRUE | 2349.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 20% | 4.0291 | 0.80582 | Reduce | 15% | 4.0291 | 0.60437 | H2 | 2 | Improving | TRUE | 1537 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Mitigation of security vulnerabilities | Person_298 | 2016-05-23 | 2022-10-28 01:00 | 60% | 2.0146 | 1.2087 | Reduce | 30% | 2.0146 | 0.60437 | H1 | 1 | -- | TRUE | 2349.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 20% | 4.0291 | 0.80582 | Reduce | 15% | 4.0291 | 0.60437 | H2 | 2 | Improving | TRUE | 1537 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Mitigation of security vulnerabilities | Person_298 | 2016-05-23 | 2022-10-28 01:00 | 60% | 2.0146 | 1.2087 | Reduce | 30% | 2.0146 | 0.60437 | H1 | 1 | -- | TRUE | 2349.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 20% | 4.0291 | 0.80582 | Reduce | 15% | 4.0291 | 0.60437 | H2 | 2 | Improving | TRUE | 1537 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Mitigation of security vulnerabilities | Person_298 | 2016-05-23 | 2022-10-28 01:00 | 60% | 2.0146 | 1.2087 | Reduce | 30% | 2.0146 | 0.60437 | H1 | 1 | -- | TRUE | 2349.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-033 | Project_026_Risk-033 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Safety Case results in a level of ability below minimum requirement | Person_519 | 2014-11-21 01:00 | 2019-02-05 01:00 | 20% | 4.0291 | 0.80582 | Reduce | 15% | 4.0291 | 0.60437 | H2 | 2 | Improving | TRUE | 1537 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-073 | Project_026_Risk-073 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Mitigation of security vulnerabilities | Person_298 | 2016-05-23 | 2022-10-28 01:00 | 60% | 2.0146 | 1.2087 | Reduce | 30% | 2.0146 | 0.60437 | H1 | 1 | -- | TRUE | 2349.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK198 | Project_024_RISK198 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Spot Mode | Person_448 | 2016-06-23 | 2017-02-19 01:00 | 50% | 1.3502 | 0.67512 | Accept | 20% | 3.0415 | 0.6083 | H3 | 3 | Worsening | TRUE | 241.0417 |  | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-08-20 01:00 | 50% | 2.4768 | 1.2384 | -- | 50% | 1.2167 | 0.60833 | H2 | 2 | Stable | TRUE | 181 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-09-19 01:00 | 50% | 2.4768 | 1.2384 | -- | 50% | 1.2167 | 0.60833 | H2 | 2 | Improving | TRUE | 211 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-10-21 01:00 | 50% | 2.4768 | 1.2384 | -- | 50% | 1.2167 | 0.60833 | H2 | 2 | Improving | TRUE | 243 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-10-21 01:00 | 50% | 2.4768 | 1.2384 | -- | 50% | 1.2167 | 0.60833 | H2 | 2 | Improving | TRUE | 243 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-10-21 01:00 | 50% | 2.4768 | 1.2384 | -- | 50% | 1.2167 | 0.60833 | H2 | 2 | Improving | TRUE | 243 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-10-21 01:00 | 50% | 2.4768 | 1.2384 | -- | 50% | 1.2167 | 0.60833 | H2 | 2 | Improving | TRUE | 243 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-007 | Project_077_T-007 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rig Failure or Damage | Person_092 | 2018-09-21 01:00 | 2020-12-08 01:00 | 30% | 2.033 | 0.6099 | Reduce | 30% | 2.033 | 0.6099 | H2 | 2 | Stable | TRUE | 809 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 | 2016-11-19 | 5% | 12.1982 | 0.60991 | Accept | 5% | 12.1982 | 0.60991 | H3 | 3 | Stable | FALSE | 394 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 5% | 12.1982 | 0.60991 | Accept | 5% | 12.1982 | 0.60991 | H3 | 3 | Stable | FALSE | 394 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 5% | 12.1982 | 0.60991 | Accept | 5% | 12.1982 | 0.60991 | H3 | 3 | Stable | FALSE | 394 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 5% | 12.1982 | 0.60991 | Accept | 5% | 12.1982 | 0.60991 | H3 | 3 | Stable | FALSE | 394 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 5% | 12.1982 | 0.60991 | Accept | 5% | 12.1982 | 0.60991 | H3 | 3 | Stable | FALSE | 394 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-10-22 01:00 | 2016-11-19 01:00 | 5% | 12.1982 | 0.60991 | Accept | 5% | 12.1982 | 0.60991 | H3 | 3 | Stable | FALSE | 394 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-11-21 01:00 | 2017-03-21 01:00 | 5% | 12.1982 | 0.60991 | Accept | 5% | 12.1982 | 0.60991 | H3 | 3 | Stable | FALSE | 486 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-015 | Project_028_Risk-015 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | STANDARDS Compliance | Person_499 | 2015-11-21 01:00 | 2017-03-21 01:00 | 5% | 12.1982 | 0.60991 | Accept | 5% | 12.1982 | 0.60991 | H3 | 3 | Stable | FALSE | 486 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 20% | 18.6688 | 3.7338 | Accept | 20% | 18.6688 | 3.7338 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 20% | 18.6688 | 3.7338 | Accept | 20% | 18.6688 | 3.7338 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 20% | 18.6688 | 3.7338 | Accept | 20% | 18.6688 | 3.7338 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-149 | Project_020_Risk-149 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs to be returned to UK | Person_703 | 2016-12-21 01:00 | 2017-11-19 01:00 | 20% | 18.6688 | 3.7338 | Accept | 20% | 18.6688 | 3.7338 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK039 | Project_017_RISK039 | Threat | Project Contingency | Open | H2 | 2 |  | Loss of Key knowledge | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 40% | 12.7219 | 5.0887 | Accept | 30% | 12.7219 | 3.8166 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_470 | 2010-04-19 | 2017-01-19 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2467 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_470 | 2010-04-19 | 2017-01-18 23:00 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2466.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_021 | 2010-04-19 | 2017-01-19 01:00 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2467.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-094 | Project_011_Risk-094 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional effort needed for PM and SEM required following Release | Person_147 | 2015-05-24 | 2018-08-21 | 70% | 0.88815 | 0.62171 | Accept | 70% | 0.88815 | 0.62171 | H2 | 2 | -- | TRUE | 1185 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-094 | Project_011_Risk-094 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional effort needed for PM and SEM required following Release | Person_147 | 2015-05-24 | 2018-08-21 | 70% | 0.88815 | 0.62171 | Accept | 70% | 0.88815 | 0.62171 | H2 | 2 | -- | TRUE | 1185 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_021 | 2010-04-19 | 2017-01-19 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2467 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-016 | Project_062_Risk-016 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier Component Unavailability | Person_664 | 2017-07-21 | 2018-12-22 01:00 | 30% | 4.183 | 1.2549 | Reduce | 15% | 4.183 | 0.62744 | H3 | 3 | Stable | FALSE | 519.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_021 | 2010-04-19 | 2017-01-19 01:00 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2467.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2679.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2679.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2679.0417 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2679.0417 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2017-08-19 01:00 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2679.0417 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-196 | Project_039_Risk-196 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integrated Assembly | Person_185 | 2016-12-21 01:00 | 2017-02-19 01:00 | 40% | 2.4183 | 0.96733 | Reduce | 30% | 2.0964 | 0.62891 | H3 | 3 | -- | TRUE | 60 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-196 | Project_039_Risk-196 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integrated Assembly | Person_185 | 2016-12-21 01:00 | 2017-02-19 01:00 | 40% | 2.4183 | 0.96733 | Reduce | 30% | 2.0964 | 0.62891 | H3 | 3 | -- | TRUE | 60 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-196 | Project_039_Risk-196 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integrated Assembly | Person_185 | 2016-12-21 01:00 | 2017-02-19 01:00 | 40% | 2.4183 | 0.96733 | Reduce | 30% | 2.0964 | 0.62891 | H3 | 3 | -- | TRUE | 60 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-196 | Project_039_Risk-196 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integrated Assembly | Person_185 | 2016-12-21 01:00 | 2017-02-19 01:00 | 40% | 2.4183 | 0.96733 | Reduce | 30% | 2.0964 | 0.62891 | H3 | 3 | -- | TRUE | 60 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-196 | Project_039_Risk-196 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integrated Assembly | Person_185 | 2016-12-21 | 2017-02-19 | 40% | 2.4183 | 0.96733 | Reduce | 30% | 2.0964 | 0.62891 | H3 | 3 | -- | TRUE | 60 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-196 | Project_039_Risk-196 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integrated Assembly | Person_185 | 2016-12-21 01:00 | 2017-02-19 01:00 | 40% | 2.4183 | 0.96733 | Reduce | 30% | 2.0964 | 0.62891 | H3 | 3 | -- | TRUE | 60 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-196 | Project_039_Risk-196 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Integrated Assembly | Person_185 | 2016-12-21 01:00 | 2017-02-19 01:00 | 40% | 2.4183 | 0.96733 | Reduce | 30% | 2.0964 | 0.62891 | H3 | 3 | -- | TRUE | 60 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R58 | Project_021_Risk-R58 | Threat | Project Contingency | Open | H2 | 2 |  | Refurbishment of equipment loaned for Testing or Trials. | Person_207 | 2010-04-19 | 2018-03-21 | 40% | 19.1897 | 7.6759 | Reduce | 20% | 19.1897 | 3.8379 | H2 | 2 | Stable | TRUE | 2893 |  | 1 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H2 | 2 |  | sub-System Cleanliness | Person_324 | 2017-06-23 | 2018-09-20 01:00 | 75% | 13.3102 | 9.9826 | Reduce | 30% | 13.3102 | 3.9931 | H2 | 2 | -- | TRUE | 454.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H2 | 2 |  | sub-System Cleanliness | Person_324 | 2017-06-23 | 2018-09-20 01:00 | 75% | 13.3102 | 9.9826 | Reduce | 30% | 13.3102 | 3.9931 | H2 | 2 | -- | TRUE | 454.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H2 | 2 |  | sub-System Cleanliness | Person_324 | 2017-06-23 | 2018-09-20 01:00 | 75% | 13.3102 | 9.9826 | Reduce | 30% | 13.3102 | 3.9931 | H2 | 2 | -- | TRUE | 454.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H2 | 2 |  | sub-System Cleanliness | Person_324 | 2017-06-23 | 2018-09-20 01:00 | 75% | 13.3102 | 9.9826 | Reduce | 30% | 13.3102 | 3.9931 | H2 | 2 | -- | TRUE | 454.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK117 | Project_066_RISK117 | Threat | Project Contingency | Open | H2 | 2 |  | Equipment qualification failures | Person_068 | 2019-03-24 | 2019-11-21 01:00 | 20% | 20.0357 | 4.0071 | Accept | 20% | 20.0357 | 4.0071 | H2 | 2 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 2 |  | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 2 |  | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 2 |  | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 2 |  | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 2 |  | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 2 |  | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 2 |  | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 2 |  | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-147 | Project_020_Risk-147 | Threat | Project Contingency | Open | H2 | 2 |  | Component taking longer to refurbish in country | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-150 | Project_020_Risk-150 | Threat | Project Contingency | Open | H2 | 2 |  | Power supply Test Environment | Person_248 | 2016-10-21 01:00 | 2017-05-22 | 60% | 6.7477 | 4.0486 | Reduce | 60% | 6.7477 | 4.0486 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-134 | Project_030_Risk-134 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Costs | Person_518 | 2014-11-21 01:00 | 2016-05-22 | 40% | 24.6132 | 9.8453 | -- | 40% | 10.541 | 4.2164 | H2 | 2 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-11-19 01:00 | 70% | 24.8225 | 17.3758 | Reduce | 48% | 8.951 | 4.2965 | H2 | 2 | Stable | TRUE | 1672.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-11-19 01:00 | 70% | 24.8225 | 17.3758 | Reduce | 48% | 8.951 | 4.2965 | H2 | 2 | Stable | TRUE | 1672.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-11-19 01:00 | 70% | 24.8225 | 17.3758 | Reduce | 48% | 8.951 | 4.2965 | H2 | 2 | Stable | TRUE | 1672.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-11-19 01:00 | 70% | 24.8225 | 17.3758 | Reduce | 48% | 8.951 | 4.2965 | H2 | 2 | Stable | TRUE | 1672.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK026 | Project_058_RISK026 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_294 | 2017-06-23 | 2019-11-07 01:00 | 80% | 31.3181 | 25.0545 | Reduce | 55% | 7.8295 | 4.3062 | H2 | 2 | -- | TRUE | 867.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK026 | Project_058_RISK026 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_294 | 2017-06-23 | 2019-11-07 01:00 | 80% | 31.3181 | 25.0545 | Reduce | 55% | 7.8295 | 4.3062 | H2 | 2 | -- | TRUE | 867.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK026 | Project_058_RISK026 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_294 | 2017-06-23 | 2019-11-07 01:00 | 80% | 31.3181 | 25.0545 | Reduce | 55% | 7.8295 | 4.3062 | H2 | 2 | -- | TRUE | 867.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK026 | Project_058_RISK026 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_294 | 2017-06-23 | 2019-11-07 01:00 | 80% | 31.3181 | 25.0545 | Reduce | 55% | 7.8295 | 4.3062 | H2 | 2 | -- | TRUE | 867.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_216 | 2014-02-20 01:00 | 2017-05-22 | 30% | 1.54 | 0.46201 | Reduce | 40% | 1.5914 | 0.63655 | H2 | 2 | Stable | TRUE | 1186.9583 |  | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2018-05-22 | 30% | 1.54 | 0.46201 | Reduce | 40% | 1.5914 | 0.63655 | H2 | 2 | Stable | TRUE | 485.9583 |  | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-001 | Project_029_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Sub-system FPGA | Person_216 | 2017-01-21 01:00 | 2017-08-20 01:00 | 30% | 1.54 | 0.46201 | Reduce | 40% | 1.5914 | 0.63655 | H2 | 2 | Stable | TRUE | 211 |  | 0 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK026 | Project_058_RISK026 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_294 | 2017-06-23 | 2019-11-07 01:00 | 80% | 31.3181 | 25.0545 | Reduce | 55% | 7.8295 | 4.3062 | H2 | 2 | -- | TRUE | 867.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK010 | Project_081_RISK010 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Increased material lead times for Spares | Person_649 | 2017-09-27 01:00 | 2019-05-16 | 10% | 6.3707 | 0.63707 | Reduce | 10% | 6.3707 | 0.63707 | H3 | 3 | Stable | TRUE | 595.9583 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK026 | Project_058_RISK026 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_294 | 2017-06-23 | 2019-11-07 01:00 | 80% | 31.3181 | 25.0545 | Reduce | 55% | 7.8295 | 4.3062 | H2 | 2 | -- | TRUE | 867.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1007 | Project_091_RISK1007 | Threat | Project Contingency | Open | H2 | 2 | Customers | Technical and Documentation Queries | Person_557 | 2018-08-22 01:00 | 2020-11-19 01:00 | 70% | 1.2791 | 0.89536 | Reduce | 50% | 1.2791 | 0.63954 | H2 | 2 | -- | TRUE | 820 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1007 | Project_091_RISK1007 | Threat | Project Contingency | Open | H2 | 2 | Customers | Technical and Documentation Queries | Person_557 | 2018-09-21 01:00 | 2020-11-19 01:00 | 70% | 1.2791 | 0.89536 | Reduce | 50% | 1.2791 | 0.63954 | H2 | 2 | -- | TRUE | 790 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-20 01:00 | 2018-11-20 01:00 | 15% | 4.3731 | 0.65596 | Reduce | 10% | 6.431 | 0.6431 | H3 | 3 | -- | FALSE | 730 |  | 0 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-20 01:00 | 2018-11-20 01:00 | 15% | 4.3731 | 0.65596 | Reduce | 10% | 6.431 | 0.6431 | H3 | 3 | Stable | FALSE | 730 |  | 0 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-20 | 2018-11-20 | 15% | 4.3731 | 0.65596 | Reduce | 10% | 6.431 | 0.6431 | H3 | 3 | Stable | FALSE | 730 |  | 0 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-19 23:00 | 2018-11-19 23:00 | 15% | 4.3731 | 0.65596 | Reduce | 10% | 6.431 | 0.6431 | H3 | 3 | Stable | FALSE | 730 |  | 0 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-19 23:00 | 2018-11-19 23:00 | 15% | 4.3731 | 0.65596 | Reduce | 10% | 6.431 | 0.6431 | H3 | 3 | Stable | FALSE | 730 |  | 0 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-19 23:00 | 2018-11-19 23:00 | 15% | 4.3731 | 0.65596 | Reduce | 10% | 6.431 | 0.6431 | H3 | 3 | Stable | FALSE | 730 |  | 0 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK005 | Project_041_RISK005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Supplier revert to original component (Supplier NRE) | Person_468 | 2016-11-19 22:00 | 2018-11-19 22:00 | 15% | 4.3731 | 0.65596 | Reduce | 10% | 6.431 | 0.6431 | H3 | 3 | Stable | FALSE | 730 |  | 0 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 2.5834 | 0.64585 | Accept | 25% | 2.5834 | 0.64585 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 2.5834 | 0.64585 | Accept | 25% | 2.5834 | 0.64585 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 2.5834 | 0.64585 | Accept | 25% | 2.5834 | 0.64585 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 2.5834 | 0.64585 | Accept | 25% | 2.5834 | 0.64585 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 2.5834 | 0.64585 | Accept | 25% | 2.5834 | 0.64585 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 2.5834 | 0.64585 | Accept | 25% | 2.5834 | 0.64585 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk005 | Project_042_Risk005 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Repairs | Person_455 | 2016-05-23 | 2020-05-23 | 25% | 2.5834 | 0.64585 | Accept | 25% | 2.5834 | 0.64585 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-001 | Project_077_T-001 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Increased Interface changes | Person_544 | 2018-07-22 | 2018-10-20 01:00 | 50% | 2.1566 | 1.0783 | Transfer | 30% | 2.1566 | 0.64697 | H2 | 2 | Stable | TRUE | 90.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--107 | Project_100_Risk--107 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supplier Costs higher than expected | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 40% | 1.6239 | 0.64955 | -- | 40% | 1.6239 | 0.64955 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK026 | Project_058_RISK026 | Threat | Financial Contingency | Open | H2 | 2 |  | Liquidated Damages | Person_294 | 2017-06-23 | 2019-11-07 01:00 | 80% | 31.3181 | 25.0545 | Reduce | 55% | 7.8295 | 4.3062 | H2 | 2 | -- | TRUE | 867.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-27 | Project_022_RISK-27 | Threat | Project Contingency | Open | H2 | 2 |  | Provision for future emerging risks | Person_703 | 2015-02-21 01:00 | 2016-11-19 01:00 | 100% | 2.3975 | 2.3975 | Accept | 100% | 4.3118 | 4.3118 | H2 | 2 | -- | TRUE | 637 |  | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-27 | Project_022_RISK-27 | Threat | Project Contingency | Open | H2 | 2 |  | Provision for future emerging risks | Person_703 | 2015-02-21 01:00 | 2016-11-19 01:00 | 100% | 2.3975 | 2.3975 | Accept | 100% | 4.3118 | 4.3118 | H2 | 2 | -- | TRUE | 637 |  | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-074 | Project_030_Risk-074 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Current operational needs and understanding | Person_639 | 2013-10-21 01:00 | 2014-05-21 | 20% | 21.9604 | 4.3921 | -- | 20% | 21.9604 | 4.3921 | H2 | 2 | -- | TRUE | 211.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-074 | Project_030_Risk-074 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Current operational needs and understanding | Person_639 | 2013-10-21 01:00 | 2014-05-21 | 20% | 21.9604 | 4.3921 | -- | 20% | 21.9604 | 4.3921 | H2 | 2 | -- | TRUE | 211.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-074 | Project_030_Risk-074 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Current operational needs and understanding | Person_639 | 2013-10-21 01:00 | 2014-05-21 | 20% | 21.9604 | 4.3921 | -- | 20% | 21.9604 | 4.3921 | H2 | 2 | -- | TRUE | 211.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-074 | Project_030_Risk-074 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Current operational needs and understanding | Person_639 | 2013-10-21 | 2014-05-21 | 20% | 21.9604 | 4.3921 | -- | 20% | 21.9604 | 4.3921 | H2 | 2 | -- | TRUE | 212 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-074 | Project_030_Risk-074 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Current operational needs and understanding | Person_639 | 2013-10-21 01:00 | 2014-05-21 | 20% | 21.9604 | 4.3921 | -- | 20% | 21.9604 | 4.3921 | H2 | 2 | -- | TRUE | 211.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-074 | Project_030_Risk-074 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Current operational needs and understanding | Person_639 | 2013-10-21 01:00 | 2014-05-21 | 20% | 21.9604 | 4.3921 | -- | 20% | 21.9604 | 4.3921 | H2 | 2 | -- | TRUE | 211.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-074 | Project_030_Risk-074 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Current operational needs and understanding | Person_639 | 2013-10-21 01:00 | 2014-05-21 | 20% | 21.9604 | 4.3921 | -- | 20% | 21.9604 | 4.3921 | H2 | 2 | -- | TRUE | 211.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-074 | Project_030_Risk-074 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Current operational needs and understanding | Person_639 | 2013-10-21 | 2014-05-21 | 20% | 21.9604 | 4.3921 | -- | 20% | 21.9604 | 4.3921 | H2 | 2 | -- | TRUE | 212 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Open | H2 | 2 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-02-19 01:00 | 50% | 11.1812 | 5.5906 | Reduce | 40% | 11.1812 | 4.4725 | H2 | 2 | -- | TRUE | 637.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Open | H2 | 2 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-04-21 | 50% | 11.1812 | 5.5906 | Reduce | 40% | 11.1812 | 4.4725 | H2 | 2 | -- | TRUE | 698 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Open | H2 | 2 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-04-21 | 50% | 11.1812 | 5.5906 | Reduce | 40% | 11.1812 | 4.4725 | H2 | 2 | -- | TRUE | 698 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Open | H2 | 2 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-04-21 | 50% | 11.1812 | 5.5906 | Reduce | 40% | 11.1812 | 4.4725 | H2 | 2 | -- | TRUE | 698 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Open | H2 | 2 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-04-21 | 50% | 11.1812 | 5.5906 | Reduce | 40% | 11.1812 | 4.4725 | H2 | 2 | -- | TRUE | 698 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK069 | Project_065_RISK069 | Threat | Project Contingency | Open | H2 | 2 |  | Transfer of Design Customer for the complete system | Person_661 | 2016-05-23 | 2018-04-21 | 50% | 11.1812 | 5.5906 | Reduce | 40% | 11.1812 | 4.4725 | H2 | 2 | -- | TRUE | 698 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 30% | 14.9935 | 4.498 | Reduce | 30% | 14.9935 | 4.498 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 30% | 14.9935 | 4.498 | Reduce | 30% | 14.9935 | 4.498 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 30% | 14.9935 | 4.498 | Reduce | 30% | 14.9935 | 4.498 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 30% | 14.9935 | 4.498 | Reduce | 30% | 14.9935 | 4.498 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-148 | Project_020_Risk-148 | Threat | Project Contingency | Open | H2 | 2 |  | Component needs non-available items | Person_703 | 2016-12-21 01:00 | 2017-05-22 | 30% | 14.9935 | 4.498 | Reduce | 30% | 14.9935 | 4.498 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK017 | Project_058_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier late deliveries | Person_294 | 2017-12-29 01:00 | 2019-08-21 01:00 | 80% | 9.7869 | 7.8295 | Reduce | 50% | 9.7869 | 4.8934 | H2 | 2 | -- | TRUE | 600 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK017 | Project_058_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier late deliveries | Person_294 | 2017-12-29 01:00 | 2019-08-21 01:00 | 80% | 9.7869 | 7.8295 | Reduce | 50% | 9.7869 | 4.8934 | H2 | 2 | -- | TRUE | 600 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-020 | Project_023_Risk-020 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Installation & Acceptance - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.81688 | 0.6535 | Exploit | 80% | 0.81688 | 0.6535 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-020 | Project_023_Risk-020 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Installation & Acceptance - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.81688 | 0.6535 | Exploit | 80% | 0.81688 | 0.6535 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-020 | Project_023_Risk-020 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Installation & Acceptance - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.81688 | 0.6535 | Exploit | 80% | 0.81688 | 0.6535 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-020 | Project_023_Risk-020 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Installation & Acceptance - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 0.81688 | 0.6535 | Exploit | 80% | 0.81688 | 0.6535 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK017 | Project_058_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier late deliveries | Person_511 | 2017-12-29 01:00 | 2019-08-21 01:00 | 70% | 9.7869 | 6.8508 | Reduce | 50% | 9.7869 | 4.8934 | H2 | 2 | -- | TRUE | 600 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK017 | Project_058_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier late deliveries | Person_511 | 2017-12-29 01:00 | 2019-08-21 01:00 | 70% | 9.7869 | 6.8508 | Reduce | 50% | 9.7869 | 4.8934 | H2 | 2 | -- | TRUE | 600 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK017 | Project_058_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier late deliveries | Person_511 | 2017-12-29 01:00 | 2019-08-21 01:00 | 70% | 9.7869 | 6.8508 | Reduce | 50% | 9.7869 | 4.8934 | H2 | 2 | -- | TRUE | 600 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK017 | Project_058_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier late deliveries | Person_511 | 2017-12-29 01:00 | 2019-08-21 01:00 | 70% | 9.7869 | 6.8508 | Reduce | 50% | 9.7869 | 4.8934 | H2 | 2 | -- | TRUE | 600 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK017 | Project_058_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier late deliveries | Person_511 | 2017-12-29 01:00 | 2019-08-21 01:00 | 70% | 9.7869 | 6.8508 | Reduce | 50% | 9.7869 | 4.8934 | H2 | 2 | -- | TRUE | 600 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 40% | 19.8087 | 7.9235 | Reduce | 25% | 19.8087 | 4.9522 | H2 | 2 | Improving | TRUE | 819 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 40% | 19.8087 | 7.9235 | Reduce | 25% | 19.8087 | 4.9522 | H2 | 2 | Improving | TRUE | 819 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK006 | Project_058_RISK006 | Threat | Project Contingency | Open | H2 | 2 |  | Customer find issues with delivered parts or documentation | Person_294 | 2017-05-23 | 2019-08-20 | 40% | 19.8087 | 7.9235 | Reduce | 25% | 19.8087 | 4.9522 | H2 | 2 | Improving | TRUE | 819 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_207 | 2013-09-20 01:00 | 2017-01-20 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1218 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 | 2017-01-20 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1218 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-01-20 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1218 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-04-21 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1308.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK001 | Project_099_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Increase in material lead time | Person_002 | 2018-04-25 | 2020-03-22 | 80% | 1.309 | 1.0472 | Reduce | 50% | 1.309 | 0.65451 | H2 | 2 | -- | TRUE | 697 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK199 | Project_024_RISK199 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Strip Mode | Person_448 | 2016-06-23 | 2017-01-19 01:00 | 30% | 1.3502 | 0.40507 | Accept | 30% | 2.2071 | 0.66213 | H2 | 2 | Stable | TRUE | 210.0417 |  | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-19 01:00 | 70% | 1.3243 | 0.92704 | Reduce | 50% | 1.3243 | 0.66217 | H1 | 1 | -- | TRUE | 162.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R037 | Project_021_Risk-R037 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Config Qualification delays due to equipment/ hardware unreliability | Person_207 | 2016-08-10 | 2016-09-19 01:00 | 50% | 1.3243 | 0.66217 | Reduce | 50% | 1.3243 | 0.66217 | H1 | 1 | -- | TRUE | 40.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-19 | 70% | 1.3243 | 0.92704 | Reduce | 50% | 1.3243 | 0.66217 | H1 | 1 | Stable | TRUE | 162 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-19 01:00 | 70% | 1.3243 | 0.92704 | Reduce | 50% | 1.3243 | 0.66217 | H1 | 1 | Stable | TRUE | 162.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 70% | 1.3243 | 0.92704 | Reduce | 50% | 1.3243 | 0.66217 | H1 | 1 | Stable | TRUE | 172.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-01-29 01:00 | 70% | 1.3243 | 0.92704 | Reduce | 50% | 1.3243 | 0.66217 | H1 | 1 | Stable | TRUE | 172.0417 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 10% | 6.6217 | 0.66217 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 10% | 6.6217 | 0.66217 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 10% | 6.6217 | 0.66217 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 | 2017-11-20 | 10% | 6.6217 | 0.66217 | -- | 10% | 6.6217 | 0.66217 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 10% | 6.6217 | 0.66217 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 10% | 6.6217 | 0.66217 | H3 | 3 | -- | FALSE | 431 |  | 1 | 1 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 10% | 6.6217 | 0.66217 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-04-21 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1308.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-04-21 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1308.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK070 | Project_076_RISK070 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Component needs to be refigured | Person_484 | 2018-05-23 | 2019-09-26 01:00 | 40% | 1.6584 | 0.66337 | Accept | 40% | 1.6584 | 0.66337 | H2 | 2 | -- | TRUE | 491.0417 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2016-07-20 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1033.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2016-07-20 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1033.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2016-07-20 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1033.9583 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 | 2016-07-20 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1034 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Rework required following integration of Customer System | Person_140 | 2015-12-22 01:00 | 2016-08-19 01:00 | 50% | 1.3291 | 0.66455 | Reduce | 50% | 1.3291 | 0.66455 | H1 | 1 | Stable | TRUE | 241 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-010 | Project_011_Risk-010 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Rework required following integration of Customer System | Person_140 | 2015-12-22 01:00 | 2016-08-19 01:00 | 50% | 1.3291 | 0.66455 | Reduce | 50% | 1.3291 | 0.66455 | H1 | 1 | Stable | TRUE | 241 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK018 | Project_029_RISK018 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Delays to platform Build Programme | Person_694 | 2018-10-22 01:00 | 2021-07-20 | 60% | 1.1122 | 0.66735 | Accept | 60% | 1.1122 | 0.66735 | H1 | 1 | Worsening | TRUE | 1001.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-21 01:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 967.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-21 01:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 967.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-21 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 968 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-21 01:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 967.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-20 23:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 968.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-20 22:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 968.0833 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-21 01:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 967.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-20 22:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 968.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-21 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 968 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-21 01:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 967.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK101 | Project_065_RISK101 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Product-line Component Drops Do Not Meet Dependencies | Person_550 | 2016-08-20 23:00 | 2019-04-16 | 50% | 4.476 | 2.238 | Reduce | 30% | 2.2362 | 0.67087 | H3 | 3 | -- | TRUE | 968.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 8% | 8.3972 | 0.67177 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 8% | 8.3972 | 0.67177 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 8% | 8.3972 | 0.67177 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 8% | 8.3972 | 0.67177 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 8% | 8.3972 | 0.67177 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 8% | 8.3972 | 0.67177 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2015-07-31 | 2017-05-15 | 35% | 0.85557 | 0.29945 | Reduce | 35% | 1.9208 | 0.67227 | H2 | 2 | Stable | TRUE | 654 |  | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 35% | 0.85557 | 0.29945 | Reduce | 35% | 1.9208 | 0.67227 | H2 | 2 | Stable | TRUE | 298 |  | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-109 | Project_029_Risk-109 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Software Build issues post-Factory Acceptance Test [System + Platform] | Person_102 | 2017-07-21 | 2018-05-15 | 35% | 0.85557 | 0.29945 | Reduce | 35% | 1.9208 | 0.67227 | H2 | 2 | Stable | TRUE | 298 |  | 0 | 1 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2016-05-23 | 2019-08-21 01:00 | 10% | 6.7334 | 0.67334 | Reduce | 10% | 6.7334 | 0.67334 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2016-05-23 | 2019-08-21 01:00 | 10% | 6.7334 | 0.67334 | Reduce | 10% | 6.7334 | 0.67334 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2016-05-23 | 2019-08-21 01:00 | 10% | 6.7334 | 0.67334 | Reduce | 10% | 6.7334 | 0.67334 | H2 | 2 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-013 | Project_077_T-013 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | More customer failures than anticipated | Person_544 | 2019-07-22 | 2020-02-21 01:00 | 20% | 3.3809 | 0.67617 | Reduce | 20% | 3.3809 | 0.67617 | H3 | 3 | Stable | FALSE | 214.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK022 | Project_042_RISK022 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence May to April | Person_455 | 2017-09-20 01:00 | 2018-09-20 01:00 | 20% | 4.6971 | 0.93941 | Accept | 18% | 3.7576 | 0.67638 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-038 | Project_028_Risk-038 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Network Installation Features | Person_542 | 2015-04-08 | 2017-08-20 | 30% | 2.2788 | 0.68363 | Accept | 30% | 2.2788 | 0.68363 | H2 | 2 | Stable | TRUE | 865 |  | 1 | 1 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK012 | Project_079_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer require additional support | Person_683 | 2017-02-20 01:00 | 2020-05-22 | 5% | 13.6897 | 0.68448 | Avoid | 5% | 13.6897 | 0.68448 | H3 | 3 | Improving | FALSE | 1186.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--102 | Project_100_Risk--102 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Demands but not provisioned | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 30% | 2.2868 | 0.68604 | Accept | 30% | 2.2868 | 0.68604 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-20 | 2020-11-20 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-19 22:00 | 2020-11-19 22:00 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-20 | 2020-11-20 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK077 | Project_065_RISK077 | Threat | Management Contingency | Open | H3 | 3 | Business Strategy and Objectives | Post design manufacturing time increases: complexity of the build not known at this time. | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 25% | 13.8434 | 3.4609 | Reduce | 10% | 6.8811 | 0.68811 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 13.7953 | 4.1386 | Reduce | 5% | 13.7953 | 0.68977 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 13.7953 | 4.1386 | Reduce | 5% | 13.7953 | 0.68977 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 13.7953 | 4.1386 | Reduce | 5% | 13.7953 | 0.68977 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 13.7953 | 4.1386 | Reduce | 5% | 13.7953 | 0.68977 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 13.7953 | 4.1386 | Reduce | 5% | 13.7953 | 0.68977 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 13.7953 | 4.1386 | Reduce | 5% | 13.7953 | 0.68977 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 13.7953 | 4.1386 | Reduce | 5% | 13.7953 | 0.68977 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-193 | Project_027_Risk-193 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | A greater number of arising technical queries | Person_110 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 13.7953 | 4.1386 | Reduce | 5% | 13.7953 | 0.68977 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-006 | Project_021_Risk-006 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Acceptance proves to be more difficult than anticipated | Person_766 | 2013-09-20 01:00 | 2017-12-17 01:00 | 60% | 12.6474 | 7.5885 | Reduce | 40% | 12.6474 | 5.059 | H2 | 2 | Stable | TRUE | 1549 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2018-04-21 | 50% | 53.244 | 26.622 | Reduce | 10% | 53.244 | 5.3244 | H2 | 2 | -- | TRUE | 645 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2018-04-21 | 50% | 53.244 | 26.622 | Reduce | 10% | 53.244 | 5.3244 | H2 | 2 | -- | TRUE | 645 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2018-04-21 | 50% | 53.244 | 26.622 | Reduce | 10% | 53.244 | 5.3244 | H2 | 2 | -- | TRUE | 645 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2018-04-21 | 50% | 53.244 | 26.622 | Reduce | 10% | 53.244 | 5.3244 | H2 | 2 | -- | TRUE | 645 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2018-04-21 | 50% | 53.244 | 26.622 | Reduce | 10% | 53.244 | 5.3244 | H2 | 2 | -- | TRUE | 645 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2018-04-21 | 50% | 53.244 | 26.622 | Reduce | 10% | 53.244 | 5.3244 | H2 | 2 | -- | TRUE | 645 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2018-04-21 | 50% | 53.244 | 26.622 | Reduce | 10% | 53.244 | 5.3244 | H2 | 2 | -- | TRUE | 645 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK023 | Project_065_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Component supplier fails to delivery to acceptable quality | Person_305 | 2016-07-15 | 2018-04-21 | 50% | 53.244 | 26.622 | Reduce | 10% | 53.244 | 5.3244 | H2 | 2 | -- | TRUE | 645 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-27 | Project_022_RISK-27 | Threat | Project Contingency | Open | H2 | 2 |  | Provision for future emerging risks | Person_703 | 2015-02-21 01:00 | 2016-09-19 01:00 | 100% | 2.3975 | 2.3975 | Accept | 100% | 5.4295 | 5.4295 | H2 | 2 | -- | TRUE | 576 |  | 0 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-021 | Project_026_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Customer may reject acceptance evidence | Person_607 | 2015-09-30 01:00 | 2022-10-28 01:00 | 50% | 2.798 | 1.399 | Reduce | 25% | 2.798 | 0.6995 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-021 | Project_026_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Customer may reject acceptance evidence | Person_607 | 2015-09-30 01:00 | 2022-10-28 01:00 | 50% | 2.798 | 1.399 | Reduce | 25% | 2.798 | 0.6995 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-021 | Project_026_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Customer may reject acceptance evidence | Person_607 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 2.798 | 0.6995 | Reduce | 25% | 2.798 | 0.6995 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-021 | Project_026_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Customer may reject acceptance evidence | Person_607 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 2.798 | 0.6995 | Reduce | 25% | 2.798 | 0.6995 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-021 | Project_026_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Customer may reject acceptance evidence | Person_607 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 2.798 | 0.6995 | Reduce | 25% | 2.798 | 0.6995 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-021 | Project_026_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Customer may reject acceptance evidence | Person_607 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 2.798 | 0.6995 | Reduce | 25% | 2.798 | 0.6995 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-021 | Project_026_Risk-021 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Customer may reject acceptance evidence | Person_607 | 2015-09-30 01:00 | 2022-10-28 01:00 | 25% | 2.798 | 0.6995 | Reduce | 25% | 2.798 | 0.6995 | H2 | 2 | -- | TRUE | 2585 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK245 | Project_024_RISK245 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Safety Team (Staff) | Person_119 | 2017-05-23 | 2017-11-19 01:00 | 30% | 2.3722 | 0.71165 | Accept | 30% | 2.3722 | 0.71165 | H1 | 1 | -- | TRUE | 180.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-05-16 | 50% | 26.9674 | 13.4837 | Avoid | 2.65% | 26.9674 | 0.71464 | H2 | 2 | Worsening | TRUE | 327 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-05-16 | 50% | 26.9674 | 13.4837 | Avoid | 2.65% | 26.9674 | 0.71464 | H2 | 2 | Worsening | TRUE | 327 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 30% | 4.7676 | 1.4303 | Reduce | 15% | 4.7676 | 0.71514 | H2 | 2 | Stable | TRUE | 1610.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 30% | 4.7676 | 1.4303 | Reduce | 15% | 4.7676 | 0.71514 | H2 | 2 | Stable | TRUE | 1610.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 30% | 4.7676 | 1.4303 | Reduce | 15% | 4.7676 | 0.71514 | H2 | 2 | Stable | TRUE | 1610.9583 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 30% | 4.7676 | 1.4303 | Reduce | 15% | 4.7676 | 0.71514 | H2 | 2 | Stable | TRUE | 1610.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 30% | 4.7676 | 1.4303 | Reduce | 15% | 4.7676 | 0.71514 | H2 | 2 | Stable | TRUE | 1610.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 01:00 | 2017-06-06 | 30% | 4.7676 | 1.4303 | Reduce | 15% | 4.7676 | 0.71514 | H2 | 2 | Stable | TRUE | 1610.9583 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_482 | 2013-01-07 | 2017-06-06 | 30% | 4.7676 | 1.4303 | Reduce | 15% | 4.7676 | 0.71514 | H2 | 2 | Stable | TRUE | 1611 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK004 | Project_060_RISK004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Cross-functional Estimates | Person_729 | 2017-11-19 01:00 | 2018-11-06 01:00 | 70% | 2.8845 | 2.0191 | Reduce | 50% | 1.4422 | 0.72112 | H2 | 2 | Improving | TRUE | 352 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-161 | Project_026_Risk-161 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer Deliverable Acceptance | Person_091 | 2015-02-21 01:00 | 2022-09-30 01:00 | 50% | 3.6174 | 1.8087 | Accept | 20% | 3.6172 | 0.72345 | H3 | 3 | -- | TRUE | 2778 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-161 | Project_026_Risk-161 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer Deliverable Acceptance | Person_091 | 2015-02-21 01:00 | 2022-09-30 01:00 | 50% | 3.6174 | 1.8087 | Accept | 20% | 3.6172 | 0.72345 | H3 | 3 | -- | TRUE | 2778 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-161 | Project_026_Risk-161 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer Deliverable Acceptance | Person_091 | 2015-02-21 01:00 | 2022-09-30 01:00 | 50% | 3.6174 | 1.8087 | Accept | 20% | 3.6172 | 0.72345 | H3 | 3 | -- | TRUE | 2778 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-161 | Project_026_Risk-161 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer Deliverable Acceptance | Person_091 | 2015-02-21 01:00 | 2022-09-30 01:00 | 50% | 3.6174 | 1.8087 | Accept | 20% | 3.6172 | 0.72345 | H3 | 3 | -- | TRUE | 2778 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-002 | Project_077_T-002 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Legacy testing Repeatability | Person_202 | 2018-10-22 01:00 | 2019-05-11 | 30% | 2.4261 | 0.72784 | Accept | 30% | 2.4261 | 0.72784 | H2 | 2 | Stable | TRUE | 200.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-113 | Project_039_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Integrated System Delay | Person_343 | 2015-07-24 | 2016-07-20 | 5% | 21.6218 | 1.0811 | Reduce | 5% | 14.6673 | 0.73337 | H2 | 2 | Improving | TRUE | 362 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK080 | Project_065_RISK080 | Threat | Management Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Systems Eng. Env. Qual. tooling & test facility cost estimate is low | Person_455 | 2016-08-04 | 2021-06-05 | 30% | 2.4509 | 0.73527 | Accept | 30% | 2.4509 | 0.73527 | H3 | 3 | Stable | TRUE | 1766 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK008 | Project_029_RISK008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Impact of sub-system Design Changes [product dependency] | Person_332 | 2016-09-20 01:00 | 2019-08-15 | 70% | 1.0695 | 0.74863 | Accept | 70% | 1.0695 | 0.74863 | H2 | 2 | Stable | TRUE | 1058.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_547 | 2018-09-19 01:00 | 2019-03-17 01:00 | 50% | 2.5081 | 1.2541 | Accept | 30% | 2.5081 | 0.75243 | H2 | 2 | Stable | TRUE | 179 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322- | Project_065_RISK322- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2018-05-23 | 2021-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-006 | Project_077_T-006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Functionality | Person_202 | 2018-08-22 01:00 | 2020-02-21 01:00 | 20% | 3.774 | 0.7548 | -- | 20% | 3.774 | 0.7548 | H3 | 3 | Stable | FALSE | 548 |  | 1 | 1 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-010 | Project_077_T-010 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Technical Directorate changes to SW/data artefacts - Internal Requirement | Person_092 | 2018-11-21 01:00 | 2020-02-21 01:00 | 40% | 1.887 | 0.7548 | Reduce | 40% | 1.887 | 0.7548 | H2 | 2 | Stable | TRUE | 457 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-320 | Project_032_Risk-320 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional Obsolesence Work | Person_406 | 2015-09-25 01:00 | 2016-05-22 | 5% | 15.1433 | 0.75717 | Reduce | 5% | 15.1433 | 0.75717 | H3 | 3 | -- | FALSE | 239.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-320 | Project_032_Risk-320 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional Obsolesence Work | Person_406 | 2015-09-25 | 2016-05-22 | 5% | 15.1433 | 0.75717 | Reduce | 5% | 15.1433 | 0.75717 | H3 | 3 | -- | FALSE | 240 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-320 | Project_032_Risk-320 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional Obsolesence Work | Person_406 | 2015-09-25 | 2016-05-22 | 5% | 15.1433 | 0.75717 | Reduce | 5% | 15.1433 | 0.75717 | H3 | 3 | -- | FALSE | 240 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-320 | Project_032_Risk-320 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional Obsolesence Work | Person_406 | 2015-09-25 | 2016-05-22 | 5% | 15.1433 | 0.75717 | Reduce | 5% | 15.1433 | 0.75717 | H3 | 3 | -- | FALSE | 240 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-320 | Project_032_Risk-320 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional Obsolesence Work | Person_406 | 2015-09-25 01:00 | 2016-05-22 | 5% | 15.1433 | 0.75717 | Reduce | 5% | 15.1433 | 0.75717 | H3 | 3 | -- | FALSE | 239.9583 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-320 | Project_032_Risk-320 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional Obsolesence Work | Person_406 | 2015-09-25 01:00 | 2016-05-22 | 5% | 15.1433 | 0.75717 | Reduce | 5% | 15.1433 | 0.75717 | H3 | 3 | -- | FALSE | 239.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-320 | Project_032_Risk-320 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional Obsolesence Work | Person_406 | 2015-09-25 01:00 | 2016-05-22 | 5% | 15.1433 | 0.75717 | Reduce | 5% | 15.1433 | 0.75717 | H3 | 3 | -- | FALSE | 239.9583 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-320 | Project_032_Risk-320 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional Obsolesence Work | Person_406 | 2015-09-25 01:00 | 2016-05-22 | 5% | 15.1433 | 0.75717 | Reduce | 5% | 15.1433 | 0.75717 | H3 | 3 | -- | FALSE | 239.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2015-12-22 01:00 | 2017-05-23 | 55% | 1.3775 | 0.75761 | Reduce | 55% | 1.3775 | 0.75761 | H2 | 2 | Stable | TRUE | 517.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-118 | Project_029_Risk-118 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Acceptance Schedule is longer in duration/delayed due to unplanned events. [Hardware availability] | Person_102 | 2017-01-21 01:00 | 2017-05-23 | 55% | 1.3775 | 0.75761 | Reduce | 55% | 1.3775 | 0.75761 | H2 | 2 | Stable | TRUE | 121.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK322-Risk- | Project_065_RISK322-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Cooling System Issues | Person_300 | 2021-04-22 | 2024-04-22 | 30% | 18.4072 | 5.5222 | Accept | 30% | 18.4072 | 5.5222 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-134 | Project_030_Risk-134 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Costs | Person_518 | 2014-11-21 01:00 | 2016-05-22 | 40% | 24.6132 | 9.8453 | -- | 40% | 13.8351 | 5.534 | H2 | 2 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-134 | Project_030_Risk-134 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Costs | Person_518 | 2014-11-21 | 2016-05-22 | 40% | 24.6132 | 9.8453 | -- | 40% | 13.8351 | 5.534 | H2 | 2 | -- | TRUE | 548 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-10-19 01:00 | 70% | 24.8225 | 17.3758 | Reduce | 48% | 12.2576 | 5.8836 | H2 | 2 | Stable | TRUE | 1641.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 2 |  | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 12.5% | 232.2192 | 29.0274 | -- | 21.5% | 27.8663 | 5.9913 | H2 | 2 | Stable | TRUE | 511 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 2 |  | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 12.5% | 232.2192 | 29.0274 | -- | 21.5% | 27.8663 | 5.9913 | H2 | 2 | Stable | TRUE | 511 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-09 | Project_022_RISK-09 | Threat | Project Contingency | Open | H2 | 2 |  | Acceptance - Issues arise | Person_393 | 2012-04-22 | 2016-09-19 01:00 | 70% | 24.8225 | 17.3758 | Reduce | 48% | 13.3846 | 6.4246 | H2 | 2 | Stable | TRUE | 1611.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK567 | Project_065_RISK567 | Threat | Project Contingency | Open | H2 | 2 |  | Schedule Risk Adjustment | Person_117 | 2018-04-21 | 2020-12-19 01:00 | 40% | 38.454 | 15.3816 | Reduce | 20% | 38.454 | 7.6908 | H2 | 2 | -- | TRUE | 973.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK567 | Project_065_RISK567 | Threat | Project Contingency | Open | H2 | 2 |  | Schedule Risk Adjustment | Person_117 | 2018-04-21 | 2020-12-19 | 40% | 38.454 | 15.3816 | Reduce | 20% | 38.454 | 7.6908 | H2 | 2 | -- | TRUE | 973 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 5.0983 | 0.76474 | H3 | 3 | Stable | FALSE | 910.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 5.0983 | 0.76474 | H3 | 3 | Stable | FALSE | 910.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 5.0983 | 0.76474 | H3 | 3 | Stable | FALSE | 910.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-008 | Project_096_Risk-008 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Spiral Software update | Person_259 | 2018-02-20 01:00 | 2018-11-16 01:00 | 30% | 3.8342 | 1.1503 | Reduce | 20% | 3.8342 | 0.76685 | H2 | 2 | Stable | TRUE | 269 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SystemC HW/SW | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Reduce | 30% | 2.5667 | 0.77001 | H2 | 2 | -- | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Accept | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SystemC HW/SW | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Reduce | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Accept | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SystemC HW/SW | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Reduce | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Accept | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SystemC HW/SW | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Reduce | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2016-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Accept | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK020 | Project_029_Risk-RISK020 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | SystemC HW/SW | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Reduce | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 881.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK018 | Project_029_Risk-RISK018 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unforeseen changes to SW interfaces as a result of Batch 2 Re-Design | Person_199 | 2017-05-23 | 2019-10-21 01:00 | 30% | 2.5667 | 0.77001 | Accept | 30% | 2.5667 | 0.77001 | H2 | 2 | Stable | TRUE | 881.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--103 | Project_100_Risk--103 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Consumable Stock Levels | Person_639 | 2018-08-22 01:00 | 2021-08-20 01:00 | 50% | 1.5417 | 0.77083 | Accept | 50% | 1.5417 | 0.77083 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-20 01:00 | 2016-11-13 01:00 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-20 01:00 | 2016-11-13 01:00 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-20 | 2016-11-13 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-19 23:00 | 2016-11-12 23:00 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-19 22:00 | 2016-11-12 22:00 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-19 23:00 | 2016-11-12 23:00 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-20 01:00 | 2016-11-13 01:00 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-20 | 2016-11-13 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-20 01:00 | 2016-11-13 01:00 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK161 | Project_065_RISK161 | Threat | Management Contingency | Open | H3 | 3 | Project Management | STTE use at site | Person_038 | 2013-02-19 23:00 | 2016-11-12 23:00 | 40% | 1.9438 | 0.77753 | Accept | 40% | 1.9438 | 0.77753 | H3 | 3 | -- | TRUE | 1362 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK567 | Project_065_RISK567 | Threat | Project Contingency | Open | H2 | 2 |  | Schedule Risk Adjustment | Person_117 | 2018-04-21 | 2020-12-19 01:00 | 40% | 38.454 | 15.3816 | Reduce | 20% | 38.454 | 7.6908 | H2 | 2 | -- | TRUE | 973.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK567 | Project_065_RISK567 | Threat | Project Contingency | Open | H2 | 2 |  | Schedule Risk Adjustment | Person_117 | 2018-04-21 | 2020-12-18 23:00 | 40% | 38.454 | 15.3816 | Reduce | 20% | 38.454 | 7.6908 | H2 | 2 | -- | TRUE | 972.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK051 | Project_017_RISK051 | Threat | Project Contingency | Open | H2 | 2 |  | Tax/European Risk | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 25% | 30.9033 | 7.7258 | Accept | 25% | 30.9033 | 7.7258 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 60% | 35.9878 | 21.5927 | Accept | 5% | 15.5947 | 0.77974 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 60% | 35.9878 | 21.5927 | Accept | 5% | 15.5947 | 0.77974 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 60% | 35.9878 | 21.5927 | Accept | 5% | 15.5947 | 0.77974 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 60% | 35.9878 | 21.5927 | Accept | 5% | 15.5947 | 0.77974 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 60% | 35.9878 | 21.5927 | Accept | 5% | 15.5947 | 0.77974 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 60% | 35.9878 | 21.5927 | Accept | 5% | 15.5947 | 0.77974 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 60% | 35.9878 | 21.5927 | Accept | 5% | 15.5947 | 0.77974 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-185 | Project_027_Risk-185 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supplier manufacturing issues | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 60% | 35.9878 | 21.5927 | Accept | 5% | 15.5947 | 0.77974 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK051 | Project_017_RISK051 | Threat | Project Contingency | Open | H2 | 2 |  | Tax/European Risk | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 25% | 30.9033 | 7.7258 | Accept | 25% | 30.9033 | 7.7258 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Reduce touch labour if Production readiness programme successful | Person_515 | 2016-11-20 01:00 | 2017-10-21 01:00 | 30% | 1.5606 | 0.46818 | Exploit | 50% | 1.5606 | 0.7803 | H2 | 2 | -- | TRUE | 335 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Reduce touch labour if Production readiness programme successful | Person_515 | 2016-11-20 | 2017-10-21 | 30% | 1.5606 | 0.46818 | Exploit | 50% | 1.5606 | 0.7803 | H2 | 2 | -- | TRUE | 335 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Reduce touch labour if Production readiness programme successful | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 30% | 1.5606 | 0.46818 | Exploit | 50% | 1.5606 | 0.7803 | H2 | 2 | -- | TRUE | 335 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Reduce touch labour if Production readiness programme successful | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 30% | 1.5606 | 0.46818 | Exploit | 50% | 1.5606 | 0.7803 | H2 | 2 | -- | TRUE | 335 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Reduce touch labour if Production readiness programme successful | Person_515 | 2016-11-19 23:00 | 2017-10-20 23:00 | 30% | 1.5606 | 0.46818 | Exploit | 50% | 1.5606 | 0.7803 | H2 | 2 | -- | TRUE | 335 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R82 | Project_041_R82 | Opportunitity | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Reduce touch labour if Production readiness programme successful | Person_515 | 2016-11-19 22:00 | 2017-10-20 22:00 | 30% | 1.5606 | 0.46818 | Exploit | 50% | 1.5606 | 0.7803 | H2 | 2 | -- | TRUE | 335 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-121 | Project_043_Risk-121 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | More Tech Pubs Update than estimated | Person_769 | 2019-01-20 22:00 | 2020-10-19 22:00 | 45% | 1.7366 | 0.78146 | Reduce | 45% | 1.7366 | 0.78146 | H1 | 1 | Stable | TRUE | 638 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK204 | Project_024_RISK204 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Stabilisation | Person_448 | 2016-05-23 | 2017-02-19 01:00 | 40% | 1.3502 | 0.54009 | Accept | 40% | 1.9561 | 0.78244 | H1 | 1 | Improving | TRUE | 272.0417 |  | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK051 | Project_017_RISK051 | Threat | Project Contingency | Open | H2 | 2 |  | Tax/European Risk | Person_084 | 2016-01-22 | 2023-02-20 | 25% | 30.9033 | 7.7258 | Accept | 25% | 30.9033 | 7.7258 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK051 | Project_017_RISK051 | Threat | Project Contingency | Open | H2 | 2 |  | Tax/European Risk | Person_084 | 2016-01-22 | 2023-02-20 | 25% | 30.9033 | 7.7258 | Accept | 25% | 30.9033 | 7.7258 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK051 | Project_017_RISK051 | Threat | Project Contingency | Open | H2 | 2 |  | Tax/European Risk | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 25% | 30.9033 | 7.7258 | Accept | 25% | 30.9033 | 7.7258 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK051 | Project_017_RISK051 | Threat | Project Contingency | Open | H2 | 2 |  | Tax/European Risk | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 25% | 30.9033 | 7.7258 | Accept | 25% | 30.9033 | 7.7258 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK051 | Project_017_RISK051 | Threat | Project Contingency | Open | H2 | 2 |  | Tax/European Risk | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 25% | 30.9033 | 7.7258 | Accept | 25% | 30.9033 | 7.7258 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK051 | Project_017_RISK051 | Threat | Project Contingency | Open | H2 | 2 |  | Tax/European Risk | Person_084 | 2016-01-21 21:00 | 2023-02-19 21:00 | 25% | 30.9033 | 7.7258 | Accept | 25% | 30.9033 | 7.7258 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-140 | Project_030_Risk-140 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to claim from Customer for extended programme | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 22.0482 | 5.7325 | -- | 40% | 19.7644 | 7.9057 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-140 | Project_030_Risk-140 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to claim from Customer for extended programme | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 22.0482 | 5.7325 | -- | 40% | 19.7644 | 7.9057 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-140 | Project_030_Risk-140 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to claim from Customer for extended programme | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 22.0482 | 5.7325 | -- | 40% | 19.7644 | 7.9057 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-140 | Project_030_Risk-140 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to claim from Customer for extended programme | Person_518 | 2014-10-22 | 2015-05-23 | 26% | 22.0482 | 5.7325 | -- | 40% | 19.7644 | 7.9057 | H2 | 2 | -- | TRUE | 213 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-140 | Project_030_Risk-140 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to claim from Customer for extended programme | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 22.0482 | 5.7325 | -- | 40% | 19.7644 | 7.9057 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-140 | Project_030_Risk-140 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to claim from Customer for extended programme | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 22.0482 | 5.7325 | -- | 40% | 19.7644 | 7.9057 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-140 | Project_030_Risk-140 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to claim from Customer for extended programme | Person_518 | 2014-10-22 01:00 | 2015-05-23 | 26% | 22.0482 | 5.7325 | -- | 40% | 19.7644 | 7.9057 | H2 | 2 | -- | TRUE | 212.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-140 | Project_030_Risk-140 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Opportunity to claim from Customer for extended programme | Person_518 | 2014-10-22 | 2015-05-23 | 26% | 22.0482 | 5.7325 | -- | 40% | 19.7644 | 7.9057 | H2 | 2 | -- | TRUE | 213 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK116 | Project_066_RISK116 | Threat | Project Contingency | Open | H2 | 2 |  | DVT Duration extension | Person_068 | 2019-03-24 | 2019-12-22 01:00 | 40% | 20.0357 | 8.0143 | Avoid | 40% | 20.0357 | 8.0143 | H2 | 2 | -- | TRUE | 273.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-20 01:00 | 2020-02-15 01:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-20 01:00 | 2020-02-15 01:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-20 | 2020-02-15 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-20 01:00 | 2020-02-15 01:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-19 23:00 | 2020-02-14 23:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-19 22:00 | 2020-02-14 22:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-20 01:00 | 2020-02-15 01:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-19 22:00 | 2020-02-14 22:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-20 | 2020-02-15 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-20 01:00 | 2020-02-15 01:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK467 | Project_065_RISK467 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Windows OS for full project is upgraded leading to complications for sub-systems | Person_661 | 2017-11-19 23:00 | 2020-02-14 23:00 | 20% | 7.4469 | 1.4894 | Reduce | 20% | 3.9299 | 0.78598 | H3 | 3 | -- | FALSE | 817 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 2 |  | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 12.5% | 232.2192 | 29.0274 | -- | 29.7% | 27.8663 | 8.2763 | H2 | 2 | Stable | TRUE | 511 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-134 | Project_030_Risk-134 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Costs | Person_518 | 2014-11-21 01:00 | 2016-05-22 | 40% | 24.6132 | 9.8453 | -- | 40% | 21.082 | 8.4328 | H2 | 2 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-134 | Project_030_Risk-134 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Costs | Person_518 | 2014-11-21 | 2016-05-22 | 40% | 24.6132 | 9.8453 | -- | 40% | 21.082 | 8.4328 | H2 | 2 | -- | TRUE | 548 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-134 | Project_030_Risk-134 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Costs | Person_518 | 2014-11-21 01:00 | 2016-05-22 | 40% | 24.6132 | 9.8453 | -- | 40% | 21.082 | 8.4328 | H2 | 2 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-134 | Project_030_Risk-134 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Costs | Person_518 | 2014-11-21 01:00 | 2016-05-22 | 40% | 24.6132 | 9.8453 | -- | 40% | 21.9604 | 8.7842 | H2 | 2 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Viewer may not work | Person_318 | 2011-04-22 | 2019-05-23 | 50% | 3.9382 | 1.9691 | Reduce | 20% | 3.9382 | 0.78764 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Viewer may not work | Person_318 | 2011-04-22 | 2019-05-23 | 50% | 3.9382 | 1.9691 | Reduce | 20% | 3.9382 | 0.78764 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Viewer may not work | Person_318 | 2011-04-22 | 2019-05-23 | 50% | 3.9382 | 1.9691 | Reduce | 20% | 3.9382 | 0.78764 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Viewer may not work | Person_318 | 2011-04-22 | 2019-05-23 | 50% | 3.9382 | 1.9691 | Reduce | 20% | 3.9382 | 0.78764 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Viewer may not work | Person_318 | 2011-04-22 | 2018-05-22 | 50% | 3.9382 | 1.9691 | Reduce | 20% | 3.9382 | 0.78764 | H2 | 2 | -- | TRUE | 2587 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Viewer may not work | Person_318 | 2011-04-22 | 2019-05-23 | 50% | 3.9382 | 1.9691 | Reduce | 20% | 3.9382 | 0.78764 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK261 | Project_024_RISK261 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Viewer may not work | Person_318 | 2016-05-23 | 2017-10-20 01:00 | 50% | 3.9382 | 1.9691 | Reduce | 20% | 3.9382 | 0.78764 | H2 | 2 | -- | TRUE | 515.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-01-20 01:00 | 30% | 5.4553 | 1.6366 | Reduce | 15% | 5.252 | 0.7878 | H2 | 2 | Stable | TRUE | 650.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-01-20 01:00 | 30% | 5.4553 | 1.6366 | Reduce | 15% | 5.252 | 0.7878 | H2 | 2 | Stable | TRUE | 650.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-01-20 01:00 | 30% | 5.4553 | 1.6366 | Reduce | 15% | 5.252 | 0.7878 | H2 | 2 | Stable | TRUE | 650.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-03-22 | 30% | 5.4553 | 1.6366 | Reduce | 15% | 5.252 | 0.7878 | H2 | 2 | Stable | TRUE | 711 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-03-22 | 30% | 5.4553 | 1.6366 | Reduce | 15% | 5.252 | 0.7878 | H2 | 2 | Stable | TRUE | 711 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK020 | Project_065_RISK020 | Threat | Management Contingency | Open | H2 | 2 | System Engineering | Interface requirements non compliant | Person_661 | 2015-06-24 | 2020-03-27 | 60% | 5.2585 | 3.1551 | Reduce | 15% | 5.2585 | 0.78877 | H2 | 2 | Stable | TRUE | 1738 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-03-21 01:00 | 35% | 1.3502 | 0.47258 | Accept | 35% | 2.2677 | 0.79369 | H2 | 2 | Worsening | TRUE | 302.0417 |  | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK200 | Project_024_RISK200 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Height Finding | Person_448 | 2016-05-23 | 2017-03-21 01:00 | 35% | 1.3502 | 0.47258 | Accept | 35% | 2.2677 | 0.79369 | H2 | 2 | Worsening | TRUE | 302.0417 |  | 0 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-05-21 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 284 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-05-21 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 284 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-05-21 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 284 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-05-21 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 284 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required for mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R032 | Project_021_Risk-R032 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Additional tasks required with mode certification | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 1.3243 | 1.0595 | Reduce | 60% | 1.3243 | 0.7946 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-134 | Project_030_Risk-134 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Costs | Person_518 | 2014-11-21 01:00 | 2016-05-22 | 40% | 24.6132 | 9.8453 | -- | 40% | 21.9604 | 8.7842 | H2 | 2 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK006 | Project_081_RISK006 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Large volume of repairs loaded to clear backlog | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 25% | 3.1854 | 0.79634 | Reduce | 25% | 3.1854 | 0.79634 | H3 | 3 | Worsening | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 2 |  | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 12.5% | 232.2192 | 29.0274 | -- | 32.7% | 27.8663 | 9.1123 | H2 | 2 | Stable | TRUE | 511 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK004 | Project_021_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Delivery by Supplier late or requires correction that causes re-start of rig testing | Person_470 | 2016-02-13 | 2016-08-20 | 50% | 1.6113 | 0.80564 | Avoid | 50% | 1.6113 | 0.80564 | H1 | 1 | Worsening | TRUE | 189 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | RISK004 | Project_021_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Delivery by Supplier late or requires correction that causes re-start of rig testing | Person_470 | 2016-02-12 23:00 | 2016-08-19 23:00 | 50% | 1.6113 | 0.80564 | Avoid | 50% | 1.6113 | 0.80564 | H1 | 1 | Worsening | TRUE | 189 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-019 | Project_077_T-019 | Threat | Project Contingency | Open | H2 | 2 | Project Management | New stakeholders/Changeovers | Person_203 | 2018-02-20 01:00 | 2020-02-21 01:00 | 30% | 2.6957 | 0.80871 | Accept | 30% | 2.6957 | 0.80871 | H2 | 2 | Stable | TRUE | 731 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK001 | Project_081_RISK001 | Threat | Management Contingency | Open | H3 | 3 | Project Management | Increase in Support Management | Person_260 | 2017-07-21 | 2021-07-21 | 40% | 2.0381 | 0.81526 | Reduce | 40% | 2.0381 | 0.81526 | H3 | 3 | Worsening | TRUE | 1461 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK541 | Project_065_RISK541 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Possible integration issues into simulator | Person_550 | 2017-10-15 01:00 | 2019-07-28 | 60% | 4.0837 | 2.4502 | Reduce | 20% | 4.0837 | 0.81675 | H3 | 3 | -- | TRUE | 650.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK541 | Project_065_RISK541 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Possible integration issues into simulator | Person_550 | 2017-10-15 | 2019-07-28 | 60% | 4.0837 | 2.4502 | Reduce | 20% | 4.0837 | 0.81675 | H3 | 3 | -- | TRUE | 651 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK541 | Project_065_RISK541 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Possible integration issues into simulator | Person_550 | 2017-10-15 01:00 | 2019-07-28 | 60% | 4.0837 | 2.4502 | Reduce | 20% | 4.0837 | 0.81675 | H3 | 3 | -- | TRUE | 650.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK541 | Project_065_RISK541 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Possible integration issues into simulator | Person_550 | 2017-10-14 23:00 | 2019-07-28 | 60% | 4.0837 | 2.4502 | Reduce | 20% | 4.0837 | 0.81675 | H3 | 3 | -- | TRUE | 651.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-106 | Project_029_Risk-106 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Opportunity to recover 50% of design effort | Person_438 | 2015-03-24 | 2017-05-08 | 80% | 1.0267 | 0.82135 | Exploit | 80% | 1.0267 | 0.82135 | H2 | 2 | Stable | TRUE | 776 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK152 | Project_038_RISK152 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test Equipment Costs | Person_640 | 2015-06-24 | 2016-08-20 01:00 | 20% | 5.4834 | 1.0967 | Accept | 15% | 5.4834 | 0.82251 | H3 | 3 | Stable | TRUE | 423.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK152 | Project_038_RISK152 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test Equipment Costs | Person_640 | 2015-06-24 | 2016-08-20 01:00 | 20% | 5.4834 | 1.0967 | Accept | 15% | 5.4834 | 0.82251 | H3 | 3 | Stable | TRUE | 423.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_575 | 2011-05-24 | 2017-08-01 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 8.2472 | 0.82472 | H3 | 3 | -- | TRUE | 2261 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_575 | 2011-05-24 | 2017-08-01 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 8.2472 | 0.82472 | H3 | 3 | -- | TRUE | 2261 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_575 | 2011-05-24 | 2017-08-01 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 8.2472 | 0.82472 | H3 | 3 | -- | TRUE | 2261 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_575 | 2011-05-24 | 2017-08-01 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 8.2472 | 0.82472 | H3 | 3 | -- | TRUE | 2261 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_575 | 2011-05-24 | 2017-08-01 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 8.2472 | 0.82472 | H3 | 3 | -- | TRUE | 2261 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Training System gained efficiency - Planning Package | Person_351 | 2011-04-22 | 2019-05-23 | 20% | 49.3354 | 9.8671 | -- | 20% | 49.3354 | 9.8671 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | RISK020 | Project_093_RISK020 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Integration - Classification | Person_342 | 2018-09-30 01:00 | 2019-05-23 | 90% | 0.91777 | 0.82599 | Accept | 90% | 0.91777 | 0.82599 | H1 | 1 | -- | TRUE | 234.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | RISK019 | Project_093_RISK019 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Integration - Combination | Person_342 | 2018-09-30 01:00 | 2019-05-23 | 90% | 0.91777 | 0.82599 | Accept | 90% | 0.91777 | 0.82599 | H1 | 1 | -- | TRUE | 234.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_093 | RISK018 | Project_093_RISK018 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Integration - Detection | Person_342 | 2018-09-30 01:00 | 2019-05-23 | 90% | 0.91777 | 0.82599 | Accept | 90% | 0.91777 | 0.82599 | H1 | 1 | -- | TRUE | 234.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK062 | Project_076_RISK062 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay - Lack of access to tools | Person_771 | 2018-05-23 | 2019-10-22 01:00 | 50% | 1.6584 | 0.82922 | Accept | 50% | 1.6584 | 0.82922 | H2 | 2 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK062 | Project_076_RISK062 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delay - Lack of access to tools | Person_771 | 2018-05-23 | 2019-10-22 01:00 | 50% | 1.6584 | 0.82922 | Accept | 50% | 1.6584 | 0.82922 | H2 | 2 | -- | TRUE | 517.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-20 01:00 | 2019-05-23 | 25% | 3.3227 | 0.83067 | Accept | 25% | 3.3227 | 0.83067 | H2 | 2 | -- | TRUE | 913.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-20 01:00 | 2018-05-22 | 25% | 3.3227 | 0.83067 | Accept | 25% | 3.3227 | 0.83067 | H2 | 2 | Stable | TRUE | 547.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-20 | 2018-05-22 | 25% | 3.3227 | 0.83067 | Accept | 25% | 3.3227 | 0.83067 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 25% | 3.3227 | 0.83067 | Accept | 25% | 3.3227 | 0.83067 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 25% | 3.3227 | 0.83067 | Accept | 25% | 3.3227 | 0.83067 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-19 23:00 | 2018-05-22 | 25% | 3.3227 | 0.83067 | Accept | 25% | 3.3227 | 0.83067 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R90 | Project_041_R90 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Digitiser and Processor Test Facilities (STTE) requires additional effort | Person_515 | 2016-11-19 22:00 | 2018-05-22 | 25% | 3.3227 | 0.83067 | Accept | 25% | 3.3227 | 0.83067 | H2 | 2 | Stable | TRUE | 548.0833 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Training System gained efficiency - Planning Package | Person_351 | 2011-04-22 | 2019-05-23 | 20% | 49.3354 | 9.8671 | -- | 20% | 49.3354 | 9.8671 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Training System gained efficiency - Planning Package | Person_351 | 2011-04-22 | 2019-05-23 | 20% | 49.3354 | 9.8671 | -- | 20% | 49.3354 | 9.8671 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Training System gained efficiency - Planning Package | Person_351 | 2011-04-22 | 2019-05-23 | 20% | 49.3354 | 9.8671 | -- | 20% | 49.3354 | 9.8671 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Training System gained efficiency - Planning Package | Person_351 | 2011-04-22 | 2018-05-22 | 20% | 49.3354 | 9.8671 | -- | 20% | 49.3354 | 9.8671 | H2 | 2 | -- | TRUE | 2587 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Training System gained efficiency - Planning Package | Person_351 | 2011-04-22 | 2019-05-23 | 20% | 49.3354 | 9.8671 | -- | 20% | 49.3354 | 9.8671 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP226 | Project_024_OPP226 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Training System gained efficiency - Planning Package | Person_351 | 2015-09-21 01:00 | 2017-06-22 | 20% | 49.3354 | 9.8671 | -- | 20% | 49.3354 | 9.8671 | H2 | 2 | -- | TRUE | 639.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK565 | Project_065_RISK565 | Threat | Project Contingency | Open | H2 | 2 |  | Software resourcing and increased effort to manage software team | Person_550 | 2018-04-20 | 2019-04-23 | 80% | 27.1882 | 21.7506 | Reduce | 40% | 27.1882 | 10.8753 | H2 | 2 | -- | TRUE | 368 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK565 | Project_065_RISK565 | Threat | Project Contingency | Open | H2 | 2 |  | Software resourcing and increased effort to manage software team | Person_550 | 2018-04-20 | 2019-04-23 | 80% | 27.1882 | 21.7506 | Reduce | 40% | 27.1882 | 10.8753 | H2 | 2 | -- | TRUE | 368 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK565 | Project_065_RISK565 | Threat | Project Contingency | Open | H2 | 2 |  | Software resourcing and increased effort to manage software team | Person_550 | 2018-04-20 | 2019-04-23 | 80% | 27.1882 | 21.7506 | Reduce | 40% | 27.1882 | 10.8753 | H2 | 2 | -- | TRUE | 368 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK565 | Project_065_RISK565 | Threat | Project Contingency | Open | H2 | 2 |  | Software resourcing and increased effort to manage software team | Person_550 | 2018-04-20 | 2019-04-23 | 80% | 27.1882 | 21.7506 | Reduce | 40% | 27.1882 | 10.8753 | H2 | 2 | -- | TRUE | 368 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK400 | Project_038_RISK400 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Recovering sunk cost due to Supply Chain | Person_330 | 2016-11-29 01:00 | 2017-03-21 01:00 | 30% | 38.2038 | 11.4611 | -- | 30% | 38.2038 | 11.4611 | H2 | 2 | -- | TRUE | 112 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK400 | Project_038_RISK400 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Recovering sunk cost due to Supply Chain | Person_330 | 2016-11-29 01:00 | 2017-03-21 01:00 | 30% | 38.2038 | 11.4611 | -- | 30% | 38.2038 | 11.4611 | H2 | 2 | -- | TRUE | 112 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-036 | Project_030_Risk-036 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Platforms Cables & Connector Kits | Person_146 | 2013-07-21 | 2015-12-20 01:00 | 40% | 4.3921 | 1.7568 | Reduce | 25% | 3.338 | 0.8345 | H3 | 3 | -- | TRUE | 882.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-036 | Project_030_Risk-036 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Platforms Cables & Connector Kits | Person_146 | 2013-07-21 | 2015-12-20 01:00 | 40% | 4.3921 | 1.7568 | Reduce | 25% | 3.338 | 0.8345 | H3 | 3 | -- | TRUE | 882.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-036 | Project_030_Risk-036 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Platforms Cables & Connector Kits | Person_146 | 2013-07-21 | 2015-12-20 | 40% | 4.3921 | 1.7568 | Reduce | 25% | 3.338 | 0.8345 | H3 | 3 | -- | TRUE | 882 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-036 | Project_030_Risk-036 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Platforms Cables & Connector Kits | Person_146 | 2013-07-21 | 2015-12-20 01:00 | 40% | 4.3921 | 1.7568 | Reduce | 25% | 3.338 | 0.8345 | H3 | 3 | -- | TRUE | 882.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-036 | Project_030_Risk-036 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Platforms Cables & Connector Kits | Person_146 | 2013-07-21 | 2015-12-20 01:00 | 40% | 4.3921 | 1.7568 | Reduce | 25% | 3.338 | 0.8345 | H3 | 3 | -- | TRUE | 882.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-036 | Project_030_Risk-036 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Platforms Cables & Connector Kits | Person_146 | 2013-07-21 | 2015-12-20 01:00 | 40% | 4.3921 | 1.7568 | Reduce | 25% | 3.338 | 0.8345 | H3 | 3 | -- | TRUE | 882.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-036 | Project_030_Risk-036 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Platforms Cables & Connector Kits | Person_146 | 2013-07-21 | 2015-12-20 | 40% | 4.3921 | 1.7568 | Reduce | 25% | 3.338 | 0.8345 | H3 | 3 | -- | TRUE | 882 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK003 | Project_035_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Qualification | Person_570 | 2015-05-24 | 2016-07-16 | 30% | 6.9524 | 2.0857 | Reduce | 23% | 3.6326 | 0.8355 | H2 | 2 | Worsening | TRUE | 419 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK003 | Project_035_RISK003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Qualification | Person_570 | 2015-05-24 | 2016-07-16 | 30% | 6.9524 | 2.0857 | Reduce | 23% | 3.6326 | 0.8355 | H2 | 2 | Worsening | TRUE | 419 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-043 | Project_062_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | User response | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 35% | 3.3464 | 1.1712 | Avoid | 25% | 3.3464 | 0.83659 | H2 | 2 | Stable | TRUE | 580.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK400 | Project_038_RISK400 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Recovering sunk cost due to Supply Chain | Person_330 | 2016-11-29 01:00 | 2017-03-21 01:00 | 30% | 38.2038 | 11.4611 | -- | 30% | 38.2038 | 11.4611 | H2 | 2 | -- | TRUE | 112 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-007 | Project_062_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Hardware Encryption / Protection | Person_479 | 2018-02-10 01:00 | 2019-03-22 | 30% | 4.183 | 1.2549 | Reduce | 20% | 4.183 | 0.83659 | H3 | 3 | Stable | FALSE | 404.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-002 | Project_098_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | External Sub-system DESIGN | Person_660 | 2018-05-23 | 2033-05-22 | 50% | 3.6379 | 1.8189 | Reduce | 30% | 2.7984 | 0.83951 | H2 | 2 | Stable | TRUE | 5478 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK400 | Project_038_RISK400 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Recovering sunk cost due to Supply Chain | Person_330 | 2016-11-29 01:00 | 2017-03-21 01:00 | 30% | 38.2038 | 11.4611 | -- | 30% | 38.2038 | 11.4611 | H2 | 2 | -- | TRUE | 112 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK400 | Project_038_RISK400 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Recovering sunk cost due to Supply Chain | Person_330 | 2016-11-29 01:00 | 2017-03-21 01:00 | 30% | 38.2038 | 11.4611 | -- | 30% | 38.2038 | 11.4611 | H2 | 2 | -- | TRUE | 112 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK400 | Project_038_RISK400 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Recovering sunk cost due to Supply Chain | Person_330 | 2016-11-29 01:00 | 2017-03-21 01:00 | 30% | 38.2038 | 11.4611 | -- | 30% | 38.2038 | 11.4611 | H2 | 2 | -- | TRUE | 112 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 2 |  | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 12.5% | 232.2192 | 29.0274 | -- | 40% | 29.6641 | 11.8657 | H2 | 2 | Stable | TRUE | 511 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK102 | Project_066_RISK102 | Threat | Project Contingency | Open | H2 | 2 |  | Support Period delays | Person_383 | 2020-05-23 | 2022-05-22 | 55% | 23.004 | 12.6522 | Avoid | 55% | 23.004 | 12.6522 | H2 | 2 | -- | TRUE | 729 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK014 | Project_001_RISK014 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Synergy with the framework contract should deliver saving | Person_674 | 2015-06-21 | 2016-06-29 | 50% | 29.3441 | 14.672 | -- | 50% | 29.3441 | 14.672 | H2 | 2 | -- | TRUE | 374 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK014 | Project_001_RISK014 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Synergy with the framework contract should deliver saving | Person_674 | 2015-06-21 | 2016-06-29 | 50% | 29.3441 | 14.672 | -- | 50% | 29.3441 | 14.672 | H2 | 2 | -- | TRUE | 374 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK014 | Project_001_RISK014 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Synergy with the framework contract should deliver saving | Person_674 | 2015-06-21 | 2016-06-29 | 50% | 29.3441 | 14.672 | -- | 50% | 29.3441 | 14.672 | H2 | 2 | -- | TRUE | 374 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK014 | Project_001_RISK014 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Synergy with the framework contract should deliver saving | Person_674 | 2015-06-21 | 2016-06-29 | 50% | 29.3441 | 14.672 | -- | 50% | 29.3441 | 14.672 | H2 | 2 | -- | TRUE | 374 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK014 | Project_001_RISK014 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Synergy with the framework contract should deliver saving | Person_674 | 2015-06-21 | 2016-06-29 | 50% | 29.3441 | 14.672 | -- | 50% | 29.3441 | 14.672 | H2 | 2 | -- | TRUE | 374 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK014 | Project_001_RISK014 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Synergy with the framework contract should deliver saving | Person_674 | 2015-06-21 | 2016-06-29 | 50% | 29.3441 | 14.672 | -- | 50% | 29.3441 | 14.672 | H2 | 2 | -- | TRUE | 374 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 2 |  | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 12.5% | 232.2192 | 29.0274 | -- | 40% | 36.9453 | 14.7781 | H2 | 2 | Stable | TRUE | 511 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-27 | Project_022_RISK-27 | Threat | Project Contingency | Open | H2 | 2 |  | Provision for future emerging risks | Person_703 | 2015-02-21 01:00 | 2016-11-19 01:00 | 100% | 2.3975 | 2.3975 | Accept | 100% | 14.8583 | 14.8583 | H2 | 2 | -- | TRUE | 637 |  | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-27 | Project_022_RISK-27 | Threat | Project Contingency | Open | H2 | 2 |  | Provision for future emerging risks | Person_703 | 2015-02-21 01:00 | 2017-04-21 | 100% | 2.3975 | 2.3975 | Accept | 100% | 14.8583 | 14.8583 | H2 | 2 | -- | TRUE | 789.9583 |  | 0 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_470 | 2012-11-20 01:00 | 2017-05-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1642.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_470 | 2012-11-20 | 2017-05-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1643 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build ()/Decision Point concludes new release required | Person_470 | 2012-11-20 01:00 | 2017-05-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1642.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_575 | 2011-05-24 | 2017-08-01 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 8.6971 | 0.86971 | H3 | 3 | -- | TRUE | 2261 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_575 | 2011-05-24 | 2017-08-01 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 8.6971 | 0.86971 | H3 | 3 | -- | TRUE | 2261 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-134 | Project_020_Risk-134 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Power Supply quality | Person_575 | 2011-05-24 | 2017-08-01 | 10% | 16.4945 | 1.6494 | Reduce | 10% | 8.6971 | 0.86971 | H3 | 3 | -- | TRUE | 2261 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK162-Risk- | Project_065_RISK162-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System aspects of Factory Acceptance Tests | Person_160 | 2021-04-22 | 2024-04-22 | 40% | 2.1974 | 0.87895 | Accept | 40% | 2.1974 | 0.87895 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_470 | 2012-11-20 01:00 | 2017-06-22 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1674.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_470 | 2012-11-20 01:00 | 2017-06-22 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1674.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_470 | 2012-11-20 01:00 | 2017-06-22 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1674.9583 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_427 | 2012-11-20 01:00 | 2017-06-22 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1674.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_427 | 2012-11-20 01:00 | 2017-06-22 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1674.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_427 | 2012-11-20 01:00 | 2017-06-22 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1674.9583 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_427 | 2012-11-20 | 2017-06-22 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1675 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2017-08-20 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 1734 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 2099.9583 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 2099.9583 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 2099.9583 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 2099.9583 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 2099.9583 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 2099.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-003 | Project_006_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Spares availability | Person_582 | 2015-05-24 | 2016-04-22 | 15% | 14.8966 | 2.2345 | Avoid | 10% | 8.8204 | 0.88204 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK004 | Project_079_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 20% | 8.8685 | 1.7737 | Reduce | 10% | 8.8685 | 0.88685 | H3 | 3 | Stable | TRUE | 1186.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK004 | Project_079_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 20% | 8.8685 | 1.7737 | Reduce | 10% | 8.8685 | 0.88685 | H3 | 3 | Stable | TRUE | 1186.9583 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_661 | 2019-09-26 01:00 | 2019-09-27 01:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-26 01:00 | 2019-09-27 01:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-26 | 2019-09-27 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-26 01:00 | 2019-09-27 01:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-25 23:00 | 2019-09-26 23:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-25 22:00 | 2019-09-26 22:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-25 23:00 | 2019-09-26 23:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-26 01:00 | 2019-09-27 01:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-25 22:00 | 2019-09-26 22:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-26 | 2019-09-27 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-26 01:00 | 2019-09-27 01:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK476 | Project_065_RISK476 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Failures are recorded after EMC and Environmental testing being conducted on the unit | Person_020 | 2019-09-25 23:00 | 2019-09-26 23:00 | 50% | 3.6003 | 1.8002 | Reduce | 50% | 1.7748 | 0.8874 | H2 | 2 | -- | TRUE | 1 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R088 | Project_085_R088 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Performance of the Telemetry system | Person_539 | 2017-12-21 | 2022-05-22 | 60% | 1.777 | 1.0662 | Reduce | 50% | 1.777 | 0.88852 | H2 | 2 | -- | TRUE | 1613 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R052 | Project_085_R052 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Test equipment upgrade | Person_028 | 2018-02-20 | 2019-05-23 | 20% | 8.8852 | 1.777 | Reduce | 10% | 8.8852 | 0.88852 | H3 | 3 | -- | TRUE | 457 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 50% | 3.5934 | 1.7967 | Reduce | 25% | 3.5934 | 0.89835 | H2 | 2 | Stable | TRUE | 2411 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-138 | Project_020_Risk-138 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Customer Warranty | Person_722 | 2012-10-20 23:00 | 2017-08-01 | 40% | 17.994 | 7.1976 | Reduce | 10% | 8.997 | 0.8997 | H3 | 3 | -- | TRUE | 1745.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-138 | Project_020_Risk-138 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Customer Warranty | Person_722 | 2012-10-20 22:00 | 2017-08-01 | 40% | 17.994 | 7.1976 | Reduce | 10% | 8.997 | 0.8997 | H3 | 3 | -- | TRUE | 1745.0833 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-138 | Project_020_Risk-138 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Customer Warranty | Person_722 | 2012-10-20 21:00 | 2017-08-01 | 40% | 17.994 | 7.1976 | Reduce | 10% | 8.997 | 0.8997 | H3 | 3 | -- | TRUE | 1745.125 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-138 | Project_020_Risk-138 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Customer Warranty | Person_722 | 2012-10-21 01:00 | 2017-08-01 | 40% | 17.994 | 7.1976 | Reduce | 10% | 8.997 | 0.8997 | H3 | 3 | -- | TRUE | 1744.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-138 | Project_020_Risk-138 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Customer Warranty | Person_722 | 2012-10-21 01:00 | 2017-08-01 | 40% | 17.994 | 7.1976 | Reduce | 10% | 8.997 | 0.8997 | H3 | 3 | -- | TRUE | 1744.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-138 | Project_020_Risk-138 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Customer Warranty | Person_722 | 2012-10-21 01:00 | 2017-08-01 | 40% | 17.994 | 7.1976 | Reduce | 10% | 8.997 | 0.8997 | H3 | 3 | -- | TRUE | 1744.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-138 | Project_020_Risk-138 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Customer Warranty | Person_722 | 2012-10-21 01:00 | 2017-08-01 | 40% | 17.994 | 7.1976 | Reduce | 10% | 8.997 | 0.8997 | H3 | 3 | -- | TRUE | 1744.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-138 | Project_020_Risk-138 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Customer Warranty | Person_722 | 2012-10-21 01:00 | 2017-08-01 | 40% | 17.994 | 7.1976 | Reduce | 10% | 8.997 | 0.8997 | H3 | 3 | -- | TRUE | 1744.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-140 | Project_020_Risk-140 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | No external equipment Support Contract | Person_575 | 2012-09-12 01:00 | 2017-08-01 | 30% | 4.4985 | 1.3495 | Accept | 30% | 2.999 | 0.8997 | H2 | 2 | -- | TRUE | 1783.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-140 | Project_020_Risk-140 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | No external equipment Support Contract | Person_575 | 2012-09-12 01:00 | 2017-08-01 | 30% | 4.4985 | 1.3495 | Accept | 30% | 2.999 | 0.8997 | H2 | 2 | -- | TRUE | 1783.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-140 | Project_020_Risk-140 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | No external equipment Support Contract | Person_575 | 2012-09-12 01:00 | 2017-08-01 | 30% | 4.4985 | 1.3495 | Accept | 30% | 2.999 | 0.8997 | H2 | 2 | -- | TRUE | 1783.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-198 | Project_039_Risk-198 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | subsystems Testing | Person_224 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 3.9995 | 1.9998 | Reduce | 30% | 3.005 | 0.9015 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-198 | Project_039_Risk-198 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | subsystems Testing | Person_224 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 3.9995 | 1.9998 | Reduce | 30% | 3.005 | 0.9015 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-198 | Project_039_Risk-198 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | subsystems Testing | Person_224 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 3.9995 | 1.9998 | Reduce | 30% | 3.005 | 0.9015 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-198 | Project_039_Risk-198 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | subsystems Testing | Person_224 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 3.9995 | 1.9998 | Reduce | 30% | 3.005 | 0.9015 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-198 | Project_039_Risk-198 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | subsystems Testing | Person_224 | 2016-09-20 | 2017-02-19 | 50% | 3.9995 | 1.9998 | Reduce | 30% | 3.005 | 0.9015 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-198 | Project_039_Risk-198 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | subsystems Testing | Person_224 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 3.9995 | 1.9998 | Reduce | 30% | 3.005 | 0.9015 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-198 | Project_039_Risk-198 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | subsystems Testing | Person_224 | 2016-09-20 01:00 | 2017-02-19 01:00 | 50% | 3.9995 | 1.9998 | Reduce | 30% | 3.005 | 0.9015 | H3 | 3 | -- | TRUE | 152 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_470 | 2013-01-07 | 2017-01-19 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1473 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_470 | 2013-01-06 23:00 | 2017-01-18 23:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1473 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1473 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 | 2017-01-19 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1473 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1473 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1473 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1473 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-01-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1473 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-08-20 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1686 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-08-20 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1686 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-08-20 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1686 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 | 2017-08-20 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1686 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_207 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R003 | Project_021_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2013-01-07 01:00 | 2017-11-19 01:00 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 1777 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--03 | Project_021_Risk--03 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Key Technical/Engineering Resource Required Across Multiple Programmes. | Person_174 | 2018-01-21 01:00 | 2019-04-23 | 60% | 2.2624 | 1.3574 | Reduce | 40% | 2.2624 | 0.90497 | H2 | 2 | Stable | TRUE | 456.9583 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 2099.9583 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R024 | Project_021_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build / Decision Point concludes new release reqd | Person_174 | 2012-11-20 01:00 | 2018-08-21 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 2099.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 40% | 2.3067 | 0.92268 | Reduce | 40% | 2.3067 | 0.92268 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 40% | 2.3067 | 0.92268 | Reduce | 40% | 2.3067 | 0.92268 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 | 2019-08-20 | 40% | 2.3067 | 0.92268 | Reduce | 40% | 2.3067 | 0.92268 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 40% | 2.3067 | 0.92268 | Reduce | 40% | 2.3067 | 0.92268 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 40% | 2.3067 | 0.92268 | Reduce | 40% | 2.3067 | 0.92268 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 40% | 2.3067 | 0.92268 | Reduce | 40% | 2.3067 | 0.92268 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 40% | 2.3067 | 0.92268 | Reduce | 40% | 2.3067 | 0.92268 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-021 | Project_018_Risk-021 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Loss of Key Resources | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 40% | 2.3067 | 0.92268 | Reduce | 40% | 2.3067 | 0.92268 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK054 | Project_042_RISK054 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Staff Retention/Business Priorities | Person_134 | 2018-09-23 01:00 | 2019-10-22 01:00 | 33% | 2.8421 | 0.93789 | Accept | 33% | 2.8421 | 0.93789 | H2 | 2 | Stable | TRUE | 394 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 9.3941 | 0.93941 | Accept | 10% | 9.3941 | 0.93941 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 9.3941 | 0.93941 | Accept | 10% | 9.3941 | 0.93941 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 9.3941 | 0.93941 | Accept | 10% | 9.3941 | 0.93941 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 9.3941 | 0.93941 | Accept | 10% | 9.3941 | 0.93941 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 9.3941 | 0.93941 | Accept | 10% | 9.3941 | 0.93941 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 9.3941 | 0.93941 | Accept | 10% | 9.3941 | 0.93941 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk007 | Project_042_Risk007 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Special to type Test Equipment availability | Person_455 | 2016-05-23 | 2020-05-23 | 10% | 9.3941 | 0.93941 | Accept | 10% | 9.3941 | 0.93941 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-017 | Project_096_Risk-017 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Thermal Analysis issues | Person_070 | 2018-05-26 | 2018-10-21 01:00 | 20% | 9.5057 | 1.9011 | Reduce | 10% | 9.4259 | 0.94259 | H3 | 3 | -- | FALSE | 148.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-18 23:00 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 6.2979 | 0.94468 | H3 | 3 | Stable | FALSE | 909.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-18 22:00 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 6.2979 | 0.94468 | H3 | 3 | Stable | FALSE | 909.9167 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-18 21:00 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 6.2979 | 0.94468 | H3 | 3 | Stable | FALSE | 909.875 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 6.2979 | 0.94468 | H3 | 3 | Stable | FALSE | 910.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-3 | Project_020_Risk-3 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Contract Acceptance and Closure process lack of definition | Person_575 | 2015-05-24 | 2017-11-19 01:00 | 50% | 6.2979 | 3.1489 | Reduce | 15% | 6.2979 | 0.94468 | H3 | 3 | Stable | FALSE | 910.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2018-11-20 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 273 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--13 | Project_021_Risk--13 | Threat | Project Contingency | Open | H2 | 2 |  | Critical or Safety PR arises in Final build /Decision Point concludes new release req | Person_174 | 2018-02-20 01:00 | 2019-08-21 01:00 | 20% | 165.5424 | 33.1085 | Reduce | 10% | 165.5424 | 16.5542 | H2 | 2 | Stable | TRUE | 547 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK053 | Project_042_RISK053 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | PR Resolution Too Slow. | Person_134 | 2018-09-23 01:00 | 2019-10-22 01:00 | 50% | 1.8897 | 0.94486 | Accept | 50% | 1.8897 | 0.94486 | H1 | 1 | -- | TRUE | 394 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 2 |  | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 12.5% | 232.2192 | 29.0274 | -- | 12.5% | 156.8004 | 19.6 | H2 | 2 | Stable | TRUE | 511 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-027 | Project_062_Risk-027 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Facility to Test modifications | Person_253 | 2018-03-23 | 2019-04-22 | 50% | 2.3703 | 1.1852 | Reduce | 40% | 2.3703 | 0.94814 | H2 | 2 | Stable | TRUE | 395 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK378 | Project_038_RISK378 | Threat | Project Contingency | Open | H2 | 2 |  | Product Baseline delivery is late | Person_151 | 2015-09-21 01:00 | 2017-02-13 01:00 | 12.5% | 232.2192 | 29.0274 | -- | 12.5% | 156.8004 | 19.6 | H2 | 2 | Stable | TRUE | 511 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK053 | Project_035_RISK053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Assembly Use of Glass Reinforced Plastics | Person_570 | 2015-03-24 | 2016-07-16 | 20% | 8.4297 | 1.6859 | Accept | 20% | 4.745 | 0.949 | H3 | 3 | Stable | FALSE | 480 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK053 | Project_035_RISK053 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Assembly Use of Glass Reinforced Plastics | Person_570 | 2015-03-24 | 2016-07-16 | 20% | 8.4297 | 1.6859 | Accept | 20% | 4.745 | 0.949 | H3 | 3 | Stable | FALSE | 480 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R024 | Project_085_R024 | Threat | Project Contingency | Open | H2 | 2 |  | Supplier Mech failure | Person_409 | 2017-11-20 | 2019-12-21 | 40% | 126.7853 | 50.7141 | Reduce | 20% | 126.7853 | 25.3571 | H2 | 2 | -- | TRUE | 761 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP234 | Project_024_OPP234 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Resources/Skills | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 20% | 129.8301 | 25.966 | -- | 20% | 129.8301 | 25.966 | H2 | 2 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP234 | Project_024_OPP234 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Resources/Skills | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 20% | 129.8301 | 25.966 | -- | 20% | 129.8301 | 25.966 | H2 | 2 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Customer Acceptance -Residual PRs or post acceptance software updates after each release cannot be absorbed | Person_147 | 2015-04-23 | 2018-08-21 | 80% | 1.1933 | 0.95464 | Reduce | 80% | 1.1933 | 0.95464 | H1 | 1 | -- | TRUE | 1216 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-090 | Project_011_Risk-090 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Customer Acceptance -Residual PRs or post acceptance software updates after each release cannot be absorbed | Person_147 | 2015-04-23 | 2018-08-21 | 80% | 1.1933 | 0.95464 | Reduce | 80% | 1.1933 | 0.95464 | H1 | 1 | -- | TRUE | 1216 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-11-20 01:00 | 50% | 4.7805 | 2.3902 | Avoid | 20% | 4.7805 | 0.9561 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK123 | Project_037_RISK123 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real world performance issues once installed | Person_334 | 2016-01-22 01:00 | 2016-11-20 01:00 | 50% | 4.7805 | 2.3902 | Avoid | 20% | 4.7805 | 0.9561 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP234 | Project_024_OPP234 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Resources/Skills | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 20% | 129.8301 | 25.966 | -- | 20% | 129.8301 | 25.966 | H2 | 2 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP234 | Project_024_OPP234 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Resources/Skills | Person_351 | 2016-02-21 01:00 | 2018-05-22 | 20% | 129.8301 | 25.966 | -- | 20% | 129.8301 | 25.966 | H2 | 2 | -- | TRUE | 820.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R080 | Project_085_R080 | Threat | Project Contingency | Open | H2 | 2 |  | Machine quote accuracy | Person_153 | 2017-11-20 | 2019-11-20 | 50% | 148.0859 | 74.043 | Reduce | 25% | 148.0859 | 37.0215 | H2 | 2 | -- | TRUE | 730 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R003 | Project_085_R003 | Threat | Project Contingency | Open | H2 | 2 |  | Marching army Customer Delay | Person_043 | 2017-12-21 | 2018-12-21 | 65% | 138.6084 | 90.0955 | Reduce | 37.5% | 138.6084 | 51.9782 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK332 | Project_034_RISK332 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 0 | 0 | Accept | 30% | 0 | 0 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK332 | Project_034_RISK332 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 0 | 0 | Accept | 30% | 0 | 0 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK332 | Project_034_RISK332 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 0 | 0 | Accept | 30% | 0 | 0 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-021 | Project_023_Risk-021 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Customer Services - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 1.1981 | 0.95847 | Exploit | 80% | 1.1981 | 0.95847 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-021 | Project_023_Risk-021 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Customer Services - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 1.1981 | 0.95847 | Exploit | 80% | 1.1981 | 0.95847 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-021 | Project_023_Risk-021 | Opportunitity | Project Contingency | Open | H2 | 2 | System Engineering | Customer Services - Preventative Maintenance | Person_253 | 2013-05-19 | 2017-05-22 | 80% | 1.1981 | 0.95847 | Exploit | 80% | 1.1981 | 0.95847 | H2 | 2 | Stable | TRUE | 1464 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_096 | Risk-009 | Project_096_Risk-009 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Assurance | Person_083 | 2018-10-05 01:00 | 2019-03-22 | 30% | 3.8342 | 1.1503 | Transfer | 25% | 3.8342 | 0.95856 | H2 | 2 | Stable | TRUE | 167.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK220 | Project_038_RISK220 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Resources needed to deliver the programme | Person_330 | 2013-09-20 01:00 | 2015-10-20 01:00 | 50% | 45.6947 | 22.8474 | Avoid | 10% | 9.5884 | 0.95884 | H2 | 2 | Stable | TRUE | 760 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 4.7948 | 0.95895 | Accept | 20% | 4.7948 | 0.95895 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 4.7948 | 0.95895 | Accept | 20% | 4.7948 | 0.95895 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 4.7948 | 0.95895 | Accept | 20% | 4.7948 | 0.95895 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 4.7948 | 0.95895 | Accept | 20% | 4.7948 | 0.95895 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 4.7948 | 0.95895 | Accept | 20% | 4.7948 | 0.95895 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 4.7948 | 0.95895 | Accept | 20% | 4.7948 | 0.95895 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk004 | Project_042_Risk004 | Threat | Project Contingency | Open | H2 | 2 | Customers | T&S (Travel and Subsistence) | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 4.7948 | 0.95895 | Accept | 20% | 4.7948 | 0.95895 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK003 | Project_083_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain late delivery against Baseline Plan (Internal and External) | Person_391 | 2018-02-20 01:00 | 2019-05-16 | 60% | 2.3988 | 1.4393 | Reduce | 40% | 2.3988 | 0.95952 | H2 | 2 | Stable | TRUE | 449.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-315 | Project_027_Risk-315 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Transition to Support - Spares | Person_060 | 2015-04-15 | 2016-05-22 | 5% | 19.1935 | 0.95968 | Accept | 5% | 19.1935 | 0.95968 | H2 | 2 | -- | TRUE | 403 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-315 | Project_027_Risk-315 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Transition to Support - Spares | Person_060 | 2015-04-15 | 2016-05-22 | 5% | 19.1935 | 0.95968 | Accept | 5% | 19.1935 | 0.95968 | H2 | 2 | -- | TRUE | 403 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-315 | Project_027_Risk-315 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Transition to Support - Spares | Person_060 | 2015-04-15 | 2016-05-22 | 5% | 19.1935 | 0.95968 | Accept | 5% | 19.1935 | 0.95968 | H2 | 2 | -- | TRUE | 403 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-315 | Project_027_Risk-315 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Transition to Support - Spares | Person_060 | 2015-04-15 | 2016-05-22 | 5% | 19.1935 | 0.95968 | Accept | 5% | 19.1935 | 0.95968 | H2 | 2 | -- | TRUE | 403 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-315 | Project_027_Risk-315 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Transition to Support - Spares | Person_060 | 2015-04-15 | 2016-05-22 | 5% | 19.1935 | 0.95968 | Accept | 5% | 19.1935 | 0.95968 | H2 | 2 | -- | TRUE | 403 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 | 2016-12-19 | 30% | 3.973 | 1.1919 | Reduce | 30% | 3.2005 | 0.96015 | H2 | 2 | Stable | TRUE | 99 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R029 | Project_021_Risk-R029 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-08-03 | 2016-10-19 | 30% | 3.973 | 1.1919 | Reduce | 30% | 3.2005 | 0.96015 | H2 | 2 | Improving | TRUE | 77 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 01:00 | 2016-12-19 01:00 | 30% | 3.973 | 1.1919 | Reduce | 30% | 3.2005 | 0.96015 | H2 | 2 | Stable | TRUE | 99 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 30% | 3.973 | 1.1919 | Reduce | 30% | 3.2005 | 0.96015 | H2 | 2 | Stable | TRUE | 133 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-007 | Project_021_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-09-11 01:00 | 2017-01-22 01:00 | 30% | 3.973 | 1.1919 | Reduce | 30% | 3.2005 | 0.96015 | H2 | 2 | Stable | TRUE | 133 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK085 | Project_076_RISK085 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | E2 Cloud - Shared Cloud License | Person_152 | 2019-02-21 01:00 | 2019-05-23 | 20% | 4.8095 | 0.96189 | Reject | 20% | 4.8095 | 0.96189 | H3 | 3 | Stable | TRUE | 90.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK332 | Project_034_RISK332 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 0 | 0 | Accept | 30% | 0 | 0 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO44 | Project_021_Risk-RO44 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to delay to release of build standard for | Person_174 | 2016-08-17 01:00 | 2016-09-03 01:00 | 10% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 221.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R042 | Project_021_Risk-R042 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to build standard issue | Person_174 | 2016-08-17 01:00 | 2016-09-03 01:00 | 10% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R043 | Project_021_Risk-R043 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to lack of Sys Eng availability | Person_174 | 2016-08-17 01:00 | 2016-09-03 01:00 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R040 | Project_021_Risk-R040 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to weather | Person_174 | 2016-08-17 01:00 | 2016-09-03 01:00 | 10% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R060 | Project_021_Risk-R060 | Threat | Project Contingency | Open | H2 | 2 |  | Trials delay due to lack of personnel | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 105.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_279 | 2016-11-22 20:00 | 2021-11-22 20:00 | 35% | 6.4382 | 2.2534 | Reduce | 15% | 6.4382 | 0.96573 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK332 | Project_034_RISK332 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 0 | 0 | Accept | 30% | 0 | 0 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO44 | Project_021_Risk-RO44 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to delay to release of build standard for | Person_174 | 2016-08-17 | 2016-09-03 | 10% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 | 2017-04-21 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 222 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R042 | Project_021_Risk-R042 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to build standard issue | Person_174 | 2016-08-17 | 2016-09-03 | 10% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R043 | Project_021_Risk-R043 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to lack of Sys Eng availability | Person_174 | 2016-08-17 | 2016-09-03 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R040 | Project_021_Risk-R040 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to weather | Person_174 | 2016-08-17 | 2016-09-03 | 10% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R060 | Project_021_Risk-R060 | Threat | Project Contingency | Open | H2 | 2 |  | Trials delay due to lack of personnel | Person_174 | 2016-11-20 | 2017-01-20 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2016-11-19 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 105 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO44 | Project_021_Risk-RO44 | Threat | Project Contingency | Open | H2 | 2 |  | delay due to delay to release of build standard for | Person_174 | 2016-08-17 01:00 | 2016-09-03 01:00 | 10% | 0 | 0 | Reduce | 5% | 0 | 0 | H3 | 3 | -- | FALSE | 17 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 221.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R060 | Project_021_Risk-R060 | Threat | Project Contingency | Open | H2 | 2 |  | Trials delay due to lack of personnel | Person_174 | 2016-11-20 01:00 | 2017-01-20 01:00 | 30% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 61 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2016-11-19 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 105.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 221.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 221.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 20% | 4.8444 | 0.96888 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 20% | 4.8444 | 0.96888 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 | 2020-09-21 | 20% | 4.8444 | 0.96888 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 20% | 4.8444 | 0.96888 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 20% | 4.8444 | 0.96888 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 22:00 | 2020-09-20 22:00 | 20% | 4.8444 | 0.96888 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 20% | 4.8444 | 0.96888 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 30% | 4.8444 | 1.4533 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 22:00 | 2020-09-20 22:00 | 20% | 4.8444 | 0.96888 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 | 2020-09-21 | 30% | 4.8444 | 1.4533 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 30% | 4.8444 | 1.4533 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK059 | Project_065_RISK059 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System will fail to meet it's requirement | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 30% | 4.8444 | 1.4533 | Reduce | 20% | 4.8444 | 0.96888 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-06 01:00 | 2020-07-16 | 30% | 4.8596 | 1.4579 | Reduce | 20% | 4.8596 | 0.97191 | H3 | 3 | -- | FALSE | 1013.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-06 | 2020-07-16 | 30% | 4.8596 | 1.4579 | Reduce | 20% | 4.8596 | 0.97191 | H3 | 3 | -- | FALSE | 1014 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-06 01:00 | 2020-07-16 | 30% | 4.8596 | 1.4579 | Reduce | 20% | 4.8596 | 0.97191 | H3 | 3 | -- | FALSE | 1013.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-05 23:00 | 2020-07-16 | 30% | 4.8596 | 1.4579 | Reduce | 20% | 4.8596 | 0.97191 | H3 | 3 | -- | FALSE | 1014.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-004 | Project_021_Risk-004 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-09-11 01:00 | 2017-04-21 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 221.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-01-04 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 151.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK063 | Project_043_RISK063 | Threat | Project Contingency | Open | H2 | 2 |  | Technical Publications overspend | Person_084 | 2014-09-13 | 2018-03-21 | 25% | 0 | 0 | -- | 5% | 0 | 0 | H3 | 3 | -- | FALSE | 1285 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | Risk-001 | Project_043_Risk-001 | Threat | Project Contingency | Open | H2 | 2 |  | Training Programme capacity | Person_658 | 2014-09-13 | 2018-03-21 | 15% | 0 | 0 | -- | 5% | 0 | 0 | H3 | 3 | -- | FALSE | 1285 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK028 | Project_043_RISK028 | Threat | Project Contingency | Open | H2 | 2 |  | Solution needs to change to account for specific platform integration | Person_051 | 2014-09-13 | 2018-03-21 | 25% | 0 | 0 | -- | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 1285 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK029 | Project_043_RISK029 | Threat | Project Contingency | Open | H2 | 2 |  | Standard testing identifies issues | Person_051 | 2014-09-13 | 2018-03-21 | 20% | 0 | 0 | -- | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 1285 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_043 | RISK031 | Project_043_RISK031 | Threat | Project Contingency | Open | H2 | 2 |  | Non delivery of Customer documentation | Person_056 | 2014-09-13 | 2018-03-21 | 10% | 0 | 0 | -- | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 1285 |  | 1 | 1 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 320 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 320 |  | 1 | 0 | 1
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 320 |  | 1 | 0 | 1
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_721 | 2016-08-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 320 |  | 1 | 0 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_482 | 2016-08-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 320 |  | 1 | 0 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_482 | 2016-08-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 320 |  | 1 | 0 | 1
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R061 | Project_021_Risk-R061 | Threat | Project Contingency | Open | H2 | 2 |  | Component Approval delay due to Suitably Qualified and experienced staff availability Resource availability | Person_482 | 2016-08-06 | 2017-06-22 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | Stable | FALSE | 320 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK038 | Project_075_RISK038 | Threat | Project Contingency | Open | H2 | 2 |  | Loss of critical personnel | Person_449 | 2017-05-23 | 2019-01-21 01:00 | 30% | 8.4371 | 2.5311 | Avoid | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 608.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R050 | Project_085_R050 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Telemetry testing is not achievable | Person_539 | 2017-12-21 | 2019-12-21 | 50% | 3.791 | 1.8955 | Reduce | 26% | 3.791 | 0.98566 | H3 | 3 | -- | TRUE | 730 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK038 | Project_075_RISK038 | Threat | Project Contingency | Open | H2 | 2 |  | Loss of critical personnel | Person_449 | 2017-05-23 | 2019-01-21 01:00 | 30% | 8.4371 | 2.5311 | Avoid | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 608.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK038 | Project_075_RISK038 | Threat | Project Contingency | Open | H2 | 2 |  | Loss of critical personnel | Person_449 | 2017-05-23 | 2019-01-21 01:00 | 30% | 8.4371 | 2.5311 | Avoid | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 608.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK038 | Project_075_RISK038 | Threat | Project Contingency | Open | H2 | 2 |  | Loss of critical personnel | Person_449 | 2017-05-23 | 2019-01-21 01:00 | 30% | 8.4371 | 2.5311 | Avoid | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 608.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK038 | Project_075_RISK038 | Threat | Project Contingency | Open | H2 | 2 |  | Loss of critical personnel | Person_449 | 2017-05-23 | 2019-01-21 01:00 | 30% | 8.4371 | 2.5311 | Avoid | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 608.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK004 | Project_099_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | New wound components do not meet specification at system level as original components | Person_002 | 2018-10-21 01:00 | 2020-03-22 | 20% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 517.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_080 | RISK005 | Project_080_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Avaliability of correct hospital stock for repair | Person_036 | 2016-11-20 01:00 | 2018-11-21 01:00 | 80% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 731 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_080 | RISK004 | Project_080_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Tooling and Test Equipment | Person_149 | 2016-11-20 01:00 | 2018-12-20 01:00 | 50% | 0 | 0 | Reduce | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 760 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK007 | Project_073_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Resources tight | Person_537 | 2017-09-20 01:00 | 2018-10-20 01:00 | 40% | 0 | 0 | Accept | 10% | 0 | 0 | H3 | 3 | -- | FALSE | 395 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK010 | Project_074_RISK010 | Threat | Project Contingency | Open | H3 | 3 |  | Trade conpliance issues | Person_493 | 2017-09-20 01:00 | 2019-11-21 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | TRUE | 792 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_073 | RISK014 | Project_073_RISK014 | Threat | Project Contingency | Open | H2 | 2 |  | Chasis Covers | Person_263 | 2018-08-22 01:00 | 2018-12-20 01:00 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | -- | FALSE | 120 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-08-20 01:00 | 50% | 4.6444 | 2.3222 | Avoid | 30% | 3.296 | 0.98881 | H2 | 2 | Worsening | TRUE | 395.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R002 | Project_021_Risk-R002 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Rig Unreliability | Person_470 | 2013-01-07 | 2016-07-20 | 50% | 1.9865 | 0.99325 | Accept | 50% | 1.9865 | 0.99325 | H1 | 1 | Stable | TRUE | 1290 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R002 | Project_021_Risk-R002 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Rig Unreliability | Person_470 | 2013-01-06 23:00 | 2016-07-20 | 50% | 1.9865 | 0.99325 | Accept | 50% | 1.9865 | 0.99325 | H1 | 1 | Stable | TRUE | 1290.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Reduce | 5% | 20.0332 | 1.0017 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Reduce | 5% | 20.0332 | 1.0017 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Reduce | 5% | 20.0332 | 1.0017 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Reduce | 5% | 20.0332 | 1.0017 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Reduce | 5% | 20.0332 | 1.0017 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Reduce | 5% | 20.0332 | 1.0017 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-01-19 01:00 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 60 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 174.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-20 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 175 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 174.9583 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-19 23:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-19 22:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 175.0833 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-19 23:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 174.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-19 22:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 175.0833 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-20 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 175 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-20 01:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 174.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK479 | Project_065_RISK479 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | An agreement is not reached on for the equpment requirements prior to SRR/SFR | Person_661 | 2017-11-19 23:00 | 2018-05-14 | 50% | 2.0043 | 1.0022 | Accept | 50% | 2.0043 | 1.0022 | H2 | 2 | -- | TRUE | 175.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-12-03 01:00 | 2021-01-20 01:00 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-03 01:00 | 2021-01-20 01:00 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-03 | 2021-01-20 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-03 | 2021-01-20 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 23:00 | 2021-01-19 23:00 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 23:00 | 2021-01-19 23:00 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 23:00 | 2021-01-19 23:00 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 21:00 | 2021-01-19 21:00 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK052 | Project_017_RISK052 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Test Equipment Failure | Person_547 | 2016-12-02 20:00 | 2021-01-19 20:00 | 50% | 3.3479 | 1.6739 | Reduce | 30% | 3.3479 | 1.0044 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Commercial Exposure Subsystem | Person_272 | 2014-05-09 | 2023-11-20 01:00 | 5% | 20.1456 | 1.0073 | -- | 5% | 20.1456 | 1.0073 | H3 | 3 | -- | TRUE | 3482.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Commercial Exposure Subsystem | Person_272 | 2016-09-20 01:00 | 2017-05-22 | 5% | 20.1456 | 1.0073 | Reduce | 5% | 20.1456 | 1.0073 | H3 | 3 | -- | TRUE | 243.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Commercial Exposure Subsystem | Person_272 | 2016-09-20 01:00 | 2017-05-22 | 5% | 20.1456 | 1.0073 | Reduce | 5% | 20.1456 | 1.0073 | H3 | 3 | -- | TRUE | 243.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Commercial Exposure Subsystem | Person_272 | 2016-09-20 01:00 | 2017-05-22 | 5% | 20.1456 | 1.0073 | Reduce | 5% | 20.1456 | 1.0073 | H3 | 3 | -- | TRUE | 243.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Commercial Exposure Subsystem | Person_272 | 2016-09-20 01:00 | 2017-05-22 | 5% | 20.1456 | 1.0073 | Reduce | 5% | 20.1456 | 1.0073 | H3 | 3 | -- | TRUE | 243.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-070 | Project_026_Risk-070 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Commercial Exposure Subsystem | Person_272 | 2016-09-20 01:00 | 2017-05-22 | 5% | 20.1456 | 1.0073 | Reduce | 5% | 20.1456 | 1.0073 | H3 | 3 | -- | TRUE | 243.9583 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | OPP1008 | Project_091_OPP1008 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Accelerate Build Programme | Person_557 | 2018-08-22 01:00 | 2022-05-21 | 50% | 2.0146 | 1.0073 | Exploit | 50% | 2.0146 | 1.0073 | H2 | 2 | -- | TRUE | 1367.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | OPP1008 | Project_091_OPP1008 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | Accelerate Build Programme | Person_557 | 2018-09-21 01:00 | 2022-05-21 | 50% | 2.0146 | 1.0073 | Exploit | 50% | 2.0146 | 1.0073 | H2 | 2 | -- | TRUE | 1337.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-319 | Project_027_Risk-319 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Facility Obsolescence (Rigs, Facilities,Software) | Person_513 | 2015-04-15 | 2017-08-20 01:00 | 40% | 8.3972 | 3.3589 | Reduce | 12% | 8.3972 | 1.0077 | H3 | 3 | -- | FALSE | 858.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-319 | Project_027_Risk-319 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Facility Obsolescence (Rigs, Facilities,Software) | Person_513 | 2015-04-15 | 2017-08-20 01:00 | 40% | 8.3972 | 3.3589 | Reduce | 12% | 8.3972 | 1.0077 | H3 | 3 | -- | FALSE | 858.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-319 | Project_027_Risk-319 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Facility Obsolescence (Rigs, Facilities,Software) | Person_513 | 2015-04-15 | 2017-08-20 01:00 | 40% | 8.3972 | 3.3589 | Reduce | 12% | 8.3972 | 1.0077 | H3 | 3 | -- | FALSE | 858.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-319 | Project_027_Risk-319 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Facility Obsolescence (Rigs, Facilities,Software) | Person_513 | 2015-04-15 | 2017-08-20 01:00 | 40% | 8.3972 | 3.3589 | Reduce | 12% | 8.3972 | 1.0077 | H3 | 3 | -- | FALSE | 858.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-319 | Project_027_Risk-319 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Facility Obsolescence (Rigs, Facilities,Software) | Person_513 | 2015-04-15 | 2017-08-20 01:00 | 40% | 8.3972 | 3.3589 | Reduce | 12% | 8.3972 | 1.0077 | H3 | 3 | -- | FALSE | 858.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-319 | Project_027_Risk-319 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Facility Obsolescence (Rigs, Facilities,Software) | Person_513 | 2015-04-15 | 2017-08-20 01:00 | 40% | 8.3972 | 3.3589 | Reduce | 12% | 8.3972 | 1.0077 | H3 | 3 | -- | FALSE | 858.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-319 | Project_027_Risk-319 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Facility Obsolescence (Rigs, Facilities,Software) | Person_513 | 2015-04-15 | 2017-08-20 01:00 | 40% | 8.3972 | 3.3589 | Reduce | 12% | 8.3972 | 1.0077 | H3 | 3 | -- | FALSE | 858.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-319 | Project_027_Risk-319 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Facility Obsolescence (Rigs, Facilities,Software) | Person_513 | 2015-04-15 | 2017-08-20 01:00 | 40% | 8.3972 | 3.3589 | Reduce | 12% | 8.3972 | 1.0077 | H3 | 3 | -- | FALSE | 858.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE-10 | Project_067_SE-10 | Threat | Project Contingency | Open | H2 | 2 |  | Configuration baseline unstable for Platform | Person_327 | 2017-10-26 | 2018-08-18 | 50% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | FALSE | 296 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | Risk-001 | Project_067_Risk-001 | Threat | Project Contingency | Open | H3 | 3 |  | Lack of Technical Control plan | Person_327 | 2017-07-21 | 2018-09-20 | 100% | 0 | 0 | Reduce | 20% | 0 | 0 | H3 | 3 | Improving | TRUE | 426 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_067 | SE005 | Project_067_SE005 | Threat | Project Contingency | Open | H2 | 2 |  | Change in Delivery Approach | Person_327 | 2018-07-07 | 2018-08-05 | 80% | 0 | 0 | -- | 20% | 0 | 0 | H3 | 3 | Stable | FALSE | 29 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-09-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 15% | 6.7418 | 1.0113 | H3 | 3 | Stable | FALSE | 426.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-09-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 15% | 6.7418 | 1.0113 | H3 | 3 | Stable | FALSE | 426.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 15% | 6.7418 | 1.0113 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 15% | 6.7418 | 1.0113 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 15% | 6.7418 | 1.0113 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 15% | 6.7418 | 1.0113 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-11-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 15% | 6.7418 | 1.0113 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK007 | Project_092_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Converters contain prohibited materials | Person_169 | 2018-02-20 01:00 | 2019-12-26 01:00 | 5% | 0.060012 | 0.0030006 | Accept | 5% | 0.060012 | 0.0030006 | H3 | 3 | -- | FALSE | 674 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk308 | Project_009_Risk308 | Threat | Project Contingency | Open | H2 | 2 |  | Industry Learner hours - new staff over an elongated period | Person_284 | 2015-08-16 | 2016-09-19 01:00 | 10% | 1.4699 | 0.14699 | Reduce | 0.4% | 1.4699 | 0.0058797 | H3 | 3 | -- | FALSE | 400.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK006 | Project_074_RISK006 | Threat | Project Contingency | Open | H3 | 3 |  | Supplier Issues | Person_263 | 2017-09-20 01:00 | 2019-11-21 01:00 | 20% | 0.039983 | 0.0079966 | Accept | 20% | 0.039983 | 0.0079966 | H3 | 3 | -- | TRUE | 792 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_071 | Risk020 | Project_071_Risk020 | Threat | Project Contingency | Open | H3 | 3 |  | Hardware availability ??? | Person_107 | 2017-11-22 01:00 | 2019-11-10 01:00 | 20% | 0.13293 | 0.026585 | -- | 10% | 0.13293 | 0.013293 | H3 | 3 | -- | TRUE | 718 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_080 | RISK001 | Project_080_RISK001 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescent Monitoring | Person_149 | 2016-11-20 01:00 | 2018-12-21 01:00 | 20% | 0.46186 | 0.092371 | Reduce | 5% | 0.3079 | 0.015395 | H3 | 3 | -- | FALSE | 761 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK007 | Project_074_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Resources | Person_493 | 2017-09-20 01:00 | 2019-11-21 01:00 | 40% | 0.079966 | 0.031986 | Reduce | 20% | 0.079966 | 0.015993 | H3 | 3 | -- | FALSE | 792 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK018 | Project_058_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Doc Pack Contents | Person_215 | 2018-03-22 | 2018-04-21 | 40% | 1.1744 | 0.46977 | Reduce | 10% | 0.19574 | 0.019574 | H3 | 3 | -- | TRUE | 30 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK018 | Project_058_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Doc Pack Contents | Person_215 | 2018-03-22 | 2018-04-21 | 40% | 1.1744 | 0.46977 | Reduce | 10% | 0.19574 | 0.019574 | H3 | 3 | -- | TRUE | 30 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK018 | Project_058_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Doc Pack Contents | Person_215 | 2018-03-22 | 2018-06-22 | 40% | 1.1744 | 0.46977 | Reduce | 10% | 0.19574 | 0.019574 | H3 | 3 | -- | TRUE | 92 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK018 | Project_058_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Doc Pack Contents | Person_215 | 2018-03-22 | 2018-06-22 | 40% | 1.1744 | 0.46977 | Reduce | 10% | 0.19574 | 0.019574 | H3 | 3 | -- | TRUE | 92 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_074 | RISK004 | Project_074_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Thermal Chamber | Person_493 | 2017-09-20 01:00 | 2019-11-21 01:00 | 20% | 0.19991 | 0.039983 | Reduce | 10% | 0.19991 | 0.019991 | H3 | 3 | -- | FALSE | 792 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK336 | Project_034_RISK336 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 0.57396 | 0.22958 | Avoid | 10% | 0.28698 | 0.028698 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK336 | Project_034_RISK336 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 0.57396 | 0.22958 | Avoid | 10% | 0.28698 | 0.028698 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK336 | Project_034_RISK336 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 0.57396 | 0.22958 | Avoid | 10% | 0.28698 | 0.028698 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK336 | Project_034_RISK336 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 0.57396 | 0.22958 | Avoid | 10% | 0.28698 | 0.028698 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_034 | RISK336 | Project_034_RISK336 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 0.57396 | 0.22958 | Avoid | 10% | 0.28698 | 0.028698 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK031 | Project_058_RISK031 | Threat | Project Contingency | Open | H3 | 3 |  | Customer Witnessing | Person_215 | 2017-05-23 | 2018-09-19 01:00 | 20% | 0.78295 | 0.15659 | Reduce | 10% | 0.39148 | 0.039148 | H3 | 3 | -- | TRUE | 484.0417 |  | 1 | 0 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Open PR's | Person_319 | 2017-04-22 | 2018-11-20 01:00 | 50% | 0.29361 | 0.1468 | Reduce | 15% | 0.29361 | 0.044041 | H3 | 3 | Improving | FALSE | 577.0417 |  | 1 | 0 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Open PR's | Person_319 | 2017-04-22 | 2018-11-20 01:00 | 50% | 0.29361 | 0.1468 | Reduce | 15% | 0.29361 | 0.044041 | H3 | 3 | Improving | FALSE | 577.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Open PR's | Person_319 | 2017-04-22 | 2018-11-20 01:00 | 50% | 0.29361 | 0.1468 | Reduce | 15% | 0.29361 | 0.044041 | H3 | 3 | Improving | FALSE | 577.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Open PR's | Person_319 | 2017-04-22 | 2018-11-20 01:00 | 50% | 0.29361 | 0.1468 | Reduce | 15% | 0.29361 | 0.044041 | H3 | 3 | Improving | FALSE | 577.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-037 | Project_028_Risk-037 | Threat | Project Contingency | Open | H2 | 2 |  | Migration to RedHat 7 | Person_542 | 2015-04-08 | 2016-08-20 | 20% | 0.44449 | 0.088898 | Accept | 10% | 0.44449 | 0.044449 | H3 | 3 | Stable | FALSE | 500 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK027 | Project_029_RISK027 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Component Supply | Person_403 | 2018-10-22 01:00 | 2019-09-20 01:00 | 75% | 2.5667 | 1.925 | Reduce | 40% | 2.5667 | 1.0267 | H2 | 2 | -- | TRUE | 333 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-057 | Project_007_R-057 | Threat | Project Contingency | Open | H2 | 2 |  | Interface cannot be fully proven until installation | Person_245 | 2015-05-24 | 2015-12-21 19:00 | 40% | 0.97576 | 0.3903 | Reduce | 10% | 0.48788 | 0.048788 | H3 | 3 | Improving | FALSE | 211.7917 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-076 | Project_007_R-076 | Threat | Project Contingency | Open | H3 | 3 |  | Contract Extension | Person_386 | 2013-12-03 19:00 | 2016-02-19 19:00 | 70% | 6.3425 | 4.4397 | Avoid | 5% | 0.97576 | 0.048788 | H3 | 3 | Stable | TRUE | 808 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK014 | Project_081_RISK014 | Threat | Project Contingency | Open | H3 | 3 |  | Supplier request financial support for Training admin. | Person_260 | 2018-02-20 01:00 | 2021-09-20 01:00 | 10% | 0.50038 | 0.050038 | Reduce | 10% | 0.50038 | 0.050038 | H3 | 3 | Stable | TRUE | 1308 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-032 | Project_028_Risk-032 | Threat | Project Contingency | Open | H3 | 3 |  | Delays to Software Validation & Development | Person_542 | 2015-04-08 | 2016-09-18 21:00 | 50% | 0.52384 | 0.26192 | Reduce | 10% | 0.52384 | 0.052384 | H3 | 3 | Stable | TRUE | 529.875 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-22 01:00 | 2019-10-22 01:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-22 | 2019-10-22 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-22 01:00 | 2019-10-22 01:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-21 23:00 | 2019-10-21 23:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-21 22:00 | 2019-10-21 22:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-21 23:00 | 2019-10-21 23:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-22 01:00 | 2019-10-22 01:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-21 22:00 | 2019-10-21 22:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2021-04-22 | 2024-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2018-05-23 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2021-04-22 | 2024-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2018-05-23 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2021-04-22 | 2024-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2018-05-23 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2021-04-22 | 2024-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2018-05-23 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2021-04-22 | 2024-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2018-05-23 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2021-04-22 | 2024-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2018-05-23 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-22 | 2019-10-22 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-22 01:00 | 2019-10-22 01:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2020-05-23 | 2023-04-23 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2021-04-22 | 2024-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160- | Project_065_RISK160- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2018-05-23 | 2021-04-22 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK120 | Project_065_RISK120 | Threat | Project Contingency | Open | H3 | 3 |  | Display current measurement fails to identify display segment fault | Person_022 | 2018-10-21 23:00 | 2019-10-21 23:00 | 30% | 0.56625 | 0.16987 | Reduce | 10% | 0.56625 | 0.056625 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk305 | Project_009_Risk305 | Threat | Project Contingency | Open | H2 | 2 |  | Availability of Sunject Matter Experts for Installation | Person_284 | 2015-08-16 | 2016-09-19 01:00 | 10% | 1.3662 | 0.13662 | Reduce | 5% | 1.3662 | 0.068308 | H3 | 3 | -- | FALSE | 400.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2020-05-23 | 2023-04-23 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK013 | Project_081_RISK013 | Threat | Project Contingency | Open | H3 | 3 |  | Additional training requested by customer. | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 15% | 0.50038 | 0.075057 | Reduce | 15% | 0.50038 | 0.075057 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module mass | Person_038 | 2017-10-01 01:00 | 2018-10-22 01:00 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 386 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2020-05-23 | 2023-04-23 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module mass | Person_038 | 2017-10-01 01:00 | 2018-10-22 01:00 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 386 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module mass | Person_038 | 2017-10-01 | 2018-10-22 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 386 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK160-Risk- | Project_065_RISK160-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Performance with Deliverable Infrastructure | Person_160 | 2020-05-23 | 2023-04-23 | 30% | 3.4651 | 1.0395 | Accept | 30% | 3.4651 | 1.0395 | H2 | 2 | -- | TRUE | 1065 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2016-07-20 | 30% | 5.4553 | 1.6366 | Reduce | 20% | 5.252 | 1.0504 | H2 | 2 | Stable | TRUE | 466 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2016-09-19 01:00 | 30% | 5.4553 | 1.6366 | Reduce | 20% | 5.252 | 1.0504 | H2 | 2 | Stable | TRUE | 527.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-043 | Project_028_Risk-043 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | PEN Testing Security Features | Person_253 | 2015-04-11 | 2017-01-20 01:00 | 30% | 5.4553 | 1.6366 | Reduce | 20% | 5.252 | 1.0504 | H2 | 2 | Stable | TRUE | 650.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module mass | Person_038 | 2017-10-01 01:00 | 2018-10-22 01:00 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 386 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2020-05-23 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Accept | 30% | 3.5496 | 1.0649 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2020-05-23 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Accept | 30% | 3.5496 | 1.0649 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2020-05-23 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Accept | 30% | 3.5496 | 1.0649 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK346- | Project_065_RISK346- | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test equipment (Simulators) | Person_160 | 2020-05-23 | 2021-05-22 | 30% | 3.5496 | 1.0649 | Accept | 30% | 3.5496 | 1.0649 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-016 | Project_077_T-016 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Autotest | Person_092 | 2018-12-09 01:00 | 2020-02-21 01:00 | 50% | 2.1341 | 1.067 | Reduce | 50% | 2.1341 | 1.067 | H2 | 2 | Stable | TRUE | 439 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-05-23 | 2019-10-21 01:00 | 25% | 3.9356 | 0.98391 | Accept | 25% | 4.2779 | 1.0695 | H2 | 2 | -- | TRUE | 1246.0417 |  | 0 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-05-23 | 2019-10-21 01:00 | 25% | 3.9356 | 0.98391 | Accept | 25% | 4.2779 | 1.0695 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 0 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 25% | 3.9356 | 0.98391 | Accept | 25% | 4.2779 | 1.0695 | H2 | 2 | Stable | TRUE | 1034 |  | 0 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 25% | 3.9356 | 0.98391 | Accept | 25% | 4.2779 | 1.0695 | H2 | 2 | Stable | TRUE | 1034 |  | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-10-21 01:00 | 25% | 3.9356 | 0.98391 | Accept | 25% | 4.2779 | 1.0695 | H2 | 2 | Stable | TRUE | 1034 |  | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK016 | Project_029_Risk-RISK016 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Batch 1 does not meet contracted acceptance criteria [knock-on into Batch 2 re-design] | Person_102 | 2016-12-21 01:00 | 2019-08-14 | 25% | 4.2779 | 1.0695 | Accept | 25% | 4.2779 | 1.0695 | H2 | 2 | Stable | TRUE | 965.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-050 | Project_026_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Post CDR Supply | Person_396 | 2014-11-21 01:00 | 2018-01-21 01:00 | 50% | 2.6861 | 1.343 | Reduce | 40% | 2.6861 | 1.0744 | H2 | 2 | -- | TRUE | 1157 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-050 | Project_026_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Post CDR Supply | Person_396 | 2014-11-21 01:00 | 2018-01-21 01:00 | 50% | 2.6861 | 1.343 | Reduce | 40% | 2.6861 | 1.0744 | H2 | 2 | -- | TRUE | 1157 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-050 | Project_026_Risk-050 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Post CDR Supply | Person_396 | 2014-11-21 01:00 | 2018-01-21 01:00 | 50% | 2.6861 | 1.343 | Reduce | 40% | 2.6861 | 1.0744 | H2 | 2 | -- | TRUE | 1157 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-047 | Project_062_Risk-047 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Redhat6 on PCI shelf | Person_253 | 2017-07-21 | 2019-03-24 | 30% | 7.1808 | 2.1542 | Avoid | 15% | 7.1808 | 1.0771 | H2 | 2 | Stable | TRUE | 611 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-18 23:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 2.6991 | 1.0796 | H2 | 2 | Stable | TRUE | 3985.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-18 22:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 2.6991 | 1.0796 | H2 | 2 | Stable | TRUE | 3985.9167 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-18 21:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 2.6991 | 1.0796 | H2 | 2 | Stable | TRUE | 3985.875 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 2.6991 | 1.0796 | H2 | 2 | Stable | TRUE | 3986.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 2.6991 | 1.0796 | H2 | 2 | Stable | TRUE | 3986.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 2.6991 | 1.0796 | H2 | 2 | Stable | TRUE | 3986.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 2.6991 | 1.0796 | H2 | 2 | Stable | TRUE | 3986.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-66 | Project_020_Risk-66 | Threat | Project Contingency | Open | H2 | 2 | Customers | Installation and Acceptance | Person_295 | 2006-03-23 | 2017-02-19 01:00 | 50% | 3.9587 | 1.9793 | Reduce | 40% | 2.6991 | 1.0796 | H2 | 2 | Stable | TRUE | 3986.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 20% | 12.1982 | 2.4396 | Accept | 10% | 10.8428 | 1.0843 | H2 | 2 | Stable | TRUE | 759.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 20% | 12.1982 | 2.4396 | Accept | 10% | 10.8428 | 1.0843 | H2 | 2 | Stable | TRUE | 759.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module mass | Person_038 | 2017-09-30 23:00 | 2018-10-21 23:00 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 386 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module mass | Person_038 | 2017-09-30 22:00 | 2018-10-21 22:00 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 386 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module mass | Person_038 | 2017-09-30 23:00 | 2018-10-21 23:00 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 386 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module characteriSuppliercs | Person_038 | 2018-10-22 01:00 | 2020-04-22 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module mass | Person_038 | 2017-09-30 22:00 | 2018-10-21 22:00 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 386 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module characteriSuppliercs | Person_038 | 2018-10-22 | 2020-04-22 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 548 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module characteriSuppliercs | Person_038 | 2018-10-22 01:00 | 2020-04-22 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 547.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK330 | Project_065_RISK330 | Threat | Project Contingency | Open | H3 | 3 |  | SubSystem module characteriSuppliercs | Person_038 | 2018-10-21 23:00 | 2020-04-22 | 10% | 1.7748 | 0.17748 | Reduce | 10% | 0.76063 | 0.076063 | H3 | 3 | -- | TRUE | 548.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK018 | Project_058_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Doc Pack Contents | Person_215 | 2018-03-22 | 2018-07-29 | 40% | 1.1744 | 0.46977 | Reduce | 20% | 0.39148 | 0.078295 | H3 | 3 | -- | TRUE | 129 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK018 | Project_058_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Doc Pack Contents | Person_215 | 2018-03-22 | 2018-07-29 | 40% | 1.1744 | 0.46977 | Reduce | 20% | 0.39148 | 0.078295 | H3 | 3 | -- | TRUE | 129 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK018 | Project_058_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Doc Pack Contents | Person_215 | 2018-03-22 | 2018-07-29 | 40% | 1.1744 | 0.46977 | Reduce | 20% | 0.39148 | 0.078295 | H3 | 3 | -- | TRUE | 129 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_012 | RISK023 | Project_012_RISK023 | Threat | Project Contingency | Open | H3 | 3 |  | Additional tests for final units | Person_359 | 2015-09-21 01:00 | 2016-04-12 | 80% | 0.20963 | 0.1677 | Accept | 40% | 0.20963 | 0.083852 | H3 | 3 | Stable | TRUE | 203.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK022 | Project_083_RISK022 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Availability of Engineering Resource | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 30% | 0 | 0 | Reduce | 20% | 5.4459 | 1.0892 | H3 | 3 | Stable | FALSE | 309 |  | 0 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-20 01:00 | 2017-07-21 | 10% | 21.8655 | 2.1865 | Reduce | 5% | 21.8655 | 1.0933 | H2 | 2 | -- | TRUE | 242.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-20 01:00 | 2017-07-21 | 10% | 21.8655 | 2.1865 | Reduce | 5% | 21.8655 | 1.0933 | H2 | 2 | Stable | TRUE | 242.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-20 | 2017-07-21 | 10% | 21.8655 | 2.1865 | Reduce | 5% | 21.8655 | 1.0933 | H2 | 2 | Stable | TRUE | 243 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-19 23:00 | 2017-07-21 | 10% | 21.8655 | 2.1865 | Reduce | 5% | 21.8655 | 1.0933 | H2 | 2 | Stable | TRUE | 243.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-19 23:00 | 2017-07-21 | 10% | 21.8655 | 2.1865 | Reduce | 5% | 21.8655 | 1.0933 | H2 | 2 | Stable | TRUE | 243.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-19 23:00 | 2017-07-21 | 10% | 21.8655 | 2.1865 | Reduce | 5% | 21.8655 | 1.0933 | H2 | 2 | Stable | TRUE | 243.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R07 | Project_041_R07 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Redesign due to critical obsolescence | Person_468 | 2016-11-19 22:00 | 2017-07-21 | 10% | 21.8655 | 2.1865 | Reduce | 5% | 21.8655 | 1.0933 | H2 | 2 | Stable | TRUE | 243.0833 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Programme Extended | Person_147 | 2013-11-20 01:00 | 2018-08-21 | 45% | 2.4326 | 1.0947 | Reduce | 45% | 2.4326 | 1.0947 | H1 | 1 | -- | TRUE | 1734.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_011 | Risk-058 | Project_011_Risk-058 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Programme Extended | Person_147 | 2013-11-20 01:00 | 2018-08-21 | 45% | 2.4326 | 1.0947 | Reduce | 45% | 2.4326 | 1.0947 | H1 | 1 | -- | TRUE | 1734.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK337 | Project_033_RISK337 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 1.7162 | 0.68649 | Avoid | 10% | 0.85811 | 0.085811 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK337 | Project_033_RISK337 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 1.7162 | 0.68649 | Avoid | 10% | 0.85811 | 0.085811 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-036 | Project_030_Risk-036 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Platforms Cables & Connector Kits | Person_146 | 2013-07-21 | 2015-12-20 01:00 | 40% | 4.3921 | 1.7568 | Reduce | 25% | 4.3921 | 1.098 | H3 | 3 | -- | TRUE | 882.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK022 | Project_079_RISK022 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 15% | 7.321 | 1.0982 | Reduce | 15% | 7.321 | 1.0982 | H3 | 3 | Stable | FALSE | 582.9583 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK022 | Project_079_RISK022 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 15% | 7.321 | 1.0982 | Reduce | 15% | 7.321 | 1.0982 | H3 | 3 | Stable | FALSE | 582.9583 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK022 | Project_079_RISK022 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 15% | 7.321 | 1.0982 | Reduce | 15% | 7.321 | 1.0982 | H3 | 3 | Stable | FALSE | 582.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK022 | Project_079_RISK022 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Test Equipment | Person_104 | 2018-01-14 01:00 | 2019-08-20 | 15% | 7.321 | 1.0982 | Reduce | 15% | 7.321 | 1.0982 | H3 | 3 | Stable | FALSE | 582.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-004 | Project_026_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Resource Project Impacts | Person_264 | 2015-05-24 | 2016-11-19 01:00 | 10% | 11.0427 | 1.1043 | Reduce | 10% | 11.0427 | 1.1043 | H2 | 2 | -- | TRUE | 545.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-004 | Project_026_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Resource Project Impacts | Person_264 | 2015-05-24 | 2016-11-19 01:00 | 10% | 11.0427 | 1.1043 | Reduce | 10% | 11.0427 | 1.1043 | H2 | 2 | -- | TRUE | 545.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-004 | Project_026_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Resource Project Impacts | Person_264 | 2015-05-24 | 2017-08-20 01:00 | 10% | 11.0427 | 1.1043 | Reduce | 10% | 11.0427 | 1.1043 | H2 | 2 | -- | TRUE | 819.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-09-20 01:00 | 30% | 5.5433 | 1.663 | Reduce | 20% | 5.5433 | 1.1087 | H3 | 3 | Stable | TRUE | 89.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-09-20 01:00 | 30% | 5.5433 | 1.663 | Reduce | 20% | 5.5433 | 1.1087 | H3 | 3 | Stable | TRUE | 89.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 1906 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 01:00 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 1906.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2017-08-20 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 1906 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | Risk11 | Project_010_Risk11 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Further obsolescence is found in the Supply Chain | Person_552 | 2012-06-01 | 2018-05-22 | 50% | 3.6965 | 1.8482 | Reduce | 30% | 3.6965 | 1.1089 | H2 | 2 | Stable | TRUE | 2181 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK337 | Project_033_RISK337 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 1.7162 | 0.68649 | Avoid | 10% | 0.85811 | 0.085811 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK337 | Project_033_RISK337 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 1.7162 | 0.68649 | Avoid | 10% | 0.85811 | 0.085811 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK337 | Project_033_RISK337 | Threat | Project Contingency | Open | H2 | 2 |  | Customer Furnished Equipment reliability | Person_330 | 2015-07-22 | 2015-12-21 18:00 | 40% | 1.7162 | 0.68649 | Avoid | 10% | 0.85811 | 0.085811 | H3 | 3 | -- | FALSE | 152.75 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK550 | Project_065_RISK550 | Threat | Project Contingency | Open | H3 | 3 |  | Customer does not provide DNS IP addresses by SFR | Person_117 | 2018-11-21 01:00 | 2018-12-22 01:00 | 60% | 1.7173 | 1.0304 | Reduce | 5% | 1.7173 | 0.085867 | H3 | 3 | -- | TRUE | 31 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK550 | Project_065_RISK550 | Threat | Project Contingency | Open | H3 | 3 |  | Customer does not provide DNS IP addresses by SFR | Person_117 | 2018-11-21 | 2018-12-22 | 60% | 1.7173 | 1.0304 | Reduce | 5% | 1.7173 | 0.085867 | H3 | 3 | -- | TRUE | 31 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK550 | Project_065_RISK550 | Threat | Project Contingency | Open | H3 | 3 |  | Customer does not provide DNS IP addresses by SFR | Person_117 | 2018-11-21 01:00 | 2018-12-22 01:00 | 60% | 1.7173 | 1.0304 | Reduce | 5% | 1.7173 | 0.085867 | H3 | 3 | -- | TRUE | 31 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK550 | Project_065_RISK550 | Threat | Project Contingency | Open | H3 | 3 |  | Customer does not provide DNS IP addresses by SFR | Person_117 | 2018-11-20 23:00 | 2018-12-21 23:00 | 60% | 1.7173 | 1.0304 | Reduce | 5% | 1.7173 | 0.085867 | H3 | 3 | -- | TRUE | 31 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk306 | Project_009_Risk306 | Threat | Project Contingency | Open | H3 | 3 |  | Supplier Component Unavailability | Person_284 | 2015-08-16 | 2016-09-19 01:00 | 10% | 0.86518 | 0.086518 | Reduce | 10% | 0.86466 | 0.086466 | H3 | 3 | -- | TRUE | 400.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk303 | Project_009_Risk303 | Threat | Project Contingency | Open | H2 | 2 |  | Design Flaw causing degradation of Power Systems | Person_248 | 2015-08-14 | 2016-05-21 | 50% | 2.594 | 1.297 | Reduce | 3.6% | 2.594 | 0.093383 | H3 | 3 | -- | FALSE | 281 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK317 | Project_065_RISK317 | Threat | Management Contingency | Open | H3 | 3 |  | Some Test Equipment estimates have come Engineering as opposed to Test Engineering. | Person_474 | 2017-05-23 | 2018-05-23 | 30% | 0.94825 | 0.28447 | Reduce | 10% | 0.94825 | 0.094825 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-077 | Project_007_R-077 | Threat | Project Contingency | Open | H3 | 3 |  | Mech Counters | Person_386 | 2013-12-03 19:00 | 2016-03-21 19:00 | 50% | 0.3903 | 0.19515 | Avoid | 50% | 0.19515 | 0.097576 | H3 | 3 | Stable | TRUE | 839 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | RISK004 | Project_041_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Change of Supplier Component (our NRE) | Person_468 | 2016-11-20 01:00 | 2018-11-20 01:00 | 25% | 0.66454 | 0.16613 | Reduce | 15% | 0.66454 | 0.099681 | H3 | 3 | -- | FALSE | 730 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-20 01:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1156.9583 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-20 01:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1156.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-20 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1157 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-20 01:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1156.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-19 23:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1157.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-19 22:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1157.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-19 23:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1157.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-20 01:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1156.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-10-19 01:00 | 50% | 2.2354 | 1.1177 | Reduce | 50% | 2.2354 | 1.1177 | H3 | 3 | Stable | TRUE | 1644.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-11-19 01:00 | 50% | 2.2354 | 1.1177 | Reduce | 50% | 2.2354 | 1.1177 | H3 | 3 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-11-19 01:00 | 50% | 2.2354 | 1.1177 | Reduce | 50% | 2.2354 | 1.1177 | H3 | 3 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-11-19 01:00 | 50% | 2.2354 | 1.1177 | Reduce | 50% | 2.2354 | 1.1177 | H3 | 3 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-58 | Project_022_RISK-58 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Handbook Update | Person_248 | 2012-04-19 | 2016-11-19 01:00 | 50% | 2.2354 | 1.1177 | Reduce | 50% | 2.2354 | 1.1177 | H3 | 3 | Stable | TRUE | 1675.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance | Person_240 | 2015-12-22 01:00 | 2016-08-14 | 25% | 4.4946 | 1.1236 | Accept | 25% | 4.4946 | 1.1236 | H2 | 2 | Stable | TRUE | 235.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance | Person_240 | 2015-12-22 01:00 | 2016-08-14 | 25% | 4.4946 | 1.1236 | Accept | 25% | 4.4946 | 1.1236 | H2 | 2 | Stable | TRUE | 235.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK172 | Project_038_RISK172 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance | Person_507 | 2015-12-22 01:00 | 2016-10-19 01:00 | 25% | 4.4946 | 1.1236 | Accept | 25% | 4.4946 | 1.1236 | H2 | 2 | Stable | TRUE | 302 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-19 22:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1157.0833 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK024 | Project_042_RISK024 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence May to April | Person_455 | 2019-09-21 01:00 | 2020-09-19 01:00 | 33% | 9.3941 | 3.1001 | Reduce | 15% | 7.5153 | 1.1273 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-133 | Project_020_Risk-133 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | External equipment Damage | Person_575 | 2011-05-24 | 2016-08-01 | 10% | 18.069 | 1.8069 | Accept | 10% | 11.3212 | 1.1321 | H3 | 3 | -- | FALSE | 1896 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-133 | Project_020_Risk-133 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | External equipment Damage | Person_575 | 2011-05-24 | 2016-08-01 | 10% | 18.069 | 1.8069 | Accept | 10% | 11.3212 | 1.1321 | H3 | 3 | -- | FALSE | 1896 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-133 | Project_020_Risk-133 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | External equipment Damage | Person_575 | 2011-05-24 | 2016-08-01 | 10% | 18.069 | 1.8069 | Accept | 10% | 11.3212 | 1.1321 | H3 | 3 | -- | FALSE | 1896 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-005 | Project_062_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Security Solution Integration | Person_245 | 2017-07-21 | 2018-11-14 01:00 | 30% | 4.6013 | 1.3804 | Avoid | 25% | 4.6013 | 1.1503 | H2 | 2 | Stable | TRUE | 481.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-20 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1157 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-20 01:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1156.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108- | Project_065_RISK108- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2018-02-19 23:00 | 2021-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1157.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK108-Risk- | Project_065_RISK108-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Importance of Process SubSystem for Prim & Sec Resolvers to be added to Risk Register | Person_732 | 2021-04-22 | 2024-04-22 | 20% | 7.6063 | 1.5213 | Reduce | 10% | 1.0142 | 0.10142 | H3 | 3 | -- | TRUE | 1096 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_594 | 2016-09-02 01:00 | 2019-11-08 01:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_594 | 2016-09-02 01:00 | 2019-11-08 01:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_594 | 2016-09-02 | 2019-11-08 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_594 | 2016-09-02 01:00 | 2019-11-08 01:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_594 | 2016-09-01 23:00 | 2019-11-07 23:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_594 | 2016-09-01 22:00 | 2019-11-07 22:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_594 | 2016-09-01 23:00 | 2019-11-07 23:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_418 | 2016-09-02 01:00 | 2019-11-08 01:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_594 | 2016-09-01 22:00 | 2019-11-07 22:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_418 | 2016-09-02 | 2019-11-08 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_418 | 2016-09-02 01:00 | 2019-11-08 01:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK028 | Project_065_RISK028 | Threat | Project Contingency | Open | H3 | 3 |  | PCB Design and Verification require more work than currently planned | Person_418 | 2016-09-01 23:00 | 2019-11-07 23:00 | 60% | 1.015 | 0.60901 | Reduce | 10% | 1.015 | 0.1015 | H3 | 3 | -- | TRUE | 1162 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R030 | Project_021_Risk-R030 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Config Qualification delay due to Major PRs | Person_207 | 2016-08-03 | 2016-10-19 01:00 | 30% | 3.973 | 1.1919 | Reduce | 30% | 3.973 | 1.1919 | H2 | 2 | -- | TRUE | 77.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK008 | Project_094_RISK008 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Increased warranty costs | Person_260 | 2020-11-20 | 2023-05-23 | 10% | 11.9805 | 1.1981 | Avoid | 10% | 11.9805 | 1.1981 | H3 | 3 | Stable | TRUE | 914 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK290 | Project_024_RISK290 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance Strategy decisions being made too late | Person_351 | 2011-04-22 | 2019-05-23 | 50% | 12.0742 | 6.0371 | -- | 10% | 12.0742 | 1.2074 | H3 | 3 | -- | FALSE | 2953 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK290 | Project_024_RISK290 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance Strategy decisions being made too late | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 50% | 12.0742 | 6.0371 | Avoid | 10% | 12.0742 | 1.2074 | H3 | 3 | Stable | FALSE | 641.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK290 | Project_024_RISK290 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance Strategy decisions being made too late | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 50% | 12.0742 | 6.0371 | Avoid | 10% | 12.0742 | 1.2074 | H3 | 3 | Stable | FALSE | 641.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK290 | Project_024_RISK290 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance Strategy decisions being made too late | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 50% | 12.0742 | 6.0371 | Avoid | 10% | 12.0742 | 1.2074 | H3 | 3 | Stable | FALSE | 641.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK014 | Project_083_RISK014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | System SW hosting Environment | Person_712 | 2018-02-20 01:00 | 2019-05-22 | 30% | 4.8313 | 1.4494 | Reduce | 25% | 4.8313 | 1.2078 | H2 | 2 | Stable | TRUE | 455.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Maintenance Schedules | Person_250 | 2015-02-21 01:00 | 2019-01-18 01:00 | 30% | 4.0291 | 1.2087 | Reduce | 30% | 4.0291 | 1.2087 | H3 | 3 | -- | TRUE | 1427 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Maintenance Schedules | Person_250 | 2015-02-21 01:00 | 2019-01-18 01:00 | 30% | 4.0291 | 1.2087 | Reduce | 30% | 4.0291 | 1.2087 | H3 | 3 | -- | TRUE | 1427 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-038 | Project_026_Risk-038 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Maintenance Schedules | Person_250 | 2015-02-21 01:00 | 2019-01-18 01:00 | 30% | 4.0291 | 1.2087 | Reduce | 30% | 4.0291 | 1.2087 | H3 | 3 | -- | TRUE | 1427 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk001 | Project_009_Risk001 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Work to complete sus-system | Person_459 | 2016-08-03 | 2016-09-19 01:00 | 100% | 1.2105 | 1.2105 | Accept | 100% | 1.2105 | 1.2105 | H1 | 1 | -- | TRUE | 47.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-033 | Project_077_T-033 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | PDA availability | Person_092 | 2018-02-20 01:00 | 2020-02-21 01:00 | 40% | 3.0327 | 1.2131 | Avoid | 40% | 3.0327 | 1.2131 | H2 | 2 | Stable | TRUE | 731 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 23:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 23:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 22:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0833 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK155 | Project_024_RISK155 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Late availability of Parameters | Person_534 | 2016-03-23 | 2016-09-11 01:00 | 30% | 4.1113 | 1.2334 | Reduce | 30% | 4.1113 | 1.2334 | H1 | 1 | Stable | TRUE | 172.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK155 | Project_024_RISK155 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Late availability of Parameters | Person_534 | 2016-03-23 | 2016-09-11 01:00 | 30% | 4.1113 | 1.2334 | Reduce | 30% | 4.1113 | 1.2334 | H1 | 1 | Stable | TRUE | 172.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK155 | Project_024_RISK155 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Late availability of Parameters | Person_534 | 2016-03-23 | 2016-09-11 01:00 | 30% | 4.1113 | 1.2334 | Reduce | 30% | 4.1113 | 1.2334 | H1 | 1 | Stable | TRUE | 172.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK394 | Project_035_RISK394 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Provision of supplier evidence | Person_631 | 2016-02-21 01:00 | 2016-08-20 01:00 | 50% | 2.4768 | 1.2384 | -- | 50% | 2.4768 | 1.2384 | H2 | 2 | Stable | TRUE | 181 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 22:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0833 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK088 | Project_076_RISK088 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Change to decision on aggregation | Person_628 | 2018-09-21 01:00 | 2019-05-16 | 10% | 12.4383 | 1.2438 | Reject | 10% | 12.4383 | 1.2438 | H3 | 3 | Stable | TRUE | 236.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R036 | Project_085_R036 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | IVV identifiying redesign required | Person_015 | 2018-12-22 | 2020-11-19 | 60% | 6.9304 | 4.1583 | Reduce | 18% | 6.9304 | 1.2475 | H3 | 3 | -- | TRUE | 698 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 23:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 23:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-21 01:00 | 50% | 2.5081 | 1.2541 | Accept | 50% | 2.5081 | 1.2541 | H2 | 2 | Stable | TRUE | 608.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-21 | 50% | 2.5081 | 1.2541 | Accept | 50% | 2.5081 | 1.2541 | H2 | 2 | Stable | TRUE | 608 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-20 23:00 | 50% | 2.5081 | 1.2541 | Accept | 50% | 2.5081 | 1.2541 | H2 | 2 | Stable | TRUE | 607.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-20 23:00 | 50% | 2.5081 | 1.2541 | Accept | 50% | 2.5081 | 1.2541 | H2 | 2 | Stable | TRUE | 607.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-20 23:00 | 50% | 2.5081 | 1.2541 | Accept | 50% | 2.5081 | 1.2541 | H2 | 2 | Stable | TRUE | 607.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R88 | Project_041_R88 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Sub Assemblies build to drawing and tested to failing when integrated into the products | Person_515 | 2017-05-23 | 2019-01-20 22:00 | 50% | 2.5081 | 1.2541 | Accept | 50% | 2.5081 | 1.2541 | H2 | 2 | Stable | TRUE | 607.9167 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 22:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 22:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0833 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-018 | Project_062_Risk-018 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Prioritisation - new or less experienced staff | Person_459 | 2017-09-20 01:00 | 2019-02-20 01:00 | 35% | 12.7044 | 4.4465 | Reduce | 10% | 12.7044 | 1.2704 | H2 | 2 | Improving | TRUE | 518 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 | 2020-09-21 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-07 22:00 | 2020-09-20 22:00 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 | 2020-09-21 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK060 | Project_065_RISK060 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | SFR&D sub-system will fail to meets reliability requirements. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 10% | 12.7232 | 1.2723 | Reduce | 10% | 12.7232 | 1.2723 | H3 | 3 | Stable | FALSE | 1474 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK056 | Project_042_RISK056 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Long Lead times for supplier items | Person_134 | 2018-09-23 01:00 | 2019-10-22 01:00 | 30% | 4.2461 | 1.2738 | Accept | 30% | 4.2461 | 1.2738 | H2 | 2 | Stable | TRUE | 394 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-02 01:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1716.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070-Risk- | Project_065_RISK070-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 23:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-192 | Project_026_Risk-192 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Late discovery of unexpected System Behaviour | Person_385 | 2016-10-21 01:00 | 2018-08-04 | 20% | 6.3794 | 1.2759 | Avoid | 20% | 6.3794 | 1.2759 | H2 | 2 | -- | TRUE | 651.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-192 | Project_026_Risk-192 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Late discovery of unexpected System Behaviour | Person_385 | 2016-10-21 01:00 | 2018-08-04 | 20% | 6.3794 | 1.2759 | Avoid | 20% | 6.3794 | 1.2759 | H2 | 2 | -- | TRUE | 651.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-192 | Project_026_Risk-192 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Late discovery of unexpected System Behaviour | Person_385 | 2016-10-21 01:00 | 2018-08-04 | 20% | 6.3794 | 1.2759 | Avoid | 20% | 6.3794 | 1.2759 | H2 | 2 | -- | TRUE | 651.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-192 | Project_026_Risk-192 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Late discovery of unexpected System Behaviour | Person_385 | 2016-10-21 01:00 | 2018-08-04 | 20% | 6.3794 | 1.2759 | Avoid | 20% | 6.3794 | 1.2759 | H2 | 2 | -- | TRUE | 651.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-192 | Project_026_Risk-192 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Late discovery of unexpected System Behaviour | Person_385 | 2016-10-21 01:00 | 2018-08-04 | 20% | 6.3794 | 1.2759 | Avoid | 20% | 6.3794 | 1.2759 | H2 | 2 | -- | TRUE | 651.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-192 | Project_026_Risk-192 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Late discovery of unexpected System Behaviour | Person_385 | 2016-10-21 01:00 | 2018-08-04 | 20% | 6.3794 | 1.2759 | Avoid | 20% | 6.3794 | 1.2759 | H2 | 2 | -- | TRUE | 651.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-192 | Project_026_Risk-192 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Late discovery of unexpected System Behaviour | Person_385 | 2016-10-21 01:00 | 2018-08-04 | 20% | 6.3794 | 1.2759 | Avoid | 20% | 6.3794 | 1.2759 | H2 | 2 | -- | TRUE | 651.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-192 | Project_026_Risk-192 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Late discovery of unexpected System Behaviour | Person_385 | 2016-10-21 01:00 | 2018-08-04 | 20% | 6.3794 | 1.2759 | Avoid | 20% | 6.3794 | 1.2759 | H2 | 2 | -- | TRUE | 651.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 50% | 26.9674 | 13.4837 | Avoid | 10% | 12.7646 | 1.2765 | H2 | 2 | Worsening | TRUE | 212.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 50% | 26.9674 | 13.4837 | Avoid | 10% | 12.7646 | 1.2765 | H2 | 2 | Worsening | TRUE | 212.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 50% | 26.9674 | 13.4837 | Avoid | 10% | 12.7646 | 1.2765 | H2 | 2 | Worsening | TRUE | 212.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 50% | 26.9674 | 13.4837 | Avoid | 10% | 12.7646 | 1.2765 | H2 | 2 | Worsening | TRUE | 212.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK218 | Project_038_RISK218 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Acceptance of Product System implementation | Person_330 | 2016-06-23 | 2017-01-21 01:00 | 50% | 26.9674 | 13.4837 | Avoid | 10% | 12.7646 | 1.2765 | H2 | 2 | Worsening | TRUE | 212.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK070- | Project_065_RISK070- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire in assembly (due to fragility in build process). | Person_661 | 2016-09-01 23:00 | 2021-05-16 | 40% | 1.0497 | 0.41987 | Reduce | 10% | 1.0497 | 0.10497 | H3 | 3 | -- | FALSE | 1717.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 2 |  | Software Issues | Person_245 | 2012-04-19 | 2016-09-19 01:00 | 50% | 0.55886 | 0.27943 | Accept | 20% | 0.55886 | 0.11177 | H3 | 3 | Stable | FALSE | 1614.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 2 |  | Software Issues | Person_245 | 2012-04-19 | 2016-10-19 01:00 | 50% | 0.55886 | 0.27943 | Accept | 20% | 0.55886 | 0.11177 | H3 | 3 | Stable | FALSE | 1644.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 2 |  | Software Issues | Person_245 | 2012-04-19 | 2016-11-19 01:00 | 50% | 0.55886 | 0.27943 | Accept | 20% | 0.55886 | 0.11177 | H3 | 3 | Stable | FALSE | 1675.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-038 | Project_029_Risk-038 | Threat | Project Contingency | Open | H2 | 2 |  | Integration and Reliability | Person_216 | 2014-03-23 | 2016-11-19 01:00 | 15% | 1.155 | 0.17325 | Reduce | 15% | 0.77001 | 0.1155 | H3 | 3 | Stable | FALSE | 972.0417 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-038 | Project_029_Risk-038 | Threat | Project Contingency | Open | H2 | 2 |  | Integration and Reliability | Person_216 | 2014-03-23 | 2016-11-19 01:00 | 15% | 1.155 | 0.17325 | Reduce | 15% | 0.77001 | 0.1155 | H3 | 3 | Stable | FALSE | 972.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-038 | Project_029_Risk-038 | Threat | Project Contingency | Open | H2 | 2 |  | Integration and Reliability | Person_216 | 2014-03-23 | 2016-11-19 01:00 | 15% | 1.155 | 0.17325 | Reduce | 15% | 0.77001 | 0.1155 | H3 | 3 | Stable | FALSE | 972.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-038 | Project_029_Risk-038 | Threat | Project Contingency | Open | H2 | 2 |  | Integration and Reliability | Person_216 | 2014-03-23 | 2016-11-19 01:00 | 15% | 1.155 | 0.17325 | Reduce | 15% | 0.77001 | 0.1155 | H3 | 3 | Stable | FALSE | 972.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK017 | Project_029_RISK017 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Data Simulator | Person_199 | 2018-10-22 01:00 | 2019-08-21 01:00 | 50% | 2.5667 | 1.2834 | Accept | 50% | 2.5667 | 1.2834 | H2 | 2 | -- | TRUE | 303 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 35% | 6.4382 | 2.2534 | -- | 20% | 6.4382 | 1.2876 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 35% | 6.4382 | 2.2534 | -- | 20% | 6.4382 | 1.2876 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-01-22 | 2023-02-20 | 35% | 6.4382 | 2.2534 | -- | 20% | 6.4382 | 1.2876 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-01-22 | 2023-02-20 | 35% | 6.4382 | 2.2534 | -- | 20% | 6.4382 | 1.2876 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 35% | 6.4382 | 2.2534 | -- | 20% | 6.4382 | 1.2876 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 35% | 6.4382 | 2.2534 | -- | 20% | 6.4382 | 1.2876 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 35% | 6.4382 | 2.2534 | -- | 20% | 6.4382 | 1.2876 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK045 | Project_017_RISK045 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Volume of production tools and Jigs | Person_084 | 2016-01-21 21:00 | 2023-02-19 21:00 | 35% | 6.4382 | 2.2534 | -- | 20% | 6.4382 | 1.2876 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK227 | Project_038_RISK227 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Verification and Acceptance of Customer Furnished Equipmnet Goods & Services | Person_330 | 2015-02-21 01:00 | 2016-05-22 | 60% | 6.4422 | 3.8653 | Avoid | 20% | 6.4422 | 1.2884 | H3 | 3 | Stable | FALSE | 455.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK227 | Project_038_RISK227 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Verification and Acceptance of Customer Furnished Equipmnet Goods & Services | Person_330 | 2015-02-21 01:00 | 2016-05-22 | 60% | 6.4422 | 3.8653 | Avoid | 20% | 6.4422 | 1.2884 | H3 | 3 | Stable | FALSE | 455.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK227 | Project_038_RISK227 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Verification and Acceptance of Customer Furnished Equipmnet Goods & Services | Person_330 | 2015-02-21 01:00 | 2016-08-20 01:00 | 60% | 6.4422 | 3.8653 | Avoid | 20% | 6.4422 | 1.2884 | H3 | 3 | Stable | FALSE | 546 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk307 | Project_009_Risk307 | Threat | Project Contingency | Open | H3 | 3 |  | Component/unit failure due to extended storage period | Person_459 | 2015-08-16 | 2016-09-19 01:00 | 10% | 1.1932 | 0.11932 | Reduce | 9.8% | 1.1932 | 0.11694 | H3 | 3 | -- | TRUE | 400.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk307 | Project_009_Risk307 | Threat | Project Contingency | Open | H3 | 3 |  | Component/unit failure due to extended storage period | Person_459 | 2015-08-16 | 2016-09-19 01:00 | 10% | 1.1932 | 0.11932 | Reduce | 9.8% | 1.1932 | 0.11694 | H3 | 3 | -- | TRUE | 400.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator too high | Person_022 | 2016-09-02 01:00 | 2019-11-23 01:00 | 70% | 2.7763 | 1.9434 | Reduce | 20% | 0.5916 | 0.11832 | H3 | 3 | -- | TRUE | 1177 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator too high | Person_022 | 2016-09-02 | 2019-11-23 | 70% | 2.7763 | 1.9434 | Reduce | 20% | 0.5916 | 0.11832 | H3 | 3 | -- | TRUE | 1177 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator too high | Person_022 | 2016-09-02 01:00 | 2019-11-23 01:00 | 70% | 2.7763 | 1.9434 | Reduce | 20% | 0.5916 | 0.11832 | H3 | 3 | -- | TRUE | 1177 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator too high | Person_022 | 2016-09-01 23:00 | 2019-11-22 23:00 | 70% | 2.7763 | 1.9434 | Reduce | 20% | 0.5916 | 0.11832 | H3 | 3 | -- | TRUE | 1177 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk307 | Project_009_Risk307 | Threat | Project Contingency | Open | H3 | 3 |  | Component/unit failure due to extended storage period | Person_284 | 2015-08-16 | 2016-09-19 01:00 | 10% | 1.1932 | 0.11932 | Reduce | 10% | 1.1932 | 0.11932 | H3 | 3 | -- | TRUE | 400.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-22 01:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 935.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-22 01:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 935.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-22 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 936 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 | 2017-08-20 | 30% | 8.7814 | 2.6344 | Reduce | 15% | 8.7832 | 1.3175 | H3 | 3 | Stable | TRUE | 585 |  | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 30% | 8.7814 | 2.6344 | Reduce | 15% | 8.7832 | 1.3175 | H3 | 3 | Stable | TRUE | 585 |  | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 30% | 8.7814 | 2.6344 | Reduce | 15% | 8.7832 | 1.3175 | H3 | 3 | Stable | TRUE | 585 |  | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-110 | Project_030_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Vendor Equipment Reliability | Person_673 | 2014-03-26 | 2016-10-10 01:00 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 929.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-112 | Project_030_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unexpected Defect volumes for In Service Support | Person_673 | 2014-05-04 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1466 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H1 | 1 | Stable | TRUE | 850.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-111 | Project_030_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unavailability of Suitably Qualified and experienced staff availability for In service Support | Person_673 | 2014-03-26 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1505 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-110 | Project_030_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Vendor Equipment Reliability | Person_673 | 2014-03-26 | 2016-10-10 01:00 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 929.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-112 | Project_030_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unexpected Defect volumes for In Service Support | Person_673 | 2014-05-04 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1466 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H1 | 1 | Stable | TRUE | 850.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-111 | Project_030_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unavailability of Suitably Qualified and experienced staff availability for In service Support | Person_673 | 2014-03-26 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1505 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-110 | Project_030_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Vendor Equipment Reliability | Person_673 | 2014-03-26 | 2016-10-10 01:00 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 929.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-112 | Project_030_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unexpected Defect volumes for In Service Support | Person_673 | 2014-05-04 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1466 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H1 | 1 | Stable | TRUE | 850.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-111 | Project_030_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unavailability of Suitably Qualified and experienced staff availability for In service Support | Person_673 | 2014-03-26 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1505 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-110 | Project_030_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Vendor Equipment Reliability | Person_673 | 2014-03-26 | 2016-10-10 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 929 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-112 | Project_030_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unexpected Defect volumes for In Service Support | Person_673 | 2014-05-04 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1466 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 | 2016-05-21 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H1 | 1 | Stable | TRUE | 851 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-111 | Project_030_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unavailability of Suitably Qualified and experienced staff availability for In service Support | Person_673 | 2014-03-26 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1505 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-110 | Project_030_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Vendor Equipment Reliability | Person_673 | 2014-03-26 | 2016-10-10 01:00 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 929.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-112 | Project_030_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unexpected Defect volumes for In Service Support | Person_673 | 2014-05-04 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1466 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H1 | 1 | Stable | TRUE | 850.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-111 | Project_030_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unavailability of Suitably Qualified and experienced staff availability for In service Support | Person_673 | 2014-03-26 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1505 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-110 | Project_030_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Vendor Equipment Reliability | Person_673 | 2014-03-26 | 2016-10-10 01:00 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 929.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-112 | Project_030_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unexpected Defect volumes for In Service Support | Person_673 | 2014-05-04 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1466 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H1 | 1 | Stable | TRUE | 850.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-111 | Project_030_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unavailability of Suitably Qualified and experienced staff availability for In service Support | Person_673 | 2014-03-26 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1505 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-110 | Project_030_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Vendor Equipment Reliability | Person_673 | 2014-03-26 | 2016-10-10 01:00 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 929.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-112 | Project_030_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unexpected Defect volumes for In Service Support | Person_673 | 2014-05-04 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1466 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 01:00 | 2016-05-21 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H1 | 1 | Stable | TRUE | 850.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-111 | Project_030_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unavailability of Suitably Qualified and experienced staff availability for In service Support | Person_673 | 2014-03-26 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1505 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-110 | Project_030_Risk-110 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Vendor Equipment Reliability | Person_673 | 2014-03-26 | 2016-10-10 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 929 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-112 | Project_030_Risk-112 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unexpected Defect volumes for In Service Support | Person_673 | 2014-05-04 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1466 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-053 | Project_030_Risk-053 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | System design fails to meet KPI | Person_283 | 2014-01-21 | 2016-05-21 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H1 | 1 | Stable | TRUE | 851 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-111 | Project_030_Risk-111 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Unavailability of Suitably Qualified and experienced staff availability for In service Support | Person_673 | 2014-03-26 | 2018-05-09 | 50% | 4.3921 | 2.196 | Reduce | 30% | 4.3921 | 1.3176 | H2 | 2 | -- | TRUE | 1505 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Non-Recurring Engineering higher than expected | Person_059 | 2016-01-22 01:00 | 2016-06-29 | 30% | 6.5968 | 1.979 | Reduce | 20% | 6.5944 | 1.3189 | H3 | 3 | -- | TRUE | 158.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Non-Recurring Engineering higher than expected | Person_059 | 2016-01-22 01:00 | 2016-06-29 | 30% | 6.5968 | 1.979 | Reduce | 20% | 6.5944 | 1.3189 | H3 | 3 | -- | TRUE | 158.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Non-Recurring Engineering higher than expected | Person_059 | 2016-01-22 | 2016-06-29 | 30% | 6.5968 | 1.979 | Reduce | 20% | 6.5944 | 1.3189 | H3 | 3 | -- | TRUE | 159 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Non-Recurring Engineering higher than expected | Person_059 | 2016-01-21 23:00 | 2016-06-29 | 30% | 6.5968 | 1.979 | Reduce | 20% | 6.5944 | 1.3189 | H3 | 3 | -- | TRUE | 159.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Non-Recurring Engineering higher than expected | Person_059 | 2016-01-21 22:00 | 2016-06-29 | 30% | 6.5968 | 1.979 | Reduce | 20% | 6.5944 | 1.3189 | H3 | 3 | -- | TRUE | 159.0833 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Non-Recurring Engineering higher than expected | Person_059 | 2016-01-21 21:00 | 2016-06-29 | 30% | 6.5968 | 1.979 | Reduce | 20% | 6.5944 | 1.3189 | H3 | 3 | -- | TRUE | 159.125 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 40% | 6.5968 | 2.6387 | Reduce | 20% | 6.5944 | 1.3189 | H3 | 3 | Improving | TRUE | 64 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK015 | Project_001_RISK015 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Non-Recurring Engineering higher than expected | Person_674 | 2016-06-01 | 2016-08-04 | 40% | 6.5968 | 2.6387 | Reduce | 20% | 6.5944 | 1.3189 | H3 | 3 | Improving | TRUE | 64 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK258 | Project_024_RISK258 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Editing of Personal Settings | Person_318 | 2016-05-23 | 2017-05-23 | 50% | 6.6127 | 3.3063 | Reduce | 20% | 6.6127 | 1.3225 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-22 01:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 935.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK004 | Project_079_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 20% | 8.8685 | 1.7737 | Reduce | 15% | 8.8685 | 1.3303 | H3 | 3 | Stable | TRUE | 1186.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK004 | Project_079_RISK004 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Attrition | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 20% | 8.8685 | 1.7737 | Reduce | 15% | 8.8685 | 1.3303 | H3 | 3 | Stable | TRUE | 1186.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 40% | 3.3367 | 1.3347 | -- | 40% | 3.3367 | 1.3347 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 40% | 3.3367 | 1.3347 | -- | 40% | 3.3367 | 1.3347 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 40% | 3.3367 | 1.3347 | -- | 40% | 3.3367 | 1.3347 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 40% | 3.3367 | 1.3347 | -- | 40% | 3.3367 | 1.3347 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK026 | Project_029_Risk-RISK026 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | HW - additional unplanned design effort | Person_216 | 2016-05-23 | 2019-10-21 01:00 | 40% | 3.3367 | 1.3347 | Reduce | 40% | 3.3367 | 1.3347 | H2 | 2 | Stable | TRUE | 1246.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 40% | 6.6769 | 2.6707 | Reduce | 20% | 6.6769 | 1.3354 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 45% | 10.7184 | 4.8233 | Reduce | 25% | 5.3592 | 1.3398 | H2 | 2 | Worsening | TRUE | 547.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-014 | Project_077_T-014 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Extra Release | Person_203 | 2020-06-23 | 2020-11-20 01:00 | 10% | 13.4785 | 1.3478 | Avoid | 10% | 13.4785 | 1.3478 | H2 | 2 | Stable | TRUE | 150.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-09-20 01:00 | 25% | 5.3935 | 1.3484 | Accept | 25% | 5.3935 | 1.3484 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-09-20 01:00 | 25% | 5.3935 | 1.3484 | Accept | 25% | 5.3935 | 1.3484 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-09-20 01:00 | 25% | 5.3935 | 1.3484 | Accept | 25% | 5.3935 | 1.3484 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-09-20 01:00 | 25% | 5.3935 | 1.3484 | Accept | 25% | 5.3935 | 1.3484 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-11-20 01:00 | 25% | 5.3935 | 1.3484 | Accept | 25% | 5.3935 | 1.3484 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK163 | Project_038_RISK163 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Additional Chamber trials | Person_531 | 2015-09-21 01:00 | 2016-11-20 01:00 | 25% | 5.3935 | 1.3484 | Accept | 25% | 5.3935 | 1.3484 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-140 | Project_020_Risk-140 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | No external equipment Support Contract | Person_575 | 2012-09-11 23:00 | 2017-08-01 | 30% | 4.4985 | 1.3495 | Accept | 30% | 4.4985 | 1.3495 | H2 | 2 | -- | TRUE | 1784.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-140 | Project_020_Risk-140 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | No external equipment Support Contract | Person_575 | 2012-09-11 22:00 | 2017-08-01 | 30% | 4.4985 | 1.3495 | Accept | 30% | 4.4985 | 1.3495 | H2 | 2 | -- | TRUE | 1784.0833 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-140 | Project_020_Risk-140 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | No external equipment Support Contract | Person_575 | 2012-09-11 21:00 | 2017-08-01 | 30% | 4.4985 | 1.3495 | Accept | 30% | 4.4985 | 1.3495 | H2 | 2 | -- | TRUE | 1784.125 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-140 | Project_020_Risk-140 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | No external equipment Support Contract | Person_575 | 2012-09-12 01:00 | 2017-08-01 | 30% | 4.4985 | 1.3495 | Accept | 30% | 4.4985 | 1.3495 | H2 | 2 | -- | TRUE | 1783.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-140 | Project_020_Risk-140 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | No external equipment Support Contract | Person_575 | 2012-09-12 01:00 | 2017-08-01 | 30% | 4.4985 | 1.3495 | Accept | 30% | 4.4985 | 1.3495 | H2 | 2 | -- | TRUE | 1783.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-002 | Project_006_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Management of Customer. | Person_582 | 2015-05-24 | 2017-04-22 | 25% | 9.1144 | 2.2786 | Reduce | 20% | 6.7623 | 1.3525 | H2 | 2 | Improving | TRUE | 699 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 6.7638 | 1.3528 | Accept | 20% | 6.7638 | 1.3528 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 6.7638 | 1.3528 | Accept | 20% | 6.7638 | 1.3528 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 6.7638 | 1.3528 | Accept | 20% | 6.7638 | 1.3528 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 6.7638 | 1.3528 | Accept | 20% | 6.7638 | 1.3528 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 6.7638 | 1.3528 | Accept | 20% | 6.7638 | 1.3528 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 6.7638 | 1.3528 | Accept | 20% | 6.7638 | 1.3528 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk003 | Project_042_Risk003 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Level of Effort Hours | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 6.7638 | 1.3528 | Accept | 20% | 6.7638 | 1.3528 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 25% | 5.4336 | 1.3584 | Accept | 25% | 5.4336 | 1.3584 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 25% | 5.4336 | 1.3584 | Accept | 25% | 5.4336 | 1.3584 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 | 2019-08-20 | 25% | 5.4336 | 1.3584 | Accept | 25% | 5.4336 | 1.3584 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 25% | 5.4336 | 1.3584 | Accept | 25% | 5.4336 | 1.3584 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 25% | 5.4336 | 1.3584 | Accept | 25% | 5.4336 | 1.3584 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 25% | 5.4336 | 1.3584 | Accept | 25% | 5.4336 | 1.3584 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 25% | 5.4336 | 1.3584 | Accept | 25% | 5.4336 | 1.3584 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-020 | Project_018_Risk-020 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Repair Model | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 25% | 5.4336 | 1.3584 | Accept | 25% | 5.4336 | 1.3584 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK089 | Project_076_RISK089 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Travel cost savings | Person_152 | 2018-09-21 01:00 | 2019-05-16 | 50% | 2.7364 | 1.3682 | Reject | 50% | 2.7364 | 1.3682 | H3 | 3 | Stable | TRUE | 236.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-125 | Project_026_Risk-125 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rectification of Residual Defects | Person_607 | 2018-10-28 01:00 | 2019-04-29 | 40% | 3.4415 | 1.3766 | Accept | 40% | 3.4415 | 1.3766 | H2 | 2 | -- | TRUE | 182.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-125 | Project_026_Risk-125 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rectification of Residual Defects | Person_607 | 2018-10-28 01:00 | 2019-04-29 | 40% | 3.4415 | 1.3766 | Accept | 40% | 3.4415 | 1.3766 | H2 | 2 | -- | TRUE | 182.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-125 | Project_026_Risk-125 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rectification of Residual Defects | Person_607 | 2018-10-28 01:00 | 2019-04-29 | 40% | 3.4415 | 1.3766 | Accept | 40% | 3.4415 | 1.3766 | H2 | 2 | -- | TRUE | 182.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-125 | Project_026_Risk-125 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rectification of Residual Defects | Person_607 | 2018-10-28 01:00 | 2019-04-29 | 40% | 3.4415 | 1.3766 | Accept | 40% | 3.4415 | 1.3766 | H2 | 2 | -- | TRUE | 182.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-125 | Project_026_Risk-125 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rectification of Residual Defects | Person_607 | 2018-10-28 01:00 | 2019-04-29 | 40% | 3.4415 | 1.3766 | Accept | 40% | 3.4415 | 1.3766 | H2 | 2 | -- | TRUE | 182.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-125 | Project_026_Risk-125 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rectification of Residual Defects | Person_607 | 2018-10-28 01:00 | 2019-04-29 | 40% | 3.4415 | 1.3766 | Accept | 40% | 3.4415 | 1.3766 | H2 | 2 | -- | TRUE | 182.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-125 | Project_026_Risk-125 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rectification of Residual Defects | Person_607 | 2018-10-28 01:00 | 2019-04-29 | 40% | 3.4415 | 1.3766 | Accept | 40% | 3.4415 | 1.3766 | H2 | 2 | -- | TRUE | 182.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-125 | Project_026_Risk-125 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rectification of Residual Defects | Person_607 | 2018-10-28 01:00 | 2019-04-29 | 40% | 3.4415 | 1.3766 | Accept | 40% | 3.4415 | 1.3766 | H2 | 2 | -- | TRUE | 182.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 50% | 13.7833 | 6.8917 | Avoid | 20% | 6.8917 | 1.3783 | H3 | 3 | Stable | FALSE | 364 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 50% | 13.7833 | 6.8917 | Avoid | 20% | 6.8917 | 1.3783 | H3 | 3 | Stable | FALSE | 364 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 50% | 13.7833 | 6.8917 | Avoid | 20% | 6.8917 | 1.3783 | H3 | 3 | Stable | FALSE | 364 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 50% | 13.7833 | 6.8917 | Avoid | 20% | 6.8917 | 1.3783 | H3 | 3 | Stable | FALSE | 364 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 50% | 13.7833 | 6.8917 | Avoid | 20% | 6.8917 | 1.3783 | H3 | 3 | Stable | FALSE | 364 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-21 23:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 936.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-21 22:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 936.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-22 01:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 935.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-21 22:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 936.0833 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-22 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 936 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-22 01:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 935.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK316 | Project_065_RISK316 | Threat | Management Contingency | Open | H2 | 2 |  | Access to critical/limited Manufacturing Resource not available when required for schedule | Person_554 | 2018-10-21 23:00 | 2021-05-15 | 40% | 4.9796 | 1.9918 | Reduce | 10% | 1.2424 | 0.12424 | H3 | 3 | -- | FALSE | 936.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK047 | Project_075_RISK047 | Threat | Project Contingency | Open | H2 | 2 |  | Line of Balance clear dates does not reconcile with schedule | Person_002 | 2018-04-22 | 2018-11-20 01:00 | 30% | 1.2656 | 0.37967 | Reduce | 10% | 1.2656 | 0.12656 | H3 | 3 | -- | FALSE | 212.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 50% | 13.9332 | 6.9666 | Avoid | 10% | 13.9332 | 1.3933 | H3 | 3 | Improving | FALSE | 547.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 50% | 13.9332 | 6.9666 | Avoid | 10% | 13.9332 | 1.3933 | H3 | 3 | Improving | FALSE | 547.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 50% | 13.9332 | 6.9666 | Avoid | 10% | 13.9332 | 1.3933 | H3 | 3 | Improving | FALSE | 547.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 50% | 13.9332 | 6.9666 | Avoid | 10% | 13.9332 | 1.3933 | H3 | 3 | Improving | FALSE | 547.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 50% | 13.9332 | 6.9666 | Avoid | 10% | 13.9332 | 1.3933 | H3 | 3 | Improving | FALSE | 547.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK226 | Project_038_RISK226 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Capacity to support enhancements or fixes post delivery | Person_330 | 2015-11-21 01:00 | 2017-05-22 | 50% | 13.9332 | 6.9666 | Avoid | 10% | 13.9332 | 1.3933 | H3 | 3 | Improving | FALSE | 547.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-06-22 | 50% | 4.6444 | 2.3222 | Avoid | 30% | 4.6444 | 1.3933 | H2 | 2 | Worsening | TRUE | 336 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK187 | Project_038_RISK187 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Technical Publications | Person_671 | 2015-07-22 | 2016-06-22 | 50% | 4.6444 | 2.3222 | Avoid | 30% | 4.6444 | 1.3933 | H2 | 2 | Worsening | TRUE | 336 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 50% | 3.5054 | 1.7527 | Reduce | 40% | 3.5054 | 1.4022 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 50% | 3.5054 | 1.7527 | Reduce | 40% | 3.5054 | 1.4022 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 50% | 3.5054 | 1.7527 | Reduce | 40% | 3.5054 | 1.4022 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 50% | 3.5054 | 1.7527 | Reduce | 40% | 3.5054 | 1.4022 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 50% | 3.5054 | 1.7527 | Reduce | 40% | 3.5054 | 1.4022 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 50% | 3.5054 | 1.7527 | Reduce | 40% | 3.5054 | 1.4022 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Testing Required | Person_289 | 2016-12-21 01:00 | 2017-05-22 | 50% | 3.5054 | 1.7527 | Reduce | 40% | 3.5054 | 1.4022 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK179 | Project_024_RISK179 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Testing Required | Person_710 | 2016-12-21 01:00 | 2017-05-22 | 50% | 3.5054 | 1.7527 | Reduce | 40% | 3.5054 | 1.4022 | H2 | 2 | Stable | TRUE | 151.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK035 | Project_075_RISK035 | Threat | Project Contingency | Open | H2 | 2 |  | Beam requirement | Person_003 | 2017-08-23 01:00 | 2018-11-20 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 15% | 0.84371 | 0.12656 | H3 | 3 | -- | FALSE | 454 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | RISK013 | Project_062_RISK013 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | System modifications and technical debt. | Person_401 | 2018-12-22 01:00 | 2019-03-11 01:00 | 60% | 3.5555 | 2.1333 | Reduce | 40% | 3.5555 | 1.4222 | H2 | 2 | Stable | TRUE | 79 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R087 | Project_085_R087 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Second iteration of design | Person_409 | 2018-11-21 | 2019-05-23 | 65% | 2.9736 | 1.9328 | Reduce | 48% | 2.9736 | 1.4273 | H2 | 2 | -- | TRUE | 183 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safey Case Release is more complicated / delayed. | Person_470 | 2013-01-07 | 2017-02-19 | 50% | 4.7676 | 2.3838 | Reduce | 30% | 4.7676 | 1.4303 | H2 | 2 | Stable | TRUE | 1504 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safey Case Release is more complicated / delayed. | Person_470 | 2013-01-06 23:00 | 2017-02-18 23:00 | 50% | 4.7676 | 2.3838 | Reduce | 30% | 4.7676 | 1.4303 | H2 | 2 | Stable | TRUE | 1504 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Release is more complicated/ delayed. | Person_470 | 2013-01-07 01:00 | 2017-02-19 01:00 | 50% | 4.7676 | 2.3838 | Reduce | 30% | 4.7676 | 1.4303 | H2 | 2 | Stable | TRUE | 1504 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Release is more complicated/ delayed. | Person_482 | 2013-01-07 | 2017-02-19 | 50% | 4.7676 | 2.3838 | Reduce | 30% | 4.7676 | 1.4303 | H2 | 2 | Stable | TRUE | 1504 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Release is more complicated/ delayed. | Person_482 | 2013-01-07 01:00 | 2017-02-19 01:00 | 50% | 4.7676 | 2.3838 | Reduce | 30% | 4.7676 | 1.4303 | H2 | 2 | Stable | TRUE | 1504 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK047 | Project_075_RISK047 | Threat | Project Contingency | Open | H2 | 2 |  | Line of Balance clear dates does not reconcile with schedule | Person_002 | 2018-04-22 | 2018-11-20 01:00 | 30% | 1.2656 | 0.37967 | Reduce | 10% | 1.2656 | 0.12656 | H3 | 3 | -- | FALSE | 212.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Performance | Person_532 | 2016-06-22 | 2016-08-19 01:00 | 30% | 4.847 | 1.4541 | Accept | 30% | 4.847 | 1.4541 | H2 | 2 | Stable | TRUE | 58.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Performance | Person_532 | 2016-06-22 | 2017-02-19 01:00 | 30% | 4.847 | 1.4541 | Accept | 30% | 4.847 | 1.4541 | H2 | 2 | Stable | TRUE | 242.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Performance | Person_532 | 2016-06-22 | 2017-02-19 01:00 | 30% | 4.847 | 1.4541 | Accept | 30% | 4.847 | 1.4541 | H2 | 2 | Stable | TRUE | 242.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Performance | Person_532 | 2016-06-22 | 2017-02-19 01:00 | 30% | 4.847 | 1.4541 | Accept | 30% | 4.847 | 1.4541 | H2 | 2 | Stable | TRUE | 242.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 30% | 4.847 | 1.4541 | Accept | 30% | 4.847 | 1.4541 | H2 | 2 | Stable | TRUE | 242.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 30% | 4.847 | 1.4541 | Accept | 30% | 4.847 | 1.4541 | H2 | 2 | Stable | TRUE | 242.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK210 | Project_024_RISK210 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Performance impacts regualotory complaince | Person_534 | 2016-06-22 | 2017-02-19 01:00 | 30% | 4.847 | 1.4541 | Accept | 30% | 4.847 | 1.4541 | H2 | 2 | Stable | TRUE | 242.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK011 | Project_029_RISK011 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Testing | Person_199 | 2019-04-23 | 2019-08-21 01:00 | 70% | 3.6362 | 2.5453 | Reduce | 40% | 3.6362 | 1.4545 | H2 | 2 | -- | TRUE | 120.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-06 01:00 | 2019-04-17 | 30% | 4.8596 | 1.4579 | Accept | 30% | 4.8596 | 1.4579 | H2 | 2 | -- | TRUE | 557.9583 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-06 01:00 | 2019-04-17 | 30% | 4.8596 | 1.4579 | Accept | 30% | 4.8596 | 1.4579 | H2 | 2 | -- | TRUE | 557.9583 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-06 | 2019-04-17 | 30% | 4.8596 | 1.4579 | Accept | 30% | 4.8596 | 1.4579 | H2 | 2 | -- | TRUE | 558 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-06 01:00 | 2019-04-17 | 30% | 4.8596 | 1.4579 | Accept | 30% | 4.8596 | 1.4579 | H2 | 2 | -- | TRUE | 557.9583 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-05 23:00 | 2019-04-17 | 30% | 4.8596 | 1.4579 | Accept | 30% | 4.8596 | 1.4579 | H2 | 2 | -- | TRUE | 558.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-05 22:00 | 2019-04-17 | 30% | 4.8596 | 1.4579 | Accept | 30% | 4.8596 | 1.4579 | H2 | 2 | -- | TRUE | 558.0833 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-05 23:00 | 2019-04-17 | 30% | 4.8596 | 1.4579 | Accept | 30% | 4.8596 | 1.4579 | H2 | 2 | -- | TRUE | 558.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK459 | Project_065_RISK459 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Delta risk for shock | Person_022 | 2017-10-05 22:00 | 2019-04-17 | 30% | 4.8596 | 1.4579 | Accept | 30% | 4.8596 | 1.4579 | H2 | 2 | -- | TRUE | 558.0833 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK005 | Project_049_RISK005 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Trial Plans and procedures | Person_639 | 2017-08-23 01:00 | 2019-08-30 01:00 | 50% | 2.9272 | 1.4636 | Accept | 50% | 2.9272 | 1.4636 | H3 | 3 | -- | TRUE | 737 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK057 | Project_042_RISK057 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Supplier Unplanned failures. | Person_129 | 2018-09-23 01:00 | 2019-10-22 01:00 | 60% | 2.4425 | 1.4655 | Accept | 60% | 2.4425 | 1.4655 | H1 | 1 | Stable | TRUE | 394 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK035 | Project_075_RISK035 | Threat | Project Contingency | Open | H2 | 2 |  | Beam requirement | Person_003 | 2017-08-23 01:00 | 2018-11-20 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 15% | 0.84371 | 0.12656 | H3 | 3 | -- | FALSE | 454 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK047 | Project_075_RISK047 | Threat | Project Contingency | Open | H2 | 2 |  | Line of Balance clear dates does not reconcile with schedule | Person_002 | 2018-04-22 | 2018-11-20 01:00 | 30% | 1.2656 | 0.37967 | Reduce | 10% | 1.2656 | 0.12656 | H3 | 3 | -- | FALSE | 212.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK035 | Project_075_RISK035 | Threat | Project Contingency | Open | H2 | 2 |  | Beam requirement | Person_003 | 2017-08-23 01:00 | 2018-11-20 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 15% | 0.84371 | 0.12656 | H3 | 3 | -- | FALSE | 454 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK047 | Project_075_RISK047 | Threat | Project Contingency | Open | H2 | 2 |  | Line of Balance clear dates does not reconcile with schedule | Person_002 | 2018-04-22 | 2018-11-20 01:00 | 30% | 1.2656 | 0.37967 | Reduce | 10% | 1.2656 | 0.12656 | H3 | 3 | -- | FALSE | 212.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK255 | Project_024_RISK255 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | More releases than expected | Person_351 | 2016-08-21 01:00 | 2017-05-22 | 40% | 7.3743 | 2.9497 | Reduce | 20% | 7.3743 | 1.4749 | H2 | 2 | -- | TRUE | 273.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK059 | Project_042_RISK059 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional Material Requirements. | Person_664 | 2018-09-23 01:00 | 2019-10-22 01:00 | 40% | 3.7576 | 1.5031 | Accept | 40% | 3.7576 | 1.5031 | H2 | 2 | Stable | TRUE | 394 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK035 | Project_075_RISK035 | Threat | Project Contingency | Open | H2 | 2 |  | Beam requirement | Person_003 | 2017-08-23 01:00 | 2018-11-20 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 15% | 0.84371 | 0.12656 | H3 | 3 | -- | FALSE | 454 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK047 | Project_075_RISK047 | Threat | Project Contingency | Open | H2 | 2 |  | Line of Balance clear dates does not reconcile with schedule | Person_002 | 2018-04-22 | 2018-11-20 01:00 | 30% | 1.2656 | 0.37967 | Reduce | 10% | 1.2656 | 0.12656 | H3 | 3 | -- | FALSE | 212.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK035 | Project_075_RISK035 | Threat | Project Contingency | Open | H2 | 2 |  | Beam requirement | Person_003 | 2017-08-23 01:00 | 2018-11-20 01:00 | 30% | 0.84371 | 0.25311 | Reduce | 15% | 0.84371 | 0.12656 | H3 | 3 | -- | FALSE | 454 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | -- | FALSE | 346 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | Improving | FALSE | 1460 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | -- | FALSE | 346 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK007 | Project_081_RISK007 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | High value supplier repair/replacements required | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 40% | 3.7834 | 1.5133 | Reduce | 40% | 3.7834 | 1.5133 | H3 | 3 | Stable | TRUE | 1454 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK244 | Project_024_RISK244 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Blue Screen Of Death (BSOD) | Person_534 | 2016-04-22 | 2016-07-21 | 10% | 15.1468 | 1.5147 | Reduce | 10% | 15.1468 | 1.5147 | H3 | 3 | Stable | FALSE | 90 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK244 | Project_024_RISK244 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Blue Screen Of Death (BSOD) | Person_534 | 2016-04-22 | 2016-07-21 | 10% | 15.1468 | 1.5147 | Reduce | 10% | 15.1468 | 1.5147 | H3 | 3 | Stable | FALSE | 90 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK244 | Project_024_RISK244 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Blue Screen Of Death (BSOD) | Person_534 | 2016-04-22 | 2016-07-21 | 10% | 15.1468 | 1.5147 | Reduce | 10% | 15.1468 | 1.5147 | H3 | 3 | Stable | FALSE | 90 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK244 | Project_024_RISK244 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Blue Screen Of Death (BSOD) | Person_534 | 2016-04-22 | 2016-07-21 | 10% | 15.1468 | 1.5147 | Reduce | 10% | 15.1468 | 1.5147 | H3 | 3 | Stable | FALSE | 90 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | Improving | FALSE | 1460 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | -- | FALSE | 346 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | Improving | FALSE | 1460 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | Improving | FALSE | 1460 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | -- | FALSE | 346 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | Improving | FALSE | 1460 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | -- | FALSE | 346 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | Improving | FALSE | 1460 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--114 | Project_100_Risk--114 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Contract Annex Items | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 50% | 3.0705 | 1.5352 | -- | 50% | 3.0705 | 1.5352 | H3 | 3 | -- | FALSE | 1094 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 8% | 19.1935 | 1.5355 | Accept | 8% | 19.1935 | 1.5355 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 8% | 19.1935 | 1.5355 | Accept | 8% | 19.1935 | 1.5355 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 8% | 19.1935 | 1.5355 | Accept | 8% | 19.1935 | 1.5355 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 8% | 19.1935 | 1.5355 | Accept | 8% | 19.1935 | 1.5355 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 8% | 19.1935 | 1.5355 | Accept | 8% | 19.1935 | 1.5355 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 8% | 19.1935 | 1.5355 | Accept | 8% | 19.1935 | 1.5355 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | Improving | FALSE | 1460 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK026 | Project_029_RISK026 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | sub-system Supply | Person_403 | 2018-10-22 01:00 | 2019-09-20 01:00 | 75% | 3.8501 | 2.8876 | Reduce | 40% | 3.8501 | 1.54 | H2 | 2 | -- | TRUE | 333 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133- | Project_065_RISK133- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2018-05-23 | 2021-04-22 | 20% | 7.7077 | 1.5415 | Accept | 20% | 7.7077 | 1.5415 | H3 | 3 | -- | FALSE | 1065 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-007 | Project_098_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Operational Damage Not Allowed | Person_439 | 2018-05-24 | 2027-05-23 | 30% | 5.1662 | 1.5499 | Accept | 30% | 5.1662 | 1.5499 | H2 | 2 | Stable | TRUE | 3286 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319- | Project_065_RISK319- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-22 | 2021-05-03 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | -- | FALSE | 346 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK319-Risk- | Project_065_RISK319-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Early life Risk of delay in the event of SubSystem failure during integration. | Person_160 | 2020-05-23 | 2024-05-22 | 10% | 1.2677 | 0.12677 | Accept | 10% | 1.2677 | 0.12677 | H3 | 3 | Improving | FALSE | 1460 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-08 | 2020-09-21 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-07 22:00 | 2020-09-20 22:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-07 22:00 | 2020-09-20 22:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-08 | 2020-09-21 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-08 01:00 | 2020-09-21 01:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK072 | Project_065_RISK072 | Threat | Project Contingency | Open | H3 | 3 |  | Vendors Don't Adhere To Standards: format unexpected issues. | Person_661 | 2016-09-07 23:00 | 2020-09-20 23:00 | 40% | 1.3032 | 0.52128 | Reduce | 10% | 1.3032 | 0.13032 | H3 | 3 | -- | TRUE | 1474 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence Monitoring Risk | Person_181 | 2016-12-03 01:00 | 2017-01-20 01:00 | 30% | 5.9458 | 1.7837 | Reduce | 15% | 0.9786 | 0.14679 | H3 | 3 | Stable | TRUE | 48 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence Monitoring Risk | Person_181 | 2016-12-03 01:00 | 2017-01-20 01:00 | 30% | 5.9458 | 1.7837 | Reduce | 15% | 0.9786 | 0.14679 | H3 | 3 | Stable | TRUE | 48 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence Monitoring Risk | Person_181 | 2016-12-03 | 2017-01-20 | 30% | 5.9458 | 1.7837 | Reduce | 15% | 0.9786 | 0.14679 | H3 | 3 | Stable | TRUE | 48 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence Monitoring Risk | Person_181 | 2016-12-03 | 2017-01-20 | 30% | 5.9458 | 1.7837 | Reduce | 15% | 0.9786 | 0.14679 | H3 | 3 | Stable | TRUE | 48 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 23:00 | 2017-01-19 23:00 | 30% | 5.9458 | 1.7837 | Reduce | 15% | 0.9786 | 0.14679 | H3 | 3 | Stable | TRUE | 48 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 23:00 | 2017-01-19 23:00 | 30% | 5.9458 | 1.7837 | Reduce | 15% | 0.9786 | 0.14679 | H3 | 3 | Stable | TRUE | 48 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 23:00 | 2017-01-19 23:00 | 30% | 5.9458 | 1.7837 | Reduce | 15% | 0.9786 | 0.14679 | H3 | 3 | Stable | TRUE | 48 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK001 | Project_017_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence Monitoring Risk | Person_181 | 2016-12-02 21:00 | 2017-01-19 21:00 | 30% | 5.9458 | 1.7837 | Reduce | 15% | 0.9786 | 0.14679 | H3 | 3 | Stable | TRUE | 48 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_009 | Risk304 | Project_009_Risk304 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Installation | Person_284 | 2015-08-16 | 2016-09-19 01:00 | 10% | 1.4699 | 0.14699 | Reduce | 10% | 1.4699 | 0.14699 | H3 | 3 | -- | FALSE | 400.0417 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 745 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 745 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 745 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 745 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 745 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 745 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 12% | 13.2195 | 1.5863 | Accept | 12% | 13.2195 | 1.5863 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 12% | 13.2195 | 1.5863 | Accept | 12% | 13.2195 | 1.5863 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 12% | 13.2195 | 1.5863 | Accept | 12% | 13.2195 | 1.5863 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 12% | 13.2195 | 1.5863 | Accept | 12% | 13.2195 | 1.5863 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 12% | 13.2195 | 1.5863 | Accept | 12% | 13.2195 | 1.5863 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 12% | 13.2195 | 1.5863 | Accept | 12% | 13.2195 | 1.5863 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 12% | 13.2195 | 1.5863 | Accept | 12% | 13.2195 | 1.5863 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-187 | Project_027_Risk-187 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Loss of a major sub-contractor | Person_317 | 2014-01-04 01:00 | 2017-08-20 01:00 | 12% | 13.2195 | 1.5863 | Accept | 12% | 13.2195 | 1.5863 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 50% | 3.1818 | 1.5909 | Accept | 50% | 3.1818 | 1.5909 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 50% | 3.1818 | 1.5909 | Accept | 50% | 3.1818 | 1.5909 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 50% | 3.1818 | 1.5909 | Accept | 50% | 3.1818 | 1.5909 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 50% | 3.1818 | 1.5909 | Accept | 50% | 3.1818 | 1.5909 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 50% | 3.1818 | 1.5909 | Accept | 50% | 3.1818 | 1.5909 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 50% | 3.1818 | 1.5909 | Accept | 50% | 3.1818 | 1.5909 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 745 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2019-10-14 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 745 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-005 | Project_029_Risk-005 | Threat | Project Contingency | Open | H3 | 3 |  | There is a risk that trials are hindered due to sub-system problems | Person_102 | 2017-09-29 01:00 | 2020-09-19 01:00 | 20% | 1.54 | 0.30801 | Accept | 20% | 0.77001 | 0.154 | H3 | 3 | Stable | TRUE | 1086 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK004 | Project_081_RISK004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Greater number of failures/ investigations | Person_260 | 2017-09-27 01:00 | 2021-09-27 01:00 | 60% | 2.685 | 1.611 | Reduce | 60% | 2.685 | 1.611 | H3 | 3 | Worsening | FALSE | 1461 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 |  | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 50% | 6.4168 | 3.2084 | Accept | 10% | 1.5614 | 0.15614 | H3 | 3 | Stable | TRUE | 516.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 |  | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 50% | 6.4168 | 3.2084 | Accept | 10% | 1.5614 | 0.15614 | H3 | 3 | Stable | TRUE | 516.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 |  | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 50% | 6.4168 | 3.2084 | Accept | 10% | 1.5614 | 0.15614 | H3 | 3 | Stable | TRUE | 516.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 |  | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 50% | 6.4168 | 3.2084 | Accept | 10% | 1.5614 | 0.15614 | H3 | 3 | Stable | TRUE | 516.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-017 | Project_029_Risk-017 | Threat | Project Contingency | Open | H3 | 3 |  | Additional Obsolescence - System | Person_102 | 2016-05-23 | 2017-10-21 01:00 | 50% | 6.4168 | 3.2084 | Accept | 10% | 1.5614 | 0.15614 | H3 | 3 | Stable | TRUE | 516.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK008 | Project_081_RISK008 | Threat | Project Contingency | Open | H3 | 3 |  | Failure to meet repair turnaround time | Person_260 | 2017-09-27 01:00 | 2021-09-20 01:00 | 10% | 1.5866 | 0.15866 | Reduce | 10% | 1.5866 | 0.15866 | H3 | 3 | Stable | TRUE | 1454 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK075 | Project_076_RISK075 | Threat | Project Contingency | Open | H2 | 2 |  | Delay in SW completion completion - Safety issues | Person_152 | 2018-07-05 | 2019-05-16 | 50% | 1.6723 | 0.83613 | Reduce | 10% | 1.6723 | 0.16723 | H3 | 3 | Stable | FALSE | 315 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK075 | Project_076_RISK075 | Threat | Project Contingency | Open | H2 | 2 |  | Delay in SW completion - Safety issues | Person_152 | 2018-07-05 | 2019-05-16 | 50% | 1.6723 | 0.83613 | Reduce | 10% | 1.6723 | 0.16723 | H3 | 3 | Stable | FALSE | 315 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 16.1945 | 1.6195 | Accept | 10% | 16.1945 | 1.6195 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 16.1945 | 1.6195 | Accept | 10% | 16.1945 | 1.6195 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 16.1945 | 1.6195 | Accept | 10% | 16.1945 | 1.6195 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 16.1945 | 1.6195 | Accept | 10% | 16.1945 | 1.6195 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 16.1945 | 1.6195 | Accept | 10% | 16.1945 | 1.6195 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK056 | Project_076_RISK056 | Threat | Project Contingency | Open | H3 | 3 |  | Peer Review Failures | Person_484 | 2018-02-20 01:00 | 2019-11-20 01:00 | 20% | 0.89832 | 0.17966 | Accept | 20% | 0.89832 | 0.17966 | H3 | 3 | -- | TRUE | 638 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK056 | Project_076_RISK056 | Threat | Project Contingency | Open | H3 | 3 |  | Peer Review Failures | Person_484 | 2018-02-20 01:00 | 2019-11-20 01:00 | 20% | 0.89832 | 0.17966 | Accept | 20% | 0.89832 | 0.17966 | H3 | 3 | -- | TRUE | 638 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK056 | Project_076_RISK056 | Threat | Project Contingency | Open | H3 | 3 |  | Peer Review Failures | Person_484 | 2018-02-20 01:00 | 2019-11-20 01:00 | 20% | 0.89832 | 0.17966 | Accept | 20% | 0.89832 | 0.17966 | H3 | 3 | -- | TRUE | 638 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK056 | Project_076_RISK056 | Threat | Project Contingency | Open | H3 | 3 |  | Peer Review Failures | Person_484 | 2018-02-20 01:00 | 2019-11-20 01:00 | 20% | 0.89832 | 0.17966 | Accept | 20% | 0.89832 | 0.17966 | H3 | 3 | Stable | TRUE | 638 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-017 | Project_039_Risk-017 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Component coupling causes unrecoverable impact | Person_596 | 2014-12-22 01:00 | 2016-08-20 01:00 | 60% | 8.1135 | 4.8681 | Avoid | 20% | 8.1135 | 1.6227 | H3 | 3 | Worsening | FALSE | 607 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK012 | Project_094_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Insufficient resources to meet the demand of the programme | Person_198 | 2018-08-22 | 2021-07-20 | 35% | 4.6804 | 1.6381 | Reduce | 35% | 4.6804 | 1.6381 | H2 | 2 | Stable | TRUE | 1063 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 25% | 10.9327 | 2.7332 | Reduce | 15% | 10.9327 | 1.6399 | H2 | 2 | Worsening | TRUE | 547.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 25% | 10.9327 | 2.7332 | Reduce | 15% | 10.9327 | 1.6399 | H2 | 2 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-20 | 2018-05-22 | 25% | 10.9327 | 2.7332 | Reduce | 15% | 10.9327 | 1.6399 | H2 | 2 | Stable | TRUE | 548 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 10.9327 | 2.7332 | Reduce | 15% | 10.9327 | 1.6399 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 10.9327 | 2.7332 | Reduce | 15% | 10.9327 | 1.6399 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 25% | 10.9327 | 2.7332 | Reduce | 15% | 10.9327 | 1.6399 | H2 | 2 | Stable | TRUE | 548.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R43 | Project_041_R43 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Procurement - Component and Supplier Leadtime | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 25% | 10.9327 | 2.7332 | Reduce | 15% | 10.9327 | 1.6399 | H2 | 2 | Stable | TRUE | 548.0833 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2016-11-19 | 20% | 0.90951 | 0.1819 | Reduce | 20% | 0.90951 | 0.1819 | H3 | 3 | Stable | FALSE | 591 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 20% | 0.90951 | 0.1819 | Reduce | 20% | 0.90951 | 0.1819 | H3 | 3 | Stable | FALSE | 591.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 20% | 0.90951 | 0.1819 | Reduce | 20% | 0.90951 | 0.1819 | H3 | 3 | Stable | FALSE | 591.0417 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 85% | 25.2325 | 21.4476 | Avoid | 8% | 20.8758 | 1.6701 | H2 | 2 | Improving | TRUE | 1278.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 85% | 25.2325 | 21.4476 | Avoid | 8% | 20.8758 | 1.6701 | H2 | 2 | Improving | TRUE | 1278.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 85% | 25.2325 | 21.4476 | Avoid | 8% | 20.8758 | 1.6701 | H2 | 2 | Improving | TRUE | 1278.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 85% | 25.2325 | 21.4476 | Avoid | 8% | 20.8758 | 1.6701 | H2 | 2 | Improving | TRUE | 1278.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 85% | 25.2325 | 21.4476 | Avoid | 8% | 20.8758 | 1.6701 | H2 | 2 | Improving | TRUE | 1278.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2016-11-17 01:00 | 85% | 25.2325 | 21.4476 | Avoid | 8% | 20.8758 | 1.6701 | H2 | 2 | Improving | TRUE | 1278.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-03-22 | 85% | 25.2325 | 21.4476 | Avoid | 8% | 20.8758 | 1.6701 | H2 | 2 | Stable | TRUE | 1403 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_023 | Risk-003 | Project_023_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Environmental Requirements Sign Off | Person_277 | 2013-05-19 | 2017-03-22 | 85% | 25.2325 | 21.4476 | Avoid | 8% | 20.8758 | 1.6701 | H2 | 2 | Stable | TRUE | 1403 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2017-05-23 | 2018-05-22 | 50% | 6.7334 | 3.3667 | Reduce | 25% | 6.7334 | 1.6833 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2017-05-23 | 2018-05-22 | 50% | 6.7334 | 3.3667 | Reduce | 25% | 6.7334 | 1.6833 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 50% | 6.7334 | 3.3667 | Reduce | 25% | 6.7334 | 1.6833 | H2 | 2 | Stable | TRUE | 806 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 50% | 6.7334 | 3.3667 | Reduce | 25% | 6.7334 | 1.6833 | H2 | 2 | Stable | TRUE | 806 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 50% | 6.7334 | 3.3667 | Reduce | 25% | 6.7334 | 1.6833 | H2 | 2 | Stable | TRUE | 806 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 50% | 6.7334 | 3.3667 | Reduce | 25% | 6.7334 | 1.6833 | H2 | 2 | Stable | TRUE | 806 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK002 | Project_058_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence of key parts | Person_236 | 2017-05-23 | 2019-08-07 | 50% | 6.7334 | 3.3667 | Reduce | 25% | 6.7334 | 1.6833 | H2 | 2 | Stable | TRUE | 806 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-09-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 25% | 6.7418 | 1.6855 | H2 | 2 | Stable | TRUE | 426.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK171 | Project_038_RISK171 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Sub-system Qual Test | Person_531 | 2015-07-22 | 2016-09-20 01:00 | 25% | 6.7418 | 1.6855 | Accept | 25% | 6.7418 | 1.6855 | H2 | 2 | Stable | TRUE | 426.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_072 | RISK086 | Project_072_RISK086 | Threat | Project Contingency | Open | H2 | 2 | Customers | Reputational Technical Risk | Person_614 | 2020-03-27 | 2021-03-25 | 30% | 5.6406 | 1.6922 | Transfer | 30% | 5.6406 | 1.6922 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2016-02-21 01:00 | 2018-05-22 | 10% | 17.0765 | 1.7076 | Accept | 10% | 17.0765 | 1.7076 | H3 | 3 | -- | FALSE | 820.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2016-02-21 01:00 | 2018-05-22 | 10% | 17.0765 | 1.7076 | Accept | 10% | 17.0765 | 1.7076 | H3 | 3 | -- | FALSE | 820.9583 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2016-02-21 01:00 | 2018-05-22 | 10% | 17.0765 | 1.7076 | Accept | 10% | 17.0765 | 1.7076 | H3 | 3 | Stable | FALSE | 820.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2016-02-21 01:00 | 2018-05-22 | 10% | 17.0765 | 1.7076 | Accept | 10% | 17.0765 | 1.7076 | H3 | 3 | Stable | FALSE | 820.9583 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 10% | 17.0765 | 1.7076 | Accept | 10% | 17.0765 | 1.7076 | H3 | 3 | Stable | FALSE | 455.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 10% | 17.0765 | 1.7076 | Accept | 10% | 17.0765 | 1.7076 | H3 | 3 | Stable | FALSE | 455.9583 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK246 | Project_024_RISK246 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Acceptance Stages 1, 2 and 3-5 | Person_288 | 2017-02-20 01:00 | 2018-05-22 | 10% | 17.0765 | 1.7076 | Accept | 10% | 17.0765 | 1.7076 | H3 | 3 | Stable | FALSE | 455.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2016-11-19 01:00 | 20% | 0.90951 | 0.1819 | Reduce | 20% | 0.90951 | 0.1819 | H3 | 3 | Stable | FALSE | 591.0417 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 20% | 0.90951 | 0.1819 | Reduce | 20% | 0.90951 | 0.1819 | H3 | 3 | Stable | FALSE | 744 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 20% | 0.90951 | 0.1819 | Reduce | 20% | 0.90951 | 0.1819 | H3 | 3 | Stable | FALSE | 744 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 20% | 0.90951 | 0.1819 | Reduce | 20% | 0.90951 | 0.1819 | H3 | 3 | Stable | FALSE | 744 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-039 | Project_028_Risk-039 | Threat | Project Contingency | Open | H2 | 2 |  | Ping Cycle Over-run Issues | Person_542 | 2015-04-08 | 2017-04-21 | 20% | 0.90951 | 0.1819 | Reduce | 20% | 0.90951 | 0.1819 | H3 | 3 | Stable | FALSE | 744 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK046 | Project_017_RISK046 | Threat | Project Contingency | Open | H3 | 3 |  | Providing Datapacks (1) | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 20% | 3.9556 | 0.79113 | -- | 20% | 0.9374 | 0.18748 | H3 | 3 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK055 | Project_017_RISK055 | Threat | Project Contingency | Open | H3 | 3 |  | Providing Datapacks (2) | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 20% | 0.9168 | 0.18336 | -- | 20% | 0.9374 | 0.18748 | H3 | 3 | -- | TRUE | 2586 |  | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK060 | Project_042_RISK060 | Threat | Project Contingency | Open | H2 | 2 |  | Delayed Materials | Person_002 | 2018-09-23 01:00 | 2019-10-22 01:00 | 20% | 0.93941 | 0.18788 | Accept | 20% | 0.93941 | 0.18788 | H3 | 3 | -- | FALSE | 394 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_060 | RISK001 | Project_060_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Procurement Prices | Person_033 | 2017-11-02 01:00 | 2018-11-20 01:00 | 70% | 5.769 | 4.0383 | Reduce | 30% | 5.769 | 1.7307 | H2 | 2 | Stable | TRUE | 383 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 30% | 8.7814 | 2.6344 | Reduce | 20% | 8.7832 | 1.7566 | H3 | 3 | Stable | TRUE | 585 |  | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 30% | 8.7814 | 2.6344 | Reduce | 20% | 8.7832 | 1.7566 | H3 | 3 | Stable | TRUE | 585 |  | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 30% | 8.7814 | 2.6344 | Reduce | 20% | 8.7832 | 1.7566 | H3 | 3 | Stable | TRUE | 585 |  | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 30% | 8.7814 | 2.6344 | Reduce | 20% | 8.7832 | 1.7566 | H3 | 3 | Stable | TRUE | 585 |  | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R007 | Project_016_Risk--R007 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Role Test Equipment | Person_306 | 2016-01-13 01:00 | 2017-08-20 01:00 | 30% | 8.7814 | 2.6344 | Reduce | 20% | 8.7832 | 1.7566 | H3 | 3 | Stable | TRUE | 585 |  | 0 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | INterface Card | Person_253 | 2015-07-22 | 2016-08-20 | 20% | 2.8408 | 0.56817 | Reduce | 10% | 1.9314 | 0.19314 | H3 | 3 | Stable | FALSE | 395 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | INterface Card | Person_253 | 2015-07-22 | 2016-09-19 01:00 | 20% | 2.8408 | 0.56817 | Reduce | 10% | 1.9314 | 0.19314 | H3 | 3 | Stable | FALSE | 425.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | INterface Card | Person_253 | 2015-07-22 | 2016-10-20 01:00 | 20% | 2.8408 | 0.56817 | Reduce | 10% | 1.9314 | 0.19314 | H3 | 3 | Stable | FALSE | 456.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | INterface Card | Person_253 | 2015-07-22 | 2016-10-20 01:00 | 20% | 2.8408 | 0.56817 | Reduce | 10% | 1.9314 | 0.19314 | H3 | 3 | Stable | FALSE | 456.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | INterface Card | Person_253 | 2015-07-22 | 2016-12-18 01:00 | 20% | 2.8408 | 0.56817 | Reduce | 10% | 1.9314 | 0.19314 | H3 | 3 | Stable | FALSE | 515.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-058 | Project_028_Risk-058 | Threat | Project Contingency | Open | H2 | 2 |  | INterface Card | Person_253 | 2015-07-22 | 2016-12-18 01:00 | 20% | 2.8408 | 0.56817 | Reduce | 10% | 1.9314 | 0.19314 | H3 | 3 | Stable | FALSE | 515.0417 |  | 1 | 0 | 1
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK012 | Project_058_RISK012 | Threat | Project Contingency | Open | H3 | 3 |  | Material Cost validity | Person_268 | 2017-05-24 | 2018-11-20 01:00 | 10% | 8.6125 | 0.86125 | Reduce | 5% | 3.9148 | 0.19574 | H3 | 3 | -- | TRUE | 545.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK012 | Project_058_RISK012 | Threat | Project Contingency | Open | H3 | 3 |  | Material Cost validity | Person_268 | 2017-05-24 | 2018-11-20 01:00 | 10% | 8.6125 | 0.86125 | Reduce | 5% | 3.9148 | 0.19574 | H3 | 3 | -- | TRUE | 545.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Items damaged in transit | Person_294 | 2017-04-23 | 2018-11-20 01:00 | 30% | 11.7443 | 3.5233 | Reduce | 10% | 1.9574 | 0.19574 | H3 | 3 | -- | TRUE | 576.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Items damaged in transit | Person_294 | 2017-04-23 | 2018-11-20 01:00 | 30% | 11.7443 | 3.5233 | Reduce | 10% | 1.9574 | 0.19574 | H3 | 3 | -- | TRUE | 576.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-21 01:00 | 2018-05-13 | 50% | 3.9172 | 1.9586 | Reduce | 5% | 3.9172 | 0.19586 | H3 | 3 | -- | FALSE | 568.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-21 01:00 | 2018-05-13 | 50% | 3.9172 | 1.9586 | Reduce | 5% | 3.9172 | 0.19586 | H3 | 3 | -- | FALSE | 568.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-21 | 2018-05-13 | 50% | 3.9172 | 1.9586 | Reduce | 5% | 3.9172 | 0.19586 | H3 | 3 | -- | FALSE | 569 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-21 01:00 | 2018-05-13 | 50% | 3.9172 | 1.9586 | Reduce | 5% | 3.9172 | 0.19586 | H3 | 3 | -- | FALSE | 568.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-20 23:00 | 2018-05-13 | 50% | 3.9172 | 1.9586 | Reduce | 5% | 3.9172 | 0.19586 | H3 | 3 | -- | FALSE | 569.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-20 22:00 | 2018-05-13 | 50% | 3.9172 | 1.9586 | Reduce | 5% | 3.9172 | 0.19586 | H3 | 3 | -- | FALSE | 569.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-20 23:00 | 2018-05-13 | 50% | 3.9172 | 1.9586 | Reduce | 5% | 3.9172 | 0.19586 | H3 | 3 | -- | FALSE | 569.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK121 | Project_065_RISK121 | Threat | Project Contingency | Open | H2 | 2 |  | Image scaling prevents manual target height estimation to the required accuracy | Person_022 | 2016-10-20 22:00 | 2018-05-13 | 50% | 3.9172 | 1.9586 | Reduce | 5% | 3.9172 | 0.19586 | H3 | 3 | -- | FALSE | 569.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 10% | 2.0249 | 0.20249 | Accept | 10% | 2.0249 | 0.20249 | H3 | 3 | Stable | FALSE | 426.0417 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Retests | Person_542 | 2015-01-22 | 2017-08-20 | 35% | 8.8098 | 3.0834 | Accept | 20% | 8.8098 | 1.762 | H2 | 2 | Stable | TRUE | 941 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 35% | 8.8098 | 3.0834 | Accept | 20% | 8.8098 | 1.762 | H2 | 2 | Stable | TRUE | 941 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 35% | 8.8098 | 3.0834 | Accept | 20% | 8.8098 | 1.762 | H2 | 2 | Stable | TRUE | 941 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 35% | 8.8098 | 3.0834 | Accept | 20% | 8.8098 | 1.762 | H2 | 2 | Stable | TRUE | 941 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 35% | 8.8098 | 3.0834 | Accept | 20% | 8.8098 | 1.762 | H2 | 2 | Stable | TRUE | 941 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 35% | 8.8098 | 3.0834 | Accept | 20% | 8.8098 | 1.762 | H2 | 2 | Stable | TRUE | 941 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 35% | 8.8098 | 3.0834 | Accept | 20% | 8.8098 | 1.762 | H2 | 2 | Stable | TRUE | 941 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-007 | Project_028_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Retests | Person_542 | 2015-01-22 01:00 | 2017-08-20 01:00 | 35% | 8.8098 | 3.0834 | Accept | 20% | 8.8098 | 1.762 | H2 | 2 | Stable | TRUE | 941 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-001 | Project_006_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Engineering Support to External Assemblies | Person_582 | 2015-05-24 | 2017-04-22 | 15% | 21.3649 | 3.2047 | Avoid | 10% | 17.6408 | 1.7641 | H2 | 2 | Stable | TRUE | 699 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Failures at Acceptance stage | Person_627 | 2017-07-21 | 2018-09-20 01:00 | 30% | 5.9059 | 1.7718 | Accept | 30% | 5.9059 | 1.7718 | H2 | 2 | Stable | TRUE | 426.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Failures at Acceptance stage | Person_449 | 2017-07-21 | 2019-04-22 | 30% | 5.9059 | 1.7718 | Accept | 30% | 5.9059 | 1.7718 | H2 | 2 | Stable | TRUE | 640 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Failures at Acceptance stage | Person_449 | 2017-07-21 | 2019-04-22 | 30% | 5.9059 | 1.7718 | Accept | 30% | 5.9059 | 1.7718 | H2 | 2 | Stable | TRUE | 640 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Failures at Acceptance stage | Person_449 | 2017-07-21 | 2019-04-22 | 30% | 5.9059 | 1.7718 | Accept | 30% | 5.9059 | 1.7718 | H2 | 2 | Stable | TRUE | 640 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK008 | Project_075_RISK008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Failures at Acceptance stage | Person_449 | 2017-07-21 | 2019-04-22 | 30% | 5.9059 | 1.7718 | Accept | 30% | 5.9059 | 1.7718 | H2 | 2 | Stable | TRUE | 640 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 10% | 2.0249 | 0.20249 | Accept | 10% | 2.0249 | 0.20249 | H3 | 3 | Stable | FALSE | 426.0417 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 10% | 2.0249 | 0.20249 | Accept | 10% | 2.0249 | 0.20249 | H3 | 3 | Stable | FALSE | 426.0417 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 10% | 2.0249 | 0.20249 | Accept | 10% | 2.0249 | 0.20249 | H3 | 3 | Stable | FALSE | 426.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK007 | Project_075_RISK007 | Threat | Project Contingency | Open | H2 | 2 |  | Range performance does not meet requirement. | Person_003 | 2017-07-21 | 2018-09-20 01:00 | 10% | 2.0249 | 0.20249 | Accept | 10% | 2.0249 | 0.20249 | H3 | 3 | Stable | FALSE | 426.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 50% | 3.5934 | 1.7967 | Reduce | 50% | 3.5934 | 1.7967 | H2 | 2 | Stable | TRUE | 2411 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 50% | 3.5934 | 1.7967 | Reduce | 50% | 3.5934 | 1.7967 | H2 | 2 | Stable | TRUE | 2411 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 50% | 3.5934 | 1.7967 | Reduce | 50% | 3.5934 | 1.7967 | H2 | 2 | Stable | TRUE | 2411 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 50% | 3.5934 | 1.7967 | Reduce | 50% | 3.5934 | 1.7967 | H2 | 2 | Stable | TRUE | 2411 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK004 | Project_029_Risk-RISK004 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Replacement of product specific Test Assets during hardware Factory Acceptance Schedule | Person_102 | 2018-08-14 | 2025-03-21 | 50% | 3.5934 | 1.7967 | Reduce | 50% | 3.5934 | 1.7967 | H2 | 2 | Stable | TRUE | 2411 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | RISK016 | Project_029_RISK016 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Out of Maintenance | Person_199 | 2018-10-22 01:00 | 2019-08-21 01:00 | 70% | 2.5667 | 1.7967 | Accept | 70% | 2.5667 | 1.7967 | H1 | 1 | -- | TRUE | 303 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK007 | Project_094_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Additional training requested | Person_620 | 2020-12-21 | 2021-07-20 | 30% | 5.9903 | 1.7971 | Avoid | 30% | 5.9903 | 1.7971 | H2 | 2 | Stable | TRUE | 211 |  | 1 | 1 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--45 | Project_021_Risk--45 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work of deliverables may be required from Customer - Customer to complete System CoD | Person_470 | 2018-05-23 | 2018-11-20 01:00 | 50% | 6.0147 | 3.0074 | Reduce | 30% | 6.0147 | 1.8044 | H2 | 2 | Stable | TRUE | 181.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--45 | Project_021_Risk--45 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Additional work on deliverables may be required from Customer | Person_470 | 2018-05-23 | 2018-11-20 01:00 | 50% | 6.0147 | 3.0074 | Reduce | 30% | 6.0147 | 1.8044 | H2 | 2 | Stable | TRUE | 181.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-133 | Project_020_Risk-133 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | External equipment Damage | Person_575 | 2011-05-24 | 2016-08-01 | 10% | 18.069 | 1.8069 | Accept | 10% | 18.069 | 1.8069 | H3 | 3 | -- | FALSE | 1896 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-133 | Project_020_Risk-133 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | External equipment Damage | Person_575 | 2011-05-24 | 2016-08-01 | 10% | 18.069 | 1.8069 | Accept | 10% | 18.069 | 1.8069 | H3 | 3 | -- | FALSE | 1896 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-133 | Project_020_Risk-133 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | External equipment Damage | Person_575 | 2011-05-24 | 2016-08-01 | 10% | 18.069 | 1.8069 | Accept | 10% | 18.069 | 1.8069 | H3 | 3 | -- | FALSE | 1896 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-133 | Project_020_Risk-133 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | External equipment Damage | Person_575 | 2011-05-24 | 2016-08-01 | 10% | 18.069 | 1.8069 | Accept | 10% | 18.069 | 1.8069 | H3 | 3 | -- | FALSE | 1896 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-133 | Project_020_Risk-133 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | External equipment Damage | Person_575 | 2011-05-24 | 2016-08-01 | 10% | 18.069 | 1.8069 | Accept | 10% | 18.069 | 1.8069 | H3 | 3 | -- | FALSE | 1896 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-161 | Project_026_Risk-161 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer Deliverable Acceptance | Person_340 | 2015-02-21 01:00 | 2022-09-30 01:00 | 50% | 3.6174 | 1.8087 | Accept | 50% | 3.6172 | 1.8086 | H3 | 3 | -- | TRUE | 2778 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-161 | Project_026_Risk-161 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer Deliverable Acceptance | Person_340 | 2015-02-21 01:00 | 2022-09-30 01:00 | 50% | 3.6174 | 1.8087 | Accept | 50% | 3.6172 | 1.8086 | H3 | 3 | -- | TRUE | 2778 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-161 | Project_026_Risk-161 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer Deliverable Acceptance | Person_091 | 2015-02-21 01:00 | 2022-09-30 01:00 | 50% | 3.6174 | 1.8087 | Accept | 50% | 3.6172 | 1.8086 | H3 | 3 | -- | TRUE | 2778 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-161 | Project_026_Risk-161 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer Deliverable Acceptance | Person_091 | 2015-02-21 01:00 | 2022-09-30 01:00 | 50% | 3.6174 | 1.8087 | Accept | 50% | 3.6172 | 1.8086 | H3 | 3 | -- | TRUE | 2778 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK220 | Project_038_RISK220 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Resources needed to deliver the programme | Person_330 | 2013-09-20 01:00 | 2015-10-20 01:00 | 50% | 45.6947 | 22.8474 | Avoid | 10% | 18.1281 | 1.8128 | H2 | 2 | Stable | TRUE | 760 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK220 | Project_038_RISK220 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of Resources needed to deliver the programme | Person_330 | 2013-09-20 01:00 | 2015-10-20 01:00 | 50% | 45.6947 | 22.8474 | Avoid | 10% | 18.1281 | 1.8128 | H2 | 2 | Stable | TRUE | 760 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 40% | 9.139 | 3.6556 | Avoid | 20% | 9.139 | 1.8278 | H3 | 3 | Stable | FALSE | 122.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 40% | 9.139 | 3.6556 | Avoid | 20% | 9.139 | 1.8278 | H3 | 3 | Stable | FALSE | 122.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 40% | 9.139 | 3.6556 | Avoid | 20% | 9.139 | 1.8278 | H3 | 3 | Stable | FALSE | 122.0417 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 40% | 9.139 | 3.6556 | Avoid | 20% | 9.139 | 1.8278 | H3 | 3 | Stable | FALSE | 122.0417 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 40% | 9.139 | 3.6556 | Avoid | 20% | 9.139 | 1.8278 | H3 | 3 | Stable | FALSE | 122.0417 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 40% | 9.139 | 3.6556 | Avoid | 20% | 9.139 | 1.8278 | H3 | 3 | Stable | FALSE | 122.0417 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 40% | 9.139 | 3.6556 | Avoid | 20% | 9.139 | 1.8278 | H3 | 3 | Stable | FALSE | 122.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK224 | Project_038_RISK224 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Fixes of Customer identified Dual System Issues during Acceptance | Person_017 | 2016-07-21 | 2016-11-20 01:00 | 40% | 9.139 | 3.6556 | Avoid | 20% | 9.139 | 1.8278 | H3 | 3 | Stable | FALSE | 122.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2011-04-22 | 2019-05-23 | 50% | 9.2179 | 4.609 | -- | 20% | 9.2179 | 1.8436 | H2 | 2 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 9.2179 | 4.609 | Reduce | 20% | 9.2179 | 1.8436 | H2 | 2 | Improving | TRUE | 306.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 9.2179 | 4.609 | Reduce | 20% | 9.2179 | 1.8436 | H2 | 2 | Improving | TRUE | 306.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 9.2179 | 4.609 | Reduce | 20% | 9.2179 | 1.8436 | H2 | 2 | Improving | TRUE | 306.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 9.2179 | 4.609 | Reduce | 20% | 9.2179 | 1.8436 | H2 | 2 | Improving | TRUE | 306.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK289 | Project_024_RISK289 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System architecture not adequate to meet performance requirements. | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 9.2179 | 4.609 | Reduce | 20% | 9.2179 | 1.8436 | H2 | 2 | Improving | TRUE | 306.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK016 | Project_083_RISK016 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Dependencies on product | Person_465 | 2018-03-17 01:00 | 2019-01-20 01:00 | 30% | 12.3182 | 3.6955 | Avoid | 15% | 12.3182 | 1.8477 | H2 | 2 | Stable | TRUE | 309 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-04-22 | 50% | 9.2746 | 4.6373 | Reduce | 20% | 9.2746 | 1.8549 | H3 | 3 | -- | FALSE | 1005 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-04-22 | 50% | 9.2746 | 4.6373 | Reduce | 20% | 9.2746 | 1.8549 | H3 | 3 | -- | FALSE | 1005 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-04-22 | 50% | 9.2746 | 4.6373 | Reduce | 20% | 9.2746 | 1.8549 | H3 | 3 | -- | FALSE | 1005 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-04-22 | 50% | 9.2746 | 4.6373 | Reduce | 20% | 9.2746 | 1.8549 | H3 | 3 | -- | FALSE | 1005 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-04-22 | 50% | 9.2746 | 4.6373 | Reduce | 20% | 9.2746 | 1.8549 | H3 | 3 | -- | FALSE | 1005 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-04-22 | 50% | 9.2746 | 4.6373 | Reduce | 20% | 9.2746 | 1.8549 | H3 | 3 | -- | FALSE | 1005 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK087 | Project_065_RISK087 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | HMI Changes | Person_661 | 2015-07-22 | 2018-04-22 | 50% | 9.2746 | 4.6373 | Reduce | 20% | 9.2746 | 1.8549 | H3 | 3 | -- | FALSE | 1005 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-08 01:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 263.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-08 01:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 263.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-08 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 264 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-08 01:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 263.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-07 23:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 264.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-07 22:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 264.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-07 23:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 264.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-08 01:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 263.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-07 22:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 264.0833 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-08 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 264 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-08 01:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 263.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK473 | Project_065_RISK473 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Insufficient HW to support all SW dev for final prod, test and INternal Early Deliveries. | Person_661 | 2017-10-07 23:00 | 2018-06-29 | 80% | 46.6519 | 37.3215 | Reduce | 20% | 9.3304 | 1.8661 | H3 | 3 | -- | FALSE | 264.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2016-09-02 01:00 | 2018-11-21 01:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 810 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 50% | 7.6063 | 3.8031 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator | Person_022 | 2016-09-02 01:00 | 2018-07-22 | 70% | 7.6063 | 5.3244 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 687.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator | Person_022 | 2016-09-02 01:00 | 2018-07-22 | 70% | 7.6063 | 5.3244 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 687.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2016-09-02 01:00 | 2018-11-21 01:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 810 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator | Person_022 | 2016-09-02 | 2018-07-22 | 70% | 7.6063 | 5.3244 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 688 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2016-09-02 | 2018-11-21 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 810 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-20 | 2020-11-20 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator | Person_022 | 2016-09-01 23:00 | 2018-07-22 | 70% | 7.6063 | 5.3244 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 688.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2016-09-01 23:00 | 2018-11-20 23:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 810 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator | Person_022 | 2016-09-01 22:00 | 2018-07-22 | 70% | 7.6063 | 5.3244 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 688.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2016-09-01 22:00 | 2018-11-20 22:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 810 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 9.3941 | 1.8788 | Accept | 20% | 9.3941 | 1.8788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 9.3941 | 1.8788 | Accept | 20% | 9.3941 | 1.8788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 9.3941 | 1.8788 | Accept | 20% | 9.3941 | 1.8788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 9.3941 | 1.8788 | Accept | 20% | 9.3941 | 1.8788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 9.3941 | 1.8788 | Accept | 20% | 9.3941 | 1.8788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 9.3941 | 1.8788 | Accept | 20% | 9.3941 | 1.8788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk002 | Project_042_Risk002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Spares | Person_455 | 2016-05-23 | 2020-05-23 | 20% | 9.3941 | 1.8788 | Accept | 20% | 9.3941 | 1.8788 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK005 | Project_079_RISK005 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 60% | 3.7631 | 2.2578 | -- | 50% | 3.7631 | 1.8815 | H2 | 2 | Stable | TRUE | 1186.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK005 | Project_079_RISK005 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 60% | 3.7631 | 2.2578 | -- | 50% | 3.7631 | 1.8815 | H2 | 2 | Stable | TRUE | 1186.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK005 | Project_079_RISK005 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 60% | 3.7631 | 2.2578 | -- | 50% | 3.7631 | 1.8815 | H2 | 2 | Stable | TRUE | 1186.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK005 | Project_079_RISK005 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Rework | Person_551 | 2017-02-20 01:00 | 2020-05-22 | 60% | 3.7631 | 2.2578 | -- | 50% | 3.7631 | 1.8815 | H2 | 2 | Stable | TRUE | 1186.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-010 | Project_062_Risk-010 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software Resource | Person_479 | 2017-07-21 | 2019-02-21 01:00 | 40% | 7.5293 | 3.0117 | Reduce | 25% | 7.5293 | 1.8823 | H2 | 2 | Stable | TRUE | 580.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 50% | 3.7714 | 1.8857 | Avoid | 50% | 3.7714 | 1.8857 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 50% | 3.7714 | 1.8857 | Avoid | 50% | 3.7714 | 1.8857 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 50% | 3.7714 | 1.8857 | Avoid | 50% | 3.7714 | 1.8857 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 50% | 3.7714 | 1.8857 | Avoid | 50% | 3.7714 | 1.8857 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 50% | 3.7714 | 1.8857 | Avoid | 50% | 3.7714 | 1.8857 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 50% | 3.7714 | 1.8857 | Avoid | 50% | 3.7714 | 1.8857 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 50% | 3.7714 | 1.8857 | Avoid | 50% | 3.7714 | 1.8857 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK001 | Project_019_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure not supported by sub-contractor | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 50% | 3.7714 | 1.8857 | Avoid | 50% | 3.7714 | 1.8857 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_692 | 2016-12-21 01:00 | 2017-12-19 01:00 | 33% | 5.7323 | 1.8917 | Reduce | 33% | 5.7323 | 1.8917 | H2 | 2 | Stable | TRUE | 363 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK036 | Project_029_Risk-RISK036 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Additional costs associated with change of supplier for Component Rack | Person_692 | 2016-12-21 01:00 | 2017-12-19 01:00 | 33% | 5.7323 | 1.8917 | Reduce | 33% | 5.7323 | 1.8917 | H2 | 2 | Stable | TRUE | 363 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-19 22:00 | 2020-11-19 22:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK342 | Project_065_RISK342 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Unexpected mechanical interactions between 2 Hardware sub-systems | Person_160 | 2019-05-24 | 2024-05-22 | 35% | 12.6771 | 4.437 | Reduce | 15% | 12.6771 | 1.9016 | H3 | 3 | -- | FALSE | 1825 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator | Person_022 | 2016-09-01 23:00 | 2018-07-22 | 70% | 7.6063 | 5.3244 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 688.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2016-09-01 23:00 | 2018-11-20 23:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 810 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2018-04-08 | 2018-11-21 01:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 227.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK086 | Project_065_RISK086 | Threat | Project Contingency | Open | H3 | 3 |  | False alarm rate presented to Operator | Person_022 | 2016-09-01 22:00 | 2018-07-22 | 70% | 7.6063 | 5.3244 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 688.0833 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2016-09-01 22:00 | 2018-11-20 22:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 810 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-201 | Project_027_Risk-201 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Transition into Support | Person_027 | 2014-01-21 01:00 | 2017-08-20 01:00 | 50% | 68.3768 | 34.1884 | Reduce | 5% | 38.387 | 1.9193 | H2 | 2 | Stable | TRUE | 1307 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-315 | Project_027_Risk-315 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Transition to Support - Spares | Person_060 | 2015-04-15 | 2016-05-22 | 10% | 19.1935 | 1.9194 | Accept | 10% | 19.1935 | 1.9194 | H2 | 2 | -- | TRUE | 403 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-315 | Project_027_Risk-315 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Transition to Support - Spares | Person_060 | 2015-04-15 | 2016-05-22 | 10% | 19.1935 | 1.9194 | Accept | 10% | 19.1935 | 1.9194 | H2 | 2 | -- | TRUE | 403 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-315 | Project_027_Risk-315 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Transition to Support - Spares | Person_060 | 2015-04-15 | 2016-05-22 | 10% | 19.1935 | 1.9194 | Accept | 10% | 19.1935 | 1.9194 | H2 | 2 | -- | TRUE | 403 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-316 | Project_027_Risk-316 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Test Equipment Obsolescence | Person_513 | 2015-04-15 | 2016-05-22 | 25% | 19.1935 | 4.7984 | Reduce | 10% | 19.1935 | 1.9194 | H3 | 3 | -- | FALSE | 403 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 50% | 3.843 | 1.9215 | Reduce | 50% | 3.843 | 1.9215 | H1 | 1 | Stable | TRUE | 549.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Subsystem does not meet requirements | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 50% | 3.843 | 1.9215 | Reduce | 50% | 3.843 | 1.9215 | H1 | 1 | Stable | TRUE | 549.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK002 | Project_083_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain Cost Increase - post Engineering design until completion of Procurement Phase | Person_391 | 2018-02-20 01:00 | 2019-01-20 01:00 | 65% | 5.8349 | 3.7927 | Reduce | 40% | 4.8385 | 1.9354 | H2 | 2 | Worsening | TRUE | 334 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 25% | 7.7469 | 1.9367 | Reduce | 25% | 7.7469 | 1.9367 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 25% | 7.7469 | 1.9367 | Reduce | 25% | 7.7469 | 1.9367 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 25% | 7.7469 | 1.9367 | Reduce | 25% | 7.7469 | 1.9367 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 | 2017-08-20 | 25% | 7.7469 | 1.9367 | Reduce | 25% | 7.7469 | 1.9367 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 25% | 7.7469 | 1.9367 | Reduce | 25% | 7.7469 | 1.9367 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 25% | 7.7469 | 1.9367 | Reduce | 25% | 7.7469 | 1.9367 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 25% | 7.7469 | 1.9367 | Reduce | 25% | 7.7469 | 1.9367 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-175 | Project_032_Risk-175 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - Software Management - Undefined SoW | Person_720 | 2012-08-21 01:00 | 2017-08-20 01:00 | 25% | 7.7469 | 1.9367 | Reduce | 25% | 7.7469 | 1.9367 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK024 | Project_083_RISK024 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Availability of Data to support Customer Deliverable updates aligned to Customer Deliverable delivery dates | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 35% | 9.2062 | 3.2222 | Reduce | 25% | 7.754 | 1.9385 | H2 | 2 | Improving | TRUE | 309 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK143 | Project_038_RISK143 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Real Time Video | Person_699 | 2016-06-23 | 2016-11-20 01:00 | 30% | 5.5433 | 1.663 | Reduce | 35% | 5.5433 | 1.9402 | H2 | 2 | Worsening | TRUE | 150.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-19 22:00 | 2020-11-19 22:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-20 | 2020-11-20 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2018-04-08 | 2018-11-21 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 227 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-20 01:00 | 2020-11-20 01:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2018-04-08 | 2018-11-21 01:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 227.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK110 | Project_065_RISK110 | Threat | Management Contingency | Open | H3 | 3 |  | Build of hardware provides challenges not yet forseen or fully overcome during Derisk Activities | Person_191 | 2016-11-19 23:00 | 2020-11-19 23:00 | 50% | 9.1275 | 4.5638 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 1461 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK085 | Project_065_RISK085 | Threat | Project Contingency | Open | H3 | 3 |  | The subsystem may require a solution involving two or three electronic assemblies rather than one. | Person_022 | 2018-04-08 | 2018-11-20 23:00 | 50% | 2.0283 | 1.0142 | Reduce | 20% | 1.0142 | 0.20283 | H3 | 3 | -- | TRUE | 226.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 50% | 4.0661 | 2.033 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 413.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 50% | 4.0661 | 2.033 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 413.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 50% | 4.0661 | 2.033 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 413.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 | 2016-04-21 | 50% | 4.0661 | 2.033 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 414 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 50% | 4.0661 | 2.033 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 413.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2020-05-23 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 729 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2020-05-23 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 729 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2020-05-23 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 729 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2020-05-23 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 729 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2020-05-23 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 729 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2020-05-23 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 729 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2019-05-24 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 1094 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2020-05-23 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 729 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2019-05-24 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 1094 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2019-05-24 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 1094 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK223 | Project_065_RISK223 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Pressure Boundary Leaks | Person_022 | 2019-05-24 | 2022-05-22 | 30% | 6.5076 | 1.9523 | Reduce | 30% | 6.5076 | 1.9523 | H2 | 2 | -- | TRUE | 1094 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-27 01:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 1282.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-27 01:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 1282.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-27 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 1282 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-27 01:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 1282.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-26 23:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 1281.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-26 22:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 1281.9167 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2023-05-24 | 2023-12-01 01:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 191.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2016-06-23 | 2019-12-26 22:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 1281.9167 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2023-05-24 | 2023-12-01 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 191 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2023-05-24 | 2023-12-01 01:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 191.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK005-Risk- | Project_065_RISK005-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | EMC non compliance | Person_047 | 2023-05-24 | 2023-11-30 23:00 | 70% | 3.935 | 2.7545 | Reduce | 50% | 3.935 | 1.9675 | H2 | 2 | Stable | TRUE | 190.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 50% | 4.0661 | 2.033 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 413.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 01:00 | 2016-04-21 | 50% | 4.0661 | 2.033 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 413.9583 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-04 | 2016-04-21 | 50% | 4.0661 | 2.033 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 414 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_010 | RISK005 | Project_010_RISK005 | Threat | Project Contingency | Open | H2 | 2 |  | Power Supply transient problems. To be closed when integration work complete | Person_552 | 2015-03-03 17:00 | 2018-04-21 | 20% | 4.0661 | 0.81322 | Reduce | 5% | 4.0661 | 0.2033 | H3 | 3 | Stable | FALSE | 1144.2917 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H3 | 3 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 40% | 1.078 | 0.43121 | Reduce | 20% | 1.078 | 0.2156 | H3 | 3 | Stable | TRUE | 1399 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 | 2019-08-21 | 15% | 26.3497 | 3.9525 | Reduce | 15% | 13.1767 | 1.9765 | H3 | 3 | Stable | FALSE | 1316 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 15% | 26.3497 | 3.9525 | Reduce | 15% | 13.1767 | 1.9765 | H3 | 3 | Stable | FALSE | 1316 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 15% | 26.3497 | 3.9525 | Reduce | 15% | 13.1767 | 1.9765 | H3 | 3 | Stable | FALSE | 1316 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 30% | 6.6217 | 1.9865 | -- | 30% | 6.6217 | 1.9865 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 | 2017-11-20 | 30% | 6.6217 | 1.9865 | -- | 30% | 6.6217 | 1.9865 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 30% | 6.6217 | 1.9865 | -- | 30% | 6.6217 | 1.9865 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 30% | 6.6217 | 1.9865 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 30% | 6.6217 | 1.9865 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP005 | Project_021_OPP005 | Opportunitity | Project Contingency | Open | H2 | 2 | Customers | Opportunity to recover costs through Climatic Testing | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 10% | 6.6217 | 0.66217 | -- | 30% | 6.6217 | 1.9865 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK154 | Project_038_RISK154 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production Tools and Jigs | Person_640 | 2015-06-24 | 2016-07-16 | 30% | 8.9142 | 2.6743 | Accept | 30% | 6.6669 | 2.0001 | H2 | 2 | Stable | TRUE | 388 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK154 | Project_038_RISK154 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production Tools and Jigs | Person_640 | 2015-06-24 | 2016-07-16 | 30% | 8.9142 | 2.6743 | Accept | 30% | 6.6669 | 2.0001 | H2 | 2 | Stable | TRUE | 388 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK154 | Project_038_RISK154 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Production Tools and Jigs | Person_640 | 2015-06-24 | 2016-08-20 01:00 | 30% | 8.9142 | 2.6743 | Accept | 30% | 6.6669 | 2.0001 | H2 | 2 | Stable | TRUE | 423.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 | 2019-09-13 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 23:00 | 2019-09-12 23:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 22:00 | 2019-09-12 22:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 23:00 | 2019-09-12 23:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 22:00 | 2019-09-12 22:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 | 2019-09-13 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-06 01:00 | 2019-09-13 01:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK117 | Project_065_RISK117 | Threat | Management Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Equipment IVV | Person_020 | 2018-10-05 23:00 | 2019-09-12 23:00 | 80% | 8.0322 | 6.4258 | Reduce | 50% | 4.006 | 2.003 | H2 | 2 | Stable | TRUE | 342 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Accept | 10% | 20.0332 | 2.0033 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Accept | 10% | 20.0332 | 2.0033 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-188 | Project_027_Risk-188 | Threat | Project Contingency | Open | H3 | 3 | System Engineering | Unidentified Technical Legacy Issue | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 20.0332 | 2.0033 | Accept | 10% | 20.0332 | 2.0033 | H3 | 3 | Stable | TRUE | 1324 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H3 | 3 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 40% | 1.078 | 0.43121 | Reduce | 20% | 1.078 | 0.2156 | H3 | 3 | Stable | TRUE | 1399 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 1 | Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 20:00 | 70% | 2.8891 | 2.0224 | Reduce | 70% | 2.8891 | 2.0224 | H1 | 1 | Worsening | TRUE | 1902.8333 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 1 | Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 20:00 | 70% | 2.8891 | 2.0224 | Reduce | 70% | 2.8891 | 2.0224 | H1 | 1 | Worsening | TRUE | 1902.8333 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 1 | Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 20:00 | 70% | 2.8891 | 2.0224 | Reduce | 70% | 2.8891 | 2.0224 | H1 | 1 | Worsening | TRUE | 1902.8333 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 1 | Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 20:00 | 70% | 2.8891 | 2.0224 | Reduce | 70% | 2.8891 | 2.0224 | H1 | 1 | Worsening | TRUE | 1902.8333 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 1 | Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 70% | 2.8891 | 2.0224 | Reduce | 70% | 2.8891 | 2.0224 | H1 | 1 | Worsening | TRUE | 1902.7917 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 1 | Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 70% | 2.8891 | 2.0224 | Reduce | 70% | 2.8891 | 2.0224 | H1 | 1 | Worsening | TRUE | 1902.7917 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 1 | Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 70% | 2.8891 | 2.0224 | Reduce | 70% | 2.8891 | 2.0224 | H1 | 1 | Worsening | TRUE | 1902.7917 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_025 | RS017 | Project_025_RS017 | Threat | Project Contingency | Open | H1 | 1 | Customers | Design Impacts on Quality | Person_157 | 2014-06-05 | 2019-08-20 19:00 | 70% | 2.8891 | 2.0224 | Reduce | 70% | 2.8891 | 2.0224 | H1 | 1 | Worsening | TRUE | 1902.7917 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H3 | 3 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 40% | 1.078 | 0.43121 | Reduce | 20% | 1.078 | 0.2156 | H3 | 3 | Stable | TRUE | 1399 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-019 | Project_029_Risk-019 | Threat | Project Contingency | Open | H3 | 3 |  | Verification Data - Systems Integration [Build to Print data] | Person_102 | 2014-01-21 01:00 | 2017-11-20 01:00 | 40% | 1.078 | 0.43121 | Reduce | 20% | 1.078 | 0.2156 | H3 | 3 | Stable | TRUE | 1399 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK044 | Project_017_RISK044 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in an in country support required | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 20% | 1.4865 | 0.29729 | -- | 15% | 1.4865 | 0.22297 | H3 | 3 | -- | FALSE | 2586 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK035 | Project_058_RISK035 | Threat | Project Contingency | Open | H3 | 3 |  | Part numbering rejection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 1.1744 | 0.23489 | Accept | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK030 | Project_058_RISK030 | Threat | Project Contingency | Open | H3 | 3 |  | Source Inspection Q1 | Person_236 | 2018-03-14 01:00 | 2018-08-06 | 50% | 2.9361 | 1.468 | Reduce | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 144.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK035 | Project_058_RISK035 | Threat | Project Contingency | Open | H3 | 3 |  | Part numbering rejection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 1.1744 | 0.23489 | Accept | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK016 | Project_001_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Cost of dealing with technical events | Person_462 | 2016-05-23 | 2016-06-29 | 30% | 10.2811 | 3.0843 | Reduce | 20% | 10.2811 | 2.0562 | H3 | 3 | -- | TRUE | 37 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK016 | Project_001_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Cost of dealing with technical events | Person_462 | 2016-05-23 | 2016-06-29 | 30% | 10.2811 | 3.0843 | Reduce | 20% | 10.2811 | 2.0562 | H3 | 3 | -- | TRUE | 37 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK016 | Project_001_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Cost of dealing with technical events | Person_462 | 2016-05-23 | 2016-06-29 | 30% | 10.2811 | 3.0843 | Reduce | 20% | 10.2811 | 2.0562 | H3 | 3 | -- | TRUE | 37 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK016 | Project_001_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Cost of dealing with technical events | Person_462 | 2016-05-23 | 2016-06-29 | 30% | 10.2811 | 3.0843 | Reduce | 20% | 10.2811 | 2.0562 | H3 | 3 | -- | TRUE | 37 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK016 | Project_001_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Cost of dealing with technical events | Person_462 | 2016-05-23 | 2016-06-29 | 30% | 10.2811 | 3.0843 | Reduce | 20% | 10.2811 | 2.0562 | H3 | 3 | -- | TRUE | 37 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK016 | Project_001_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Cost of dealing with technical events | Person_462 | 2016-05-23 | 2016-06-29 | 30% | 10.2811 | 3.0843 | Reduce | 20% | 10.2811 | 2.0562 | H3 | 3 | -- | TRUE | 37 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK016 | Project_001_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Cost of dealing with technical events | Person_462 | 2016-06-01 | 2016-08-04 | 30% | 10.2811 | 3.0843 | Reduce | 20% | 10.2811 | 2.0562 | H3 | 3 | -- | TRUE | 64 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK016 | Project_001_RISK016 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Cost of dealing with technical events | Person_462 | 2016-06-01 | 2016-08-04 | 30% | 10.2811 | 3.0843 | Reduce | 20% | 10.2811 | 2.0562 | H3 | 3 | -- | TRUE | 64 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK030 | Project_058_RISK030 | Threat | Project Contingency | Open | H3 | 3 |  | Source Inspection Q1 | Person_236 | 2018-03-14 01:00 | 2018-08-06 | 50% | 2.9361 | 1.468 | Reduce | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 144.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK035 | Project_058_RISK035 | Threat | Project Contingency | Open | H3 | 3 |  | Part numbering rejection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 1.1744 | 0.23489 | Accept | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK030 | Project_058_RISK030 | Threat | Project Contingency | Open | H3 | 3 |  | Source Inspection Q1 | Person_236 | 2018-03-14 01:00 | 2018-08-06 | 50% | 2.9361 | 1.468 | Reduce | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 144.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_585 | 2016-12-21 01:00 | 2017-05-03 | 40% | 10.4903 | 4.1961 | Reduce | 20% | 10.4903 | 2.0981 | H2 | 2 | Stable | TRUE | 132.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 40% | 10.4903 | 4.1961 | Reduce | 20% | 10.4903 | 2.0981 | H2 | 2 | Stable | TRUE | 132.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 40% | 10.4903 | 4.1961 | Reduce | 20% | 10.4903 | 2.0981 | H2 | 2 | Stable | TRUE | 132.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 40% | 10.4903 | 4.1961 | Reduce | 20% | 10.4903 | 2.0981 | H2 | 2 | Stable | TRUE | 132.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 40% | 10.4903 | 4.1961 | Reduce | 20% | 10.4903 | 2.0981 | H2 | 2 | Stable | TRUE | 132.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 40% | 10.4903 | 4.1961 | Reduce | 20% | 10.4903 | 2.0981 | H2 | 2 | Stable | TRUE | 132.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 40% | 10.4903 | 4.1961 | Reduce | 20% | 10.4903 | 2.0981 | H2 | 2 | Stable | TRUE | 132.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK180 | Project_024_RISK180 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | High Accelerated Life Testing (HALT) | Person_289 | 2016-12-21 01:00 | 2017-05-03 | 40% | 10.4903 | 4.1961 | Reduce | 20% | 10.4903 | 2.0981 | H2 | 2 | Stable | TRUE | 132.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 25% | 8.3972 | 2.0993 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 25% | 8.3972 | 2.0993 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-189 | Project_027_Risk-189 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Major Component obsolescence | Person_513 | 2014-01-04 01:00 | 2017-08-20 01:00 | 30% | 8.3972 | 2.5191 | Reduce | 25% | 8.3972 | 2.0993 | H2 | 2 | Stable | TRUE | 1324 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R051 | Project_085_R051 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | There is a risk that the test equipment electrical refit is more complex than estimated | Person_028 | 2018-03-23 | 2020-01-22 | 20% | 10.5437 | 2.1087 | Accept | 20% | 10.5437 | 2.1087 | H3 | 3 | -- | TRUE | 670 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK035 | Project_058_RISK035 | Threat | Project Contingency | Open | H3 | 3 |  | Part numbering rejection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 1.1744 | 0.23489 | Accept | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK030 | Project_058_RISK030 | Threat | Project Contingency | Open | H3 | 3 |  | Source Inspection Q1 | Person_236 | 2018-03-14 01:00 | 2018-08-06 | 50% | 2.9361 | 1.468 | Reduce | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 144.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK035 | Project_058_RISK035 | Threat | Project Contingency | Open | H3 | 3 |  | Part numbering rejection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 1.1744 | 0.23489 | Accept | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK035 | Project_058_RISK035 | Threat | Project Contingency | Open | H3 | 3 |  | Part numbering rejection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 1.1744 | 0.23489 | Accept | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK035 | Project_058_RISK035 | Threat | Project Contingency | Open | H3 | 3 |  | Part numbering rejection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 1.1744 | 0.23489 | Accept | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 | 2016-08-20 | 20% | 12.1982 | 2.4396 | Accept | 20% | 10.8428 | 2.1686 | H2 | 2 | Stable | TRUE | 546 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2016-10-20 01:00 | 20% | 12.1982 | 2.4396 | Accept | 20% | 10.8428 | 2.1686 | H2 | 2 | Stable | TRUE | 607 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2016-10-20 01:00 | 20% | 12.1982 | 2.4396 | Accept | 20% | 10.8428 | 2.1686 | H2 | 2 | Stable | TRUE | 607 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2016-11-19 01:00 | 20% | 12.1982 | 2.4396 | Accept | 20% | 10.8428 | 2.1686 | H2 | 2 | Stable | TRUE | 637 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 20% | 12.1982 | 2.4396 | Accept | 20% | 10.8428 | 2.1686 | H2 | 2 | Stable | TRUE | 759.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-003 | Project_028_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Recorder unavailability | Person_253 | 2015-02-21 01:00 | 2017-03-22 | 20% | 12.1982 | 2.4396 | Accept | 20% | 10.8428 | 2.1686 | H2 | 2 | Stable | TRUE | 759.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK035 | Project_058_RISK035 | Threat | Project Contingency | Open | H3 | 3 |  | Part numbering rejection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 1.1744 | 0.23489 | Accept | 20% | 1.1744 | 0.23489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 |  | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2016-09-20 01:00 | 50% | 1.2445 | 0.62224 | -- | 20% | 1.2167 | 0.24333 | H3 | 3 | Improving | TRUE | 607 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP004 | Project_081_OPP004 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Less repairs than planned in base costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 20% | 1.2204 | 0.24409 | -- | 20% | 1.2204 | 0.24409 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK039 | Project_075_RISK039 | Threat | Project Contingency | Open | H2 | 2 |  | Energy Meter untested | Person_003 | 2018-02-19 01:00 | 2018-08-20 | 50% | 4.2185 | 2.1093 | Reduce | 10% | 2.5311 | 0.25311 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK039 | Project_075_RISK039 | Threat | Project Contingency | Open | H2 | 2 |  | Energy Meter untested | Person_003 | 2018-02-19 01:00 | 2018-08-20 | 50% | 4.2185 | 2.1093 | Reduce | 10% | 2.5311 | 0.25311 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK039 | Project_075_RISK039 | Threat | Project Contingency | Open | H2 | 2 |  | Energy Meter untested | Person_003 | 2018-02-19 01:00 | 2018-08-20 | 50% | 4.2185 | 2.1093 | Reduce | 10% | 2.5311 | 0.25311 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK039 | Project_075_RISK039 | Threat | Project Contingency | Open | H2 | 2 |  | Energy Meter untested | Person_003 | 2018-02-19 01:00 | 2018-08-20 | 50% | 4.2185 | 2.1093 | Reduce | 10% | 2.5311 | 0.25311 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK039 | Project_075_RISK039 | Threat | Project Contingency | Open | H2 | 2 |  | Energy Meter untested | Person_003 | 2018-02-19 01:00 | 2018-08-20 | 50% | 4.2185 | 2.1093 | Reduce | 10% | 2.5311 | 0.25311 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-028 | Project_029_Risk-028 | Threat | Project Contingency | Open | H2 | 2 |  | Test Assets (for system integration - repair of test assets) | Person_102 | 2015-02-21 01:00 | 2020-05-22 | 40% | 1.2834 | 0.51334 | Reduce | 20% | 1.2834 | 0.25667 | H3 | 3 | Stable | FALSE | 1916.9583 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-028 | Project_029_Risk-028 | Threat | Project Contingency | Open | H2 | 2 |  | Test Assets (for system integration - repair of test assets) | Person_102 | 2015-02-21 01:00 | 2020-05-22 | 40% | 1.2834 | 0.51334 | Reduce | 20% | 1.2834 | 0.25667 | H3 | 3 | Stable | FALSE | 1916.9583 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-028 | Project_029_Risk-028 | Threat | Project Contingency | Open | H2 | 2 |  | Test Assets (for system integration - repair of test assets) | Person_102 | 2015-02-21 01:00 | 2020-05-22 | 40% | 1.2834 | 0.51334 | Reduce | 20% | 1.2834 | 0.25667 | H3 | 3 | Stable | FALSE | 1916.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-028 | Project_029_Risk-028 | Threat | Project Contingency | Open | H2 | 2 |  | Test Assets (for system integration - repair of test assets) | Person_102 | 2015-02-21 01:00 | 2020-05-22 | 40% | 1.2834 | 0.51334 | Reduce | 20% | 1.2834 | 0.25667 | H3 | 3 | Stable | FALSE | 1916.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-004 | Project_026_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Resource Project Impacts | Person_264 | 2015-05-24 | 2016-11-19 01:00 | 30% | 11.0427 | 3.3128 | Accept | 20% | 11.0427 | 2.2085 | H2 | 2 | -- | TRUE | 545.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK009 | Project_001_RISK009 | Threat | Project Contingency | Open | H3 | 3 | Customers | Increased prime contractor overhead | Person_059 | 2016-02-20 01:00 | 2016-06-19 | 40% | 11.0494 | 4.4198 | Reduce | 20% | 11.0494 | 2.2099 | H3 | 3 | -- | TRUE | 119.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK009 | Project_001_RISK009 | Threat | Project Contingency | Open | H3 | 3 | Customers | Increased prime contractor overhead | Person_059 | 2016-02-20 01:00 | 2016-06-19 | 40% | 11.0494 | 4.4198 | Reduce | 20% | 11.0494 | 2.2099 | H3 | 3 | -- | TRUE | 119.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK009 | Project_001_RISK009 | Threat | Project Contingency | Open | H3 | 3 | Customers | Increased prime contractor overhead | Person_059 | 2016-02-20 | 2016-06-19 | 40% | 11.0494 | 4.4198 | Reduce | 20% | 11.0494 | 2.2099 | H3 | 3 | -- | TRUE | 120 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK009 | Project_001_RISK009 | Threat | Project Contingency | Open | H3 | 3 | Customers | Increased prime contractor overhead | Person_059 | 2016-02-19 23:00 | 2016-06-19 | 40% | 11.0494 | 4.4198 | Reduce | 20% | 11.0494 | 2.2099 | H3 | 3 | -- | TRUE | 120.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK009 | Project_001_RISK009 | Threat | Project Contingency | Open | H3 | 3 | Customers | Increased prime contractor overhead | Person_059 | 2016-02-19 22:00 | 2016-06-19 | 40% | 11.0494 | 4.4198 | Reduce | 20% | 11.0494 | 2.2099 | H3 | 3 | -- | TRUE | 120.0833 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK009 | Project_001_RISK009 | Threat | Project Contingency | Open | H3 | 3 | Customers | Increased prime contractor overhead | Person_059 | 2016-02-19 21:00 | 2016-06-19 | 40% | 11.0494 | 4.4198 | Reduce | 20% | 11.0494 | 2.2099 | H3 | 3 | -- | TRUE | 120.125 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK018 | Project_092_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Connectors | Person_169 | 2018-10-31 01:00 | 2019-03-21 | 15% | 5.3485 | 0.80227 | Accept | 5% | 5.3485 | 0.26742 | H3 | 3 | -- | TRUE | 140.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-022 | Project_062_Risk-022 | Threat | Project Contingency | Open | H2 | 2 |  | Registers Might Be Unstable | Person_479 | 2017-07-21 | 2018-10-21 01:00 | 25% | 1.3385 | 0.33464 | Reduce | 20% | 1.3385 | 0.26771 | H3 | 3 | Stable | FALSE | 457.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK019 | Project_081_RISK019 | Threat | Management Contingency | Open | H3 | 3 |  | Misc costs incurred at trials | Person_260 | 2018-05-23 | 2021-09-20 01:00 | 20% | 1.3425 | 0.2685 | Avoid | 20% | 1.3425 | 0.2685 | H3 | 3 | Stable | TRUE | 1216.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP002 | Project_081_OPP002 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Core Management team shared across other programmes | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 30% | 0.91533 | 0.2746 | Exploit | 30% | 0.91533 | 0.2746 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK032 | Project_058_RISK032 | Threat | Project Contingency | Open | H3 | 3 |  | Component Free Issue | Person_537 | 2018-03-22 | 2018-05-22 | 20% | 2.9361 | 0.58721 | Avoid | 10% | 2.9361 | 0.29361 | H3 | 3 | -- | TRUE | 61 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-318 | Project_027_Risk-318 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Supportability Stategy for Repairs | Person_060 | 2015-04-15 | 2016-05-22 | 40% | 11.0962 | 4.4385 | Reduce | 20% | 11.0962 | 2.2192 | H3 | 3 | -- | TRUE | 403 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R028 | Project_085_R028 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | New diode performance issues | Person_409 | 2017-12-21 | 2019-05-23 | 30% | 14.8086 | 4.4426 | Reduce | 15% | 14.8086 | 2.2213 | H3 | 3 | -- | FALSE | 518 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 40% | 8.9019 | 3.5608 | Reduce | 25% | 8.9019 | 2.2255 | H3 | 3 | -- | TRUE | 1225.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 40% | 8.9019 | 3.5608 | Reduce | 25% | 8.9019 | 2.2255 | H3 | 3 | -- | TRUE | 1225.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 40% | 8.9019 | 3.5608 | Reduce | 25% | 8.9019 | 2.2255 | H3 | 3 | -- | TRUE | 1225.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 40% | 8.9019 | 3.5608 | Reduce | 25% | 8.9019 | 2.2255 | H3 | 3 | -- | TRUE | 1225.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 40% | 8.9019 | 3.5608 | Reduce | 25% | 8.9019 | 2.2255 | H3 | 3 | -- | TRUE | 1225.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 | 2019-05-23 | 40% | 8.9019 | 3.5608 | Reduce | 25% | 8.9019 | 2.2255 | H3 | 3 | -- | TRUE | 1226 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 40% | 8.9019 | 3.5608 | Reduce | 25% | 8.9019 | 2.2255 | H3 | 3 | -- | TRUE | 1225.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R008 | Project_016_Risk--R008 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Additional Travel & Subsistence | Person_574 | 2016-01-13 01:00 | 2019-05-23 | 40% | 8.9019 | 3.5608 | Reduce | 25% | 8.9019 | 2.2255 | H3 | 3 | -- | TRUE | 1225.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 20% | 11.1654 | 2.2331 | Accept | 20% | 11.1654 | 2.2331 | H2 | 2 | Stable | TRUE | 155.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 20% | 11.1654 | 2.2331 | Accept | 20% | 11.1654 | 2.2331 | H2 | 2 | Stable | TRUE | 155.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 20% | 11.1654 | 2.2331 | Accept | 20% | 11.1654 | 2.2331 | H2 | 2 | Stable | TRUE | 155.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 20% | 11.1654 | 2.2331 | Accept | 20% | 11.1654 | 2.2331 | H2 | 2 | Stable | TRUE | 155.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 20% | 11.1654 | 2.2331 | Accept | 20% | 11.1654 | 2.2331 | H2 | 2 | Stable | TRUE | 155.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-159 | Project_026_Risk-159 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer requested additional trials/testing support | Person_362 | 2017-05-23 | 2019-02-25 01:00 | 50% | 4.4768 | 2.2384 | Accept | 50% | 4.4768 | 2.2384 | H3 | 3 | -- | TRUE | 643.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-159 | Project_026_Risk-159 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer requested additional trials/testing support | Person_362 | 2017-05-23 | 2019-02-25 01:00 | 50% | 4.4768 | 2.2384 | Accept | 50% | 4.4768 | 2.2384 | H3 | 3 | -- | TRUE | 643.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-159 | Project_026_Risk-159 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer requested additional trials/testing support | Person_362 | 2017-05-23 | 2019-02-25 01:00 | 50% | 4.4768 | 2.2384 | Accept | 50% | 4.4768 | 2.2384 | H3 | 3 | -- | TRUE | 643.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-159 | Project_026_Risk-159 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer requested additional trials/testing support | Person_362 | 2017-05-23 | 2019-02-25 01:00 | 50% | 4.4768 | 2.2384 | Accept | 50% | 4.4768 | 2.2384 | H3 | 3 | -- | TRUE | 643.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-159 | Project_026_Risk-159 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer requested additional trials/testing support | Person_362 | 2017-05-23 | 2019-02-25 01:00 | 50% | 4.4768 | 2.2384 | Accept | 50% | 4.4768 | 2.2384 | H3 | 3 | -- | TRUE | 643.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-159 | Project_026_Risk-159 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer requested additional trials/testing support | Person_362 | 2017-05-23 | 2019-02-25 01:00 | 50% | 4.4768 | 2.2384 | Accept | 50% | 4.4768 | 2.2384 | H3 | 3 | -- | TRUE | 643.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-159 | Project_026_Risk-159 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer requested additional trials/testing support | Person_362 | 2017-05-23 | 2019-02-25 01:00 | 50% | 4.4768 | 2.2384 | Accept | 50% | 4.4768 | 2.2384 | H2 | 2 | -- | TRUE | 643.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-159 | Project_026_Risk-159 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer requested additional trials/testing support | Person_362 | 2017-05-23 | 2019-02-25 01:00 | 50% | 4.4768 | 2.2384 | Accept | 50% | 4.4768 | 2.2384 | H2 | 2 | -- | TRUE | 643.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 01:00 | 2020-08-20 01:00 | 50% | 4.4778 | 2.2389 | Accept | 50% | 4.4778 | 2.2389 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_015 | RISK001 | Project_015_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Labour Risk | Person_662 | 2015-08-21 | 2020-08-20 | 50% | 4.4778 | 2.2389 | Accept | 50% | 4.4778 | 2.2389 | H2 | 2 | Stable | TRUE | 1826 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK144 | Project_049_RISK144 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Equipment Packaging | Person_282 | 2019-06-09 | 2020-08-24 01:00 | 60% | 4.4872 | 2.6923 | Reduce | 50% | 4.4872 | 2.2436 | H3 | 3 | -- | TRUE | 442.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK032 | Project_058_RISK032 | Threat | Project Contingency | Open | H3 | 3 |  | Component Free Issue | Person_537 | 2018-03-22 | 2018-05-22 | 20% | 2.9361 | 0.58721 | Avoid | 10% | 2.9361 | 0.29361 | H3 | 3 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK032 | Project_058_RISK032 | Threat | Project Contingency | Open | H3 | 3 |  | Component Free Issue | Person_537 | 2018-03-22 | 2018-05-22 | 20% | 2.9361 | 0.58721 | Avoid | 10% | 2.9361 | 0.29361 | H3 | 3 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK032 | Project_058_RISK032 | Threat | Project Contingency | Open | H3 | 3 |  | Component Free Issue | Person_537 | 2018-03-22 | 2018-05-22 | 20% | 2.9361 | 0.58721 | Avoid | 10% | 2.9361 | 0.29361 | H3 | 3 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK032 | Project_058_RISK032 | Threat | Project Contingency | Open | H3 | 3 |  | Component Free Issue | Person_537 | 2018-03-22 | 2018-05-22 | 20% | 2.9361 | 0.58721 | Avoid | 10% | 2.9361 | 0.29361 | H3 | 3 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK032 | Project_058_RISK032 | Threat | Project Contingency | Open | H3 | 3 |  | Component Free Issue | Person_537 | 2018-03-22 | 2018-05-22 | 20% | 2.9361 | 0.58721 | Avoid | 10% | 2.9361 | 0.29361 | H3 | 3 | -- | TRUE | 61 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK032 | Project_058_RISK032 | Threat | Project Contingency | Open | H3 | 3 |  | Component Free Issue | Person_537 | 2018-03-22 | 2018-05-22 | 20% | 2.9361 | 0.58721 | Avoid | 10% | 2.9361 | 0.29361 | H3 | 3 | -- | TRUE | 61 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-03 | 2021-05-03 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2017-08-17 01:00 | 30% | 7.5153 | 2.2546 | -- | 30% | 7.5153 | 2.2546 | H2 | 2 | -- | TRUE | 451.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2017-08-17 | 30% | 7.5153 | 2.2546 | -- | 30% | 7.5153 | 2.2546 | H2 | 2 | -- | TRUE | 451 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2017-08-17 01:00 | 30% | 7.5153 | 2.2546 | -- | 30% | 7.5153 | 2.2546 | H2 | 2 | -- | TRUE | 451.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2017-08-17 01:00 | 30% | 7.5153 | 2.2546 | -- | 30% | 7.5153 | 2.2546 | H2 | 2 | -- | TRUE | 451.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2017-08-17 01:00 | 30% | 7.5153 | 2.2546 | -- | 30% | 7.5153 | 2.2546 | H2 | 2 | -- | TRUE | 451.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2017-08-17 01:00 | 30% | 7.5153 | 2.2546 | -- | 30% | 7.5153 | 2.2546 | H2 | 2 | -- | TRUE | 451.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK019 | Project_042_RISK019 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Refurbishment Costs Exceeding the Budget | Person_371 | 2016-05-23 | 2017-08-17 01:00 | 30% | 7.5153 | 2.2546 | -- | 30% | 7.5153 | 2.2546 | H2 | 2 | -- | TRUE | 451.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | OPP002 | Project_042_OPP002 | Opportunitity | Project Contingency | Open | H2 | 2 | Bid Management | Supplier Underspend. | Person_455 | 2021-01-21 01:00 | 2021-05-22 | 20% | 11.2729 | 2.2546 | Accept | 20% | 11.2729 | 2.2546 | H2 | 2 | -- | TRUE | 120.9583 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-03 | 2021-05-03 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-03 | 2021-05-03 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-03 | 2021-05-03 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-03 | 2021-05-03 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--118 | Project_100_Risk--118 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Recovery of Costs through support | Person_565 | 2018-08-22 01:00 | 2021-08-20 01:00 | 75% | 3.0679 | 2.3009 | Exploit | 75% | 3.0679 | 2.3009 | H2 | 2 | -- | TRUE | 1094 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-03 | 2021-05-03 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_160 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_020 | 2020-07-01 | 2020-07-11 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 10 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_020 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_020 | 2020-07-01 | 2020-07-11 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 10 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_020 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_020 | 2020-07-01 | 2020-07-11 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 10 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_020 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309- | Project_065_RISK309- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_020 | 2020-07-01 | 2020-07-11 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 10 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK309-Risk- | Project_065_RISK309-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Thermal estimate of the system | Person_020 | 2020-05-23 | 2024-05-22 | 30% | 4.5722 | 1.3717 | Reduce | 10% | 3.116 | 0.3116 | H3 | 3 | -- | TRUE | 1460 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 40% | 3.187 | 1.2748 | Reduce | 20% | 1.5935 | 0.3187 | H3 | 3 | Stable | FALSE | 302.0417 |  | 1 | 0 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 40% | 3.187 | 1.2748 | Reduce | 20% | 1.5935 | 0.3187 | H3 | 3 | Stable | FALSE | 302.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK059 | Project_076_RISK059 | Threat | Project Contingency | Open | H2 | 2 |  | Hazard Analysis Delay - SSS | Person_771 | 2018-05-23 | 2018-10-22 01:00 | 20% | 6.4264 | 1.2853 | Reduce | 5% | 6.4264 | 0.32132 | H3 | 3 | -- | FALSE | 152.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK059 | Project_076_RISK059 | Threat | Project Contingency | Open | H2 | 2 |  | Hazard Analysis Delay - SSS | Person_771 | 2018-05-23 | 2018-10-22 01:00 | 20% | 6.4264 | 1.2853 | Reduce | 5% | 6.4264 | 0.32132 | H3 | 3 | -- | FALSE | 152.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK059 | Project_076_RISK059 | Threat | Project Contingency | Open | H2 | 2 |  | Hazard Analysis Delay - SSS | Person_771 | 2018-05-23 | 2018-10-22 01:00 | 20% | 6.4264 | 1.2853 | Reduce | 5% | 6.4264 | 0.32132 | H3 | 3 | -- | FALSE | 152.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK005 | Project_081_RISK005 | Threat | Project Contingency | Open | H3 | 3 |  | Marching army Customer costs for duration of contract | Person_260 | 2021-05-23 | 2021-09-27 01:00 | 20% | 1.6598 | 0.33196 | Reduce | 20% | 1.6598 | 0.33196 | H3 | 3 | Stable | TRUE | 127.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK333 | Project_033_RISK333 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 1.1155 | 0.33466 | Avoid | 30% | 1.1155 | 0.33466 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK333 | Project_033_RISK333 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 1.1155 | 0.33466 | Avoid | 30% | 1.1155 | 0.33466 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK333 | Project_033_RISK333 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 1.1155 | 0.33466 | Avoid | 30% | 1.1155 | 0.33466 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK333 | Project_033_RISK333 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 1.1155 | 0.33466 | Avoid | 30% | 1.1155 | 0.33466 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R007 | Project_085_R007 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Requirements management additional support required | Person_042 | 2018-12-22 | 2022-05-22 | 40% | 7.6945 | 3.0778 | Reduce | 30% | 7.6945 | 2.3084 | H2 | 2 | -- | TRUE | 1247 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK333 | Project_033_RISK333 | Threat | Project Contingency | Open | H3 | 3 |  | Driver update | Person_330 | 2015-02-20 18:00 | 2015-06-24 | 30% | 1.1155 | 0.33466 | Avoid | 30% | 1.1155 | 0.33466 | H3 | 3 | -- | TRUE | 123.25 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 40% | 3.3748 | 1.3499 | Reduce | 10% | 3.3748 | 0.33748 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 40% | 3.3748 | 1.3499 | Reduce | 10% | 3.3748 | 0.33748 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 40% | 3.3748 | 1.3499 | Reduce | 10% | 3.3748 | 0.33748 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 40% | 3.3748 | 1.3499 | Reduce | 10% | 3.3748 | 0.33748 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK004 | Project_075_RISK004 | Threat | Project Contingency | Open | H2 | 2 |  | Additional Material required for investigations | Person_627 | 2017-07-21 | 2018-11-20 01:00 | 40% | 3.3748 | 1.3499 | Reduce | 10% | 3.3748 | 0.33748 | H3 | 3 | Stable | FALSE | 487.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK021 | Project_081_RISK021 | Threat | Financial Contingency | Open | H3 | 3 |  | Increase of bank fees and other direct costs | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 15% | 2.27 | 0.3405 | Avoid | 15% | 2.27 | 0.3405 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 |  | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 50% | 1.2445 | 0.62224 | -- | 15% | 2.303 | 0.34545 | H3 | 3 | Worsening | TRUE | 730 |  | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK017 | Project_081_RISK017 | Threat | Project Contingency | Open | H3 | 3 |  | Extended working hours during site visits | Person_419 | 2017-09-20 01:00 | 2021-09-20 01:00 | 30% | 1.1716 | 0.35149 | Reduce | 30% | 1.1716 | 0.35149 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK048 | Project_058_RISK048 | Threat | Project Contingency | Open | H3 | 3 |  | Acceptance overheads (Legacy) | Person_072 | 2018-07-17 | 2019-05-23 | 40% | 1.1744 | 0.46977 | Reduce | 30% | 1.1744 | 0.35233 | H3 | 3 | -- | TRUE | 310 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK048 | Project_058_RISK048 | Threat | Project Contingency | Open | H3 | 3 |  | Acceptance overheads (Legacy) | Person_072 | 2018-07-17 | 2019-05-23 | 40% | 1.1744 | 0.46977 | Reduce | 30% | 1.1744 | 0.35233 | H3 | 3 | -- | TRUE | 310 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK048 | Project_058_RISK048 | Threat | Project Contingency | Open | H3 | 3 |  | Acceptance overheads (Legacy) | Person_072 | 2018-07-17 | 2019-05-23 | 40% | 1.1744 | 0.46977 | Reduce | 30% | 1.1744 | 0.35233 | H3 | 3 | -- | TRUE | 310 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Upgrades | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 35% | 6.6957 | 2.3435 | -- | 35% | 6.6951 | 2.3433 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Upgrades | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 35% | 6.6957 | 2.3435 | -- | 35% | 6.6951 | 2.3433 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Upgrades | Person_084 | 2016-01-22 | 2023-02-20 | 35% | 6.6957 | 2.3435 | -- | 35% | 6.6951 | 2.3433 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Upgrades | Person_084 | 2016-01-22 | 2023-02-20 | 35% | 6.6957 | 2.3435 | -- | 35% | 6.6951 | 2.3433 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Upgrades | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 35% | 6.6957 | 2.3435 | -- | 35% | 6.6951 | 2.3433 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Upgrades | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 35% | 6.6957 | 2.3435 | -- | 35% | 6.6951 | 2.3433 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Upgrades | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 35% | 6.6957 | 2.3435 | -- | 35% | 6.6951 | 2.3433 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK040 | Project_017_RISK040 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Upgrades | Person_084 | 2016-01-21 21:00 | 2023-02-19 21:00 | 35% | 6.6957 | 2.3435 | -- | 35% | 6.6951 | 2.3433 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-08 01:00 | 2019-09-26 01:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-08 01:00 | 2019-09-26 01:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-08 01:00 | 2019-09-26 01:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-08 01:00 | 2019-09-26 01:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-08 | 2019-09-26 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-08 | 2019-09-26 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-08 01:00 | 2019-09-26 01:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-07 23:00 | 2019-09-25 23:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-07 23:00 | 2019-09-25 23:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-07 22:00 | 2019-09-25 22:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-07 22:00 | 2019-09-25 22:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-07 23:00 | 2019-09-25 23:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_418 | 2016-09-08 01:00 | 2019-09-26 01:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK029 | Project_049_RISK029 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Customer Deliverable Acceptance | Person_526 | 2017-08-23 01:00 | 2019-11-18 01:00 | 50% | 5.2201 | 2.6101 | Reduce | 45% | 5.2201 | 2.3491 | H2 | 2 | -- | TRUE | 817 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-052 | Project_026_Risk-052 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Resolution of Hardware/Software Obsolescence under estimated | Person_250 | 2017-07-20 | 2022-10-28 01:00 | 100% | 7.8344 | 7.8344 | Reduce | 30% | 7.8344 | 2.3503 | H2 | 2 | -- | TRUE | 1926.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-052 | Project_026_Risk-052 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Resolution of Hardware/Software Obsolescence under estimated | Person_250 | 2017-07-20 | 2022-10-28 01:00 | 100% | 7.8344 | 7.8344 | Reduce | 30% | 7.8344 | 2.3503 | H2 | 2 | -- | TRUE | 1926.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-052 | Project_026_Risk-052 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Resolution of Hardware/Software Obsolescence under estimated | Person_250 | 2017-07-20 | 2022-10-28 01:00 | 100% | 7.8344 | 7.8344 | Reduce | 30% | 7.8344 | 2.3503 | H2 | 2 | -- | TRUE | 1926.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-052 | Project_026_Risk-052 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Resolution of Hardware/Software Obsolescence under estimated | Person_250 | 2017-07-20 | 2022-10-28 01:00 | 100% | 7.8344 | 7.8344 | Reduce | 30% | 7.8344 | 2.3503 | H2 | 2 | -- | TRUE | 1926.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-052 | Project_026_Risk-052 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Resolution of Hardware/Software Obsolescence under estimated | Person_250 | 2017-07-20 | 2022-10-28 01:00 | 100% | 7.8344 | 7.8344 | Reduce | 30% | 7.8344 | 2.3503 | H2 | 2 | -- | TRUE | 1926.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-052 | Project_026_Risk-052 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Resolution of Hardware/Software Obsolescence under estimated | Person_250 | 2017-07-20 | 2022-10-28 01:00 | 100% | 7.8344 | 7.8344 | Reduce | 30% | 7.8344 | 2.3503 | H2 | 2 | -- | TRUE | 1926.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-052 | Project_026_Risk-052 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Resolution of Hardware/Software Obsolescence under estimated | Person_250 | 2017-07-20 | 2022-10-28 01:00 | 100% | 7.8344 | 7.8344 | Reduce | 30% | 7.8344 | 2.3503 | H2 | 2 | -- | TRUE | 1926.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-052 | Project_026_Risk-052 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Resolution of Hardware/Software Obsolescence under estimated | Person_250 | 2017-07-20 | 2022-10-28 01:00 | 100% | 7.8344 | 7.8344 | Reduce | 30% | 7.8344 | 2.3503 | H2 | 2 | -- | TRUE | 1926.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK117 | Project_049_RISK117 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Joint Protocols - apply for all installations | Person_410 | 2017-08-23 01:00 | 2019-10-09 01:00 | 40% | 10.4852 | 4.1941 | Reduce | 30% | 7.8377 | 2.3513 | H2 | 2 | -- | TRUE | 777 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | OPP002 | Project_094_OPP002 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Integration schedule improved | Person_198 | 2018-08-22 | 2021-03-22 | 30% | 7.987 | 2.3961 | -- | 30% | 7.987 | 2.3961 | H2 | 2 | Stable | TRUE | 943 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK005 | Project_094_RISK005 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project extension due to schedule slippage | Person_198 | 2021-04-22 | 2022-05-22 | 20% | 11.9805 | 2.3961 | Reduce | 20% | 11.9805 | 2.3961 | H3 | 3 | Stable | TRUE | 395 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK009 | Project_001_RISK009 | Threat | Project Contingency | Open | H3 | 3 | Customers | Increased prime contractor overhead | Person_674 | 2016-08-04 | 2016-08-04 | 40% | 10.6706 | 4.2682 | Reduce | 30% | 8.0029 | 2.4009 | H3 | 3 | -- | TRUE | 0 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK009 | Project_001_RISK009 | Threat | Project Contingency | Open | H3 | 3 | Customers | Increased prime contractor overhead | Person_674 | 2016-08-04 | 2016-08-04 | 40% | 10.6706 | 4.2682 | Reduce | 30% | 8.0029 | 2.4009 | H3 | 3 | -- | TRUE | 0 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Resource Availability (Threat) | Person_518 | 2016-01-13 | 2019-08-21 | 20% | 12.0547 | 2.4109 | Accept | 20% | 12.0547 | 2.4109 | H3 | 3 | -- | TRUE | 1316 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Resource Availability (Threat) | Person_518 | 2016-01-13 01:00 | 2019-08-21 01:00 | 20% | 12.0547 | 2.4109 | Accept | 20% | 12.0547 | 2.4109 | H3 | 3 | -- | TRUE | 1316 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R013 | Project_016_Risk--R013 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Resource Availability (Threat) | Person_518 | 2016-01-13 01:00 | 2019-08-21 01:00 | 20% | 12.0547 | 2.4109 | Accept | 20% | 12.0547 | 2.4109 | H3 | 3 | -- | TRUE | 1316 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R035 | Project_085_R035 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Vehicle drawings not up to date | Person_015 | 2017-12-21 | 2020-11-19 | 30% | 16.1118 | 4.8335 | Reduce | 15% | 16.1118 | 2.4168 | H3 | 3 | -- | FALSE | 1064 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-017 | Project_026_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Delays in platform Build | Person_630 | 2018-01-21 01:00 | 2021-09-10 01:00 | 30% | 8.0582 | 2.4175 | Accept | 30% | 8.0582 | 2.4175 | H3 | 3 | -- | TRUE | 1328 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-017 | Project_026_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Delays in platform Build | Person_630 | 2018-01-21 01:00 | 2021-09-10 01:00 | 30% | 8.0582 | 2.4175 | Accept | 30% | 8.0582 | 2.4175 | H3 | 3 | -- | TRUE | 1328 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-017 | Project_026_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Delays in platform Build | Person_630 | 2018-01-21 01:00 | 2021-09-10 01:00 | 30% | 8.0582 | 2.4175 | Accept | 30% | 8.0582 | 2.4175 | H3 | 3 | -- | TRUE | 1328 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-017 | Project_026_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Delays in platform Build | Person_630 | 2018-01-21 01:00 | 2021-09-10 01:00 | 30% | 8.0582 | 2.4175 | Accept | 30% | 8.0582 | 2.4175 | H3 | 3 | -- | TRUE | 1328 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-017 | Project_026_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Delays in platform Build | Person_630 | 2018-01-21 01:00 | 2021-09-10 01:00 | 30% | 8.0582 | 2.4175 | Accept | 30% | 8.0582 | 2.4175 | H3 | 3 | -- | TRUE | 1328 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-017 | Project_026_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Delays in platform Build | Person_630 | 2018-01-21 01:00 | 2021-09-10 01:00 | 30% | 8.0582 | 2.4175 | Accept | 30% | 8.0582 | 2.4175 | H3 | 3 | -- | TRUE | 1328 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-017 | Project_026_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Delays in platform Build | Person_630 | 2018-01-21 01:00 | 2021-09-10 01:00 | 30% | 8.0582 | 2.4175 | Accept | 30% | 8.0582 | 2.4175 | H3 | 3 | -- | TRUE | 1328 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-017 | Project_026_Risk-017 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Delays in platform Build | Person_630 | 2018-01-21 01:00 | 2021-09-10 01:00 | 30% | 8.0582 | 2.4175 | Accept | 30% | 8.0582 | 2.4175 | H3 | 3 | -- | TRUE | 1328 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK232 | Project_038_RISK232 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Integration more complex than expected | Person_531 | 2015-11-21 01:00 | 2016-08-21 01:00 | 30% | 27.7165 | 8.3149 | Reduce | 18.5% | 13.1091 | 2.4252 | H3 | 3 | Improving | FALSE | 274 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK232 | Project_038_RISK232 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Integration more complex than expected | Person_531 | 2015-11-21 01:00 | 2016-11-20 01:00 | 30% | 27.7165 | 8.3149 | Reduce | 18.5% | 13.1091 | 2.4252 | H3 | 3 | Improving | FALSE | 365 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 15% | 16.1945 | 2.4292 | Accept | 15% | 16.1945 | 2.4292 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 15% | 16.1945 | 2.4292 | Accept | 15% | 16.1945 | 2.4292 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-196 | Project_027_Risk-196 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Aging equipment resulting in increasing failure rates | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 15% | 16.1945 | 2.4292 | Accept | 15% | 16.1945 | 2.4292 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014-Risk- | Project_065_RISK014-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_594 | 2016-09-07 22:00 | 2019-09-25 22:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_418 | 2016-09-08 | 2019-09-26 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_418 | 2016-09-08 01:00 | 2019-09-26 01:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK014- | Project_065_RISK014- | Threat | Project Contingency | Open | H2 | 2 |  | Underwater Cable failure during flex testing occurs. | Person_418 | 2016-09-07 23:00 | 2019-09-25 23:00 | 30% | 2.434 | 0.7302 | Reduce | 15% | 2.434 | 0.3651 | H3 | 3 | -- | FALSE | 1113 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-003 | Project_029_Risk-003 | Threat | Project Contingency | Open | H3 | 3 |  | Customer Furnished Equipmnet - Acceptance Trials Assets | Person_585 | 2017-09-22 01:00 | 2019-08-21 01:00 | 3% | 27.1644 | 0.81493 | Accept | 3% | 12.8336 | 0.38501 | H3 | 3 | Stable | TRUE | 698 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-08 01:00 | 2019-11-20 01:00 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-08 | 2019-11-20 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK133 | Project_049_RISK133 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Repeat Trials | Person_639 | 2018-12-16 01:00 | 2019-10-09 01:00 | 30% | 8.2789 | 2.4837 | Accept | 30% | 8.2789 | 2.4837 | H3 | 3 | -- | TRUE | 297 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 20% | 11.1654 | 2.2331 | Accept | 20% | 12.4637 | 2.4927 | H2 | 2 | Stable | TRUE | 155.0417 |  | 0 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK237 | Project_024_RISK237 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Customer coding standard Compliance | Person_534 | 2017-05-25 | 2017-10-27 01:00 | 20% | 11.1654 | 2.2331 | Accept | 20% | 12.4637 | 2.4927 | H2 | 2 | Stable | TRUE | 155.0417 |  | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repair costs | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 10% | 25.1176 | 2.5118 | Avoid | 10% | 25.1176 | 2.5118 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repair costs | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 10% | 25.1176 | 2.5118 | Avoid | 10% | 25.1176 | 2.5118 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repair costs | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 10% | 25.1176 | 2.5118 | Avoid | 10% | 25.1176 | 2.5118 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repair costs | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 10% | 25.1176 | 2.5118 | Avoid | 10% | 25.1176 | 2.5118 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repair costs | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 10% | 25.1176 | 2.5118 | Avoid | 10% | 25.1176 | 2.5118 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repair costs | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 10% | 25.1176 | 2.5118 | Avoid | 10% | 25.1176 | 2.5118 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repair costs | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 10% | 25.1176 | 2.5118 | Avoid | 10% | 25.1176 | 2.5118 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK003 | Project_019_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repair costs | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 10% | 25.1176 | 2.5118 | Avoid | 10% | 25.1176 | 2.5118 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK106 | Project_066_RISK106 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software TRS | Person_507 | 2018-08-23 01:00 | 2018-11-20 01:00 | 30% | 12.6151 | 3.7845 | Reduce | 20% | 12.6151 | 2.523 | H3 | 3 | -- | FALSE | 89 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-07 23:00 | 2019-11-19 23:00 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-07 22:00 | 2019-11-19 22:00 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-07 23:00 | 2019-11-19 23:00 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_418 | 2016-09-08 01:00 | 2019-11-20 01:00 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_418 | 2016-09-08 | 2019-11-20 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_418 | 2016-09-08 01:00 | 2019-11-20 01:00 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_418 | 2016-09-07 23:00 | 2019-11-19 23:00 | 45% | 1.9776 | 0.88993 | Reduce | 20% | 1.9776 | 0.39553 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK018 | Project_081_RISK018 | Threat | Project Contingency | Open | H3 | 3 |  | Additional trials support requested (+3) | Person_260 | 2018-05-23 | 2021-07-21 | 20% | 2.0259 | 0.40519 | Reduce | 20% | 2.0259 | 0.40519 | H3 | 3 | Stable | TRUE | 1155 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK331 | Project_033_RISK331 | Threat | Project Contingency | Open | H3 | 3 |  | Exchange Rate | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 50% | 0.85811 | 0.42906 | Accept | 50% | 0.85811 | 0.42906 | H3 | 3 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK331 | Project_033_RISK331 | Threat | Project Contingency | Open | H3 | 3 |  | Exchange Rate | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 50% | 0.85811 | 0.42906 | Accept | 50% | 0.85811 | 0.42906 | H3 | 3 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 01:00 | 2019-08-20 | 50% | 5.126 | 2.563 | Accept | 50% | 5.126 | 2.563 | H2 | 2 | Stable | TRUE | 1032.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 01:00 | 2019-08-20 | 50% | 5.126 | 2.563 | Accept | 50% | 5.126 | 2.563 | H2 | 2 | Stable | TRUE | 1032.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 | 2019-08-20 | 50% | 5.126 | 2.563 | Accept | 50% | 5.126 | 2.563 | H2 | 2 | Stable | TRUE | 1033 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 01:00 | 2019-08-20 | 50% | 5.126 | 2.563 | Accept | 50% | 5.126 | 2.563 | H2 | 2 | Stable | TRUE | 1032.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-21 01:00 | 2019-08-20 | 50% | 5.126 | 2.563 | Accept | 50% | 5.126 | 2.563 | H2 | 2 | Stable | TRUE | 1032.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 23:00 | 2019-08-20 | 50% | 5.126 | 2.563 | Accept | 50% | 5.126 | 2.563 | H2 | 2 | Stable | TRUE | 1033.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 23:00 | 2019-08-20 | 50% | 5.126 | 2.563 | Accept | 50% | 5.126 | 2.563 | H2 | 2 | Stable | TRUE | 1033.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-001 | Project_018_Risk-001 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase in Repair costs | Person_084 | 2016-10-20 23:00 | 2019-08-20 | 50% | 5.126 | 2.563 | Accept | 50% | 5.126 | 2.563 | H2 | 2 | Stable | TRUE | 1033.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 20% | 12.815 | 2.563 | Accept | 20% | 12.815 | 2.563 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 20% | 12.815 | 2.563 | Accept | 20% | 12.815 | 2.563 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 | 2019-08-20 | 20% | 12.815 | 2.563 | Accept | 20% | 12.815 | 2.563 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 20% | 12.815 | 2.563 | Accept | 20% | 12.815 | 2.563 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 20% | 12.815 | 2.563 | Accept | 20% | 12.815 | 2.563 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 20% | 12.815 | 2.563 | Accept | 20% | 12.815 | 2.563 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 20% | 12.815 | 2.563 | Accept | 20% | 12.815 | 2.563 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-002 | Project_018_Risk-002 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Volume of Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 20% | 12.815 | 2.563 | Accept | 20% | 12.815 | 2.563 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Worsening | TRUE | 374 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 | 2017-02-19 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Worsening | TRUE | 374 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Worsening | TRUE | 374 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-11-19 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Worsening | TRUE | 647 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-02-19 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Improving | TRUE | 374 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 | 2017-11-19 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Worsening | TRUE | 647 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 50% | 17.2826 | 8.6413 | Reduce | 15% | 17.2826 | 2.5924 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK331 | Project_033_RISK331 | Threat | Project Contingency | Open | H3 | 3 |  | Exchange Rate | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 50% | 0.85811 | 0.42906 | Accept | 50% | 0.85811 | 0.42906 | H3 | 3 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK331 | Project_033_RISK331 | Threat | Project Contingency | Open | H3 | 3 |  | Exchange Rate | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 50% | 0.85811 | 0.42906 | Accept | 50% | 0.85811 | 0.42906 | H3 | 3 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_033 | RISK331 | Project_033_RISK331 | Threat | Project Contingency | Open | H3 | 3 |  | Exchange Rate | Person_330 | 2015-01-21 18:00 | 2015-04-23 | 50% | 0.85811 | 0.42906 | Accept | 50% | 0.85811 | 0.42906 | H3 | 3 | -- | TRUE | 91.25 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK118 | Project_066_RISK118 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Generation of Inspection and Analysis Evidence | Person_068 | 2018-09-21 01:00 | 2019-11-20 01:00 | 50% | 5.1944 | 2.5972 | Reduce | 50% | 5.1944 | 2.5972 | H2 | 2 | -- | TRUE | 425 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R001 | Project_044_Risk-R001 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | subsystem1 development | Person_358 | 2017-12-22 01:00 | 2019-11-20 01:00 | 20% | 17.3851 | 3.477 | Reduce | 15% | 17.3851 | 2.6078 | H2 | 2 | Stable | TRUE | 698 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK012 | Project_058_RISK012 | Threat | Project Contingency | Open | H3 | 3 |  | Material Cost validity | Person_268 | 2017-05-24 | 2018-11-20 01:00 | 30% | 8.6125 | 2.5837 | Reduce | 5% | 8.6125 | 0.43062 | H3 | 3 | -- | TRUE | 545.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Open | H2 | 2 |  | PTFE cables | Person_418 | 2016-11-13 01:00 | 2019-08-20 | 50% | 4.3229 | 2.1615 | Reduce | 10% | 4.3229 | 0.43229 | H3 | 3 | -- | FALSE | 1009.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Open | H2 | 2 |  | PTFE cables | Person_418 | 2016-11-13 | 2019-08-20 | 50% | 4.3229 | 2.1615 | Reduce | 10% | 4.3229 | 0.43229 | H3 | 3 | -- | FALSE | 1010 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Open | H2 | 2 |  | PTFE cables | Person_418 | 2016-11-13 01:00 | 2019-08-20 | 50% | 4.3229 | 2.1615 | Reduce | 10% | 4.3229 | 0.43229 | H3 | 3 | -- | FALSE | 1009.9583 |  | 1 | 0 | 1
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-017 | Project_021_Risk-017 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target. | Person_061 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R009 | Project_021_Risk-R009 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond (revised) target. | Person_482 | 2013-01-07 01:00 | 2018-02-04 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 1854 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--12 | Project_021_Risk--12 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Safety Case Delayed Completion beyond target | Person_061 | 2018-02-20 01:00 | 2019-02-20 01:00 | 60% | 6.6769 | 4.0061 | Reduce | 40% | 6.6769 | 2.6707 | H2 | 2 | Stable | TRUE | 365 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK006 | Project_095_RISK006 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Increase in Support Management | Person_286 | 2018-07-22 | 2023-07-22 | 20% | 2.2256 | 0.44513 | -- | 20% | 13.3538 | 2.6708 | H2 | 2 | -- | TRUE | 1826 |  | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK335 | Project_065_RISK335 | Threat | Project Contingency | Open | H2 | 2 |  | PTFE cables | Person_418 | 2016-11-12 23:00 | 2019-08-20 | 50% | 4.3229 | 2.1615 | Reduce | 10% | 4.3229 | 0.43229 | H3 | 3 | -- | FALSE | 1010.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-072 | Project_030_Risk-072 | Opportunitity | Project Contingency | Open | H3 | 3 |  | System fleet wide license agreement | Person_541 | 2013-07-21 | 2015-03-22 | 10% | 4.3921 | 0.43921 | Exploit | 10% | 4.3921 | 0.43921 | H3 | 3 | -- | TRUE | 609 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-072 | Project_030_Risk-072 | Opportunitity | Project Contingency | Open | H3 | 3 |  | System fleet wide license agreement | Person_541 | 2013-07-21 | 2015-03-22 | 10% | 4.3921 | 0.43921 | Exploit | 10% | 4.3921 | 0.43921 | H3 | 3 | -- | TRUE | 609 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-072 | Project_030_Risk-072 | Opportunitity | Project Contingency | Open | H3 | 3 |  | System fleet wide license agreement | Person_541 | 2013-07-21 | 2015-03-22 | 10% | 4.3921 | 0.43921 | Exploit | 10% | 4.3921 | 0.43921 | H3 | 3 | -- | TRUE | 609 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-072 | Project_030_Risk-072 | Opportunitity | Project Contingency | Open | H3 | 3 |  | System fleet wide license agreement | Person_541 | 2013-07-21 | 2015-03-22 | 10% | 4.3921 | 0.43921 | Exploit | 10% | 4.3921 | 0.43921 | H3 | 3 | -- | TRUE | 609 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK030 | Project_083_RISK030 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Additional (unknown) support as result of sub-system learning within supply and customer | Person_644 | 2017-11-20 01:00 | 2020-11-19 01:00 | 40% | 6.7219 | 2.6887 | Accept | 40% | 6.7219 | 2.6887 | H3 | 3 | Stable | TRUE | 1095 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 35% | 7.689 | 2.6911 | Accept | 35% | 7.689 | 2.6911 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 35% | 7.689 | 2.6911 | Accept | 35% | 7.689 | 2.6911 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 | 2019-08-20 | 35% | 7.689 | 2.6911 | Accept | 35% | 7.689 | 2.6911 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 35% | 7.689 | 2.6911 | Accept | 35% | 7.689 | 2.6911 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 35% | 7.689 | 2.6911 | Accept | 35% | 7.689 | 2.6911 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 35% | 7.689 | 2.6911 | Accept | 35% | 7.689 | 2.6911 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 35% | 7.689 | 2.6911 | Accept | 35% | 7.689 | 2.6911 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-019 | Project_018_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | External SME Repairs | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 35% | 7.689 | 2.6911 | Accept | 35% | 7.689 | 2.6911 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK133-Risk- | Project_065_RISK133-Risk- | Threat | Project Contingency | Open | H2 | 2 | System Engineering | System Modification due to System EMC Issues | Person_160 | 2021-04-22 | 2024-04-22 | 35% | 7.7077 | 2.6977 | Accept | 35% | 7.7077 | 2.6977 | H2 | 2 | -- | TRUE | 1096 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-072 | Project_030_Risk-072 | Opportunitity | Project Contingency | Open | H3 | 3 |  | System fleet wide license agreement | Person_541 | 2013-07-21 | 2015-03-22 | 10% | 4.3921 | 0.43921 | Exploit | 10% | 4.3921 | 0.43921 | H3 | 3 | -- | TRUE | 609 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-072 | Project_030_Risk-072 | Opportunitity | Project Contingency | Open | H3 | 3 |  | System fleet wide license agreement | Person_541 | 2013-07-21 | 2015-03-22 | 10% | 4.3921 | 0.43921 | Exploit | 10% | 4.3921 | 0.43921 | H3 | 3 | -- | TRUE | 609 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-072 | Project_030_Risk-072 | Opportunitity | Project Contingency | Open | H3 | 3 |  | System fleet wide license agreement | Person_541 | 2013-07-21 | 2015-03-22 | 10% | 4.3921 | 0.43921 | Exploit | 10% | 4.3921 | 0.43921 | H3 | 3 | -- | TRUE | 609 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-072 | Project_030_Risk-072 | Opportunitity | Project Contingency | Open | H3 | 3 |  | System fleet wide license agreement | Person_541 | 2013-07-21 | 2015-03-22 | 10% | 4.3921 | 0.43921 | Exploit | 10% | 4.3921 | 0.43921 | H3 | 3 | -- | TRUE | 609 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-142 | Project_020_Risk-142 | Threat | Project Contingency | Open | H3 | 3 |  | More Outstanding ECs and PRs than expected | Person_492 | 2017-02-19 23:00 | 2017-08-01 | 50% | 0.8997 | 0.44985 | -- | 50% | 0.8997 | 0.44985 | H3 | 3 | -- | TRUE | 162.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-119 | Project_029_Risk-119 | Opportunitity | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Not required to support on load & offload of Customer Furnished Equipmnet | Person_585 | 2017-05-23 | 2020-04-16 | 80% | 5.1334 | 4.1067 | Exploit | 80% | 3.4137 | 2.731 | H2 | 2 | Stable | TRUE | 1059 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 50% | 13.7833 | 6.8917 | Avoid | 20% | 13.7833 | 2.7567 | H3 | 3 | Stable | FALSE | 364 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 50% | 13.7833 | 6.8917 | Avoid | 20% | 13.7833 | 2.7567 | H3 | 3 | Stable | FALSE | 364 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK225 | Project_038_RISK225 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Problems in Setting to Work/acceptance | Person_017 | 2016-05-23 | 2017-05-22 | 50% | 13.7833 | 6.8917 | Avoid | 20% | 13.7833 | 2.7567 | H3 | 3 | Stable | FALSE | 364 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer equipment does not allow for full coverage of STTE and Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-21 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 29 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer equipment does not allow for full coverage of STTE and Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-21 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 29 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer equipment does not allow for full coverage of STTE and Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-21 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 29 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer equipment does not allow for full coverage of STTE and Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-21 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 29 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer equipment does not allow for full coverage of STTE and Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-21 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 29 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer equipment does not allow for full coverage of STTE and Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-21 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 29 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer equipment does not allow for full coverage of STTE and Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-21 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 29 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer simulator equipment does not allow for full coverage of Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-13 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 21 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer equipment does not allow for full coverage of STTE and Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-21 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 29 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer simulator equipment does not allow for full coverage of Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-13 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 21 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer simulator equipment does not allow for full coverage of Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-13 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 21 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK482 | Project_065_RISK482 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Customer simulator equipment does not allow for full coverage of Standalone scenarios | Person_661 | 2018-04-22 | 2018-05-13 | 50% | 5.5176 | 2.7588 | Accept | 50% | 5.5176 | 2.7588 | H2 | 2 | -- | TRUE | 21 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 27.5907 | 2.7591 | Accept | 10% | 27.5907 | 2.7591 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 27.5907 | 2.7591 | Accept | 10% | 27.5907 | 2.7591 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 27.5907 | 2.7591 | Accept | 10% | 27.5907 | 2.7591 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 27.5907 | 2.7591 | Accept | 10% | 27.5907 | 2.7591 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 27.5907 | 2.7591 | Accept | 10% | 27.5907 | 2.7591 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 27.5907 | 2.7591 | Accept | 10% | 27.5907 | 2.7591 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 27.5907 | 2.7591 | Accept | 10% | 27.5907 | 2.7591 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-186 | Project_027_Risk-186 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Potential for composite suppliers going out of business | Person_166 | 2014-01-04 01:00 | 2017-08-20 01:00 | 10% | 27.5907 | 2.7591 | Accept | 10% | 27.5907 | 2.7591 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 4.6352 | 3.7081 | Reduce | 60% | 4.6352 | 2.7811 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 4.6352 | 3.7081 | Reduce | 60% | 4.6352 | 2.7811 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 4.6352 | 3.7081 | Reduce | 60% | 4.6352 | 2.7811 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 4.6352 | 3.7081 | Reduce | 60% | 4.6352 | 2.7811 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 4.6352 | 3.7081 | Reduce | 60% | 4.6352 | 2.7811 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 4.6352 | 3.7081 | Reduce | 60% | 4.6352 | 2.7811 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 4.6352 | 3.7081 | Reduce | 60% | 4.6352 | 2.7811 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R031 | Project_021_Risk-R031 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Completion of mode certification is delayed due to resource conflicts/ limited resourcing | Person_207 | 2016-08-10 | 2017-11-19 01:00 | 80% | 4.6352 | 3.7081 | Reduce | 60% | 4.6352 | 2.7811 | H1 | 1 | Worsening | TRUE | 466.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 50% | 9.2728 | 4.6364 | Reduce | 30% | 9.2728 | 2.7819 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 50% | 9.2728 | 4.6364 | Reduce | 30% | 9.2728 | 2.7819 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 50% | 9.2728 | 4.6364 | Reduce | 30% | 9.2728 | 2.7819 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 50% | 9.2728 | 4.6364 | Reduce | 30% | 9.2728 | 2.7819 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 50% | 9.2728 | 4.6364 | Reduce | 30% | 9.2728 | 2.7819 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 50% | 9.2728 | 4.6364 | Reduce | 30% | 9.2728 | 2.7819 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 50% | 9.2728 | 4.6364 | Reduce | 30% | 9.2728 | 2.7819 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R005 | Project_016_Risk--R005 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Acceptance Sign Off | Person_574 | 2016-05-23 | 2019-05-23 | 50% | 9.2728 | 4.6364 | Reduce | 30% | 9.2728 | 2.7819 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP068 | Project_024_OPP068 | Opportunitity | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Customer acceptance of iterative sell-off approach | Person_535 | 2016-07-21 | 2017-11-19 01:00 | 20% | 9.3045 | 1.8609 | -- | 30% | 9.3045 | 2.7913 | H2 | 2 | Stable | TRUE | 486.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP068 | Project_024_OPP068 | Opportunitity | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Customer acceptance of iterative sell-off approach | Person_535 | 2016-07-21 | 2017-11-19 01:00 | 20% | 9.3045 | 1.8609 | -- | 30% | 9.3045 | 2.7913 | H2 | 2 | Stable | TRUE | 486.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP068 | Project_024_OPP068 | Opportunitity | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Customer acceptance of iterative sell-off approach | Person_535 | 2016-07-21 | 2017-11-19 01:00 | 20% | 9.3045 | 1.8609 | -- | 30% | 9.3045 | 2.7913 | H2 | 2 | Stable | TRUE | 486.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | OPP068 | Project_024_OPP068 | Opportunitity | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Customer acceptance of iterative sell-off approach | Person_535 | 2016-07-21 | 2017-11-19 01:00 | 20% | 9.3045 | 1.8609 | -- | 30% | 9.3045 | 2.7913 | H2 | 2 | Stable | TRUE | 486.0417 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-04-22 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1247.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-04-22 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1247.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 | 2018-04-22 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1248 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-04-22 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1247.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-20 23:00 | 2018-04-22 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1248.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-20 22:00 | 2018-04-22 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1248.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-07-20 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1336.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-20 22:00 | 2018-04-22 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1248.0833 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 | 2018-07-20 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1337 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-21 01:00 | 2018-07-20 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1336.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK095 | Project_065_RISK095 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Legacy COTS Items in SFR&D configuration do not comply with shock requirement | Person_661 | 2014-11-20 23:00 | 2018-07-20 | 50% | 28.0275 | 14.0137 | Reduce | 10% | 28.0275 | 2.8027 | H3 | 3 | Stable | FALSE | 1337.0417 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-142 | Project_020_Risk-142 | Threat | Project Contingency | Open | H3 | 3 |  | More Outstanding ECs and PRs than expected | Person_492 | 2017-02-19 22:00 | 2017-08-01 | 50% | 0.8997 | 0.44985 | -- | 50% | 0.8997 | 0.44985 | H3 | 3 | -- | TRUE | 162.0833 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-142 | Project_020_Risk-142 | Threat | Project Contingency | Open | H3 | 3 |  | More Outstanding ECs and PRs than expected | Person_492 | 2017-02-19 21:00 | 2017-08-01 | 50% | 0.8997 | 0.44985 | -- | 50% | 0.8997 | 0.44985 | H3 | 3 | -- | TRUE | 162.125 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-142 | Project_020_Risk-142 | Threat | Project Contingency | Open | H3 | 3 |  | More Outstanding ECs and PRs than expected | Person_492 | 2017-02-20 01:00 | 2017-08-01 | 50% | 0.8997 | 0.44985 | -- | 50% | 0.8997 | 0.44985 | H3 | 3 | -- | TRUE | 161.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-142 | Project_020_Risk-142 | Threat | Project Contingency | Open | H3 | 3 |  | More Outstanding ECs and PRs than expected | Person_492 | 2017-02-20 01:00 | 2017-08-01 | 50% | 0.8997 | 0.44985 | -- | 50% | 0.8997 | 0.44985 | H3 | 3 | -- | TRUE | 161.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-142 | Project_020_Risk-142 | Threat | Project Contingency | Open | H3 | 3 |  | More Outstanding ECs and PRs than expected | Person_492 | 2017-02-20 01:00 | 2017-08-01 | 50% | 0.8997 | 0.44985 | -- | 50% | 0.8997 | 0.44985 | H3 | 3 | -- | TRUE | 161.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK225 | Project_024_RISK225 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | SW verification against SRSs required | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 5.6866 | 2.8433 | Reduce | 50% | 5.6866 | 2.8433 | H1 | 1 | Stable | TRUE | 306.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-142 | Project_020_Risk-142 | Threat | Project Contingency | Open | H3 | 3 |  | More Outstanding ECs and PRs than expected | Person_492 | 2017-02-20 01:00 | 2017-08-01 | 50% | 0.8997 | 0.44985 | -- | 50% | 0.8997 | 0.44985 | H3 | 3 | -- | TRUE | 161.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 15% | 19.1935 | 2.879 | Accept | 15% | 19.1935 | 2.879 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 15% | 19.1935 | 2.879 | Accept | 15% | 19.1935 | 2.879 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-194 | Project_027_Risk-194 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | The effect of specialist supplier obsolescence on complex assemblies | Person_074 | 2014-01-04 01:00 | 2017-08-20 01:00 | 15% | 19.1935 | 2.879 | Accept | 15% | 19.1935 | 2.879 | H3 | 3 | Stable | FALSE | 1324 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-142 | Project_020_Risk-142 | Threat | Project Contingency | Open | H3 | 3 |  | More Outstanding ECs and PRs than expected | Person_492 | 2017-02-20 01:00 | 2017-08-01 | 50% | 0.8997 | 0.44985 | -- | 50% | 0.8997 | 0.44985 | H3 | 3 | -- | TRUE | 161.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP003 | Project_081_OPP003 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Supplier abilities mature exponentially throughout contract requiring less FSE support | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 25% | 1.8307 | 0.45767 | -- | 25% | 1.8307 | 0.45767 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 |  | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2016-09-20 01:00 | 50% | 1.2445 | 0.62224 | -- | 20% | 2.303 | 0.46059 | H3 | 3 | Improving | TRUE | 607 |  | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 |  | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2016-09-20 01:00 | 50% | 1.2445 | 0.62224 | -- | 20% | 2.303 | 0.46059 | H3 | 3 | Worsening | TRUE | 607 |  | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 |  | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 50% | 1.2445 | 0.62224 | -- | 20% | 2.303 | 0.46059 | H3 | 3 | Worsening | TRUE | 730 |  | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 |  | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 50% | 1.2445 | 0.62224 | -- | 20% | 2.303 | 0.46059 | H3 | 3 | Worsening | TRUE | 730 |  | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 |  | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 50% | 1.2445 | 0.62224 | -- | 20% | 2.303 | 0.46059 | H3 | 3 | Worsening | TRUE | 730 |  | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK290 | Project_035_RISK290 | Threat | Project Contingency | Open | H3 | 3 |  | Face-to-Face Arbitration | Person_699 | 2015-01-22 01:00 | 2017-01-21 01:00 | 50% | 1.2445 | 0.62224 | -- | 20% | 2.303 | 0.46059 | H3 | 3 | Worsening | TRUE | 730 |  | 0 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK047 | Project_058_RISK047 | Threat | Project Contingency | Open | H3 | 3 |  | Tray Obsolsence | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Accept | 40% | 1.1744 | 0.46977 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK047 | Project_058_RISK047 | Threat | Project Contingency | Open | H3 | 3 |  | Tray Obsolsence | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Accept | 40% | 1.1744 | 0.46977 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK047 | Project_058_RISK047 | Threat | Project Contingency | Open | H3 | 3 |  | Tray Obsolsence | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Accept | 40% | 1.1744 | 0.46977 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK047 | Project_058_RISK047 | Threat | Project Contingency | Open | H3 | 3 |  | Tray Obsolsence | Person_511 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Accept | 40% | 1.1744 | 0.46977 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK047 | Project_058_RISK047 | Threat | Project Contingency | Open | H3 | 3 |  | Tray Obsolsence | Person_511 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Accept | 40% | 1.1744 | 0.46977 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK047 | Project_058_RISK047 | Threat | Project Contingency | Open | H3 | 3 |  | Tray Obsolsence | Person_511 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Accept | 40% | 1.1744 | 0.46977 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK047 | Project_058_RISK047 | Threat | Project Contingency | Open | H3 | 3 |  | Tray Obsolsence | Person_511 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Accept | 40% | 1.1744 | 0.46977 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | OP001 | Project_083_OP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Supply chain | Cross Project Procurement | Person_391 | 2018-02-20 01:00 | 2018-12-20 01:00 | 20% | 4.2141 | 0.84283 | Exploit | 70% | 4.2141 | 2.9499 | H3 | 3 | Stable | FALSE | 303 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 60% | 5.8424 | 3.5054 | Reduce | 60% | 4.9768 | 2.9861 | H1 | 1 | Stable | TRUE | 549.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_002 | Portfolio_002 | Project_006 | Risk-004 | Project_006_Risk-004 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Internal Assemblies | Person_582 | 2014-05-23 | 2017-04-22 | 20% | 23.521 | 4.7042 | Avoid | 15% | 20.0321 | 3.0048 | H2 | 2 | Stable | TRUE | 1065 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Standard Compliance | Person_272 | 2014-05-09 | 2023-11-20 01:00 | 5% | 60.4367 | 3.0218 | Accept | 5% | 60.4367 | 3.0218 | H3 | 3 | -- | FALSE | 3482.0417 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Standard Compliance | Person_272 | 2014-05-09 | 2023-11-20 01:00 | 5% | 60.4367 | 3.0218 | Accept | 5% | 60.4367 | 3.0218 | H3 | 3 | -- | FALSE | 3482.0417 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2023-11-20 01:00 | 5% | 60.4367 | 3.0218 | Accept | 5% | 60.4367 | 3.0218 | H3 | 3 | -- | FALSE | 2617 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-02-19 01:00 | 5% | 60.4367 | 3.0218 | Accept | 5% | 60.4367 | 3.0218 | H3 | 3 | -- | FALSE | 152 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-02-19 01:00 | 5% | 60.4367 | 3.0218 | Accept | 5% | 60.4367 | 3.0218 | H3 | 3 | -- | FALSE | 152 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-02-19 01:00 | 5% | 60.4367 | 3.0218 | Accept | 5% | 60.4367 | 3.0218 | H3 | 3 | Improving | FALSE | 152 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-071 | Project_026_Risk-071 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Standard Compliance | Person_272 | 2016-09-20 01:00 | 2017-02-19 01:00 | 5% | 60.4367 | 3.0218 | Accept | 5% | 60.4367 | 3.0218 | H3 | 3 | Improving | FALSE | 152 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 30% | 10.1533 | 3.046 | -- | 30% | 10.1533 | 3.046 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 | 2017-11-20 | 30% | 10.1533 | 3.046 | -- | 30% | 10.1533 | 3.046 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 30% | 10.1533 | 3.046 | -- | 30% | 10.1533 | 3.046 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK007 | Project_099_RISK007 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Material availability issues | Person_243 | 2017-09-21 01:00 | 2019-01-27 01:00 | 50% | 7.7422 | 3.8711 | Reduce | 40% | 7.7422 | 3.0969 | H2 | 2 | -- | TRUE | 493 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK047 | Project_058_RISK047 | Threat | Project Contingency | Open | H3 | 3 |  | Tray Obsolsence | Person_511 | 2016-05-23 | 2019-08-21 01:00 | 40% | 1.1744 | 0.46977 | Accept | 40% | 1.1744 | 0.46977 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2011-04-22 | 2019-05-23 | 50% | 10.9057 | 5.4529 | Reduce | 40% | 7.7898 | 3.1159 | H1 | 1 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 50% | 10.9057 | 5.4529 | Reduce | 40% | 7.7898 | 3.1159 | H1 | 1 | Worsening | TRUE | 641.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 50% | 10.9057 | 5.4529 | Reduce | 40% | 7.7898 | 3.1159 | H1 | 1 | Worsening | TRUE | 641.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Retained systems re-design or modification | Person_585 | 2016-08-20 01:00 | 2016-12-02 01:00 | 5% | 62.3617 | 3.1181 | Accept | 5% | 62.3617 | 3.1181 | H2 | 2 | Improving | TRUE | 104 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2016-12-02 01:00 | 5% | 62.3617 | 3.1181 | Accept | 5% | 62.3617 | 3.1181 | H2 | 2 | Improving | TRUE | 104 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2016-12-02 01:00 | 5% | 62.3617 | 3.1181 | Accept | 5% | 62.3617 | 3.1181 | H2 | 2 | Improving | TRUE | 104 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2016-12-02 01:00 | 5% | 62.3617 | 3.1181 | Accept | 5% | 62.3617 | 3.1181 | H2 | 2 | Improving | TRUE | 104 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2017-02-19 01:00 | 5% | 62.3617 | 3.1181 | Accept | 5% | 62.3617 | 3.1181 | H2 | 2 | Improving | TRUE | 183 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2017-02-19 01:00 | 5% | 62.3617 | 3.1181 | Accept | 5% | 62.3617 | 3.1181 | H2 | 2 | Improving | TRUE | 183 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Retained systems re-design or modification | Person_289 | 2016-08-20 01:00 | 2017-02-19 01:00 | 5% | 62.3617 | 3.1181 | Accept | 5% | 62.3617 | 3.1181 | H2 | 2 | Improving | TRUE | 183 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK047 | Project_024_RISK047 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Retained systems re-design or modification | Person_710 | 2016-08-20 01:00 | 2017-02-19 01:00 | 5% | 62.3617 | 3.1181 | Accept | 5% | 62.3617 | 3.1181 | H2 | 2 | Improving | TRUE | 183 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 |  | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-11-20 01:00 | 20% | 3.1633 | 0.63267 | Accept | 15% | 3.1633 | 0.4745 | H3 | 3 | Stable | TRUE | 515.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK517 | Project_065_RISK517 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | New Design | Person_418 | 2017-12-21 01:00 | 2019-05-22 | 20% | 20.9088 | 4.1818 | Reduce | 15% | 20.9088 | 3.1363 | H3 | 3 | -- | FALSE | 516.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK517 | Project_065_RISK517 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | New Design | Person_418 | 2017-12-21 | 2019-05-22 | 20% | 20.9088 | 4.1818 | Reduce | 15% | 20.9088 | 3.1363 | H3 | 3 | -- | FALSE | 517 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK517 | Project_065_RISK517 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | New Design | Person_418 | 2017-12-21 01:00 | 2019-05-22 | 20% | 20.9088 | 4.1818 | Reduce | 15% | 20.9088 | 3.1363 | H3 | 3 | -- | FALSE | 516.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK517 | Project_065_RISK517 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | New Design | Person_418 | 2017-12-20 23:00 | 2019-05-22 | 20% | 20.9088 | 4.1818 | Reduce | 15% | 20.9088 | 3.1363 | H3 | 3 | -- | FALSE | 517.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Worsening | TRUE | 972.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 | 2017-05-21 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Worsening | TRUE | 973 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Worsening | TRUE | 972.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Worsening | TRUE | 972.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Worsening | TRUE | 972.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Worsening | TRUE | 972.9583 |  | 1 | 0 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Worsening | TRUE | 972.9583 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2016-12-20 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Improving | TRUE | 821 |  | 1 | 0 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2017-05-21 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Worsening | TRUE | 972.9583 |  | 1 | 0 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 | 2016-12-20 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Improving | TRUE | 821 |  | 1 | 0 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Improving | TRUE | 1247 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 1247 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 1247 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 1247 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 1247 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 1247 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 1247 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 1247 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 01:00 | 2018-02-19 01:00 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 1247 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 212.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 212.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 212.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 212.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 212.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 212.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Stable | TRUE | 212.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--10 | Project_021_Risk--10 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_652 | 2018-08-22 01:00 | 2019-03-23 | 70% | 10.4954 | 7.3468 | Reduce | 30% | 10.4954 | 3.1486 | H2 | 2 | Improving | TRUE | 212.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-005 | Project_077_T-005 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | SSTP/SSTR overspend | Person_202 | 2018-10-22 01:00 | 2020-02-21 01:00 | 30% | 10.5469 | 3.1641 | Reduce | 30% | 10.5469 | 3.1641 | H2 | 2 | Stable | TRUE | 487 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R013 | Project_085_R013 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lead free' design implications | Person_042 | 2017-12-21 | 2021-02-19 | 40% | 31.6963 | 12.6785 | Reduce | 10% | 31.6963 | 3.1696 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK002 | Project_094_RISK002 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Facilities or equipment for training not available | Person_198 | 2020-12-21 | 2021-05-22 | 20% | 15.974 | 3.1948 | Reduce | 20% | 15.974 | 3.1948 | H3 | 3 | Stable | TRUE | 152 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1004 | Project_091_RISK1004 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Cost of material exceeds the cost estimate | Person_557 | 2018-08-22 01:00 | 2021-05-23 | 50% | 6.3954 | 3.1977 | Accept | 50% | 6.3954 | 3.1977 | H2 | 2 | -- | TRUE | 1004.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_022 | Project_091 | RISK1004 | Project_091_RISK1004 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Cost of material exceeds the cost estimate | Person_557 | 2018-09-21 01:00 | 2021-05-23 | 50% | 6.3954 | 3.1977 | Accept | 50% | 6.3954 | 3.1977 | H2 | 2 | -- | TRUE | 974.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK032 | Project_075_RISK032 | Threat | Project Contingency | Open | H2 | 2 |  | If the requirement we have specified isnt achieved, the product becomes unsellable. | Person_449 | 2018-02-20 01:00 | 2018-08-21 | 30% | 3.1976 | 0.95929 | Reduce | 15% | 3.1976 | 0.47965 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK032 | Project_075_RISK032 | Threat | Project Contingency | Open | H2 | 2 |  | If the requirement we have specified isnt achieved, the product becomes unsellable. | Person_449 | 2018-02-20 01:00 | 2018-08-21 | 30% | 3.1976 | 0.95929 | Reduce | 15% | 3.1976 | 0.47965 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK032 | Project_075_RISK032 | Threat | Project Contingency | Open | H2 | 2 |  | If the requirement we have specified isnt achieved, the product becomes unsellable. | Person_449 | 2018-02-20 01:00 | 2018-08-21 | 30% | 3.1976 | 0.95929 | Reduce | 15% | 3.1976 | 0.47965 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK084 | Project_076_RISK084 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Safety assessment creates the need for additional development activities | Person_484 | 2018-09-21 01:00 | 2019-05-23 | 39% | 8.2922 | 3.234 | Accept | 39% | 8.2922 | 3.234 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R044 | Project_085_R044 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | New source fail to produce | Person_098 | 2017-12-21 | 2019-04-22 | 30% | 26.9813 | 8.0944 | Reduce | 12% | 26.9813 | 3.2378 | H3 | 3 | -- | FALSE | 487 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-21 | 2017-06-21 | 70% | 10.8044 | 7.5631 | Reduce | 30% | 10.8044 | 3.2413 | H2 | 2 | Worsening | TRUE | 1004 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R010 | Project_021_Risk-R010 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Development Closure | Person_766 | 2014-09-20 23:00 | 2017-06-21 | 70% | 10.8044 | 7.5631 | Reduce | 30% | 10.8044 | 3.2413 | H2 | 2 | Worsening | TRUE | 1004.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 40% | 16.2288 | 6.4915 | Reduce | 20% | 16.2288 | 3.2458 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 40% | 16.2288 | 6.4915 | Reduce | 20% | 16.2288 | 3.2458 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 40% | 16.2288 | 6.4915 | Reduce | 20% | 16.2288 | 3.2458 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 40% | 16.2288 | 6.4915 | Reduce | 20% | 16.2288 | 3.2458 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Additional Trials - Increased Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 40% | 16.2288 | 6.4915 | Reduce | 20% | 16.2288 | 3.2458 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 40% | 16.2288 | 6.4915 | Reduce | 20% | 16.2288 | 3.2458 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 40% | 16.2288 | 6.4915 | Reduce | 20% | 16.2288 | 3.2458 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK176 | Project_024_RISK176 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Additional Trials e.g. product - Cost | Person_073 | 2016-05-23 | 2017-02-19 01:00 | 40% | 16.2288 | 6.4915 | Reduce | 20% | 16.2288 | 3.2458 | H2 | 2 | Stable | TRUE | 272.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK072 | Project_049_RISK072 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Training Systems | Person_524 | 2019-10-17 01:00 | 2019-12-28 01:00 | 50% | 10.8741 | 5.437 | Reduce | 30% | 10.8741 | 3.2622 | H2 | 2 | -- | TRUE | 72 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Subsystem does not meet requirements | Person_351 | 2011-04-22 | 2019-05-23 | 40% | 25.4467 | 10.1787 | -- | 30% | 10.9057 | 3.2717 | H1 | 1 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Subsystem does not meet requirements | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 40% | 25.4467 | 10.1787 | Reduce | 30% | 10.9057 | 3.2717 | H1 | 1 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Subsystem does not meet requirements | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 40% | 25.4467 | 10.1787 | Reduce | 30% | 10.9057 | 3.2717 | H1 | 1 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK287 | Project_024_RISK287 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Subsystem does not meet requirements | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 40% | 25.4467 | 10.1787 | Reduce | 30% | 10.9057 | 3.2717 | H1 | 1 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 30% | 16.3694 | 4.9108 | Reduce | 20% | 16.3683 | 3.2737 | H3 | 3 | Worsening | TRUE | 2806 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 30% | 16.3694 | 4.9108 | Reduce | 20% | 16.3683 | 3.2737 | H3 | 3 | Worsening | TRUE | 2806 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 30% | 16.3694 | 4.9108 | Reduce | 20% | 16.3683 | 3.2737 | H3 | 3 | Worsening | TRUE | 2806 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 30% | 16.3694 | 4.9108 | Reduce | 20% | 16.3683 | 3.2737 | H3 | 3 | Stable | TRUE | 2806 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 30% | 16.3694 | 4.9108 | Reduce | 20% | 16.3683 | 3.2737 | H3 | 3 | Stable | TRUE | 2806 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-019 | Project_026_Risk-019 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Customer interaction and reporting may be much greater than anticipated | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 30% | 16.3694 | 4.9108 | Reduce | 20% | 16.3683 | 3.2737 | H3 | 3 | Stable | TRUE | 2806 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK032 | Project_075_RISK032 | Threat | Project Contingency | Open | H2 | 2 |  | If the requirement we have specified isnt achieved, the product becomes unsellable. | Person_449 | 2018-02-20 01:00 | 2018-08-21 | 30% | 3.1976 | 0.95929 | Reduce | 15% | 3.1976 | 0.47965 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK309 | Project_035_RISK309 | Threat | Project Contingency | Open | H3 | 3 |  | Facility performance unacceptable during Scenario testing | Person_303 | 2015-03-24 | 2016-06-15 | 30% | 3.2155 | 0.96464 | Accept | 15% | 3.2155 | 0.48232 | H3 | 3 | Stable | TRUE | 449 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK309 | Project_035_RISK309 | Threat | Project Contingency | Open | H3 | 3 |  | Facility performance unacceptable during Scenario testing | Person_303 | 2015-03-24 | 2016-10-13 01:00 | 30% | 3.2155 | 0.96464 | Accept | 15% | 3.2155 | 0.48232 | H3 | 3 | Stable | TRUE | 569.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Increase in Supply Chain Material Costs and Lead Times | Person_403 | 2018-04-22 | 2019-05-16 | 50% | 6.6521 | 3.326 | Accept | 50% | 6.6521 | 3.326 | H2 | 2 | Stable | TRUE | 389 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2016-05-23 | 2019-07-21 | 35% | 9.505 | 3.3267 | Reduce | 35% | 9.505 | 3.3267 | H2 | 2 | Stable | TRUE | 1154 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2016-05-23 | 2019-07-21 | 35% | 9.505 | 3.3267 | Reduce | 35% | 9.505 | 3.3267 | H2 | 2 | Stable | TRUE | 1154 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2016-05-23 | 2019-07-21 | 35% | 9.505 | 3.3267 | Reduce | 35% | 9.505 | 3.3267 | H2 | 2 | Stable | TRUE | 1154 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2017-01-21 01:00 | 2019-07-21 | 35% | 9.505 | 3.3267 | Reduce | 35% | 9.505 | 3.3267 | H2 | 2 | Stable | TRUE | 910.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK003 | Project_029_Risk-RISK003 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Increase in Supply Chain Material Costs [technical scope] | Person_466 | 2017-01-21 01:00 | 2019-07-21 | 35% | 9.505 | 3.3267 | Reduce | 35% | 9.505 | 3.3267 | H2 | 2 | Stable | TRUE | 910.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK054 | Project_017_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Longer than forecast Supplier turnaround times | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 45% | 16.0697 | 7.2314 | Reduce | 25% | 13.3915 | 3.3479 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK054 | Project_017_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Longer than forecast Supplier turnaround times | Person_375 | 2016-01-22 01:00 | 2023-02-20 01:00 | 45% | 16.0697 | 7.2314 | Reduce | 25% | 13.3915 | 3.3479 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK054 | Project_017_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Longer than forecast Supplier turnaround times | Person_375 | 2016-01-22 | 2023-02-20 | 45% | 16.0697 | 7.2314 | Reduce | 25% | 13.3915 | 3.3479 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK054 | Project_017_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Longer than forecast Supplier turnaround times | Person_375 | 2016-01-22 | 2023-02-20 | 45% | 16.0697 | 7.2314 | Reduce | 25% | 13.3915 | 3.3479 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK054 | Project_017_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Longer than forecast Supplier turnaround times | Person_375 | 2016-01-21 23:00 | 2023-02-19 23:00 | 45% | 16.0697 | 7.2314 | Reduce | 25% | 13.3915 | 3.3479 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK054 | Project_017_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Longer than forecast Supplier turnaround times | Person_375 | 2016-01-21 23:00 | 2023-02-19 23:00 | 45% | 16.0697 | 7.2314 | Reduce | 25% | 13.3915 | 3.3479 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK054 | Project_017_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Longer than forecast Supplier turnaround times | Person_375 | 2016-01-21 23:00 | 2023-02-19 23:00 | 45% | 16.0697 | 7.2314 | Reduce | 25% | 13.3915 | 3.3479 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK054 | Project_017_RISK054 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Longer than forecast Supplier turnaround times | Person_375 | 2016-01-21 21:00 | 2023-02-19 21:00 | 45% | 16.0697 | 7.2314 | Reduce | 25% | 13.3915 | 3.3479 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-032 | Project_026_Risk-032 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Data sharing may be more complex than anticipated | Person_362 | 2014-05-09 | 2018-12-27 01:00 | 75% | 4.4768 | 3.3576 | Reduce | 75% | 4.4768 | 3.3576 | H2 | 2 | -- | TRUE | 1693.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-032 | Project_026_Risk-032 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Data sharing may be more complex than anticipated | Person_362 | 2014-05-09 | 2018-12-27 01:00 | 75% | 4.4768 | 3.3576 | Reduce | 75% | 4.4768 | 3.3576 | H2 | 2 | -- | TRUE | 1693.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-032 | Project_026_Risk-032 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Data sharing may be more complex than anticipated | Person_362 | 2014-05-09 | 2018-12-27 01:00 | 75% | 4.4768 | 3.3576 | Reduce | 75% | 4.4768 | 3.3576 | H2 | 2 | -- | TRUE | 1693.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-032 | Project_026_Risk-032 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Data sharing may be more complex than anticipated | Person_362 | 2014-05-09 | 2018-12-27 01:00 | 75% | 4.4768 | 3.3576 | Reduce | 75% | 4.4768 | 3.3576 | H2 | 2 | -- | TRUE | 1693.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-032 | Project_026_Risk-032 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Data sharing may be more complex than anticipated | Person_362 | 2014-05-09 | 2018-12-27 01:00 | 75% | 4.4768 | 3.3576 | Reduce | 75% | 4.4768 | 3.3576 | H2 | 2 | -- | TRUE | 1693.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-032 | Project_026_Risk-032 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Data sharing may be more complex than anticipated | Person_362 | 2014-05-09 | 2018-12-27 01:00 | 75% | 4.4768 | 3.3576 | Reduce | 75% | 4.4768 | 3.3576 | H2 | 2 | -- | TRUE | 1693.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-032 | Project_026_Risk-032 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Data sharing may be more complex than anticipated | Person_362 | 2014-05-09 | 2017-08-20 01:00 | 75% | 4.4768 | 3.3576 | Reduce | 75% | 4.4768 | 3.3576 | H2 | 2 | -- | TRUE | 1199.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK309 | Project_035_RISK309 | Threat | Project Contingency | Open | H3 | 3 |  | Facility performance unacceptable during Scenario testing | Person_303 | 2015-03-24 | 2016-10-13 01:00 | 30% | 3.2155 | 0.96464 | Accept | 15% | 3.2155 | 0.48232 | H3 | 3 | Stable | TRUE | 569.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK308 | Project_035_RISK308 | Threat | Project Contingency | Open | H3 | 3 |  | Facility performance during Live trials | Person_303 | 2015-05-24 | 2016-11-20 01:00 | 30% | 3.2155 | 0.96464 | Accept | 15% | 3.2155 | 0.48232 | H3 | 3 | Improving | TRUE | 546.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2011-04-22 | 2019-05-23 | 50% | 8.5688 | 4.2844 | -- | 40% | 8.5688 | 3.4275 | H1 | 1 | -- | TRUE | 2953 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 8.5688 | 4.2844 | Reduce | 40% | 8.5688 | 3.4275 | H1 | 1 | Worsening | TRUE | 306.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK293 | Project_024_RISK293 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 8.5688 | 4.2844 | Reduce | 40% | 8.5688 | 3.4275 | H1 | 1 | Worsening | TRUE | 306.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 10% | 34.363 | 3.4363 | Avoid | 10% | 34.363 | 3.4363 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 10% | 34.363 | 3.4363 | Avoid | 10% | 34.363 | 3.4363 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 10% | 34.363 | 3.4363 | Avoid | 10% | 34.363 | 3.4363 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 | 2017-08-20 | 10% | 34.363 | 3.4363 | Avoid | 10% | 34.363 | 3.4363 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 10% | 34.363 | 3.4363 | Avoid | 10% | 34.363 | 3.4363 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 10% | 34.363 | 3.4363 | Avoid | 10% | 34.363 | 3.4363 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 10% | 34.363 | 3.4363 | Avoid | 10% | 34.363 | 3.4363 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-127 | Project_032_Risk-127 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project Increased Defect Support | Person_136 | 2014-08-22 01:00 | 2017-08-20 01:00 | 10% | 34.363 | 3.4363 | Avoid | 10% | 34.363 | 3.4363 | H3 | 3 | Stable | FALSE | 1094 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK222 | Project_038_RISK222 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design Acceptance is difficult to obtain from Customer | Person_017 | 2015-09-21 01:00 | 2016-11-20 01:00 | 60% | 22.9223 | 13.7534 | Avoid | 15% | 22.9223 | 3.4383 | H2 | 2 | Stable | TRUE | 426 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK073 | Project_049_RISK073 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Configuration/Obsolescence | Person_282 | 2019-10-09 01:00 | 2020-08-24 01:00 | 80% | 17.2646 | 13.8117 | Reduce | 20% | 17.2646 | 3.4529 | H3 | 3 | -- | TRUE | 320 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R003 | Project_044_Risk-R003 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Mono vs stereo Component | Person_358 | 2018-01-19 01:00 | 2018-10-22 01:00 | 40% | 17.3851 | 6.954 | Reduce | 20% | 17.3851 | 3.477 | H3 | 3 | Stable | FALSE | 276 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK122 | Project_049_RISK122 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Supplier Documentation | Person_526 | 2017-08-23 01:00 | 2019-12-18 01:00 | 40% | 9.9467 | 3.9787 | Reduce | 35% | 9.9467 | 3.4813 | H3 | 3 | -- | TRUE | 847 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK437 | Project_065_RISK437 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Change to System cabinet interface | Person_047 | 2018-03-21 | 2022-09-14 01:00 | 70% | 5.0032 | 3.5023 | Accept | 70% | 5.0032 | 3.5023 | H1 | 1 | -- | TRUE | 1638.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK437 | Project_065_RISK437 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Change to System cabinet interface | Person_047 | 2018-03-21 | 2022-09-14 01:00 | 70% | 5.0032 | 3.5023 | Accept | 70% | 5.0032 | 3.5023 | H1 | 1 | -- | TRUE | 1638.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK437 | Project_065_RISK437 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Change to System cabinet interface | Person_047 | 2018-03-21 | 2022-09-14 | 70% | 5.0032 | 3.5023 | Accept | 70% | 5.0032 | 3.5023 | H1 | 1 | -- | TRUE | 1638 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK437 | Project_065_RISK437 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Change to System cabinet interface | Person_047 | 2018-03-21 | 2022-09-14 01:00 | 70% | 5.0032 | 3.5023 | Accept | 70% | 5.0032 | 3.5023 | H1 | 1 | -- | TRUE | 1638.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK437 | Project_065_RISK437 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Change to System cabinet interface | Person_047 | 2018-03-21 | 2022-09-13 23:00 | 70% | 5.0032 | 3.5023 | Accept | 70% | 5.0032 | 3.5023 | H1 | 1 | -- | TRUE | 1637.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK437 | Project_065_RISK437 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Change to System cabinet interface | Person_047 | 2018-03-21 | 2022-09-13 22:00 | 70% | 5.0032 | 3.5023 | Accept | 70% | 5.0032 | 3.5023 | H1 | 1 | -- | TRUE | 1637.9167 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK437 | Project_065_RISK437 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Change to System cabinet interface | Person_047 | 2018-03-21 | 2022-09-13 22:00 | 70% | 5.0032 | 3.5023 | Accept | 70% | 5.0032 | 3.5023 | H1 | 1 | -- | TRUE | 1637.9167 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2011-04-22 | 2019-05-23 | 60% | 5.8424 | 3.5054 | -- | 60% | 5.8424 | 3.5054 | H1 | 1 | -- | TRUE | 2953 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 60% | 5.8424 | 3.5054 | Reduce | 60% | 5.8424 | 3.5054 | H1 | 1 | Stable | TRUE | 641.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 60% | 5.8424 | 3.5054 | Reduce | 60% | 5.8424 | 3.5054 | H1 | 1 | Stable | TRUE | 641.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 60% | 5.8424 | 3.5054 | Reduce | 60% | 5.8424 | 3.5054 | H1 | 1 | Stable | TRUE | 641.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK288 | Project_024_RISK288 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Unplanned obsolescence and/or repairs to rig assets. | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 60% | 5.8424 | 3.5054 | Reduce | 60% | 5.8424 | 3.5054 | H1 | 1 | Stable | TRUE | 549.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 50% | 7.0313 | 3.5156 | Accept | 50% | 7.0313 | 3.5156 | H1 | 1 | Worsening | TRUE | 547.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-20 | 2018-05-22 | 50% | 7.0313 | 3.5156 | Accept | 50% | 7.0313 | 3.5156 | H1 | 1 | Worsening | TRUE | 548 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 50% | 7.0313 | 3.5156 | Accept | 50% | 7.0313 | 3.5156 | H1 | 1 | Worsening | TRUE | 548.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 50% | 7.0313 | 3.5156 | Accept | 50% | 7.0313 | 3.5156 | H1 | 1 | Worsening | TRUE | 548.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 50% | 7.0313 | 3.5156 | Accept | 50% | 7.0313 | 3.5156 | H1 | 1 | Worsening | TRUE | 548.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R44 | Project_041_R44 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Source Change and cost change | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 50% | 7.0313 | 3.5156 | Accept | 50% | 7.0313 | 3.5156 | H1 | 1 | Worsening | TRUE | 548.0833 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.1867 | 3.5934 | Accept | 50% | 7.1867 | 3.5934 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.1867 | 3.5934 | Accept | 50% | 7.1867 | 3.5934 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.1867 | 3.5934 | Accept | 50% | 7.1867 | 3.5934 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK006 | Project_094_RISK006 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Additional freight costs | Person_198 | 2020-08-21 | 2022-05-22 | 30% | 11.9805 | 3.5942 | Reduce | 30% | 11.9805 | 3.5942 | H3 | 3 | Stable | TRUE | 639 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK162 | Project_038_RISK162 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of SFRD funding for Product in future years to exempte contract obligation for Obsolesence | Person_330 | 2016-05-23 | 2017-05-22 | 20% | 17.9783 | 3.5957 | Accept | 20% | 17.9783 | 3.5957 | H3 | 3 | -- | FALSE | 364 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK162 | Project_038_RISK162 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of SFRD funding for Product in future years to exempte contract obligation for Obsolesence | Person_330 | 2016-05-23 | 2017-05-22 | 20% | 17.9783 | 3.5957 | Accept | 20% | 17.9783 | 3.5957 | H3 | 3 | -- | FALSE | 364 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK162 | Project_038_RISK162 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of SFRD funding for Product in future years to exempte contract obligation for Obsolesence | Person_330 | 2016-05-23 | 2017-05-22 | 20% | 17.9783 | 3.5957 | Accept | 20% | 17.9783 | 3.5957 | H3 | 3 | -- | FALSE | 364 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK162 | Project_038_RISK162 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of SFRD funding for Product in future years to exempte contract obligation for Obsolesence | Person_330 | 2016-05-23 | 2017-05-22 | 20% | 17.9783 | 3.5957 | Accept | 20% | 17.9783 | 3.5957 | H3 | 3 | -- | FALSE | 364 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK162 | Project_038_RISK162 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of SFRD funding for Product in future years to exempte contract obligation for Obsolesence | Person_330 | 2016-05-23 | 2017-05-22 | 20% | 17.9783 | 3.5957 | Accept | 20% | 17.9783 | 3.5957 | H3 | 3 | -- | FALSE | 364 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK162 | Project_038_RISK162 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of SFRD funding for Product in future years to exempte contract obligation for Obsolesence | Person_330 | 2016-05-23 | 2017-05-22 | 20% | 17.9783 | 3.5957 | Accept | 20% | 17.9783 | 3.5957 | H3 | 3 | -- | FALSE | 364 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK162 | Project_038_RISK162 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of SFRD funding for Product in future years to exempte contract obligation for Obsolesence | Person_330 | 2016-05-23 | 2017-05-22 | 20% | 17.9783 | 3.5957 | Accept | 20% | 17.9783 | 3.5957 | H3 | 3 | -- | FALSE | 364 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK162 | Project_038_RISK162 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Lack of SFRD funding for Product in future years to exempte contract obligation for Obsolesence | Person_330 | 2016-05-23 | 2017-05-22 | 20% | 17.9783 | 3.5957 | Accept | 20% | 17.9783 | 3.5957 | H3 | 3 | -- | FALSE | 364 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Material/Labour Overspend | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.2272 | 3.6136 | Accept | 50% | 7.2272 | 3.6136 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | General Material/Labour Overspend | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.2272 | 3.6136 | Accept | 50% | 7.2272 | 3.6136 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.3646 | 3.6823 | Accept | 50% | 7.3646 | 3.6823 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.3646 | 3.6823 | Accept | 50% | 7.3646 | 3.6823 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.3646 | 3.6823 | Accept | 50% | 7.3646 | 3.6823 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_013 | RISK001 | Project_013_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Risk of Overspend on Labour or Materials | Person_662 | 2015-05-24 | 2022-05-22 | 50% | 7.3848 | 3.6924 | Accept | 50% | 7.3848 | 3.6924 | H2 | 2 | Stable | TRUE | 2555 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK159 | Project_024_RISK159 | Threat | Project Contingency | Open | H1 | 1 | System Engineering | Extension of planned safety team work | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 40% | 9.2439 | 3.6976 | Accept | 40% | 9.2439 | 3.6976 | H1 | 1 | Worsening | TRUE | 394 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK272 | Project_024_RISK272 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Function implementation | Person_318 | 2016-03-23 | 2016-11-20 01:00 | 50% | 7.4544 | 3.7272 | Reduce | 50% | 7.4544 | 3.7272 | H1 | 1 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK272 | Project_024_RISK272 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Function implementation | Person_318 | 2016-03-23 | 2016-11-20 01:00 | 50% | 7.4544 | 3.7272 | Reduce | 50% | 7.4544 | 3.7272 | H1 | 1 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK272 | Project_024_RISK272 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Function implementation | Person_318 | 2016-03-23 | 2016-11-20 01:00 | 50% | 7.4544 | 3.7272 | Reduce | 50% | 7.4544 | 3.7272 | H1 | 1 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK272 | Project_024_RISK272 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Function implementation | Person_318 | 2016-03-23 | 2016-11-20 01:00 | 50% | 7.4544 | 3.7272 | Reduce | 50% | 7.4544 | 3.7272 | H1 | 1 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK272 | Project_024_RISK272 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Function implementation | Person_318 | 2016-03-23 | 2016-11-20 01:00 | 50% | 7.4544 | 3.7272 | Reduce | 50% | 7.4544 | 3.7272 | H1 | 1 | -- | TRUE | 242.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK272 | Project_024_RISK272 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Function implementation | Person_318 | 2016-03-23 | 2017-02-20 01:00 | 50% | 7.4544 | 3.7272 | Reduce | 50% | 7.4544 | 3.7272 | H1 | 1 | -- | TRUE | 334.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043- | Project_065_RISK043- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2020-04-22 | 2021-04-22 | 30% | 3.2453 | 0.9736 | Reduce | 15% | 3.2453 | 0.4868 | H3 | 3 | -- | FALSE | 365 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_007 | R-078 | Project_007_R-078 | Threat | Project Contingency | Open | H3 | 3 |  | Environment Conditions | Person_356 | 2013-12-03 19:00 | 2016-03-21 19:00 | 20% | 2.4394 | 0.48788 | Accept | 20% | 2.4394 | 0.48788 | H3 | 3 | Stable | TRUE | 839 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R027 | Project_085_R027 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Pressure Profile cannot be achieved | Person_042 | 2018-07-22 | 2019-05-23 | 60% | 8.3165 | 4.9899 | Reduce | 45% | 8.3165 | 3.7424 | H2 | 2 | -- | TRUE | 305 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-064 | Project_008_Risk-064 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional Tech Pubs Headcount needed to clear Backlog | Person_565 | 2015-05-24 | 2017-03-22 | 50% | 9.3748 | 4.6874 | Accept | 40% | 9.3748 | 3.7499 | H2 | 2 | -- | TRUE | 668 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2016-08-20 | 35% | 20.3303 | 7.1156 | Accept | 20% | 18.975 | 3.795 | H2 | 2 | Stable | TRUE | 120 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2016-09-19 01:00 | 35% | 20.3303 | 7.1156 | Accept | 20% | 18.975 | 3.795 | H2 | 2 | Stable | TRUE | 150.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2016-10-15 01:00 | 35% | 20.3303 | 7.1156 | Accept | 20% | 18.975 | 3.795 | H2 | 2 | Stable | TRUE | 176.0417 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2016-11-19 01:00 | 35% | 20.3303 | 7.1156 | Accept | 20% | 18.975 | 3.795 | H2 | 2 | Stable | TRUE | 211.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-02-19 01:00 | 35% | 20.3303 | 7.1156 | Accept | 20% | 18.975 | 3.795 | H2 | 2 | Stable | TRUE | 303.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-02-19 01:00 | 35% | 20.3303 | 7.1156 | Accept | 20% | 18.975 | 3.795 | H2 | 2 | Stable | TRUE | 303.0417 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-04-21 | 35% | 20.3303 | 7.1156 | Accept | 20% | 18.975 | 3.795 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-005 | Project_028_Risk-005 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | EMC Testing | Person_070 | 2016-04-22 | 2017-04-21 | 35% | 20.3303 | 7.1156 | Accept | 20% | 18.975 | 3.795 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK033 | Project_079_RISK033 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Completion of Build in year 4 or 5 | Person_683 | 2018-09-30 01:00 | 2020-08-21 01:00 | 50% | 0.98209 | 0.49104 | -- | 50% | 0.98209 | 0.49104 | H3 | 3 | Stable | TRUE | 691 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK041 | Project_076_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Availability of prototype Hardware Dependency on projects | Person_474 | 2016-06-03 | 2019-10-22 01:00 | 80% | 2.4877 | 1.9901 | Reduce | 20% | 2.4877 | 0.49753 | H3 | 3 | -- | FALSE | 1236.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK041 | Project_076_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Availability of prototype Hardware Dependency on projects | Person_474 | 2016-06-03 | 2019-10-22 01:00 | 80% | 2.4877 | 1.9901 | Reduce | 20% | 2.4877 | 0.49753 | H3 | 3 | -- | FALSE | 1236.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK041 | Project_076_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Availability of prototype Hardware Dependency on projects | Person_152 | 2016-06-03 | 2019-10-22 01:00 | 80% | 2.4877 | 1.9901 | Reduce | 20% | 2.4877 | 0.49753 | H3 | 3 | -- | FALSE | 1236.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK041 | Project_076_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Availability of prototype Hardware Dependency on projects | Person_152 | 2016-06-03 | 2019-10-22 01:00 | 80% | 2.4877 | 1.9901 | Reduce | 20% | 2.4877 | 0.49753 | H3 | 3 | -- | FALSE | 1236.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK041 | Project_076_RISK041 | Threat | Project Contingency | Open | H2 | 2 |  | Availability of prototype Hardware Dependency on projects | Person_152 | 2016-06-03 | 2019-05-23 | 80% | 2.4877 | 1.9901 | Reduce | 20% | 2.4877 | 0.49753 | H3 | 3 | -- | FALSE | 1084 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK030 | Project_075_RISK030 | Threat | Project Contingency | Open | H2 | 2 |  | Ease of build in production | Person_449 | 2017-04-22 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 20% | 2.5311 | 0.50622 | H3 | 3 | -- | FALSE | 639.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK030 | Project_075_RISK030 | Threat | Project Contingency | Open | H2 | 2 |  | Ease of build in production | Person_449 | 2017-04-22 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 20% | 2.5311 | 0.50622 | H3 | 3 | -- | FALSE | 639.0417 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK030 | Project_075_RISK030 | Threat | Project Contingency | Open | H2 | 2 |  | Ease of build in production | Person_449 | 2017-04-22 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 20% | 2.5311 | 0.50622 | H3 | 3 | -- | FALSE | 639.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK030 | Project_075_RISK030 | Threat | Project Contingency | Open | H2 | 2 |  | Ease of build in production | Person_449 | 2017-04-22 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 20% | 2.5311 | 0.50622 | H3 | 3 | -- | FALSE | 639.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK030 | Project_075_RISK030 | Threat | Project Contingency | Open | H2 | 2 |  | Ease of build in production | Person_449 | 2017-04-22 | 2019-01-21 01:00 | 50% | 2.5311 | 1.2656 | Reduce | 20% | 2.5311 | 0.50622 | H3 | 3 | -- | FALSE | 639.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 2 |  | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 20% | 2.6071 | 0.52143 | Reduce | 20% | 2.6071 | 0.52143 | H3 | 3 | Stable | FALSE | 322 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 2 |  | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 20% | 2.6071 | 0.52143 | Reduce | 20% | 2.6071 | 0.52143 | H3 | 3 | Stable | FALSE | 322 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 2 |  | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 20% | 2.6071 | 0.52143 | Reduce | 20% | 2.6071 | 0.52143 | H3 | 3 | Stable | FALSE | 322 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 2 |  | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 20% | 2.6071 | 0.52143 | Reduce | 20% | 2.6071 | 0.52143 | H3 | 3 | Stable | FALSE | 322 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 2 |  | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 20% | 2.6071 | 0.52143 | Reduce | 20% | 2.6071 | 0.52143 | H3 | 3 | Stable | FALSE | 322 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 2 |  | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 20% | 2.6071 | 0.52143 | Reduce | 20% | 2.6071 | 0.52143 | H3 | 3 | Stable | FALSE | 322 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 2 |  | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 20% | 2.6071 | 0.52143 | Reduce | 20% | 2.6071 | 0.52143 | H3 | 3 | Stable | FALSE | 322 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK380 | Project_035_RISK380 | Threat | Project Contingency | Open | H2 | 2 |  | Data Throttling Algorithm | Person_699 | 2016-01-03 01:00 | 2016-11-20 01:00 | 20% | 2.6071 | 0.52143 | Reduce | 20% | 2.6071 | 0.52143 | H3 | 3 | Stable | FALSE | 322 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-013 | Project_062_Risk-013 | Threat | Project Contingency | Open | H2 | 2 |  | Unavailability of Network | Person_479 | 2017-07-21 | 2018-11-20 01:00 | 25% | 3.5555 | 0.88888 | Reduce | 15% | 3.5555 | 0.53333 | H3 | 3 | Improving | FALSE | 487.0417 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK399 | Project_038_RISK399 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Baseline Rationalisation | Person_151 | 2017-03-22 | 2017-05-15 | 40% | 1.3484 | 0.53935 | -- | 40% | 1.3484 | 0.53935 | H3 | 3 | Stable | TRUE | 54 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_092 | RISK016 | Project_092_RISK016 | Threat | Project Contingency | Open | H2 | 2 |  | Power Source for Converters | Person_169 | 2019-03-08 01:00 | 2019-10-22 01:00 | 30% | 3.6382 | 1.0914 | Reduce | 15% | 3.6382 | 0.54572 | H3 | 3 | -- | FALSE | 228 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK020 | Project_081_RISK020 | Threat | Project Contingency | Open | H3 | 3 |  | Travel Cost Increases | Person_260 | 2017-09-20 01:00 | 2021-09-20 01:00 | 30% | 1.8307 | 0.5492 | Reduce | 30% | 1.8307 | 0.5492 | H3 | 3 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software delays Impacting schedule | Person_692 | 2017-05-23 | 2019-07-21 | 33.3% | 11.5502 | 3.8462 | Reduce | 33.3% | 11.5502 | 3.8462 | H2 | 2 | Stable | TRUE | 789 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software delays Impacting schedule | Person_692 | 2017-05-23 | 2019-07-21 | 33.3% | 11.5502 | 3.8462 | Reduce | 33.3% | 11.5502 | 3.8462 | H2 | 2 | Stable | TRUE | 789 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_029 | Risk-RISK035 | Project_029_Risk-RISK035 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software delays Impacting schedule | Person_585 | 2017-10-21 01:00 | 2019-07-21 | 33.3% | 11.5502 | 3.8462 | Accept | 33.3% | 11.5502 | 3.8462 | H2 | 2 | Stable | TRUE | 637.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2017-12-19 01:00 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 88 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2020-03-21 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 910.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 | 2020-03-21 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 911 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2020-03-21 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 910.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 80% | 8.7765 | 7.0212 | Reduce | 45% | 8.7765 | 3.9494 | H1 | 1 | Stable | TRUE | 306.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK295 | Project_024_RISK295 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Insufficient Acceptance team experience | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 80% | 8.7765 | 7.0212 | Reduce | 45% | 8.7765 | 3.9494 | H1 | 1 | Stable | TRUE | 306.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 15% | 26.3497 | 3.9525 | Accept | 15% | 26.3497 | 3.9525 | H3 | 3 | Stable | TRUE | 1316 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 15% | 26.3497 | 3.9525 | Reduce | 15% | 26.3497 | 3.9525 | H3 | 3 | Improving | TRUE | 1316 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 15% | 26.3497 | 3.9525 | Reduce | 15% | 26.3497 | 3.9525 | H3 | 3 | Improving | TRUE | 1316 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 15% | 26.3497 | 3.9525 | Reduce | 15% | 26.3497 | 3.9525 | H3 | 3 | Improving | TRUE | 1316 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R006 | Project_016_Risk--R006 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Delay of processing | Person_306 | 2016-01-13 01:00 | 2019-08-21 01:00 | 15% | 26.3497 | 3.9525 | Reduce | 15% | 26.3497 | 3.9525 | H3 | 3 | Improving | TRUE | 1316 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 25% | 15.8141 | 3.9535 | Accept | 25% | 15.8141 | 3.9535 | H3 | 3 | Stable | TRUE | 91 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 25% | 15.8141 | 3.9535 | Accept | 25% | 15.8141 | 3.9535 | H3 | 3 | Stable | TRUE | 91 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 25% | 15.8141 | 3.9535 | Accept | 25% | 15.8141 | 3.9535 | H3 | 3 | Stable | TRUE | 91 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 25% | 15.8141 | 3.9535 | Accept | 25% | 15.8141 | 3.9535 | H3 | 3 | Stable | TRUE | 91 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 25% | 15.8141 | 3.9535 | Accept | 25% | 15.8141 | 3.9535 | H3 | 3 | Stable | TRUE | 91 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 25% | 15.8141 | 3.9535 | Accept | 25% | 15.8141 | 3.9535 | H3 | 3 | Stable | TRUE | 91 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 25% | 15.8141 | 3.9535 | Accept | 25% | 15.8141 | 3.9535 | H3 | 3 | Stable | TRUE | 91 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-034 | Project_008_Risk-034 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Post Contract completion activity lack of budget allocation | Person_565 | 2018-05-22 | 2018-08-21 | 25% | 15.8141 | 3.9535 | Accept | 25% | 15.8141 | 3.9535 | H3 | 3 | Stable | TRUE | 91 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 23:00 | 2020-03-21 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 911.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 22:00 | 2020-03-21 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 911.0833 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 23:00 | 2020-03-21 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 911.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2019-11-28 01:00 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 797 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK004 | Project_094_RISK004 | Threat | Project Contingency | Open | H3 | 3 | System Integration, Verification & Validation | Acceptance trial success criteria not achieved | Person_419 | 2019-11-21 | 2020-02-21 | 20% | 19.9676 | 3.9935 | Reduce | 20% | 19.9676 | 3.9935 | H3 | 3 | Stable | TRUE | 92 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | OPP001 | Project_094_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 | Supply chain | UPC savings | Person_198 | 2018-08-22 | 2019-09-20 | 20% | 19.9676 | 3.9935 | -- | 20% | 19.9676 | 3.9935 | H3 | 3 | Stable | TRUE | 394 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 22:00 | 2020-03-21 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 911.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK002 | Project_079_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2022-05-22 | 15% | 26.7842 | 4.0176 | Avoid | 15% | 26.7842 | 4.0176 | H3 | 3 | Stable | FALSE | 1916.9583 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK002 | Project_079_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2022-05-22 | 15% | 26.7842 | 4.0176 | Avoid | 15% | 26.7842 | 4.0176 | H3 | 3 | Stable | FALSE | 1916.9583 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK002 | Project_079_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2022-05-22 | 15% | 26.7842 | 4.0176 | Avoid | 15% | 26.7842 | 4.0176 | H3 | 3 | Stable | FALSE | 1916.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK002 | Project_079_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Security | Person_106 | 2017-02-20 01:00 | 2022-05-22 | 15% | 26.7842 | 4.0176 | Avoid | 15% | 26.7842 | 4.0176 | H3 | 3 | Stable | FALSE | 1916.9583 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 75% | 10.7184 | 8.0388 | Reduce | 75% | 5.3592 | 4.0194 | H1 | 1 | Worsening | TRUE | 547.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-20 | 2018-05-22 | 75% | 10.7184 | 8.0388 | Reduce | 75% | 5.3592 | 4.0194 | H1 | 1 | Worsening | TRUE | 548 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 75% | 10.7184 | 8.0388 | Reduce | 75% | 5.3592 | 4.0194 | H1 | 1 | Worsening | TRUE | 548.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 75% | 10.7184 | 8.0388 | Reduce | 75% | 5.3592 | 4.0194 | H1 | 1 | Worsening | TRUE | 548.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 75% | 10.7184 | 8.0388 | Reduce | 75% | 5.3592 | 4.0194 | H1 | 1 | Worsening | TRUE | 548.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R65 | Project_041_R65 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Procurement - Supply Chain Validity | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 75% | 10.7184 | 8.0388 | Reduce | 75% | 5.3592 | 4.0194 | H1 | 1 | Worsening | TRUE | 548.0833 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 | 2019-11-28 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 797 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-22 01:00 | 2019-11-28 01:00 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 797 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK009 | Project_065_RISK009 | Threat | Project Contingency | Open | H2 | 2 |  | Colour Representation in Video Image Distortion | Person_305 | 2017-09-21 23:00 | 2019-11-27 23:00 | 50% | 5.5323 | 2.7662 | Reduce | 10% | 5.5323 | 0.55323 | H3 | 3 | Stable | FALSE | 797 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 |  | Environment Conditions | Person_393 | 2012-04-19 | 2016-09-19 01:00 | 20% | 2.7943 | 0.55886 | Accept | 20% | 2.7943 | 0.55886 | H3 | 3 | Stable | TRUE | 1614.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-51 | Project_022_RISK-51 | Threat | Project Contingency | Open | H3 | 3 |  | Environment Conditions | Person_393 | 2012-04-19 | 2016-10-19 01:00 | 20% | 2.7943 | 0.55886 | Accept | 20% | 2.7943 | 0.55886 | H3 | 3 | Stable | TRUE | 1644.0417 |  | 1 | 1 | 0
2017-10-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H2 | 2 |  | Owned Test Equipment at Customer site | Person_324 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | FALSE | 1185.0417 |  | 1 | 0 | 1
2017-11-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H2 | 2 |  | Owned Test Equipment at Customer site | Person_324 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | FALSE | 1185.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H2 | 2 |  | Owned Test Equipment at Customer site | Person_324 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | FALSE | 1185.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H2 | 2 |  | Owned Test Equipment at Customer site | Person_324 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | FALSE | 1185.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK033 | Project_058_RISK033 | Threat | Project Contingency | Open | H3 | 3 |  | Test and Acceptance Review | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK032 | Project_058_RISK032 | Threat | Project Contingency | Open | H2 | 2 |  | Component Free Issue | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | FALSE | 1185.0417 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK034 | Project_058_RISK034 | Threat | Project Contingency | Open | H2 | 2 |  | Failure during integration/PTS | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Accept | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | FALSE | 1185.0417 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK033 | Project_058_RISK033 | Threat | Project Contingency | Open | H3 | 3 |  | Test and Acceptance Review | Person_072 | 2018-03-22 | 2019-11-15 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK034 | Project_058_RISK034 | Threat | Project Contingency | Open | H3 | 3 |  | Failure during integration/PTS | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Accept | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 | 2017-11-20 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP004 | Project_021_OPP004 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Opportunity to recover costs through efficiencies | Person_427 | 2016-09-15 01:00 | 2017-11-20 01:00 | 20% | 10.1533 | 2.0307 | -- | 40% | 10.1533 | 4.0613 | H2 | 2 | -- | TRUE | 431 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 50% | 10.1787 | 5.0893 | Reduce | 40% | 10.1787 | 4.0715 | H1 | 1 | Worsening | TRUE | 641.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK003 | Project_095_RISK003 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Level of repairs | Person_489 | 2018-07-22 | 2023-07-22 | 30% | 13.7227 | 4.1168 | -- | 30% | 13.7227 | 4.1168 | H2 | 2 | -- | TRUE | 1826 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-073 | Project_008_Risk-073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional Effort Required to Support Boundary case | Person_565 | 2016-03-23 | 2018-08-21 | 75% | 8.8382 | 6.6286 | Reduce | 75% | 5.5239 | 4.1429 | H2 | 2 | -- | TRUE | 881 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK075 | Project_076_RISK075 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Delay in SW completion due to safety workload | Person_152 | 2018-07-05 | 2019-05-16 | 50% | 16.5844 | 8.2922 | Reduce | 25% | 16.5844 | 4.1461 | H2 | 2 | Stable | TRUE | 315 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK112 | Project_065_RISK112 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Budget & Availability | Person_688 | 2016-03-23 | 2019-05-23 | 60% | 10.4206 | 6.2524 | Reduce | 40% | 10.4206 | 4.1682 | H2 | 2 | -- | TRUE | 1156 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Further Problem Report Growth | Person_351 | 2016-02-21 01:00 | 2017-08-20 01:00 | 40% | 41.7534 | 16.7013 | Reduce | 20% | 20.8767 | 4.1753 | H2 | 2 | -- | TRUE | 546 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Number of Problem Reports greater than planned | Person_351 | 2016-02-21 01:00 | 2017-08-20 01:00 | 40% | 41.7534 | 16.7013 | Reduce | 20% | 20.8767 | 4.1753 | H2 | 2 | -- | TRUE | 546 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Number of Problem Reports greater than planned | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 40% | 41.7534 | 16.7013 | Reduce | 20% | 20.8767 | 4.1753 | H2 | 2 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Number of Problem Reports greater than planned | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 40% | 41.7534 | 16.7013 | Reduce | 20% | 20.8767 | 4.1753 | H2 | 2 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Number of Problem Reports greater than planned | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 40% | 41.7534 | 16.7013 | Reduce | 20% | 20.8767 | 4.1753 | H2 | 2 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 40% | 41.7534 | 16.7013 | Reduce | 20% | 20.8767 | 4.1753 | H2 | 2 | Stable | TRUE | 549.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK238 | Project_024_RISK238 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Number of Problem Reports greater than planned | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 40% | 41.7534 | 16.7013 | Reduce | 20% | 20.8767 | 4.1753 | H2 | 2 | Stable | TRUE | 549.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 26% | 16.2047 | 4.2132 | Avoid | 26% | 16.2047 | 4.2132 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H3 | 3 |  | Owned Test Equipment at Customer site | Person_324 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK296 | Project_024_RISK296 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 8.5688 | 4.2844 | Accept | 50% | 8.5688 | 4.2844 | H1 | 1 | Worsening | TRUE | 306.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 8.5688 | 4.2844 | Accept | 50% | 8.5688 | 4.2844 | H1 | 1 | Worsening | TRUE | 306.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK291 | Project_024_RISK291 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | LoE Engineering support required post completion in addition to BCR | Person_351 | 2017-09-21 01:00 | 2018-07-25 | 50% | 8.5688 | 4.2844 | Accept | 50% | 8.5688 | 4.2844 | H1 | 1 | Worsening | TRUE | 306.9583 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK033 | Project_058_RISK033 | Threat | Project Contingency | Open | H3 | 3 |  | Test and Acceptance Review | Person_072 | 2018-03-22 | 2019-11-15 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK034 | Project_058_RISK034 | Threat | Project Contingency | Open | H3 | 3 |  | Failure during integration/PTS | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Accept | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H3 | 3 |  | Owned Test Equipment at Customer site | Person_324 | 2016-05-23 | 2019-08-21 01:00 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK033 | Project_058_RISK033 | Threat | Project Contingency | Open | H3 | 3 |  | Test and Acceptance Review | Person_072 | 2018-03-22 | 2019-11-15 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK034 | Project_058_RISK034 | Threat | Project Contingency | Open | H3 | 3 |  | Failure during integration/PTS | Person_414 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Accept | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H3 | 3 |  | Owned Test Equipment at Customer site | Person_511 | 2017-05-23 | 2019-07-21 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 789 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK033 | Project_058_RISK033 | Threat | Project Contingency | Open | H3 | 3 |  | Test and Acceptance Review | Person_072 | 2018-03-22 | 2019-11-15 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK034 | Project_058_RISK034 | Threat | Project Contingency | Open | H3 | 3 |  | Failure during integration/PTS | Person_414 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Accept | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H3 | 3 |  | Owned Test Equipment at Customer site | Person_511 | 2017-05-23 | 2019-07-21 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 789 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK033 | Project_058_RISK033 | Threat | Project Contingency | Open | H3 | 3 |  | Test and Acceptance Review | Person_072 | 2018-03-22 | 2019-11-15 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK034 | Project_058_RISK034 | Threat | Project Contingency | Open | H3 | 3 |  | Failure during integration/PTS | Person_414 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Accept | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H3 | 3 |  | Owned Test Equipment at Customer site | Person_511 | 2017-05-23 | 2019-07-21 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 789 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK033 | Project_058_RISK033 | Threat | Project Contingency | Open | H3 | 3 |  | Test and Acceptance Review | Person_072 | 2018-03-22 | 2019-11-15 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 21:00 | 2015-12-19 21:00 | 40% | 10.7826 | 4.3131 | Accept | 40% | 10.7826 | 4.3131 | H2 | 2 | Worsening | TRUE | 299 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 21:00 | 2015-12-19 21:00 | 40% | 10.7826 | 4.3131 | Accept | 40% | 10.7826 | 4.3131 | H2 | 2 | Worsening | TRUE | 299 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 20:00 | 2015-12-19 20:00 | 40% | 10.7826 | 4.3131 | Accept | 40% | 10.7826 | 4.3131 | H2 | 2 | Worsening | TRUE | 299 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-24 01:00 | 2016-06-23 | 40% | 10.7826 | 4.3131 | Accept | 40% | 10.7826 | 4.3131 | H2 | 2 | Worsening | TRUE | 484.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-24 | 2016-06-23 | 40% | 10.7826 | 4.3131 | Accept | 40% | 10.7826 | 4.3131 | H2 | 2 | Worsening | TRUE | 485 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 23:00 | 2016-06-23 | 40% | 10.7826 | 4.3131 | Accept | 40% | 10.7826 | 4.3131 | H2 | 2 | Worsening | TRUE | 485.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 22:00 | 2016-06-23 | 40% | 10.7826 | 4.3131 | Accept | 40% | 10.7826 | 4.3131 | H2 | 2 | Worsening | TRUE | 485.0833 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK118 | Project_037_RISK118 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Product does not deliver the inputs/depdencies required by the Project by the req'd dates | Person_330 | 2015-02-23 21:00 | 2016-06-23 | 40% | 10.7826 | 4.3131 | Accept | 40% | 10.7826 | 4.3131 | H2 | 2 | Worsening | TRUE | 485.125 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 20% | 21.6852 | 4.337 | -- | 20% | 21.6852 | 4.337 | H3 | 3 | Stable | TRUE | 1094.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 20% | 21.6852 | 4.337 | -- | 20% | 21.6852 | 4.337 | H3 | 3 | Stable | TRUE | 1094.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 20% | 21.6852 | 4.337 | -- | 20% | 21.6852 | 4.337 | H3 | 3 | Stable | TRUE | 1094.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 20% | 21.6852 | 4.337 | -- | 20% | 21.6852 | 4.337 | H3 | 3 | Stable | TRUE | 1094.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 20% | 21.6852 | 4.337 | -- | 20% | 21.6852 | 4.337 | H3 | 3 | Stable | TRUE | 1094.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 20% | 21.6852 | 4.337 | -- | 20% | 21.6852 | 4.337 | H3 | 3 | Stable | TRUE | 1094.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H3 | 3 | Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 20% | 21.6852 | 4.337 | -- | 20% | 21.6852 | 4.337 | H3 | 3 | Stable | TRUE | 1094.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 5% | 87.6137 | 4.3807 | Reduce | 5% | 87.6137 | 4.3807 | H3 | 3 | Stable | TRUE | 1673.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-03-22 | 5% | 87.6137 | 4.3807 | Reduce | 5% | 87.6137 | 4.3807 | H3 | 3 | Stable | TRUE | 1674 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-03-22 | 5% | 87.6137 | 4.3807 | Reduce | 5% | 87.6137 | 4.3807 | H3 | 3 | Stable | TRUE | 1674 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 | 2017-03-22 | 5% | 87.6137 | 4.3807 | Reduce | 5% | 87.6137 | 4.3807 | H3 | 3 | Stable | TRUE | 1674 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 5% | 87.6137 | 4.3807 | Reduce | 5% | 87.6137 | 4.3807 | H3 | 3 | Stable | TRUE | 1673.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 5% | 87.6137 | 4.3807 | Reduce | 5% | 87.6137 | 4.3807 | H3 | 3 | Stable | TRUE | 1673.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 5% | 87.6137 | 4.3807 | Reduce | 5% | 87.6137 | 4.3807 | H3 | 3 | Stable | TRUE | 1673.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-125 | Project_032_Risk-125 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Project Obsolesence | Person_406 | 2012-08-21 01:00 | 2017-03-22 | 5% | 87.6137 | 4.3807 | Reduce | 5% | 87.6137 | 4.3807 | H3 | 3 | Stable | TRUE | 1673.9583 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK034 | Project_058_RISK034 | Threat | Project Contingency | Open | H3 | 3 |  | Failure during integration/PTS | Person_414 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Accept | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H3 | 3 |  | Owned Test Equipment at Customer site | Person_511 | 2017-05-23 | 2019-07-21 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 789 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK033 | Project_058_RISK033 | Threat | Project Contingency | Open | H3 | 3 |  | Test and Acceptance Review | Person_072 | 2018-03-22 | 2019-11-15 01:00 | 20% | 2.9361 | 0.58721 | Reduce | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK034 | Project_058_RISK034 | Threat | Project Contingency | Open | H3 | 3 |  | Failure during integration/PTS | Person_414 | 2016-05-23 | 2019-08-21 01:00 | 20% | 2.9361 | 0.58721 | Accept | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK016 | Project_058_RISK016 | Threat | Project Contingency | Open | H3 | 3 |  | Owned Test Equipment at Customer site | Person_511 | 2017-05-23 | 2019-07-21 | 40% | 2.9361 | 1.1744 | Avoid | 20% | 2.9361 | 0.58721 | H3 | 3 | -- | TRUE | 789 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK008 | Project_001_RISK008 | Threat | Project Contingency | Open | H3 | 3 |  | Customer offered T&Cs not favourable to our | Person_446 | 2016-02-20 01:00 | 2016-06-19 | 30% | 4.0015 | 1.2004 | Reduce | 15% | 4.0015 | 0.60022 | H3 | 3 | -- | TRUE | 119.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK008 | Project_001_RISK008 | Threat | Project Contingency | Open | H3 | 3 |  | Customer offered T&Cs not favourable to our | Person_446 | 2016-02-20 01:00 | 2016-06-19 | 30% | 4.0015 | 1.2004 | Reduce | 15% | 4.0015 | 0.60022 | H3 | 3 | -- | TRUE | 119.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK008 | Project_001_RISK008 | Threat | Project Contingency | Open | H3 | 3 |  | Customer offered T&Cs not favourable to our | Person_446 | 2016-02-20 | 2016-06-19 | 30% | 4.0015 | 1.2004 | Reduce | 15% | 4.0015 | 0.60022 | H3 | 3 | -- | TRUE | 120 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-113 | Project_039_Risk-113 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Integrated System Delay | Person_343 | 2015-07-24 | 2016-07-20 | 50% | 21.6218 | 10.8109 | Reduce | 30% | 14.6673 | 4.4002 | H2 | 2 | Stable | TRUE | 362 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--113 | Project_100_Risk--113 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Supplier Risk | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 50% | 8.9416 | 4.4708 | -- | 50% | 8.9416 | 4.4708 | H2 | 2 | -- | TRUE | 1094 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK008 | Project_001_RISK008 | Threat | Project Contingency | Open | H3 | 3 |  | Customer offered T&Cs not favourable to our | Person_446 | 2016-02-19 23:00 | 2016-06-19 | 30% | 4.0015 | 1.2004 | Reduce | 15% | 4.0015 | 0.60022 | H3 | 3 | -- | TRUE | 120.0417 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK008 | Project_001_RISK008 | Threat | Project Contingency | Open | H3 | 3 |  | Customer offered T&Cs not favourable to our | Person_446 | 2016-02-19 22:00 | 2016-06-19 | 30% | 4.0015 | 1.2004 | Reduce | 15% | 4.0015 | 0.60022 | H3 | 3 | -- | TRUE | 120.0833 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_001 | RISK008 | Project_001_RISK008 | Threat | Project Contingency | Open | H3 | 3 |  | Customer offered T&Cs not favourable to our | Person_446 | 2016-02-19 21:00 | 2016-06-19 | 30% | 4.0015 | 1.2004 | Reduce | 15% | 4.0015 | 0.60022 | H3 | 3 | -- | TRUE | 120.125 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R022 | Project_044_Risk-R022 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_763 | 2018-11-20 01:00 | 2020-01-20 01:00 | 10% | 6.0365 | 0.60365 | Accept | 10% | 6.0365 | 0.60365 | H3 | 3 | Stable | FALSE | 426 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK021 | Project_049_RISK021 | Threat | Project Contingency | Open | H2 | 2 | Customers | Customer Personnel Change | Person_218 | 2017-08-23 01:00 | 2019-11-18 01:00 | 60% | 8.9745 | 5.3847 | Reduce | 50% | 8.9745 | 4.4872 | H2 | 2 | -- | TRUE | 817 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 30% | 26.9674 | 8.0902 | Avoid | 30% | 14.9819 | 4.4946 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 30% | 26.9674 | 8.0902 | Avoid | 30% | 14.9819 | 4.4946 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 30% | 26.9674 | 8.0902 | Avoid | 30% | 14.9819 | 4.4946 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 30% | 26.9674 | 8.0902 | Avoid | 30% | 14.9819 | 4.4946 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 30% | 26.9674 | 8.0902 | Avoid | 30% | 14.9819 | 4.4946 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 30% | 26.9674 | 8.0902 | Avoid | 30% | 14.9819 | 4.4946 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 30% | 26.9674 | 8.0902 | Avoid | 30% | 14.9819 | 4.4946 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK219 | Project_038_RISK219 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Difficulty delivering Industrial Participation (IP) Obligations | Person_330 | 2016-06-23 | 2017-05-22 | 30% | 26.9674 | 8.0902 | Avoid | 30% | 14.9819 | 4.4946 | H2 | 2 | Stable | TRUE | 333 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-20 23:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1216.9583 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-20 23:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1216.9583 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-20 22:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1216.9167 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-20 22:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1216.9167 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK294 | Project_065_RISK294 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | System Signature effect | Person_038 | 2020-05-22 | 2021-05-22 | 40% | 11.5024 | 4.601 | Accept | 40% | 11.5024 | 4.601 | H2 | 2 | -- | TRUE | 365 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-12-03 01:00 | 2021-01-20 01:00 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-03 01:00 | 2021-01-20 01:00 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-03 | 2021-01-20 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-03 | 2021-01-20 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 23:00 | 2021-01-19 23:00 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 23:00 | 2021-01-19 23:00 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 23:00 | 2021-01-19 23:00 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 21:00 | 2021-01-19 21:00 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK025 | Project_017_RISK025 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_547 | 2016-12-02 20:00 | 2021-01-19 20:00 | 50% | 15.9667 | 7.9834 | Reduce | 30% | 15.4517 | 4.6355 | H2 | 2 | -- | TRUE | 1509 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R047 | Project_085_R047 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Separation Issues | Person_042 | 2020-10-21 | 2022-05-22 | 50% | 16.0051 | 8.0026 | Reduce | 29% | 16.0051 | 4.6415 | H2 | 2 | -- | TRUE | 578 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-202 | Project_027_Risk-202 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Changes in Safety Legislation | Person_695 | 2014-08-22 01:00 | 2017-08-19 01:00 | 100% | 18.5937 | 18.5937 | Reduce | 25% | 18.5937 | 4.6484 | H2 | 2 | -- | TRUE | 1093 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-202 | Project_027_Risk-202 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Changes in Safety Legislation | Person_695 | 2014-08-22 01:00 | 2017-08-19 01:00 | 100% | 18.5937 | 18.5937 | Reduce | 25% | 18.5937 | 4.6484 | H2 | 2 | -- | TRUE | 1093 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-202 | Project_027_Risk-202 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Changes in Safety Legislation | Person_695 | 2014-08-22 01:00 | 2017-08-19 01:00 | 100% | 18.5937 | 18.5937 | Reduce | 25% | 18.5937 | 4.6484 | H2 | 2 | -- | TRUE | 1093 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-202 | Project_027_Risk-202 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Changes in Safety Legislation | Person_695 | 2014-08-22 01:00 | 2017-08-19 01:00 | 100% | 18.5937 | 18.5937 | Reduce | 25% | 18.5937 | 4.6484 | H2 | 2 | -- | TRUE | 1093 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-202 | Project_027_Risk-202 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Changes in Safety Legislation | Person_695 | 2014-08-22 01:00 | 2017-08-19 01:00 | 100% | 18.5937 | 18.5937 | Reduce | 25% | 18.5937 | 4.6484 | H2 | 2 | -- | TRUE | 1093 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-202 | Project_027_Risk-202 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Changes in Safety Legislation | Person_695 | 2014-08-22 01:00 | 2017-08-19 01:00 | 100% | 18.5937 | 18.5937 | Reduce | 25% | 18.5937 | 4.6484 | H2 | 2 | -- | TRUE | 1093 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-202 | Project_027_Risk-202 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Changes in Safety Legislation | Person_695 | 2014-08-22 01:00 | 2017-08-19 01:00 | 100% | 18.5937 | 18.5937 | Reduce | 25% | 18.5937 | 4.6484 | H2 | 2 | -- | TRUE | 1093 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_027 | Risk-202 | Project_027_Risk-202 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Changes in Safety Legislation | Person_695 | 2014-08-22 01:00 | 2017-08-19 01:00 | 100% | 18.5937 | 18.5937 | Reduce | 25% | 18.5937 | 4.6484 | H2 | 2 | -- | TRUE | 1093 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-05-23 | 2017-05-22 | 30% | 33.7558 | 10.1267 | Reduce | 20% | 23.3694 | 4.6739 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-10-21 01:00 | 2017-08-20 01:00 | 30% | 33.7558 | 10.1267 | Reduce | 20% | 23.3694 | 4.6739 | H2 | 2 | Stable | TRUE | 303 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 30% | 33.7558 | 10.1267 | Reduce | 20% | 23.3694 | 4.6739 | H2 | 2 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 30% | 33.7558 | 10.1267 | Reduce | 20% | 23.3694 | 4.6739 | H2 | 2 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 30% | 33.7558 | 10.1267 | Reduce | 20% | 23.3694 | 4.6739 | H2 | 2 | Stable | TRUE | 641.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-064 | Project_008_Risk-064 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional Tech Pubs Headcount needed to clear Backlog | Person_565 | 2015-05-24 | 2017-03-22 | 70% | 9.3748 | 6.5624 | Reduce | 50% | 9.3748 | 4.6874 | H2 | 2 | -- | TRUE | 668 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-064 | Project_008_Risk-064 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional Tech Pubs Headcount needed to clear Backlog | Person_565 | 2015-05-24 | 2017-03-22 | 50% | 9.3748 | 4.6874 | Accept | 50% | 9.3748 | 4.6874 | H2 | 2 | -- | TRUE | 668 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 30% | 15.6782 | 4.7035 | Transfer | 30% | 15.6782 | 4.7035 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 | 2017-07-20 | 30% | 15.6782 | 4.7035 | Transfer | 30% | 15.6782 | 4.7035 | H2 | 2 | Stable | TRUE | 1794 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 | 2017-07-20 | 30% | 15.6782 | 4.7035 | Transfer | 30% | 15.6782 | 4.7035 | H2 | 2 | Stable | TRUE | 1794 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 | 2017-07-20 | 30% | 15.6782 | 4.7035 | Transfer | 30% | 15.6782 | 4.7035 | H2 | 2 | Stable | TRUE | 1794 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 30% | 15.6782 | 4.7035 | Transfer | 30% | 15.6782 | 4.7035 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 30% | 15.6782 | 4.7035 | Transfer | 30% | 15.6782 | 4.7035 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-131 | Project_032_Risk-131 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | SubSystem Failure | Person_360 | 2012-08-21 01:00 | 2017-07-20 | 30% | 15.6782 | 4.7035 | Transfer | 30% | 15.6782 | 4.7035 | H2 | 2 | Stable | TRUE | 1793.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK003 | Project_094_RISK003 | Threat | Project Contingency | Open | H3 | 3 | Hardware/Software development | Issues experienced during system integration | Person_198 | 2019-08-22 | 2020-11-20 | 30% | 15.974 | 4.7922 | Reduce | 30% | 15.974 | 4.7922 | H3 | 3 | Stable | TRUE | 456 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-035 | Project_026_Risk-035 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Interfacing between system elements more complex than anticipated | Person_385 | 2017-05-23 | 2018-08-04 | 50% | 16.1164 | 8.0582 | Reduce | 30% | 16.1164 | 4.8349 | H2 | 2 | Worsening | TRUE | 438 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK008 | Project_099_RISK008 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Acceptance required | Person_366 | 2018-03-22 | 2018-12-20 01:00 | 20% | 24.1841 | 4.8368 | Reduce | 20% | 24.1841 | 4.8368 | H3 | 3 | -- | FALSE | 273.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 30% | 38.17 | 11.451 | Reduce | 25% | 19.4745 | 4.8686 | H2 | 2 | Stable | TRUE | 549.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK213 | Project_024_RISK213 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Rigs requireaccreditation as "Special to Type" Test equipment | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 30% | 38.17 | 11.451 | Reduce | 25% | 19.4745 | 4.8686 | H2 | 2 | Stable | TRUE | 549.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-20 22:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1216.9167 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-20 22:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1216.9167 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-21 01:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1217.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048- | Project_065_RISK048- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-20 23:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1216.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK048-Risk- | Project_065_RISK048-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Reliability Risk of using 26 gauge wire during warranty period. | Person_559 | 2017-05-23 | 2020-09-20 23:00 | 20% | 6.298 | 1.2596 | Reduce | 10% | 6.298 | 0.6298 | H3 | 3 | -- | FALSE | 1216.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK013 | Project_094_RISK013 | Threat | Project Contingency | Open | H3 | 3 | Other Risks and Contingencies | Other risks | Person_198 | 2018-08-22 | 2022-05-22 | 10% | 49.1298 | 4.913 | Reduce | 10% | 49.1298 | 4.913 | H3 | 3 | Stable | TRUE | 1369 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-21 01:00 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 973.9583 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-21 01:00 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 973.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-21 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 974 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-20 23:00 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 974.0417 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-20 22:00 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 974.0833 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-21 01:00 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 973.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-20 22:00 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 974.0833 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-21 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 974 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-21 01:00 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 973.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK099 | Project_065_RISK099 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Development Hardware Not Available When Needed | Person_550 | 2016-08-20 23:00 | 2019-04-22 | 30% | 65.9211 | 19.7763 | Reduce | 15% | 32.9606 | 4.9441 | H3 | 3 | -- | FALSE | 974.0417 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 |  | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-08-13 | 20% | 3.1633 | 0.63267 | Accept | 20% | 3.1633 | 0.63267 | H3 | 3 | Stable | TRUE | 416 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 |  | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-08-13 | 20% | 3.1633 | 0.63267 | Accept | 20% | 3.1633 | 0.63267 | H3 | 3 | Stable | TRUE | 416 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 |  | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-08-20 01:00 | 20% | 3.1633 | 0.63267 | Accept | 20% | 3.1633 | 0.63267 | H3 | 3 | Stable | TRUE | 423.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK090 | Project_076_RISK090 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Reduction in LoE as project tapers off during final year | Person_628 | 2018-09-21 01:00 | 2019-05-16 | 50% | 9.9506 | 4.9753 | Reject | 50% | 9.9506 | 4.9753 | H2 | 2 | Stable | TRUE | 236.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rejected concessions | Person_766 | 2016-02-11 | 2017-02-19 | 50% | 36.8056 | 18.4028 | Reduce | 15% | 33.5499 | 5.0325 | H2 | 2 | Worsening | TRUE | 374 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Rejected concessions | Person_766 | 2016-02-10 23:00 | 2017-02-18 23:00 | 50% | 36.8056 | 18.4028 | Reduce | 15% | 33.5499 | 5.0325 | H2 | 2 | Worsening | TRUE | 374 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 |  | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-10-21 01:00 | 20% | 3.1633 | 0.63267 | Accept | 20% | 3.1633 | 0.63267 | H3 | 3 | Stable | TRUE | 485.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 |  | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-10-21 01:00 | 20% | 3.1633 | 0.63267 | Accept | 20% | 3.1633 | 0.63267 | H3 | 3 | Stable | TRUE | 485.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 |  | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-10-21 01:00 | 20% | 3.1633 | 0.63267 | Accept | 20% | 3.1633 | 0.63267 | H3 | 3 | Stable | TRUE | 485.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK312 | Project_035_RISK312 | Threat | Project Contingency | Open | H3 | 3 |  | Audio Performance inadequate | Person_303 | 2015-06-24 | 2016-10-21 01:00 | 20% | 3.1633 | 0.63267 | Accept | 20% | 3.1633 | 0.63267 | H3 | 3 | Stable | TRUE | 485.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK011 | Project_081_RISK011 | Threat | Project Contingency | Open | H3 | 3 |  | Additional quantities of spares/material/STTE requested by customer | Person_260 | 2017-07-21 | 2019-07-22 | 10% | 6.3707 | 0.63707 | Reduce | 10% | 6.3707 | 0.63707 | H3 | 3 | Stable | TRUE | 731 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_037 | RISK249 | Project_037_RISK249 | Threat | Project Contingency | Open | H2 | 2 |  | Increase in Installation time in country | Person_330 | 2016-03-23 | 2017-01-19 01:00 | 40% | 3.187 | 1.2748 | Reduce | 20% | 3.187 | 0.6374 | H3 | 3 | Stable | FALSE | 302.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2021-04-22 | 2024-04-22 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 1096 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2013-02-20 01:00 | 2023-02-20 01:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2021-04-22 | 2024-04-22 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2013-02-20 01:00 | 2023-02-20 01:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2021-04-22 | 2024-04-22 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2013-02-20 | 2023-02-20 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2021-04-22 | 2024-04-22 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2013-02-20 01:00 | 2023-02-20 01:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2021-04-22 | 2024-04-22 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2013-02-19 23:00 | 2023-02-19 23:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2021-04-22 | 2024-04-22 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2013-02-19 22:00 | 2023-02-19 22:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2021-04-22 | 2024-04-22 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2013-02-19 23:00 | 2023-02-19 23:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 3652 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 698 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 698 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 698 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 698 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 698 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 698 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 698 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_179 | 2016-05-23 | 2018-09-19 01:00 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 849.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_047 | 2016-05-23 | 2018-04-21 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 698 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_179 | 2016-05-23 | 2018-09-19 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 849 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_179 | 2016-05-23 | 2018-09-19 01:00 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 849.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK064 | Project_065_RISK064 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Power Supply - Motor Controller Interface | Person_179 | 2016-05-23 | 2018-09-18 23:00 | 50% | 25.3543 | 12.6771 | Reduce | 20% | 25.3543 | 5.0709 | H3 | 3 | Stable | FALSE | 848.9583 |  | 1 | 0 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 50% | 10.1787 | 5.0893 | Reduce | 50% | 10.1787 | 5.0893 | H1 | 1 | Worsening | TRUE | 549.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK286 | Project_024_RISK286 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Requirement sell off more difficult than expected | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 50% | 10.1787 | 5.0893 | Reduce | 50% | 10.1787 | 5.0893 | H1 | 1 | Worsening | TRUE | 549.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_160 | 2022-05-14 | 2023-02-18 01:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 280.0417 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_160 | 2020-07-19 | 2020-08-15 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 27 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2021-04-22 | 2024-04-22 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 1096 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_300 | 2013-02-19 22:00 | 2023-02-19 22:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 3652 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_160 | 2022-05-14 | 2023-02-18 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 280 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_160 | 2020-07-19 | 2020-08-15 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 27 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_160 | 2022-05-14 | 2023-02-18 01:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 280.0417 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_160 | 2020-07-19 | 2020-08-15 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 27 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304-Risk- | Project_065_RISK304-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_160 | 2022-05-14 | 2023-02-17 23:00 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 279.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK304- | Project_065_RISK304- | Threat | Project Contingency | Open | H2 | 2 |  | Simulation equipment delivered through IVQ does not replicate real life leading to performance issue | Person_160 | 2020-07-19 | 2020-08-15 | 20% | 3.2479 | 0.64958 | Accept | 20% | 3.2479 | 0.64958 | H3 | 3 | -- | FALSE | 27 |  | 1 | 1 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK071 | Project_076_RISK071 | Threat | Project Contingency | Open | H3 | 3 |  | System development of components | Person_474 | 2018-03-23 | 2018-11-20 01:00 | 80% | 6.6337 | 5.307 | Reduce | 10% | 6.6337 | 0.66337 | H3 | 3 | -- | TRUE | 242.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK071 | Project_076_RISK071 | Threat | Project Contingency | Open | H3 | 3 |  | System development of components | Person_474 | 2018-03-23 | 2018-11-20 01:00 | 80% | 6.6337 | 5.307 | Reduce | 10% | 6.6337 | 0.66337 | H3 | 3 | -- | TRUE | 242.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK071 | Project_076_RISK071 | Threat | Project Contingency | Open | H3 | 3 |  | System development of components | Person_474 | 2018-03-23 | 2018-11-20 01:00 | 80% | 6.6337 | 5.307 | Reduce | 10% | 6.6337 | 0.66337 | H3 | 3 | Stable | TRUE | 242.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK071 | Project_076_RISK071 | Threat | Project Contingency | Open | H3 | 3 |  | System development of components | Person_474 | 2018-03-23 | 2018-11-20 01:00 | 80% | 6.6337 | 5.307 | Reduce | 10% | 6.6337 | 0.66337 | H3 | 3 | Stable | TRUE | 242.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_018 | Project_075 | RISK046 | Project_075_RISK046 | Threat | Project Contingency | Open | H2 | 2 |  | Over temperature causing damage due to misalignment | Person_449 | 2017-12-20 01:00 | 2018-07-21 | 100% | 28.686 | 28.686 | Reduce | 20% | 3.3748 | 0.67497 | H3 | 3 | -- | FALSE | 212.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_062 | Risk-023 | Project_062_Risk-023 | Threat | Project Contingency | Open | H2 | 2 |  | Change In Security Boundary | Person_031 | 2017-07-21 | 2019-02-21 01:00 | 30% | 4.6013 | 1.3804 | Reduce | 15% | 4.6013 | 0.69019 | H3 | 3 | Stable | FALSE | 580.0417 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-20 | 2019-01-23 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-19 23:00 | 2019-01-22 23:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-19 22:00 | 2019-01-22 22:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-19 23:00 | 2019-01-22 23:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_418 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-19 22:00 | 2019-01-22 22:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_418 | 2016-10-20 | 2019-01-23 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_418 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK232 | Project_038_RISK232 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Integration more complex than expected | Person_531 | 2015-11-21 01:00 | 2016-08-21 01:00 | 30% | 27.7165 | 8.3149 | Reduce | 18.5% | 27.7165 | 5.1275 | H2 | 2 | Improving | TRUE | 274 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK232 | Project_038_RISK232 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Integration more complex than expected | Person_531 | 2015-11-21 01:00 | 2016-08-21 01:00 | 30% | 27.7165 | 8.3149 | Reduce | 18.5% | 27.7165 | 5.1275 | H2 | 2 | Improving | TRUE | 274 |  | 1 | 0 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2017-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2017-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2017-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2017-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2017-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2017-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-RO21 | Project_021_Risk-RO21 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2016-02-11 01:00 | 2017-12-20 01:00 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 678 |  | 1 | 0 | 0
2018-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 0 | 0
2018-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 0 | 0
2018-07-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_766 | 2018-08-22 01:00 | 2019-03-23 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Worsening | TRUE | 212.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk--07 | Project_021_Risk--07 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Rejected concessions | Person_615 | 2018-08-22 01:00 | 2019-03-23 | 60% | 17.2826 | 10.3696 | Reduce | 30% | 17.2826 | 5.1848 | H2 | 2 | Improving | TRUE | 212.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 50% | 10.5249 | 5.2625 | Reduce | 50% | 10.5249 | 5.2625 | H2 | 2 | Worsening | TRUE | 1497 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 50% | 10.5249 | 5.2625 | Reduce | 50% | 10.5249 | 5.2625 | H2 | 2 | Worsening | TRUE | 1497 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 50% | 10.5249 | 5.2625 | Reduce | 50% | 10.5249 | 5.2625 | H2 | 2 | Worsening | TRUE | 1497 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 50% | 10.5249 | 5.2625 | Reduce | 50% | 10.5249 | 5.2625 | H2 | 2 | Stable | TRUE | 1497 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 50% | 10.5249 | 5.2625 | Reduce | 50% | 10.5249 | 5.2625 | H2 | 2 | Stable | TRUE | 1497 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-007 | Project_026_Risk-007 | Threat | Project Contingency | Open | H2 | 2 | Customers | Additional requests for information and attendance at meetings | Person_264 | 2014-11-21 01:00 | 2018-12-27 01:00 | 50% | 10.5249 | 5.2625 | Reduce | 50% | 10.5249 | 5.2625 | H2 | 2 | Stable | TRUE | 1497 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041-Risk- | Project_065_RISK041-Risk- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_418 | 2016-10-19 23:00 | 2019-01-22 23:00 | 25% | 8.5342 | 2.1336 | Reduce | 10% | 6.9065 | 0.69065 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_008 | Project_044 | Risk-R024 | Project_044_Risk-R024 | Threat | Project Contingency | Open | H2 | 2 |  | Receiver System Performance | Person_763 | 2017-11-20 01:00 | 2019-11-21 01:00 | 20% | 4.8292 | 0.96584 | Accept | 15% | 4.8292 | 0.72438 | H3 | 3 | Stable | FALSE | 731 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_594 | 2016-09-08 01:00 | 2020-02-14 01:00 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 1254 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_594 | 2016-09-08 01:00 | 2020-02-14 01:00 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 1254 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_594 | 2016-09-08 | 2020-02-14 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 1254 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_594 | 2016-09-07 23:00 | 2020-02-13 23:00 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 1254 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_594 | 2016-09-07 22:00 | 2020-02-13 22:00 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 1254 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_594 | 2016-09-07 23:00 | 2020-02-13 23:00 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 1254 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_160 | 2020-05-23 | 2021-07-20 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 423 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_594 | 2016-09-07 22:00 | 2020-02-13 22:00 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 1254 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_160 | 2020-05-23 | 2021-07-20 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 423 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_160 | 2020-05-23 | 2021-07-20 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 423 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK088 | Project_065_RISK088 | Threat | Project Contingency | Open | H3 | 3 |  | Connector Results In System Failure/Unreliable Performance | Person_160 | 2020-05-23 | 2021-07-20 | 60% | 4.9897 | 2.9938 | Reduce | 15% | 4.9897 | 0.74846 | H3 | 3 | -- | TRUE | 423 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK029 | Project_058_RISK029 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence (general) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 20% | 3.9148 | 0.78295 | Reduce | 20% | 3.9148 | 0.78295 | H3 | 3 | -- | FALSE | 1185.0417 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK029 | Project_058_RISK029 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence (general) | Person_294 | 2018-03-14 01:00 | 2018-11-07 01:00 | 60% | 3.9148 | 2.3489 | Reduce | 20% | 3.9148 | 0.78295 | H3 | 3 | -- | TRUE | 238 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK029 | Project_058_RISK029 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence (general) | Person_294 | 2018-03-14 01:00 | 2018-11-07 01:00 | 60% | 3.9148 | 2.3489 | Reduce | 20% | 3.9148 | 0.78295 | H3 | 3 | -- | TRUE | 238 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK029 | Project_058_RISK029 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence (general) | Person_294 | 2018-03-14 01:00 | 2018-11-07 01:00 | 60% | 3.9148 | 2.3489 | Reduce | 20% | 3.9148 | 0.78295 | H3 | 3 | -- | TRUE | 238 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK029 | Project_058_RISK029 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence (general) | Person_294 | 2018-03-14 01:00 | 2018-11-07 01:00 | 60% | 3.9148 | 2.3489 | Reduce | 20% | 3.9148 | 0.78295 | H3 | 3 | -- | TRUE | 238 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK029 | Project_058_RISK029 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence (general) | Person_294 | 2018-03-14 01:00 | 2018-11-07 01:00 | 60% | 3.9148 | 2.3489 | Reduce | 20% | 3.9148 | 0.78295 | H3 | 3 | -- | TRUE | 238 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK029 | Project_058_RISK029 | Threat | Project Contingency | Open | H3 | 3 |  | Obsolescence (general) | Person_294 | 2018-03-14 01:00 | 2018-11-07 01:00 | 60% | 3.9148 | 2.3489 | Reduce | 20% | 3.9148 | 0.78295 | H3 | 3 | -- | TRUE | 238 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK080 | Project_076_RISK080 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Additional technical support required to supplier | Person_621 | 2018-09-21 01:00 | 2019-05-23 | 50% | 10.7798 | 5.3899 | Accept | 50% | 10.7798 | 5.3899 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK081 | Project_076_RISK081 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | New Safety tagged requirements are defined, increasing safety workload | Person_771 | 2018-09-21 01:00 | 2019-05-23 | 40% | 13.5163 | 5.4065 | Accept | 40% | 13.5163 | 5.4065 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK029 | Project_058_RISK029 | Threat | Project Contingency | Open | H2 | 2 |  | Obsolescence (general) | Person_294 | 2018-03-14 01:00 | 2018-11-07 01:00 | 60% | 3.9148 | 2.3489 | Reduce | 20% | 3.9148 | 0.78295 | H3 | 3 | -- | FALSE | 238 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK052 | Project_076_RISK052 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Cost reduction on non software work packages | Person_474 | 2018-03-23 | 2018-06-22 | 20% | 3.9802 | 0.79605 | Reject | 20% | 3.9802 | 0.79605 | H3 | 3 | -- | TRUE | 91 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK024 | Project_081_RISK024 | Threat | Project Contingency | Open | H2 | 2 |  | Customer- Training | Person_115 | 2017-09-27 01:00 | 2021-11-27 01:00 | 60% | 1.3425 | 0.80549 | Reduce | 60% | 1.3425 | 0.80549 | H3 | 3 | Stable | FALSE | 1522 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-19 | 2020-11-20 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-18 23:00 | 2020-11-19 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-18 22:00 | 2020-11-19 22:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-18 23:00 | 2020-11-19 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_418 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-18 22:00 | 2020-11-19 22:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_418 | 2016-10-19 | 2020-11-20 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_418 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045-Risk- | Project_065_RISK045-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_418 | 2016-10-18 23:00 | 2020-11-19 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 15% | 5.5577 | 0.83365 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 2 |  | Platform Acceptance | Person_500 | 2015-11-21 | 2017-01-20 | 35% | 4.2355 | 1.4824 | Reduce | 20% | 4.2355 | 0.8471 | H3 | 3 | Stable | FALSE | 426 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 2 |  | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-01-20 01:00 | 35% | 4.2355 | 1.4824 | Reduce | 20% | 4.2355 | 0.8471 | H3 | 3 | Stable | FALSE | 426 |  | 1 | 0 | 1
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 2 |  | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-04-21 | 35% | 4.2355 | 1.4824 | Reduce | 20% | 4.2355 | 0.8471 | H3 | 3 | Stable | FALSE | 516.9583 |  | 1 | 0 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 2 |  | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-04-21 | 35% | 4.2355 | 1.4824 | Reduce | 20% | 4.2355 | 0.8471 | H3 | 3 | Stable | FALSE | 516.9583 |  | 1 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 2 |  | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-04-21 | 35% | 4.2355 | 1.4824 | Reduce | 20% | 4.2355 | 0.8471 | H3 | 3 | Stable | FALSE | 516.9583 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_028 | Risk-010 | Project_028_Risk-010 | Threat | Project Contingency | Open | H2 | 2 |  | Platform Acceptance | Person_500 | 2015-11-21 01:00 | 2017-04-21 | 35% | 4.2355 | 1.4824 | Reduce | 20% | 4.2355 | 0.8471 | H3 | 3 | Stable | FALSE | 516.9583 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK055 | Project_058_RISK055 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Source Inspection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 30% | 2.9361 | 0.88082 | -- | 30% | 2.9361 | 0.88082 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK055 | Project_058_RISK055 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Source Inspection | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 30% | 2.9361 | 0.88082 | -- | 30% | 2.9361 | 0.88082 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK002 | Project_095_RISK002 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Greater number of failure investigations than anticipated | Person_489 | 2018-07-22 | 2023-07-22 | 30% | 18.4445 | 5.5334 | -- | 30% | 18.4445 | 5.5334 | H2 | 2 | -- | TRUE | 1826 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK015 | Project_081_RISK015 | Threat | Management Contingency | Open | H3 | 3 |  | Our being liable for freight costs. | Person_260 | 2018-03-23 | 2021-09-20 01:00 | 30% | 3.0511 | 0.91533 | Reduce | 30% | 3.0511 | 0.91533 | H3 | 3 | Stable | TRUE | 1277.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK016 | Project_081_RISK016 | Threat | Project Contingency | Open | H3 | 3 |  | Additional visit support requested by Customer/Supplier | Person_260 | 2017-10-21 01:00 | 2021-09-20 01:00 | 40% | 2.331 | 0.93242 | Reduce | 40% | 2.331 | 0.93242 | H3 | 3 | Stable | TRUE | 1430 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 911 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 23:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 910.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 22:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 910.9167 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 23:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 910.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 22:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 910.9167 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 911 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-21 01:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK017 | Project_065_RISK017 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Unplanned tasks demanded of the project | Person_563 | 2015-06-24 | 2017-12-20 23:00 | 80% | 35.2369 | 28.1895 | Reduce | 30% | 18.4979 | 5.5494 | H2 | 2 | Stable | TRUE | 910.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-035 | Project_077_T-035 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Cost of succession planning | Person_545 | 2018-04-22 | 2021-04-22 | 50% | 6.7392 | 3.3696 | -- | 50% | 11.2545 | 5.6273 | H2 | 2 | Stable | TRUE | 1096 |  | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 30% | 29.4599 | 8.838 | Accept | 30% | 18.7882 | 5.6365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 30% | 29.4599 | 8.838 | Accept | 30% | 18.7882 | 5.6365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 30% | 29.4599 | 8.838 | Accept | 30% | 18.7882 | 5.6365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 30% | 29.4599 | 8.838 | Accept | 30% | 18.7882 | 5.6365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 30% | 29.4599 | 8.838 | Accept | 30% | 18.7882 | 5.6365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 30% | 29.4599 | 8.838 | Accept | 30% | 18.7882 | 5.6365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | Risk001 | Project_042_Risk001 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Obsolescence | Person_455 | 2016-05-23 | 2020-05-23 | 30% | 29.4599 | 8.838 | Accept | 30% | 18.7882 | 5.6365 | H2 | 2 | Stable | TRUE | 1461 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK155 | Project_024_RISK155 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Late availability of Parameters | Person_534 | 2016-03-23 | 2016-09-11 01:00 | 30% | 4.1113 | 1.2334 | Reduce | 30% | 19.0417 | 5.7125 | H1 | 1 | Stable | TRUE | 172.0417 |  | 0 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-151 | Project_020_Risk-151 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Reduced PM loading from final year | Person_575 | 2017-08-21 01:00 | 2018-05-21 | 60% | 1.5745 | 0.94468 | Exploit | 60% | 1.5745 | 0.94468 | H3 | 3 | -- | TRUE | 272.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK009 | Project_099_RISK009 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Increased cost due to Supplier Quote Revalidation | Person_243 | 2017-09-21 01:00 | 2019-01-27 01:00 | 60% | 14.2932 | 8.5759 | Reduce | 40% | 14.2932 | 5.7173 | H2 | 2 | -- | TRUE | 493 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 40% | 14.541 | 5.8164 | Accept | 40% | 14.541 | 5.8164 | H1 | 1 | Stable | TRUE | 211.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 40% | 14.541 | 5.8164 | Accept | 40% | 14.541 | 5.8164 | H1 | 1 | Stable | TRUE | 211.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 40% | 14.541 | 5.8164 | Accept | 40% | 14.541 | 5.8164 | H1 | 1 | Stable | TRUE | 211.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 40% | 14.541 | 5.8164 | Accept | 40% | 14.541 | 5.8164 | H1 | 1 | Stable | TRUE | 211.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 40% | 14.541 | 5.8164 | Accept | 40% | 14.541 | 5.8164 | H1 | 1 | Stable | TRUE | 211.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2017-08-20 01:00 | 40% | 14.541 | 5.8164 | Accept | 40% | 14.541 | 5.8164 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_289 | 2016-05-23 | 2016-12-20 01:00 | 40% | 14.541 | 5.8164 | Accept | 40% | 14.541 | 5.8164 | H1 | 1 | Stable | TRUE | 211.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK058 | Project_024_RISK058 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Retained items require additional, un-budgeted repairs to CoC | Person_641 | 2016-05-23 | 2017-08-20 01:00 | 40% | 14.541 | 5.8164 | Accept | 40% | 14.541 | 5.8164 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 30% | 19.4745 | 5.8424 | Accept | 30% | 19.4745 | 5.8424 | H1 | 1 | Stable | TRUE | 182.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 30% | 19.4745 | 5.8424 | Accept | 30% | 19.4745 | 5.8424 | H1 | 1 | Stable | TRUE | 182.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 30% | 19.4745 | 5.8424 | Accept | 30% | 19.4745 | 5.8424 | H1 | 1 | Stable | TRUE | 182.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 30% | 19.4745 | 5.8424 | Accept | 30% | 19.4745 | 5.8424 | H1 | 1 | Stable | TRUE | 182.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 30% | 19.4745 | 5.8424 | Accept | 30% | 19.4745 | 5.8424 | H1 | 1 | Stable | TRUE | 182.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 30% | 19.4745 | 5.8424 | Accept | 30% | 19.4745 | 5.8424 | H1 | 1 | Stable | TRUE | 182.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK209 | Project_024_RISK209 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Major Return to Service | Person_073 | 2016-11-20 01:00 | 2017-05-22 | 30% | 19.4745 | 5.8424 | Accept | 30% | 19.4745 | 5.8424 | H2 | 2 | Stable | TRUE | 182.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-151 | Project_020_Risk-151 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Reduced PM loading from final year | Person_575 | 2017-08-21 01:00 | 2018-05-21 | 60% | 1.5745 | 0.94468 | Exploit | 60% | 1.5745 | 0.94468 | H3 | 3 | -- | TRUE | 272.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 40% | 15.5623 | 6.2249 | Reduce | 38% | 15.5623 | 5.9137 | H1 | 1 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 40% | 15.5623 | 6.2249 | Reduce | 38% | 15.5623 | 5.9137 | H1 | 1 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 40% | 15.5623 | 6.2249 | Reduce | 38% | 15.5623 | 5.9137 | H1 | 1 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 40% | 15.5623 | 6.2249 | Reduce | 38% | 15.5623 | 5.9137 | H1 | 1 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | People unable to sustain the pace | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 40% | 15.5623 | 6.2249 | Reduce | 38% | 15.5623 | 5.9137 | H1 | 1 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 40% | 15.5623 | 6.2249 | Reduce | 38% | 15.5623 | 5.9137 | H1 | 1 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 40% | 15.5623 | 6.2249 | Reduce | 38% | 15.5623 | 5.9137 | H1 | 1 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK151 | Project_024_RISK151 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Key Resources- Single Point of Failure | Person_413 | 2015-11-21 01:00 | 2017-05-22 | 40% | 15.5623 | 6.2249 | Reduce | 38% | 15.5623 | 5.9137 | H1 | 1 | Stable | TRUE | 547.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R005 | Project_085_R005 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Supply Chain Travel costs | Person_043 | 2017-12-21 | 2018-12-21 | 30% | 23.6938 | 7.1081 | Reduce | 25% | 23.6938 | 5.9234 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-114 | Project_039_Risk-114 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Dual Cutoff | Person_343 | 2015-07-25 | 2016-06-23 | 50% | 19.8331 | 9.9165 | Reduce | 30% | 19.8331 | 5.9499 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_039 | Risk-114 | Project_039_Risk-114 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Dual Cutoff | Person_343 | 2015-07-25 | 2016-06-23 | 50% | 19.8331 | 9.9165 | Reduce | 30% | 19.8331 | 5.9499 | H2 | 2 | Stable | TRUE | 334 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 50% | 11.9444 | 5.9722 | Accept | 50% | 11.9444 | 5.9722 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 50% | 11.9444 | 5.9722 | Accept | 50% | 11.9444 | 5.9722 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 50% | 11.9444 | 5.9722 | Accept | 50% | 11.9444 | 5.9722 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 50% | 11.9444 | 5.9722 | Accept | 50% | 11.9444 | 5.9722 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Additional minor releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 50% | 11.9444 | 5.9722 | Accept | 50% | 11.9444 | 5.9722 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Additional minor point releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 50% | 11.9444 | 5.9722 | Accept | 50% | 11.9444 | 5.9722 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Additional minor point releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 50% | 11.9444 | 5.9722 | Accept | 50% | 11.9444 | 5.9722 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK182 | Project_024_RISK182 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Additional minor point releases | Person_073 | 2016-05-23 | 2017-08-20 01:00 | 50% | 11.9444 | 5.9722 | Accept | 50% | 11.9444 | 5.9722 | H1 | 1 | Stable | TRUE | 454.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-151 | Project_020_Risk-151 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Reduced PM loading from final year | Person_575 | 2017-08-21 01:00 | 2018-05-21 | 60% | 1.5745 | 0.94468 | Exploit | 60% | 1.5745 | 0.94468 | H3 | 3 | -- | TRUE | 272.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-151 | Project_020_Risk-151 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Reduced PM loading from final year | Person_575 | 2017-08-21 01:00 | 2018-05-21 | 60% | 1.5745 | 0.94468 | Exploit | 60% | 1.5745 | 0.94468 | H3 | 3 | -- | TRUE | 272.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 30% | 19.9938 | 5.9981 | Accept | 30% | 19.9938 | 5.9981 | H1 | 1 | Improving | TRUE | 394 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 30% | 19.9938 | 5.9981 | Accept | 30% | 19.9938 | 5.9981 | H1 | 1 | Improving | TRUE | 394 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 30% | 19.9938 | 5.9981 | Accept | 30% | 19.9938 | 5.9981 | H1 | 1 | Improving | TRUE | 394 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_119 | 2016-10-21 01:00 | 2017-11-19 01:00 | 30% | 19.9938 | 5.9981 | Accept | 30% | 19.9938 | 5.9981 | H1 | 1 | Improving | TRUE | 394 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 30% | 19.9938 | 5.9981 | Accept | 30% | 19.9938 | 5.9981 | H1 | 1 | Improving | TRUE | 270 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 30% | 19.9938 | 5.9981 | Accept | 30% | 19.9938 | 5.9981 | H1 | 1 | Improving | TRUE | 270 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK243 | Project_024_RISK243 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Insufficient Suitably Qualified and experienced staff availability for System Safety Analysis | Person_288 | 2017-02-22 01:00 | 2017-11-19 01:00 | 30% | 19.9938 | 5.9981 | Accept | 30% | 19.9938 | 5.9981 | H2 | 2 | Improving | TRUE | 270 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-14 01:00 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 918.9583 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-14 01:00 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 918.9583 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-14 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 919 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-14 01:00 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 918.9583 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-13 23:00 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 919.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-14 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 919 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-13 22:00 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 919.0833 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-13 23:00 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 919.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-14 01:00 | 2019-04-23 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 889.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-13 22:00 | 2019-05-22 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 919.0833 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-14 | 2019-04-23 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 890 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-14 01:00 | 2019-04-23 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 889.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK066 | Project_065_RISK066 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Software Technical Issues & Delays | Person_550 | 2016-11-13 23:00 | 2019-04-23 | 60% | 30.3406 | 18.2044 | Reduce | 40% | 15.0013 | 6.0005 | H2 | 2 | -- | TRUE | 890.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-030 | Project_008_Risk-030 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Transition from old to new Standard causing additional unexpected work | Person_639 | 2013-09-20 01:00 | 2016-06-22 | 75% | 17.2187 | 12.914 | Accept | 75% | 8.0017 | 6.0013 | H1 | 1 | Stable | TRUE | 1005.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-030 | Project_008_Risk-030 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Transition from old to new Standard causing additional unexpected work | Person_639 | 2013-09-20 01:00 | 2016-06-22 | 75% | 17.2187 | 12.914 | Accept | 75% | 8.0017 | 6.0013 | H1 | 1 | Stable | TRUE | 1005.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 20% | 30.1713 | 6.0343 | Avoid | 20% | 30.1713 | 6.0343 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 20% | 30.1713 | 6.0343 | Avoid | 20% | 30.1713 | 6.0343 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 20% | 30.1713 | 6.0343 | Avoid | 20% | 30.1713 | 6.0343 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 20% | 30.1713 | 6.0343 | Avoid | 20% | 30.1713 | 6.0343 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 20% | 30.1713 | 6.0343 | Avoid | 20% | 30.1713 | 6.0343 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 20% | 30.1713 | 6.0343 | Avoid | 20% | 30.1713 | 6.0343 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 20% | 30.1713 | 6.0343 | Avoid | 20% | 30.1713 | 6.0343 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK002 | Project_019_RISK002 | Threat | Project Contingency | Open | H2 | 2 | Logistic support and Services | Repairs could be higher than the predicted resulting in more repairs than expected | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 20% | 30.1713 | 6.0343 | Avoid | 20% | 30.1713 | 6.0343 | H2 | 2 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 911 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 23:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 910.9583 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 22:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 910.9167 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 23:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 910.9583 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 22:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 910.9167 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 911 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-21 01:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 911.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK018 | Project_065_RISK018 | Threat | Management Contingency | Open | H2 | 2 | Hardware/Software development | Development environment for HW, SW or FW does not last the full life of the contract. | Person_455 | 2015-06-24 | 2017-12-20 23:00 | 70% | 20.6835 | 14.4785 | Reduce | 30% | 20.6835 | 6.2051 | H2 | 2 | Stable | TRUE | 910.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK078 | Project_076_RISK078 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Schedule Slippage due to change in resource allocation | Person_152 | 2018-08-25 01:00 | 2019-09-20 01:00 | 75% | 8.2922 | 6.2191 | Accept | 75% | 8.2922 | 6.2191 | H1 | 1 | Stable | TRUE | 391 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_020 | Risk-151 | Project_020_Risk-151 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Reduced PM loading from final year | Person_575 | 2017-08-21 01:00 | 2018-05-21 | 60% | 1.5745 | 0.94468 | Exploit | 60% | 1.5745 | 0.94468 | H3 | 3 | -- | TRUE | 272.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_035 | RISK313 | Project_035_RISK313 | Threat | Project Contingency | Open | H2 | 2 |  | Deployed Performance inadequate | Person_303 | 2015-05-24 | 2016-11-20 01:00 | 30% | 6.3266 | 1.898 | Accept | 15% | 6.3266 | 0.949 | H3 | 3 | Improving | FALSE | 546.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_099 | RISK006 | Project_099_RISK006 | Threat | Project Contingency | Open | H3 | 3 |  | Increase in material cost | Person_002 | 2018-07-08 | 2020-03-22 | 50% | 1.9058 | 0.95288 | Accept | 50% | 1.9058 | 0.95288 | H3 | 3 | -- | TRUE | 623 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK054 | Project_076_RISK054 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Consider descoping component S levels | Person_152 | 2018-03-23 | 2018-05-23 | 50% | 1.9072 | 0.9536 | Reject | 50% | 1.9072 | 0.9536 | H3 | 3 | -- | TRUE | 61 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK054 | Project_076_RISK054 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Consider descoping Component S levels | Person_152 | 2018-03-23 | 2018-12-22 01:00 | 50% | 1.9072 | 0.9536 | Reject | 50% | 1.9072 | 0.9536 | H3 | 3 | -- | TRUE | 274.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-002 | Project_026_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Multi entity operating model inefficiencies’ | Person_362 | 2014-11-21 01:00 | 2023-10-22 01:00 | 100% | 6.2496 | 6.2496 | Accept | 100% | 6.2496 | 6.2496 | H2 | 2 | -- | TRUE | 3257 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2016-11-19 01:00 | 50% | 28.2191 | 14.1096 | -- | 50% | 12.4997 | 6.2499 | H2 | 2 | Stable | TRUE | 729 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2016-11-19 01:00 | 50% | 28.2191 | 14.1096 | -- | 50% | 12.4997 | 6.2499 | H2 | 2 | Stable | TRUE | 729 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-60 | Project_022_RISK-60 | Threat | Project Contingency | Open | H3 | 3 |  | Platform Acceptance extends | Person_703 | 2016-11-02 01:00 | 2016-12-20 01:00 | 60% | 1.5942 | 0.95652 | Reduce | 60% | 1.5942 | 0.95652 | H3 | 3 | -- | TRUE | 48 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK076 | Project_049_RISK076 | Threat | Project Contingency | Open | H3 | 3 | Logistic support and Services | Spares & Repairs | Person_282 | 2018-08-24 01:00 | 2020-08-24 01:00 | 50% | 15.7203 | 7.8601 | Reduce | 40% | 15.7203 | 6.2881 | H3 | 3 | -- | TRUE | 731 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-60 | Project_022_RISK-60 | Threat | Project Contingency | Open | H3 | 3 |  | Platform Acceptance extends | Person_703 | 2016-11-02 01:00 | 2016-12-20 01:00 | 60% | 1.5942 | 0.95652 | Reduce | 60% | 1.5942 | 0.95652 | H3 | 3 | -- | TRUE | 48 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-60 | Project_022_RISK-60 | Threat | Project Contingency | Open | H3 | 3 |  | Platform Acceptance extends | Person_703 | 2016-11-02 01:00 | 2016-12-20 01:00 | 60% | 1.5942 | 0.95652 | Reduce | 60% | 1.5942 | 0.95652 | H3 | 3 | -- | TRUE | 48 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 951.0417 |  | 0 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-08-18 01:00 | 50% | 16.3745 | 8.1873 | Reduce | 40% | 16.3745 | 6.5498 | H2 | 2 | Stable | TRUE | 1721 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-08-18 01:00 | 50% | 16.3745 | 8.1873 | Reduce | 40% | 16.3745 | 6.5498 | H2 | 2 | Stable | TRUE | 1721 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_005 | Risk-034 | Project_005_Risk-034 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Project delay causes cost impact to project | Person_470 | 2011-12-02 01:00 | 2016-08-18 01:00 | 50% | 16.3745 | 8.1873 | Reduce | 40% | 16.3745 | 6.5498 | H2 | 2 | Stable | TRUE | 1721 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 20% | 33.1085 | 6.6217 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 | 20% | 33.1085 | 6.6217 | -- | 20% | 33.1085 | 6.6217 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 20% | 33.1085 | 6.6217 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-073 | Project_008_Risk-073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Additional Effort Required to Support Boundary case | Person_565 | 2016-03-23 | 2018-08-21 | 75% | 8.8382 | 6.6286 | Accept | 75% | 8.8382 | 6.6286 | H2 | 2 | -- | TRUE | 881 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 50% | 13.3529 | 6.6765 | Accept | 50% | 13.3529 | 6.6765 | H2 | 2 | Improving | TRUE | 1057 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 50% | 13.3529 | 6.6765 | Accept | 50% | 13.3529 | 6.6765 | H2 | 2 | Improving | TRUE | 1057 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 50% | 13.3529 | 6.6765 | Accept | 50% | 13.3529 | 6.6765 | H2 | 2 | Improving | TRUE | 1057 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 50% | 13.3529 | 6.6765 | Accept | 50% | 13.3529 | 6.6765 | H2 | 2 | Improving | TRUE | 1057 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 50% | 13.3529 | 6.6765 | Accept | 50% | 13.3529 | 6.6765 | H2 | 2 | Improving | TRUE | 1057 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 50% | 13.3529 | 6.6765 | Accept | 50% | 13.3529 | 6.6765 | H2 | 2 | Improving | TRUE | 1057 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R011 | Project_016_Risk--R011 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Finance Hours | Person_697 | 2016-06-23 | 2019-05-16 | 50% | 13.3529 | 6.6765 | Accept | 50% | 13.3529 | 6.6765 | H2 | 2 | Improving | TRUE | 1057 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 1 | Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-07 01:00 | 2017-10-19 01:00 | 5% | 9.6346 | 0.48173 | Exploit | 70% | 9.6346 | 6.7442 | H1 | 1 | Stable | TRUE | 1016 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 1 | Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-07 01:00 | 2017-10-19 01:00 | 5% | 9.6346 | 0.48173 | Exploit | 70% | 9.6346 | 6.7442 | H1 | 1 | Stable | TRUE | 1016 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 1 | Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-07 | 2017-10-19 | 5% | 9.6346 | 0.48173 | Exploit | 70% | 9.6346 | 6.7442 | H1 | 1 | Stable | TRUE | 1016 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 1 | Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-07 01:00 | 2017-10-19 01:00 | 5% | 9.6346 | 0.48173 | Exploit | 70% | 9.6346 | 6.7442 | H1 | 1 | Stable | TRUE | 1016 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 1 | Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-06 23:00 | 2017-10-18 23:00 | 5% | 9.6346 | 0.48173 | Exploit | 70% | 9.6346 | 6.7442 | H1 | 1 | Stable | TRUE | 1016 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 1 | Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-06 22:00 | 2017-10-18 22:00 | 5% | 9.6346 | 0.48173 | Exploit | 70% | 9.6346 | 6.7442 | H1 | 1 | Stable | TRUE | 1016 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 1 | Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-06 23:00 | 2017-10-18 23:00 | 5% | 9.6346 | 0.48173 | Exploit | 70% | 9.6346 | 6.7442 | H1 | 1 | Stable | TRUE | 1016 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK002 | Project_065_RISK002 | Opportunitity | Project Contingency | Open | H1 | 1 | Acquisition and offsets | New supplier for enclosure | Person_598 | 2015-01-06 22:00 | 2017-10-18 22:00 | 5% | 9.6346 | 0.48173 | Exploit | 70% | 9.6346 | 6.7442 | H1 | 1 | Stable | TRUE | 1016 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 30% | 25.966 | 7.7898 | Accept | 30% | 22.5039 | 6.7512 | H1 | 1 | Improving | TRUE | 193.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2017-08-18 01:00 | 30% | 25.966 | 7.7898 | Accept | 30% | 22.5039 | 6.7512 | H1 | 1 | Improving | TRUE | 452.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 30% | 25.966 | 7.7898 | Accept | 30% | 22.5039 | 6.7512 | H1 | 1 | Improving | TRUE | 193.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Equipment environmental failure | Person_710 | 2016-05-23 | 2017-05-22 | 30% | 25.966 | 7.7898 | Accept | 30% | 22.5039 | 6.7512 | H2 | 2 | Improving | TRUE | 364 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK086 | Project_076_RISK086 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Reduction in modules that require full safety process | Person_771 | 2018-09-21 01:00 | 2019-05-23 | 50% | 13.5163 | 6.7581 | Reject | 50% | 13.5163 | 6.7581 | H2 | 2 | Stable | TRUE | 243.9583 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 951.0417 |  | 0 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-29 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 951 |  | 0 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 951.0417 |  | 0 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-28 23:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 950.9583 |  | 0 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-28 22:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 950.9167 |  | 0 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 951.0417 |  | 0 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-28 22:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 950.9167 |  | 0 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-29 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 951 |  | 0 | 0 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-002 | Project_026_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Multi entity operating model inefficiencies’ | Person_362 | 2014-11-21 01:00 | 2023-10-22 01:00 | 100% | 6.7866 | 6.7866 | Accept | 100% | 6.7866 | 6.7866 | H2 | 2 | -- | TRUE | 3257 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-002 | Project_026_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Multi entity operating model inefficiencies’ | Person_362 | 2014-11-21 01:00 | 2023-10-22 01:00 | 100% | 6.7866 | 6.7866 | Accept | 100% | 6.7866 | 6.7866 | H2 | 2 | -- | TRUE | 3257 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-002 | Project_026_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Multi entity operating model inefficiencies’ | Person_362 | 2014-11-21 01:00 | 2023-10-22 01:00 | 100% | 6.7866 | 6.7866 | Accept | 100% | 6.7866 | 6.7866 | H2 | 2 | -- | TRUE | 3257 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-002 | Project_026_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Multi entity operating model inefficiencies’ | Person_362 | 2014-11-21 01:00 | 2023-10-22 01:00 | 100% | 6.7866 | 6.7866 | Accept | 100% | 6.7866 | 6.7866 | H2 | 2 | -- | TRUE | 3257 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-002 | Project_026_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Multi entity operating model inefficiencies’ | Person_362 | 2014-11-21 01:00 | 2023-10-22 01:00 | 100% | 6.7866 | 6.7866 | Accept | 100% | 6.7866 | 6.7866 | H2 | 2 | -- | TRUE | 3257 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-002 | Project_026_Risk-002 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Multi entity operating model inefficiencies’ | Person_362 | 2014-11-21 01:00 | 2023-10-22 01:00 | 100% | 6.7866 | 6.7866 | Accept | 100% | 6.7866 | 6.7866 | H2 | 2 | -- | TRUE | 3257 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 10% | 68.1262 | 6.8126 | Accept | 10% | 68.1262 | 6.8126 | H2 | 2 | Improving | TRUE | 333 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 10% | 68.1262 | 6.8126 | Accept | 10% | 68.1262 | 6.8126 | H2 | 2 | Improving | TRUE | 333 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 10% | 68.1262 | 6.8126 | Accept | 10% | 68.1262 | 6.8126 | H2 | 2 | Improving | TRUE | 333 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 10% | 68.1262 | 6.8126 | Accept | 10% | 68.1262 | 6.8126 | H2 | 2 | Improving | TRUE | 333 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 10% | 68.1262 | 6.8126 | Accept | 10% | 68.1262 | 6.8126 | H2 | 2 | Improving | TRUE | 333 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 10% | 68.1262 | 6.8126 | Accept | 10% | 68.1262 | 6.8126 | H2 | 2 | Improving | TRUE | 333 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK253 | Project_024_RISK253 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Insufficient parts to complete framework Warranty | Person_289 | 2016-05-23 | 2017-04-21 | 10% | 68.1262 | 6.8126 | Accept | 10% | 68.1262 | 6.8126 | H2 | 2 | Improving | TRUE | 333 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 30% | 22.8501 | 6.855 | Accept | 30% | 22.8501 | 6.855 | H1 | 1 | Improving | TRUE | 181.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 30% | 22.8501 | 6.855 | Accept | 30% | 22.8501 | 6.855 | H1 | 1 | Improving | TRUE | 181.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 30% | 22.8501 | 6.855 | Accept | 30% | 22.8501 | 6.855 | H1 | 1 | Improving | TRUE | 181.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 30% | 22.8501 | 6.855 | Accept | 30% | 22.8501 | 6.855 | H1 | 1 | Improving | TRUE | 181.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 30% | 22.8501 | 6.855 | Accept | 30% | 22.8501 | 6.855 | H1 | 1 | Improving | TRUE | 181.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 30% | 22.8501 | 6.855 | Accept | 30% | 22.8501 | 6.855 | H1 | 1 | Improving | TRUE | 181.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK242 | Project_024_RISK242 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Increased acceptance effort | Person_288 | 2017-11-20 01:00 | 2018-05-21 | 30% | 22.8501 | 6.855 | Accept | 30% | 22.8501 | 6.855 | H2 | 2 | Improving | TRUE | 181.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-072 | Project_008_Risk-072 | Opportunitity | Project Contingency | Open | H2 | 2 | Supply chain | Saving on budget for repairs | Person_565 | 2016-01-22 01:00 | 2018-08-21 | 50% | 13.8255 | 6.9127 | -- | 50% | 13.8255 | 6.9127 | H3 | 3 | Improving | FALSE | 941.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-072 | Project_008_Risk-072 | Opportunitity | Project Contingency | Open | H2 | 2 | Supply chain | Saving on budget for repairs | Person_565 | 2016-01-22 01:00 | 2018-08-21 | 50% | 13.8255 | 6.9127 | -- | 50% | 13.8255 | 6.9127 | H3 | 3 | Improving | FALSE | 941.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_003 | Project_100 | Risk--115 | Project_100_Risk--115 | Threat | Project Contingency | Open | H2 | 2 | Other Risks and Contingencies | Supplier Additional Labour Risk | Person_567 | 2018-08-22 01:00 | 2021-08-20 01:00 | 50% | 13.8286 | 6.9143 | -- | 50% | 13.8286 | 6.9143 | H2 | 2 | -- | TRUE | 1094 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 20% | 35.0206 | 7.0041 | Accept | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_374 | 2016-01-22 01:00 | 2023-02-20 01:00 | 20% | 35.0206 | 7.0041 | Accept | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_374 | 2016-01-22 | 2023-02-20 | 20% | 35.0206 | 7.0041 | Accept | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_374 | 2016-01-22 | 2023-02-20 | 20% | 35.0206 | 7.0041 | Accept | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 20% | 35.0206 | 7.0041 | Accept | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 20% | 35.0206 | 7.0041 | Accept | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_374 | 2016-01-21 23:00 | 2023-02-19 23:00 | 20% | 35.0206 | 7.0041 | Accept | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_374 | 2016-01-21 21:00 | 2023-02-19 21:00 | 20% | 35.0206 | 7.0041 | Accept | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK050 | Project_017_RISK050 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Dependancy of Supplier | Person_279 | 2016-01-21 20:00 | 2023-02-19 20:00 | 20% | 35.0206 | 7.0041 | Reduce | 20% | 35.0206 | 7.0041 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-29 01:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 951.0417 |  | 0 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK043-Risk- | Project_065_RISK043-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Change to screen termination on causes integration issues, EMC test (and issues post installation). | Person_160 | 2021-04-22 | 2023-11-28 23:00 | 30% | 6.4391 | 1.9317 | Reduce | 15% | 6.44 | 0.966 | H3 | 3 | -- | FALSE | 950.9583 |  | 0 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_005 | Project_042 | RISK051 | Project_042_RISK051 | Opportunitity | Project Contingency | Open | H1 | 1 | Project Management | Main external component Refurbishment Savings | Person_455 | 2019-05-24 | 2020-09-20 01:00 | 80% | 9.3941 | 7.5153 | -- | 80% | 9.3941 | 7.5153 | H1 | 1 | Stable | TRUE | 485.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 50% | 15.0856 | 7.5428 | Avoid | 50% | 15.0856 | 7.5428 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 50% | 15.0856 | 7.5428 | Avoid | 50% | 15.0856 | 7.5428 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 50% | 15.0856 | 7.5428 | Avoid | 50% | 15.0856 | 7.5428 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 50% | 15.0856 | 7.5428 | Avoid | 50% | 15.0856 | 7.5428 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 50% | 15.0856 | 7.5428 | Avoid | 50% | 15.0856 | 7.5428 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 50% | 15.0856 | 7.5428 | Avoid | 50% | 15.0856 | 7.5428 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 50% | 15.0856 | 7.5428 | Avoid | 50% | 15.0856 | 7.5428 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK004 | Project_019_RISK004 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Enclosure | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 50% | 15.0856 | 7.5428 | Avoid | 50% | 15.0856 | 7.5428 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK057 | Project_076_RISK057 | Threat | Project Contingency | Open | H2 | 2 |  | SubSystem measures not in place and work to implement not in the budget | Person_484 | 2018-02-20 01:00 | 2018-08-21 | 10% | 9.6742 | 0.96742 | Accept | 10% | 9.6742 | 0.96742 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK057 | Project_076_RISK057 | Threat | Project Contingency | Open | H2 | 2 |  | SubSystem measures not in place and work to implement not in the budget | Person_484 | 2018-02-20 01:00 | 2018-08-21 | 10% | 9.6742 | 0.96742 | Accept | 10% | 9.6742 | 0.96742 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 1 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK057 | Project_076_RISK057 | Threat | Project Contingency | Open | H2 | 2 |  | SubSystem measures not in place and work to implement not in the budget | Person_484 | 2018-02-20 01:00 | 2018-08-21 | 10% | 9.6742 | 0.96742 | Accept | 10% | 9.6742 | 0.96742 | H3 | 3 | -- | FALSE | 181.9583 |  | 1 | 1 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK057 | Project_076_RISK057 | Threat | Project Contingency | Open | H2 | 2 |  | SubSystem measures not in place and work to implement not in the budget | Person_484 | 2018-02-20 01:00 | 2018-08-21 | 10% | 9.6742 | 0.96742 | Accept | 10% | 9.6742 | 0.96742 | H3 | 3 | Stable | FALSE | 181.9583 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK027 | Project_058_RISK027 | Threat | Project Contingency | Open | H3 | 3 |  | Damage to repair parts | Person_109 | 2018-03-22 | 2019-11-15 01:00 | 40% | 4.8934 | 1.9574 | Reduce | 20% | 4.8934 | 0.97869 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK027 | Project_058_RISK027 | Threat | Project Contingency | Open | H3 | 3 |  | Damage to repair parts | Person_109 | 2018-03-22 | 2019-11-15 01:00 | 40% | 4.8934 | 1.9574 | Reduce | 20% | 4.8934 | 0.97869 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 01:00 | 2023-12-22 01:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 01:00 | 2023-12-22 01:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 | 2023-12-22 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 23:00 | 2023-12-21 23:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 22:00 | 2023-12-21 22:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 23:00 | 2023-12-21 23:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 01:00 | 2023-12-22 01:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 22:00 | 2023-12-21 22:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 | 2023-12-22 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-21 01:00 | 2023-12-22 01:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK073 | Project_065_RISK073 | Threat | Project Contingency | Open | H2 | 2 | Project Management | General - Resource Availability and Efficiency (Resource Problems) | Person_563 | 2017-10-20 23:00 | 2023-12-21 23:00 | 40% | 30.1969 | 12.0788 | Reduce | 25% | 30.1969 | 7.5492 | H2 | 2 | Stable | TRUE | 2253 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R048 | Project_085_R048 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Increase FTE scope of work | Person_028 | 2018-01-20 | 2019-11-20 | 20% | 50.5999 | 10.12 | Reduce | 15% | 50.5999 | 7.59 | H2 | 2 | -- | TRUE | 669 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 01:00 | 2016-08-20 01:00 | 30% | 25.3619 | 7.6086 | Reduce | 30% | 25.3619 | 7.6086 | H2 | 2 | Stable | TRUE | 1460 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 | 2016-08-20 | 30% | 25.3619 | 7.6086 | Reduce | 30% | 25.3619 | 7.6086 | H2 | 2 | Stable | TRUE | 1460 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 | 2016-08-20 | 30% | 25.3619 | 7.6086 | Reduce | 30% | 25.3619 | 7.6086 | H2 | 2 | Stable | TRUE | 1460 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 | 2016-08-20 | 30% | 25.3619 | 7.6086 | Reduce | 30% | 25.3619 | 7.6086 | H2 | 2 | Stable | TRUE | 1460 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 01:00 | 2016-08-20 01:00 | 30% | 25.3619 | 7.6086 | Reduce | 30% | 25.3619 | 7.6086 | H2 | 2 | Stable | TRUE | 1460 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 01:00 | 2016-08-20 01:00 | 30% | 25.3619 | 7.6086 | Reduce | 30% | 25.3619 | 7.6086 | H2 | 2 | Stable | TRUE | 1460 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-126 | Project_032_Risk-126 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Supply Chain - Delivery to Contract Requirement | Person_590 | 2012-08-21 01:00 | 2016-08-20 01:00 | 30% | 25.3619 | 7.6086 | Reduce | 30% | 25.3619 | 7.6086 | H2 | 2 | Stable | TRUE | 1460 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 30% | 112.3463 | 33.7039 | Reduce | 20% | 38.196 | 7.6392 | H2 | 2 | Stable | TRUE | 272 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 30% | 112.3463 | 33.7039 | Reduce | 20% | 38.196 | 7.6392 | H2 | 2 | Stable | TRUE | 272 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 30% | 112.3463 | 33.7039 | Reduce | 20% | 38.196 | 7.6392 | H2 | 2 | Stable | TRUE | 272 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK010 | Project_094_RISK010 | Threat | Project Contingency | Open | H3 | 3 | Supply chain | Increased cost of manufacture | Person_193 | 2019-04-23 | 2020-05-22 | 40% | 19.1689 | 7.6675 | Reduce | 40% | 19.1689 | 7.6675 | H3 | 3 | Stable | TRUE | 395 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK027 | Project_058_RISK027 | Threat | Project Contingency | Open | H3 | 3 |  | Damage to repair parts | Person_109 | 2018-03-22 | 2019-11-15 01:00 | 40% | 4.8934 | 1.9574 | Reduce | 20% | 4.8934 | 0.97869 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK027 | Project_058_RISK027 | Threat | Project Contingency | Open | H3 | 3 |  | Damage to repair parts | Person_109 | 2018-03-22 | 2019-11-15 01:00 | 40% | 4.8934 | 1.9574 | Reduce | 20% | 4.8934 | 0.97869 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK027 | Project_058_RISK027 | Threat | Project Contingency | Open | H3 | 3 |  | Damage to repair parts | Person_109 | 2018-03-22 | 2019-11-15 01:00 | 40% | 4.8934 | 1.9574 | Reduce | 20% | 4.8934 | 0.97869 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK027 | Project_058_RISK027 | Threat | Project Contingency | Open | H3 | 3 |  | Damage to repair parts | Person_109 | 2018-03-22 | 2019-11-15 01:00 | 40% | 4.8934 | 1.9574 | Reduce | 20% | 4.8934 | 0.97869 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK027 | Project_058_RISK027 | Threat | Project Contingency | Open | H3 | 3 |  | Damage to repair parts | Person_109 | 2018-03-22 | 2019-11-15 01:00 | 40% | 4.8934 | 1.9574 | Reduce | 20% | 4.8934 | 0.97869 | H3 | 3 | -- | TRUE | 603.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK281 | Project_024_RISK281 | Threat | Project Contingency | Open | H2 | 2 |  | COTs SW License | Person_318 | 2016-03-23 | 2019-05-23 | 10% | 9.8671 | 0.98671 | Accept | 10% | 9.8671 | 0.98671 | H3 | 3 | -- | FALSE | 1156 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK281 | Project_024_RISK281 | Threat | Project Contingency | Open | H2 | 2 |  | COTs SW License | Person_318 | 2016-03-23 | 2019-05-23 | 10% | 9.8671 | 0.98671 | Accept | 10% | 9.8671 | 0.98671 | H3 | 3 | -- | FALSE | 1156 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK281 | Project_024_RISK281 | Threat | Project Contingency | Open | H2 | 2 |  | COTs SW License | Person_318 | 2016-03-23 | 2018-05-22 | 10% | 9.8671 | 0.98671 | Accept | 10% | 9.8671 | 0.98671 | H3 | 3 | -- | FALSE | 790 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-05-22 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-05-22 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-05-22 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-05-22 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_095 | RISK001 | Project_095_RISK001 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | increased spares budget | Person_229 | 2018-07-22 | 2023-07-22 | 70% | 11.0667 | 7.7467 | -- | 70% | 11.0667 | 7.7467 | H1 | 1 | -- | TRUE | 1826 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment environmental failure | Person_585 | 2016-05-23 | 2016-12-02 01:00 | 30% | 25.966 | 7.7898 | Accept | 30% | 25.966 | 7.7898 | H1 | 1 | Improving | TRUE | 193.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 30% | 25.966 | 7.7898 | Accept | 30% | 25.966 | 7.7898 | H1 | 1 | Improving | TRUE | 193.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 30% | 25.966 | 7.7898 | Accept | 30% | 25.966 | 7.7898 | H1 | 1 | Improving | TRUE | 193.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK048 | Project_024_RISK048 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment environmental failure | Person_289 | 2016-05-23 | 2016-12-02 01:00 | 30% | 25.966 | 7.7898 | Accept | 30% | 25.966 | 7.7898 | H1 | 1 | Improving | TRUE | 193.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-05-22 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-05-22 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-10-22 01:00 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 517.0417 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-05-22 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 364 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-10-22 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 517 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-10-22 01:00 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 517.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK436 | Project_065_RISK436 | Threat | Project Contingency | Open | H2 | 2 |  | Shock Requirement | Person_038 | 2017-05-23 | 2018-10-21 23:00 | 50% | 13.1842 | 6.5921 | Reduce | 20% | 5.0709 | 1.0142 | H3 | 3 | -- | FALSE | 516.9583 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R046 | Project_085_R046 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Separation system redesign | Person_015 | 2017-12-21 | 2022-05-22 | 60% | 16.0051 | 9.6031 | Reduce | 50% | 16.0051 | 8.0026 | H2 | 2 | -- | TRUE | 1613 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-20 | 2019-01-23 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-121 | Project_026_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Customers | Contracting with Customer | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 60% | 58.3371 | 35.0022 | Reduce | 20% | 40.0785 | 8.0157 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-121 | Project_026_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Customers | Contracting with Customer | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 60% | 58.3371 | 35.0022 | Reduce | 20% | 40.0785 | 8.0157 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-121 | Project_026_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Customers | Contracting with Customer | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 60% | 58.3371 | 35.0022 | Reduce | 20% | 40.0785 | 8.0157 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-121 | Project_026_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Customers | Contracting with Customer | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 60% | 58.3371 | 35.0022 | Reduce | 20% | 40.0785 | 8.0157 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-121 | Project_026_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Customers | Contracting with Customer | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 60% | 58.3371 | 35.0022 | Reduce | 20% | 40.0785 | 8.0157 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-121 | Project_026_Risk-121 | Threat | Project Contingency | Open | H2 | 2 | Customers | Contracting with Customer | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 60% | 58.3371 | 35.0022 | Reduce | 20% | 40.0785 | 8.0157 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-19 23:00 | 2019-01-22 23:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-19 22:00 | 2019-01-22 22:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2017-01-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2017-02-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2017-03-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184 |  | 1 | 1 | 0
2017-04-22 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2017-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2017-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Opportunity to submit additional CCPs | Person_522 | 2014-05-25 | 2017-08-21 01:00 | 20% | 33.1085 | 6.6217 | -- | 25% | 33.1085 | 8.2771 | H2 | 2 | -- | TRUE | 1184.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-063 | Project_008_Risk-063 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Customer Annex | Person_639 | 2015-08-22 01:00 | 2018-05-21 | 100% | 13.6519 | 13.6519 | Reduce | 100% | 8.2858 | 8.2858 | H2 | 2 | Improving | TRUE | 1002.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK083 | Project_076_RISK083 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Higher than expected level of bug fixing required | Person_152 | 2018-09-21 01:00 | 2019-09-20 01:00 | 50% | 16.5844 | 8.2922 | Accept | 50% | 16.5844 | 8.2922 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK082 | Project_076_RISK082 | Threat | Project Contingency | Open | H2 | 2 | System Integration, Verification & Validation | Additional project integration support is required | Person_152 | 2018-09-21 01:00 | 2019-09-20 01:00 | 40% | 20.7305 | 8.2922 | Accept | 40% | 20.7305 | 8.2922 | H2 | 2 | Stable | TRUE | 364 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-19 23:00 | 2019-01-22 23:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_418 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_594 | 2016-10-19 22:00 | 2019-01-22 22:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK009 | Project_094_RISK009 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Financial instability/loss of quality/abilities of suppliers for batch 2 | Person_281 | 2020-08-21 | 2021-05-22 | 30% | 28.1143 | 8.4343 | Reduce | 30% | 28.1143 | 8.4343 | H2 | 2 | Stable | TRUE | 274 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 | 2016-11-19 | 70% | 12.1398 | 8.4978 | Accept | 70% | 12.1398 | 8.4978 | H1 | 1 | Stable | TRUE | 287 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-05 23:00 | 2016-11-18 23:00 | 70% | 12.1398 | 8.4978 | Accept | 70% | 12.1398 | 8.4978 | H1 | 1 | Stable | TRUE | 287 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-11-19 01:00 | 70% | 12.1398 | 8.4978 | Accept | 70% | 12.1398 | 8.4978 | H1 | 1 | Stable | TRUE | 287 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 | 2016-11-19 | 70% | 12.1398 | 8.4978 | Accept | 70% | 12.1398 | 8.4978 | H1 | 1 | Stable | TRUE | 287 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-11-19 01:00 | 70% | 12.1398 | 8.4978 | Accept | 70% | 12.1398 | 8.4978 | H1 | 1 | Stable | TRUE | 287 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-12-20 01:00 | 70% | 12.1398 | 8.4978 | Accept | 70% | 12.1398 | 8.4978 | H1 | 1 | Stable | TRUE | 318 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-12-20 01:00 | 70% | 12.1398 | 8.4978 | Accept | 70% | 12.1398 | 8.4978 | H1 | 1 | Stable | TRUE | 318 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | Risk-R017 | Project_021_Risk-R017 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Effort to address Hexavalent Chromium issue is unknown at time of baseline | Person_470 | 2016-02-06 01:00 | 2016-12-20 01:00 | 70% | 12.1398 | 8.4978 | Accept | 70% | 12.1398 | 8.4978 | H1 | 1 | Stable | TRUE | 318 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 23:00 | 2019-08-20 23:00 | 50% | 17.0468 | 8.5234 | Avoid | 50% | 17.0468 | 8.5234 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 22:00 | 2019-08-20 22:00 | 50% | 17.0468 | 8.5234 | Avoid | 50% | 17.0468 | 8.5234 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 50% | 17.0468 | 8.5234 | Avoid | 50% | 17.0468 | 8.5234 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 21:00 | 2019-08-20 21:00 | 50% | 17.0468 | 8.5234 | Avoid | 50% | 17.0468 | 8.5234 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 20:00 | 2019-08-20 20:00 | 50% | 17.0468 | 8.5234 | Avoid | 50% | 17.0468 | 8.5234 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 19:00 | 2019-08-20 19:00 | 50% | 17.0468 | 8.5234 | Avoid | 50% | 17.0468 | 8.5234 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 18:00 | 2019-08-20 18:00 | 50% | 17.0468 | 8.5234 | Avoid | 50% | 17.0468 | 8.5234 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_019 | RISK005 | Project_019_RISK005 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Supplier Repairs Higher than predicted | Person_299 | 2014-08-21 17:00 | 2019-08-20 17:00 | 50% | 17.0468 | 8.5234 | Avoid | 50% | 17.0468 | 8.5234 | H1 | 1 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK011 | Project_094_RISK011 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Unplanned redesign activity | Person_198 | 2018-08-22 | 2020-05-22 | 40% | 21.4052 | 8.5621 | Reduce | 40% | 21.4052 | 8.5621 | H2 | 2 | Stable | TRUE | 639 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 30% | 112.3463 | 33.7039 | Reduce | 20% | 43.1036 | 8.6207 | H2 | 2 | Stable | TRUE | 272 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Additional CCPs and Trade Deal | Person_522 | 2014-05-25 | 2016-10-19 | 20% | 43.3721 | 8.6744 | -- | 20% | 43.3721 | 8.6744 | H2 | 2 | -- | TRUE | 878 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_021 | OPP001 | Project_021_OPP001 | Opportunitity | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Additional CCPs and Trade Deal | Person_522 | 2014-05-25 | 2016-10-18 23:00 | 20% | 43.3721 | 8.6744 | -- | 20% | 43.3721 | 8.6744 | H2 | 2 | -- | TRUE | 877.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_418 | 2016-10-20 | 2019-01-23 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_418 | 2016-10-20 01:00 | 2019-01-23 01:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R029 | Project_085_R029 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Yield issues requiring redesign | Person_409 | 2017-12-21 | 2024-05-22 | 50% | 22.5091 | 11.2545 | Reduce | 40% | 22.5091 | 9.0036 | H2 | 2 | -- | TRUE | 2344 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R079 | Project_085_R079 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Clean Room provision not adequate | Person_153 | 2017-12-21 | 2019-10-22 | 60% | 22.746 | 13.6476 | Reduce | 40% | 22.746 | 9.0984 | H2 | 2 | -- | TRUE | 670 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK041- | Project_065_RISK041- | Threat | Project Contingency | Open | H3 | 3 |  | Unit Assemby does not perform as required | Person_418 | 2016-10-19 23:00 | 2019-01-22 23:00 | 25% | 8.5342 | 2.1336 | Reduce | 15% | 6.9065 | 1.036 | H3 | 3 | -- | TRUE | 825 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK026 | Project_079_RISK026 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 30% | 30.653 | 9.1959 | -- | 30% | 30.653 | 9.1959 | H2 | 2 | Stable | TRUE | 384 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK026 | Project_079_RISK026 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 30% | 30.653 | 9.1959 | -- | 30% | 30.653 | 9.1959 | H2 | 2 | Stable | TRUE | 384 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 01:00 | 2016-08-21 01:00 | 30% | 37.5906 | 11.2772 | Reduce | 25% | 37.5906 | 9.3977 | H2 | 2 | Stable | TRUE | 0 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 01:00 | 2016-08-21 01:00 | 30% | 37.5906 | 11.2772 | Reduce | 25% | 37.5906 | 9.3977 | H2 | 2 | Stable | TRUE | 0 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 | 2016-08-21 | 30% | 37.5906 | 11.2772 | Reduce | 25% | 37.5906 | 9.3977 | H2 | 2 | Stable | TRUE | 0 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 01:00 | 2016-08-21 01:00 | 30% | 37.5906 | 11.2772 | Reduce | 25% | 37.5906 | 9.3977 | H2 | 2 | Stable | TRUE | 0 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-21 01:00 | 2016-08-21 01:00 | 30% | 37.5906 | 11.2772 | Reduce | 25% | 37.5906 | 9.3977 | H2 | 2 | Stable | TRUE | 0 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 23:00 | 2016-08-20 23:00 | 30% | 37.5906 | 11.2772 | Reduce | 25% | 37.5906 | 9.3977 | H2 | 2 | Stable | TRUE | 0 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 23:00 | 2016-08-20 23:00 | 30% | 37.5906 | 11.2772 | Reduce | 25% | 37.5906 | 9.3977 | H2 | 2 | Stable | TRUE | 0 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | Risk-003 | Project_018_Risk-003 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Test Equipment Failure | Person_084 | 2016-08-20 23:00 | 2016-08-20 23:00 | 30% | 37.5906 | 11.2772 | Reduce | 25% | 37.5906 | 9.3977 | H2 | 2 | Stable | TRUE | 0 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H3 | 3 | Contractual/Legal | Customer maybe difficult to work with | Person_574 | 2016-01-13 01:00 | 2019-08-21 01:00 | 60% | 23.9549 | 14.3729 | Reduce | 40% | 23.9549 | 9.5819 | H3 | 3 | -- | TRUE | 1316 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK092 | Project_076_RISK092 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Labour Rate Change | Person_628 | 2019-05-24 | 2019-08-22 01:00 | 50% | 19.3622 | 9.6811 | Accept | 50% | 19.3626 | 9.6813 | H2 | 2 | Stable | TRUE | 90.0417 |  | 0 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK023 | Project_081_RISK023 | Threat | Project Contingency | Open | H2 | 2 |  | Risk of funding requirement | Person_115 | 2017-09-27 01:00 | 2021-09-27 01:00 | 60% | 1.7696 | 1.0618 | Reduce | 60% | 1.7696 | 1.0618 | H3 | 3 | Stable | FALSE | 1461 |  | 1 | 1 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK014 | Project_079_RISK014 | Threat | Project Contingency | Open | H3 | 3 |  | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 5% | 21.725 | 1.0862 | Reduce | 5% | 21.725 | 1.0862 | H3 | 3 | Improving | TRUE | 388 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK014 | Project_079_RISK014 | Threat | Project Contingency | Open | H3 | 3 |  | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 5% | 21.725 | 1.0862 | Reduce | 5% | 21.725 | 1.0862 | H3 | 3 | Stable | TRUE | 388 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK014 | Project_079_RISK014 | Threat | Project Contingency | Open | H3 | 3 |  | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 5% | 21.725 | 1.0862 | Reduce | 5% | 21.725 | 1.0862 | H3 | 3 | Stable | TRUE | 388 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK014 | Project_079_RISK014 | Threat | Project Contingency | Open | H3 | 3 |  | Material Obsolecence | Person_718 | 2017-09-29 01:00 | 2018-10-22 01:00 | 5% | 21.725 | 1.0862 | Reduce | 5% | 21.725 | 1.0862 | H3 | 3 | Stable | TRUE | 388 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_279 | 2016-11-22 20:00 | 2023-02-19 20:00 | 40% | 49.4398 | 19.7759 | Reduce | 20% | 49.4398 | 9.888 | H2 | 2 | Stable | TRUE | 2280 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK516 | Project_065_RISK516 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence material program does not achieve performance | Person_418 | 2017-12-21 01:00 | 2024-07-16 | 50% | 20.4694 | 10.2347 | Accept | 50% | 20.4694 | 10.2347 | H2 | 2 | -- | TRUE | 2398.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK516 | Project_065_RISK516 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence material program does not achieve performance | Person_418 | 2017-12-21 | 2024-07-16 | 50% | 20.4694 | 10.2347 | Accept | 50% | 20.4694 | 10.2347 | H2 | 2 | -- | TRUE | 2399 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK516 | Project_065_RISK516 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence material program does not achieve performance | Person_418 | 2017-12-21 01:00 | 2024-07-16 | 50% | 20.4694 | 10.2347 | Accept | 50% | 20.4694 | 10.2347 | H2 | 2 | -- | TRUE | 2398.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK516 | Project_065_RISK516 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Obsolescence material program does not achieve performance | Person_418 | 2017-12-20 23:00 | 2024-07-16 | 50% | 20.4694 | 10.2347 | Accept | 50% | 20.4694 | 10.2347 | H2 | 2 | -- | TRUE | 2399.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-006 | Project_098_Risk-006 | Threat | Project Contingency | Open | H1 | 1 | Logistic support and Services | Level of repairs | Person_360 | 2018-05-24 | 2027-05-23 | 50% | 20.665 | 10.3325 | Accept | 50% | 20.665 | 10.3325 | H1 | 1 | -- | TRUE | 3286 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer maybe difficult to work with | Person_574 | 2016-01-13 01:00 | 2019-08-21 01:00 | 60% | 23.9549 | 14.3729 | Reduce | 43.86% | 23.8312 | 10.4533 | H2 | 2 | -- | TRUE | 1316 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer maybe difficult to work with | Person_574 | 2016-01-13 01:00 | 2019-08-21 01:00 | 60% | 23.9549 | 14.3729 | Reduce | 43.86% | 23.8312 | 10.4533 | H2 | 2 | -- | TRUE | 1316 |  | 1 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer maybe difficult to work with | Person_574 | 2016-01-13 01:00 | 2019-08-21 01:00 | 60% | 23.9549 | 14.3729 | Reduce | 43.86% | 23.8312 | 10.4533 | H2 | 2 | -- | TRUE | 1316 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer maybe difficult to work with | Person_574 | 2016-01-13 | 2019-08-21 | 60% | 23.9549 | 14.3729 | Reduce | 43.86% | 23.8312 | 10.4533 | H2 | 2 | -- | TRUE | 1316 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer maybe difficult to work with | Person_574 | 2016-01-13 01:00 | 2019-08-21 01:00 | 60% | 23.9549 | 14.3729 | Reduce | 43.86% | 23.8312 | 10.4533 | H2 | 2 | -- | TRUE | 1316 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer maybe difficult to work with | Person_574 | 2016-01-13 01:00 | 2019-08-21 01:00 | 60% | 23.9549 | 14.3729 | Reduce | 43.86% | 23.8312 | 10.4533 | H2 | 2 | -- | TRUE | 1316 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R009 | Project_016_Risk--R009 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Customer maybe difficult to work with | Person_574 | 2016-01-13 01:00 | 2019-08-21 01:00 | 60% | 23.9549 | 14.3729 | Reduce | 43.86% | 23.9549 | 10.5075 | H2 | 2 | -- | TRUE | 1316 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 50% | 28.2191 | 14.1096 | -- | 80% | 13.2573 | 10.6058 | H1 | 1 | Stable | TRUE | 911.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 50% | 28.2191 | 14.1096 | -- | 80% | 13.2573 | 10.6058 | H1 | 1 | Stable | TRUE | 911.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 50% | 28.2191 | 14.1096 | -- | 80% | 13.2573 | 10.6058 | H1 | 1 | Stable | TRUE | 911.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 50% | 28.2191 | 14.1096 | -- | 80% | 13.2573 | 10.6058 | H1 | 1 | Stable | TRUE | 911.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 50% | 28.2191 | 14.1096 | -- | 80% | 13.2573 | 10.6058 | H1 | 1 | Stable | TRUE | 911.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-043 | Project_008_Risk-043 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Joint courseware and tech pubs team | Person_280 | 2014-11-21 01:00 | 2017-05-21 | 50% | 28.2191 | 14.1096 | -- | 80% | 13.2573 | 10.6058 | H1 | 1 | Stable | TRUE | 911.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_563 | 2017-05-23 | 2019-11-20 01:00 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 911.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_563 | 2017-05-23 | 2019-11-20 01:00 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 911.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_563 | 2017-05-23 | 2019-11-20 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 911 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_563 | 2017-05-23 | 2019-11-20 01:00 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 911.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_563 | 2017-05-23 | 2019-11-19 23:00 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 910.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_563 | 2017-05-23 | 2019-11-19 22:00 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 910.9167 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_049 | 2018-03-23 | 2020-07-20 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 850 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_563 | 2017-05-23 | 2019-11-19 22:00 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 910.9167 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_049 | 2018-03-23 | 2020-07-20 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 850 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_049 | 2018-03-23 | 2020-07-20 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 850 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK423 | Project_065_RISK423 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | Major Element Obsolescence | Person_049 | 2018-03-23 | 2020-07-20 | 40% | 38.4709 | 15.3884 | Reduce | 40% | 27.3826 | 10.953 | H2 | 2 | -- | TRUE | 850 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_094 | RISK001 | Project_094_RISK001 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Immature Prime not qualified to deliver SoW | Person_198 | 2018-08-22 | 2021-08-21 | 40% | 27.9546 | 11.1818 | Reduce | 40% | 27.9546 | 11.1818 | H2 | 2 | Stable | TRUE | 1095 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 30% | 112.3463 | 33.7039 | Reduce | 20% | 56.0866 | 11.2173 | H2 | 2 | Stable | TRUE | 272 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 30% | 112.3463 | 33.7039 | Reduce | 20% | 56.0866 | 11.2173 | H2 | 2 | Stable | TRUE | 272 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK012 | Project_049_RISK012 | Threat | Project Contingency | Open | H2 | 2 | Project Management | UK Suitably Qualified and experienced staff availability Resource | Person_218 | 2017-08-23 01:00 | 2019-11-18 01:00 | 50% | 22.4361 | 11.2181 | Accept | 50% | 22.4361 | 11.2181 | H2 | 2 | -- | TRUE | 817 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_002 | Portfolio_017 | Project_072 | RISK101 | Project_072_RISK101 | Opportunitity | Project Contingency | Open | H2 | 2 | Hardware/Software development | SW Scope Update | Person_195 | 2018-07-21 | 2018-08-01 | 90% | 12.4856 | 11.237 | -- | 90% | 12.4856 | 11.237 | H2 | 2 | Improving | TRUE | 11 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-102 | Project_026_Risk-102 | Threat | Financial Contingency | Open | H2 | 2 | Contractual/Legal | Liquidated Damages imposed | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 5% | 244.3581 | 12.2179 | Accept | 5% | 227.5702 | 11.3785 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-102 | Project_026_Risk-102 | Threat | Financial Contingency | Open | H2 | 2 | Contractual/Legal | Liquidated Damages imposed | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 5% | 244.3581 | 12.2179 | Accept | 5% | 227.5702 | 11.3785 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-102 | Project_026_Risk-102 | Threat | Financial Contingency | Open | H2 | 2 | Contractual/Legal | Liquidated Damages imposed | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 5% | 244.3581 | 12.2179 | Accept | 5% | 227.5702 | 11.3785 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-102 | Project_026_Risk-102 | Threat | Financial Contingency | Open | H2 | 2 | Contractual/Legal | Liquidated Damages imposed | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 5% | 244.3581 | 12.2179 | Accept | 5% | 227.5702 | 11.3785 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-102 | Project_026_Risk-102 | Threat | Financial Contingency | Open | H2 | 2 | Contractual/Legal | Liquidated Damages imposed | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 5% | 244.3581 | 12.2179 | Accept | 5% | 227.5702 | 11.3785 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-102 | Project_026_Risk-102 | Threat | Financial Contingency | Open | H2 | 2 | Contractual/Legal | Liquidated Damages imposed | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 5% | 244.3581 | 12.2179 | Accept | 5% | 227.5702 | 11.3785 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-102 | Project_026_Risk-102 | Threat | Financial Contingency | Open | H2 | 2 | Contractual/Legal | Liquidated Damages imposed | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 5% | 244.3581 | 12.2179 | Accept | 5% | 227.5702 | 11.3785 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-102 | Project_026_Risk-102 | Threat | Financial Contingency | Open | H2 | 2 | Contractual/Legal | Liquidated Damages imposed | Person_264 | 2015-02-21 01:00 | 2022-10-28 01:00 | 5% | 244.3581 | 12.2179 | Accept | 5% | 227.5702 | 11.3785 | H2 | 2 | -- | TRUE | 2806 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-139 | Project_030_Risk-139 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Customer License Costs | Person_518 | 2014-07-25 | 2014-10-22 01:00 | 26% | 43.9208 | 11.4194 | -- | 26% | 43.9208 | 11.4194 | H1 | 1 | -- | TRUE | 89.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-139 | Project_030_Risk-139 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Customer License Costs | Person_518 | 2014-07-25 | 2014-10-22 01:00 | 26% | 43.9208 | 11.4194 | -- | 26% | 43.9208 | 11.4194 | H1 | 1 | -- | TRUE | 89.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-139 | Project_030_Risk-139 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Customer License Costs | Person_518 | 2014-07-25 | 2014-10-22 01:00 | 26% | 43.9208 | 11.4194 | -- | 26% | 43.9208 | 11.4194 | H1 | 1 | -- | TRUE | 89.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-139 | Project_030_Risk-139 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Customer License Costs | Person_518 | 2014-07-25 | 2014-10-22 | 26% | 43.9208 | 11.4194 | -- | 26% | 43.9208 | 11.4194 | H1 | 1 | -- | TRUE | 89 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-139 | Project_030_Risk-139 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Customer License Costs | Person_518 | 2014-07-25 | 2014-10-22 01:00 | 26% | 43.9208 | 11.4194 | -- | 26% | 43.9208 | 11.4194 | H1 | 1 | -- | TRUE | 89.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-139 | Project_030_Risk-139 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Customer License Costs | Person_518 | 2014-07-25 | 2014-10-22 01:00 | 26% | 43.9208 | 11.4194 | -- | 26% | 43.9208 | 11.4194 | H1 | 1 | -- | TRUE | 89.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-139 | Project_030_Risk-139 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Customer License Costs | Person_518 | 2014-07-25 | 2014-10-22 01:00 | 26% | 43.9208 | 11.4194 | -- | 26% | 43.9208 | 11.4194 | H1 | 1 | -- | TRUE | 89.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_004 | Project_030 | Risk-139 | Project_030_Risk-139 | Opportunitity | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Customer License Costs | Person_518 | 2014-07-25 | 2014-10-22 | 26% | 43.9208 | 11.4194 | -- | 26% | 43.9208 | 11.4194 | H1 | 1 | -- | TRUE | 89 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-20 | 2020-10-21 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-20 | 2020-10-21 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-19 | 2020-11-20 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-19 23:00 | 2020-10-20 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2016-10-04 01:00 | 40% | 90.8811 | 36.3524 | Reduce | 30% | 39.3904 | 11.8171 | H1 | 1 | Stable | TRUE | 44 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2016-10-04 01:00 | 40% | 90.8811 | 36.3524 | Reduce | 30% | 39.3904 | 11.8171 | H1 | 1 | Stable | TRUE | 44 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2016-10-04 01:00 | 40% | 90.8811 | 36.3524 | Reduce | 30% | 39.3904 | 11.8171 | H1 | 1 | Stable | TRUE | 44 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2017-05-14 | 40% | 90.8811 | 36.3524 | Reduce | 30% | 39.3904 | 11.8171 | H1 | 1 | Stable | TRUE | 265.9583 |  | 1 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2017-05-14 | 40% | 90.8811 | 36.3524 | Reduce | 30% | 39.3904 | 11.8171 | H1 | 1 | Stable | TRUE | 265.9583 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | System issues general | Person_388 | 2016-08-21 01:00 | 2017-05-14 | 40% | 90.8811 | 36.3524 | Reduce | 30% | 39.3904 | 11.8171 | H1 | 1 | Stable | TRUE | 265.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-074 | Project_008_Risk-074 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Re-design/Beyond Economic Repair costs | Person_565 | 2016-05-23 | 2016-11-19 01:00 | 100% | 11.8369 | 11.8369 | Accept | 100% | 11.8369 | 11.8369 | H1 | 1 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-074 | Project_008_Risk-074 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Re-design/Beyond Economic Repair costs | Person_565 | 2016-05-23 | 2016-11-19 01:00 | 100% | 11.8369 | 11.8369 | Accept | 100% | 11.8369 | 11.8369 | H1 | 1 | Stable | TRUE | 180.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-05-21 | 50% | 23.6737 | 11.8369 | -- | 50% | 23.6737 | 11.8369 | H3 | 3 | -- | FALSE | 272.9583 |  | 1 | 1 | 1
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-05-21 | 50% | 23.6737 | 11.8369 | -- | 50% | 23.6737 | 11.8369 | H3 | 3 | -- | FALSE | 272.9583 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-05-21 | 50% | 23.6737 | 11.8369 | -- | 50% | 23.6737 | 11.8369 | H3 | 3 | -- | FALSE | 272.9583 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-05-21 | 50% | 23.6737 | 11.8369 | -- | 50% | 23.6737 | 11.8369 | H3 | 3 | -- | FALSE | 272.9583 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-080 | Project_008_Risk-080 | Opportunitity | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Recovery of Costs | Person_565 | 2016-08-21 01:00 | 2017-05-21 | 50% | 23.6737 | 11.8369 | -- | 50% | 23.6737 | 11.8369 | H3 | 3 | -- | FALSE | 272.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R043 | Project_085_R043 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Supplier financial risk | Person_098 | 2017-12-21 | 2019-04-22 | 60% | 29.6172 | 17.7703 | Reduce | 40% | 29.6172 | 11.8469 | H2 | 2 | -- | TRUE | 487 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-19 23:00 | 2020-10-20 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Qual failure | Person_585 | 2016-06-22 | 2016-11-20 01:00 | 40% | 30.2764 | 12.1106 | Accept | 40% | 30.2764 | 12.1106 | H1 | 1 | Improving | TRUE | 151.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 40% | 30.2764 | 12.1106 | Accept | 40% | 30.2764 | 12.1106 | H1 | 1 | Improving | TRUE | 151.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 40% | 30.2764 | 12.1106 | Accept | 40% | 30.2764 | 12.1106 | H1 | 1 | Improving | TRUE | 151.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 40% | 30.2764 | 12.1106 | Accept | 40% | 30.2764 | 12.1106 | H1 | 1 | Improving | TRUE | 151.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 40% | 30.2764 | 12.1106 | Accept | 40% | 30.2764 | 12.1106 | H1 | 1 | Improving | TRUE | 151.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2017-08-12 | 40% | 30.2764 | 12.1106 | Accept | 40% | 30.2764 | 12.1106 | H1 | 1 | Improving | TRUE | 416 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Qual failure | Person_289 | 2016-06-22 | 2016-11-20 01:00 | 40% | 30.2764 | 12.1106 | Accept | 40% | 30.2764 | 12.1106 | H1 | 1 | Improving | TRUE | 151.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK177 | Project_024_RISK177 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | Qual failure | Person_710 | 2016-06-22 | 2017-05-22 | 40% | 30.2764 | 12.1106 | Accept | 40% | 30.2764 | 12.1106 | H1 | 1 | Improving | TRUE | 334 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 49% | 30.7697 | 15.0772 | Accept | 50% | 24.3561 | 12.1781 | H1 | 1 | Worsening | TRUE | 154 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 49% | 30.7697 | 15.0772 | Accept | 50% | 24.3561 | 12.1781 | H1 | 1 | Worsening | TRUE | 154 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 49% | 30.7697 | 15.0772 | Accept | 50% | 24.3561 | 12.1781 | H1 | 1 | Worsening | TRUE | 154 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-03-22 | 49% | 30.7697 | 15.0772 | Accept | 50% | 24.3561 | 12.1781 | H1 | 1 | Worsening | TRUE | 213.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK026 | Project_079_RISK026 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 40% | 30.653 | 12.2612 | -- | 40% | 30.653 | 12.2612 | H2 | 2 | Stable | TRUE | 384 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK026 | Project_079_RISK026 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Clause on Joint Proposal | Person_261 | 2018-05-04 | 2019-05-23 | 40% | 30.653 | 12.2612 | -- | 40% | 30.653 | 12.2612 | H2 | 2 | Stable | TRUE | 384 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment integration - Audio and Video recording | Person_585 | 2016-08-20 01:00 | 2017-01-21 01:00 | 40% | 30.7697 | 12.3079 | Accept | 40% | 30.7697 | 12.3079 | H1 | 1 | Worsening | TRUE | 154 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-158 | Project_026_Risk-158 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Increased Customer costs | Person_396 | 2015-02-21 01:00 | 2019-02-25 01:00 | 50% | 24.8462 | 12.4231 | Accept | 50% | 24.8462 | 12.4231 | H2 | 2 | -- | TRUE | 1465 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-158 | Project_026_Risk-158 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Increased Customer costs | Person_396 | 2015-02-21 01:00 | 2023-11-20 01:00 | 50% | 24.8462 | 12.4231 | Accept | 50% | 24.8462 | 12.4231 | H2 | 2 | -- | TRUE | 3194 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-158 | Project_026_Risk-158 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Increased Customer costs | Person_396 | 2015-02-21 01:00 | 2023-11-20 01:00 | 50% | 24.8462 | 12.4231 | Accept | 50% | 24.8462 | 12.4231 | H2 | 2 | -- | TRUE | 3194 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-158 | Project_026_Risk-158 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Increased Customer costs | Person_690 | 2015-02-21 01:00 | 2023-11-20 01:00 | 50% | 24.8462 | 12.4231 | Accept | 50% | 24.8462 | 12.4231 | H2 | 2 | -- | TRUE | 3194 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-20 | 2023-02-20 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-20 01:00 | 2023-02-20 01:00 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-19 23:00 | 2023-02-19 23:00 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-19 22:00 | 2023-02-19 22:00 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-19 23:00 | 2023-02-19 23:00 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-20 01:00 | 2023-03-22 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3681.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-19 22:00 | 2023-02-19 22:00 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3652 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-20 | 2023-03-22 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3682 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-20 01:00 | 2023-03-22 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3681.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK350 | Project_065_RISK350 | Threat | Management Contingency | Open | H2 | 2 | Business Strategy and Objectives | complex integration needs between sub-system functions during development | Person_192 | 2013-02-19 23:00 | 2023-03-22 | 50% | 25.1514 | 12.5757 | Accept | 50% | 25.1514 | 12.5757 | H2 | 2 | -- | TRUE | 3682.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | T-003 | Project_077_T-003 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | SW Resource availability | Person_509 | 2018-05-23 | 2020-02-21 01:00 | 50% | 25.1598 | 12.5799 | Reduce | 50% | 25.1598 | 12.5799 | H1 | 1 | Worsening | TRUE | 639.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-18 23:00 | 2020-11-19 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK247 | Project_024_RISK247 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Materials | Person_288 | 2016-01-22 01:00 | 2016-05-22 | 50% | 25.966 | 12.983 | Accept | 50% | 25.966 | 12.983 | H1 | 1 | -- | TRUE | 120.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-19 22:00 | 2020-10-20 22:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-19 22:00 | 2020-10-20 22:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-18 22:00 | 2020-11-19 22:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-19 23:00 | 2020-10-20 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2016-05-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-158 | Project_026_Risk-158 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Increased Customer costs | Person_396 | 2015-02-21 01:00 | 2019-02-25 01:00 | 50% | 27.1831 | 13.5915 | Accept | 50% | 27.1831 | 13.5915 | H2 | 2 | -- | TRUE | 1465 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-158 | Project_026_Risk-158 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Increased Customer costs | Person_396 | 2015-02-21 01:00 | 2019-02-25 01:00 | 50% | 27.1831 | 13.5915 | Accept | 50% | 27.1831 | 13.5915 | H2 | 2 | -- | TRUE | 1465 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-158 | Project_026_Risk-158 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Increased Customer costs | Person_396 | 2015-02-21 01:00 | 2019-02-25 01:00 | 50% | 27.1831 | 13.5915 | Accept | 50% | 27.1831 | 13.5915 | H2 | 2 | -- | TRUE | 1465 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_003 | Portfolio_006 | Project_026 | Risk-158 | Project_026_Risk-158 | Threat | Project Contingency | Open | H2 | 2 | Contractual/Legal | Increased Customer costs | Person_396 | 2015-02-21 01:00 | 2019-02-25 01:00 | 50% | 24.8462 | 12.4231 | Accept | 50% | 27.1831 | 13.5915 | H2 | 2 | -- | TRUE | 1465 |  | 0 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK252 | Project_024_RISK252 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Non acceptance of the sub system | Person_289 | 2018-05-22 | 2018-05-22 | 15% | 90.8811 | 13.6322 | Accept | 15% | 90.8811 | 13.6322 | H2 | 2 | -- | TRUE | 0 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK252 | Project_024_RISK252 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Non acceptance of the sub system | Person_289 | 2018-05-22 | 2018-05-22 | 15% | 90.8811 | 13.6322 | Accept | 15% | 90.8811 | 13.6322 | H2 | 2 | -- | TRUE | 0 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK252 | Project_024_RISK252 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Non acceptance of the sub system | Person_289 | 2018-05-22 | 2018-05-22 | 15% | 90.8811 | 13.6322 | Accept | 15% | 90.8811 | 13.6322 | H2 | 2 | -- | TRUE | 0 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK252 | Project_024_RISK252 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Non acceptance of the sub system | Person_289 | 2018-05-22 | 2018-05-22 | 15% | 90.8811 | 13.6322 | Accept | 15% | 90.8811 | 13.6322 | H2 | 2 | -- | TRUE | 0 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK252 | Project_024_RISK252 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Non acceptance of the sub system | Person_289 | 2017-05-23 | 2018-05-22 | 15% | 90.8811 | 13.6322 | Accept | 15% | 90.8811 | 13.6322 | H2 | 2 | -- | TRUE | 364 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK252 | Project_024_RISK252 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Non acceptance of the sub system | Person_289 | 2018-05-22 | 2018-05-22 | 15% | 90.8811 | 13.6322 | Accept | 15% | 90.8811 | 13.6322 | H2 | 2 | -- | TRUE | 0 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK252 | Project_024_RISK252 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Non acceptance of the sub system | Person_351 | 2018-05-22 | 2018-05-22 | 15% | 90.8811 | 13.6322 | Accept | 15% | 90.8811 | 13.6322 | H2 | 2 | -- | TRUE | 0 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R012 | Project_085_R012 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | REACH/ROHS non compliance | Person_015 | 2017-12-21 | 2018-12-21 | 40% | 69.2847 | 27.7139 | Reduce | 20% | 69.2847 | 13.8569 | H2 | 2 | -- | TRUE | 365 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-077 | Project_008_Risk-077 | Opportunitity | Project Contingency | Open | H2 | 2 | Supply chain | product Spares | Person_565 | 2016-07-21 | 2017-01-19 01:00 | 100% | 14.2042 | 14.2042 | -- | 100% | 14.2042 | 14.2042 | H2 | 2 | Stable | TRUE | 182.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 40% | 35.885 | 14.354 | Accept | 40% | 35.885 | 14.354 | H1 | 1 | Worsening | TRUE | 178.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-19 23:00 | 2020-10-20 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-18 23:00 | 2020-11-19 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_418 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_418 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_418 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-19 22:00 | 2020-10-20 22:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_594 | 2016-10-19 22:00 | 2020-10-20 22:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R034 | Project_085_R034 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Design deviation | Person_409 | 2018-12-22 | 2020-05-22 | 60% | 29.6172 | 17.7703 | Reduce | 50% | 29.6172 | 14.8086 | H2 | 2 | -- | TRUE | 517 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_594 | 2016-10-18 22:00 | 2020-11-19 22:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_418 | 2016-10-20 | 2020-10-21 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_418 | 2016-10-20 | 2020-10-21 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_418 | 2016-10-19 | 2020-11-20 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_418 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_418 | 2016-10-20 01:00 | 2020-10-21 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_418 | 2016-10-19 01:00 | 2020-11-20 01:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046-Risk- | Project_065_RISK046-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_418 | 2016-10-19 23:00 | 2020-10-20 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK046- | Project_065_RISK046- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid corrosion | Person_418 | 2016-10-19 23:00 | 2020-10-20 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1462 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK045- | Project_065_RISK045- | Threat | Project Contingency | Open | H2 | 2 |  | Fluid weep causes System to fail | Person_418 | 2016-10-18 23:00 | 2020-11-19 23:00 | 50% | 5.5577 | 2.7788 | Reduce | 20% | 5.5577 | 1.1115 | H3 | 3 | -- | FALSE | 1493 |  | 1 | 0 | 1
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 2 |  | Software Issues | Person_245 | 2012-04-19 | 2016-11-19 01:00 | 50% | 0.55886 | 0.27943 | Accept | 20% | 5.5886 | 1.1177 | H3 | 3 | Stable | FALSE | 1675.0417 |  | 0 | 0 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Go to Offshore initiative | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 15% | 7.7172 | 1.1576 | -- | 15% | 7.7172 | 1.1576 | H3 | 3 | -- | FALSE | 547.9583 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Go to Offshore initiative | Person_468 | 2016-11-20 01:00 | 2018-05-22 | 15% | 7.7172 | 1.1576 | -- | 15% | 7.7172 | 1.1576 | H3 | 3 | Stable | FALSE | 547.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Go to Offshore initiative | Person_468 | 2016-11-20 | 2018-05-22 | 15% | 7.7172 | 1.1576 | -- | 15% | 7.7172 | 1.1576 | H3 | 3 | Stable | FALSE | 548 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-120 | Project_032_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | Project Management | System STTE Equipment Roll Out | Person_768 | 2014-03-23 | 2017-03-23 | 90% | 16.7112 | 15.04 | Accept | 90% | 16.7112 | 15.04 | H2 | 2 | Stable | TRUE | 1096 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-120 | Project_032_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | Project Management | System STTE Equipment Roll Out | Person_768 | 2014-03-23 | 2017-03-23 | 90% | 16.7112 | 15.04 | Accept | 90% | 16.7112 | 15.04 | H2 | 2 | Stable | TRUE | 1096 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-120 | Project_032_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | Project Management | System STTE Equipment Roll Out | Person_768 | 2014-03-23 | 2017-03-23 | 90% | 16.7112 | 15.04 | Accept | 90% | 16.7112 | 15.04 | H2 | 2 | Stable | TRUE | 1096 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-120 | Project_032_Risk-120 | Threat | Project Contingency | Open | H2 | 2 | Project Management | System STTE Equipment Roll Out | Person_768 | 2014-03-23 | 2017-03-23 | 90% | 16.7112 | 15.04 | Accept | 90% | 16.7112 | 15.04 | H2 | 2 | Stable | TRUE | 1096 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 49% | 30.7697 | 15.0772 | Accept | 49% | 30.7697 | 15.0772 | H1 | 1 | Worsening | TRUE | 154 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 49% | 30.7697 | 15.0772 | Accept | 49% | 30.7697 | 15.0772 | H1 | 1 | Worsening | TRUE | 154 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK189 | Project_024_RISK189 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | Equipment integration - Audio and Video recording | Person_289 | 2016-08-20 01:00 | 2017-01-21 01:00 | 49% | 30.7697 | 15.0772 | Accept | 49% | 30.7697 | 15.0772 | H1 | 1 | Worsening | TRUE | 154 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Go to Offshore initiative | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 15% | 7.7172 | 1.1576 | -- | 15% | 7.7172 | 1.1576 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK103 | Project_066_RISK103 | Threat | Project Contingency | Open | H1 | 1 | Acquisition and offsets | Drive Unit Cost | Person_060 | 2018-06-23 | 2018-08-21 | 70% | 21.7053 | 15.1937 | Accept | 70% | 21.7053 | 15.1937 | H1 | 1 | -- | TRUE | 59 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK034 | Project_049_RISK034 | Threat | Project Contingency | Open | H2 | 2 | Finance | Supplier VOP Escalation | Person_218 | 2018-01-21 01:00 | 2018-11-20 01:00 | 50% | 31.4106 | 15.7053 | Accept | 50% | 31.4106 | 15.7053 | H2 | 2 | -- | TRUE | 303 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 30% | 53.0293 | 15.9088 | Reduce | 30% | 53.0293 | 15.9088 | H3 | 3 | Worsening | TRUE | 1825 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 30% | 53.0293 | 15.9088 | Reduce | 30% | 53.0293 | 15.9088 | H3 | 3 | Worsening | TRUE | 1825 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 30% | 53.0293 | 15.9088 | Reduce | 30% | 53.0293 | 15.9088 | H3 | 3 | Worsening | TRUE | 1825 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 | 2017-08-20 | 30% | 53.0293 | 15.9088 | Reduce | 30% | 53.0293 | 15.9088 | H3 | 3 | Worsening | TRUE | 1825 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 30% | 53.0293 | 15.9088 | Reduce | 30% | 53.0293 | 15.9088 | H3 | 3 | Worsening | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 30% | 53.0293 | 15.9088 | Reduce | 30% | 53.0293 | 15.9088 | H3 | 3 | Worsening | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 30% | 53.0293 | 15.9088 | Reduce | 30% | 53.0293 | 15.9088 | H3 | 3 | Worsening | TRUE | 1825 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-177 | Project_032_Risk-177 | Threat | Project Contingency | Open | H3 | 3 | Project Management | WPD - sub-system Ageing of Equipments | Person_381 | 2012-08-21 01:00 | 2017-08-20 01:00 | 30% | 53.0293 | 15.9088 | Reduce | 30% | 53.0293 | 15.9088 | H3 | 3 | Worsening | TRUE | 1825 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 48% | 33.2985 | 15.9833 | Avoid | 48% | 33.2985 | 15.9833 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 48% | 33.2985 | 15.9833 | Avoid | 48% | 33.2985 | 15.9833 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 48% | 33.2985 | 15.9833 | Avoid | 48% | 33.2985 | 15.9833 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 | 2017-08-20 | 48% | 33.2985 | 15.9833 | Avoid | 48% | 33.2985 | 15.9833 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 48% | 33.2985 | 15.9833 | Avoid | 48% | 33.2985 | 15.9833 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 48% | 33.2985 | 15.9833 | Avoid | 48% | 33.2985 | 15.9833 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_002 | Project_032 | Risk-128 | Project_032_Risk-128 | Threat | Project Contingency | Open | H3 | 3 | Project Management | Project estimated Level of Repairs | Person_136 | 2012-08-21 01:00 | 2017-08-20 01:00 | 48% | 33.2985 | 15.9833 | Avoid | 48% | 33.2985 | 15.9833 | H3 | 3 | Stable | TRUE | 1825 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Go to Offshore initiative | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 15% | 7.7172 | 1.1576 | -- | 15% | 7.7172 | 1.1576 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Go to Offshore initiative | Person_468 | 2016-11-19 23:00 | 2018-05-22 | 15% | 7.7172 | 1.1576 | -- | 15% | 7.7172 | 1.1576 | H3 | 3 | Stable | FALSE | 548.0417 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_041 | R85 | Project_041_R85 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Go to Offshore initiative | Person_468 | 2016-11-19 22:00 | 2018-05-22 | 15% | 7.7172 | 1.1576 | -- | 15% | 7.7172 | 1.1576 | H3 | 3 | Stable | FALSE | 548.0833 |  | 1 | 1 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Items damaged in transit | Person_294 | 2017-04-23 | 2018-11-20 01:00 | 30% | 11.7443 | 3.5233 | Reduce | 10% | 11.7443 | 1.1744 | H3 | 3 | -- | TRUE | 576.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Items damaged in transit | Person_294 | 2017-04-23 | 2018-11-20 01:00 | 30% | 11.7443 | 3.5233 | Reduce | 10% | 11.7443 | 1.1744 | H3 | 3 | -- | TRUE | 576.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK060 | Project_058_RISK060 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Obsolescence (address via LTB only) | Person_236 | 2018-07-22 | 2018-08-05 | 10% | 3.9148 | 0.39148 | -- | 30% | 3.9148 | 1.1744 | H3 | 3 | -- | TRUE | 14 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK060 | Project_058_RISK060 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Obsolescence (address via LTB only) | Person_236 | 2018-07-22 | 2018-08-05 | 10% | 3.9148 | 0.39148 | -- | 30% | 3.9148 | 1.1744 | H3 | 3 | -- | TRUE | 14 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | OPP001 | Project_081_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Reduction in Spares UPC | Person_260 | 2017-07-21 | 2019-05-16 | 20% | 6.1022 | 1.2204 | -- | 20% | 6.1022 | 1.2204 | H3 | 3 | Stable | TRUE | 664 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK280 | Project_024_RISK280 | Threat | Project Contingency | Open | H2 | 2 |  | Port SW to supportable Runtime environment | Person_331 | 2019-01-22 01:00 | 2019-05-23 | 4% | 32.4575 | 1.2983 | Accept | 4% | 32.4575 | 1.2983 | H3 | 3 | -- | FALSE | 120.9583 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK280 | Project_024_RISK280 | Threat | Project Contingency | Open | H2 | 2 |  | Port SW to supportable Runtime environment | Person_331 | 2019-01-22 01:00 | 2019-05-23 | 4% | 32.4575 | 1.2983 | Accept | 4% | 32.4575 | 1.2983 | H3 | 3 | -- | FALSE | 120.9583 |  | 1 | 1 | 1
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK280 | Project_024_RISK280 | Threat | Project Contingency | Open | H2 | 2 |  | Port SW to supportable Runtime environment | Person_331 | 2019-01-22 01:00 | 2018-05-22 | 4% | 32.4575 | 1.2983 | Accept | 4% | 32.4575 | 1.2983 | H3 | 3 | -- | FALSE | -245.0417 |  | 1 | 1 | 1
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK280 | Project_024_RISK280 | Threat | Project Contingency | Open | H2 | 2 |  | Port SW to supportable Runtime environment | Person_331 | 2016-12-21 01:00 | 2017-01-20 01:00 | 4% | 32.4575 | 1.2983 | Accept | 4% | 32.4575 | 1.2983 | H3 | 3 | -- | FALSE | 30 |  | 1 | 1 | 1
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK280 | Project_024_RISK280 | Threat | Project Contingency | Open | H2 | 2 |  | Port SW to supportable Runtime environment | Person_331 | 2016-12-21 01:00 | 2017-04-21 | 4% | 32.4575 | 1.2983 | Accept | 4% | 32.4575 | 1.2983 | H3 | 3 | -- | FALSE | 120.9583 |  | 1 | 1 | 1
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK013- | Project_065_RISK013- | Threat | Project Contingency | Open | H2 | 2 |  | Supplier delivers non-compliant component due to specification misunderstanding | Person_594 | 2017-03-23 | 2018-06-09 | 30% | 13.3921 | 4.0176 | Reduce | 20% | 7.6883 | 1.5377 | H3 | 3 | -- | FALSE | 443 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_007 | Project_083 | RISK017 | Project_083_RISK017 | Threat | Project Contingency | Open | H2 | 2 |  | Modules Obsolescence Resolution - Domestic Programmes | Person_712 | 2018-03-17 01:00 | 2019-01-20 01:00 | 15% | 10.3732 | 1.556 | Reduce | 15% | 10.3732 | 1.556 | H3 | 3 | Stable | FALSE | 309 |  | 1 | 1 | 1
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 2 |  | Software Issues | Person_245 | 2012-04-19 | 2016-11-19 01:00 | 50% | 0.55886 | 0.27943 | Accept | 20% | 7.824 | 1.5648 | H3 | 3 | Stable | FALSE | 1675.0417 |  | 0 | 0 | 1
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-47 | Project_022_RISK-47 | Threat | Project Contingency | Open | H2 | 2 |  | Software Issues | Person_245 | 2012-04-19 | 2016-11-19 01:00 | 50% | 0.55886 | 0.27943 | Accept | 20% | 7.824 | 1.5648 | H3 | 3 | Stable | FALSE | 1675.0417 |  | 0 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK060 | Project_058_RISK060 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Obsolescence (address via LTB only) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 3.9148 | 1.5659 | -- | 40% | 3.9148 | 1.5659 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK060 | Project_058_RISK060 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Obsolescence (address via LTB only) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 40% | 3.9148 | 1.5659 | -- | 40% | 3.9148 | 1.5659 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK060 | Project_058_RISK060 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Obsolescence (address via LTB only) | Person_236 | 2016-05-23 | 2019-08-21 01:00 | 10% | 3.9148 | 0.39148 | -- | 40% | 3.9148 | 1.5659 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK060 | Project_058_RISK060 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Obsolescence (address via LTB only) | Person_236 | 2016-05-23 | 2019-08-21 01:00 | 10% | 3.9148 | 0.39148 | -- | 40% | 3.9148 | 1.5659 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Items damaged in transit | Person_294 | 2017-04-23 | 2018-11-20 01:00 | 10% | 15.659 | 1.5659 | Accept | 10% | 15.659 | 1.5659 | H3 | 3 | -- | TRUE | 576.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Items damaged in transit | Person_294 | 2017-04-23 | 2018-11-20 01:00 | 10% | 15.659 | 1.5659 | Accept | 10% | 15.659 | 1.5659 | H3 | 3 | -- | TRUE | 576.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Items damaged in transit | Person_294 | 2017-04-23 | 2018-11-20 01:00 | 10% | 15.659 | 1.5659 | Accept | 10% | 15.659 | 1.5659 | H3 | 3 | -- | TRUE | 576.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 35% | 4.6134 | 1.6147 | -- | 35% | 4.6134 | 1.6147 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 35% | 4.6134 | 1.6147 | -- | 35% | 4.6134 | 1.6147 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 | 2019-08-20 | 35% | 4.6134 | 1.6147 | -- | 35% | 4.6134 | 1.6147 | H3 | 3 | Stable | TRUE | 1094 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 35% | 4.6134 | 1.6147 | -- | 35% | 4.6134 | 1.6147 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-21 01:00 | 2019-08-20 | 35% | 4.6134 | 1.6147 | -- | 35% | 4.6134 | 1.6147 | H3 | 3 | Stable | TRUE | 1093.9583 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R023 | Project_085_R023 | Threat | Project Contingency | Open | H1 | 1 | Business Strategy and Objectives | Knock on impact of supplier failure | Person_409 | 2017-12-21 | 2019-12-21 | 50% | 33.7754 | 16.8877 | Reduce | 50% | 33.7754 | 16.8877 | H1 | 1 | -- | TRUE | 730 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK151 | Project_049_RISK151 | Threat | Project Contingency | Open | H2 | 2 | Project Management | Late Delivery | Person_218 | 2017-08-23 01:00 | 2019-10-09 01:00 | 90% | 21.1648 | 19.0483 | Reduce | 80% | 21.1648 | 16.9318 | H2 | 2 | -- | TRUE | 777 |  | 1 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 48.16% | 78.4174 | 37.7697 | Reduce | 29.67% | 59.2155 | 17.5692 | H1 | 1 | Worsening | TRUE | 549.9583 |  | 1 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 35% | 4.6134 | 1.6147 | -- | 35% | 4.6134 | 1.6147 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 35% | 4.6134 | 1.6147 | -- | 35% | 4.6134 | 1.6147 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_018 | OPP001 | Project_018_OPP001 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Increase in Operating Hours (Opportunity) | Person_084 | 2016-08-20 23:00 | 2019-08-20 | 35% | 4.6134 | 1.6147 | -- | 35% | 4.6134 | 1.6147 | H3 | 3 | Stable | TRUE | 1094.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | Risk108 | Project_066_Risk108 | Threat | Project Contingency | Open | H2 | 2 |  | Availability of HCI | Person_507 | 2019-02-21 01:00 | 2019-05-24 | 50% | 8.3482 | 4.1741 | Reduce | 20% | 8.3482 | 1.6696 | H3 | 3 | -- | FALSE | 91.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK055 | Project_076_RISK055 | Opportunitity | Project Contingency | Open | H2 | 2 |  | Review scope of what currently contains code | Person_474 | 2018-03-23 | 2018-07-20 | 20% | 8.9556 | 1.7911 | Reject | 20% | 8.9556 | 1.7911 | H3 | 3 | -- | FALSE | 119 |  | 1 | 1 | 1
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 25% | 71.9682 | 17.992 | -- | 25% | 71.9682 | 17.992 | H3 | 3 | -- | TRUE | 668.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 25% | 71.9682 | 17.992 | -- | 25% | 71.9682 | 17.992 | H3 | 3 | -- | TRUE | 668.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 25% | 71.9682 | 17.992 | -- | 25% | 71.9682 | 17.992 | H3 | 3 | -- | TRUE | 668.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 25% | 71.9682 | 17.992 | -- | 25% | 71.9682 | 17.992 | H3 | 3 | -- | TRUE | 668.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 25% | 71.9682 | 17.992 | -- | 25% | 71.9682 | 17.992 | H3 | 3 | -- | TRUE | 668.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-079 | Project_008_Risk-079 | Opportunitity | Project Contingency | Open | H3 | 3 | Business Strategy and Objectives | Regulations Phase 3 and 4 | Person_565 | 2016-10-21 01:00 | 2018-08-21 | 25% | 71.9682 | 17.992 | -- | 25% | 71.9682 | 17.992 | H3 | 3 | -- | TRUE | 668.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2017-01-21 01:00 | 2018-07-25 | 47.69% | 79.0146 | 37.6821 | Reduce | 29.47% | 62.617 | 18.4526 | H1 | 1 | Worsening | TRUE | 549.9583 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_016 | Project_076 | RISK079 | Project_076_RISK079 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Resources required to finish project | Person_152 | 2019-03-24 | 2019-05-16 | 69.96% | 26.535 | 18.5639 | Accept | 69.96% | 26.535 | 18.5639 | H1 | 1 | Stable | TRUE | 53 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-59 | Project_022_RISK-59 | Threat | Project Contingency | Open | H3 | 3 |  | Platform Acceptance needs re-running | Person_703 | 2016-11-05 01:00 | 2016-12-20 01:00 | 60% | 3.1883 | 1.913 | Reduce | 60% | 3.1883 | 1.913 | H3 | 3 | -- | TRUE | 45 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-59 | Project_022_RISK-59 | Threat | Project Contingency | Open | H3 | 3 |  | Platform Acceptance needs re-running | Person_703 | 2016-11-05 01:00 | 2016-12-20 01:00 | 60% | 3.1883 | 1.913 | Reduce | 60% | 3.1883 | 1.913 | H3 | 3 | -- | TRUE | 45 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-59 | Project_022_RISK-59 | Threat | Project Contingency | Open | H3 | 3 |  | Platform Acceptance needs re-running | Person_703 | 2016-11-05 01:00 | 2016-12-20 01:00 | 60% | 3.1883 | 1.913 | Reduce | 60% | 3.1883 | 1.913 | H3 | 3 | -- | TRUE | 45 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 40% | 49.4398 | 19.7759 | -- | 40% | 49.4398 | 19.7759 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_084 | 2016-01-22 01:00 | 2023-02-20 01:00 | 40% | 49.4398 | 19.7759 | -- | 40% | 49.4398 | 19.7759 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_084 | 2016-01-22 | 2023-02-20 | 40% | 49.4398 | 19.7759 | -- | 40% | 49.4398 | 19.7759 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_084 | 2016-01-22 | 2023-02-20 | 40% | 49.4398 | 19.7759 | -- | 40% | 49.4398 | 19.7759 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 40% | 49.4398 | 19.7759 | -- | 40% | 49.4398 | 19.7759 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 40% | 49.4398 | 19.7759 | -- | 40% | 49.4398 | 19.7759 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_084 | 2016-01-21 23:00 | 2023-02-19 23:00 | 40% | 49.4398 | 19.7759 | -- | 40% | 49.4398 | 19.7759 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_017 | RISK041 | Project_017_RISK041 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Software issue input | Person_084 | 2016-01-21 21:00 | 2023-02-19 21:00 | 40% | 49.4398 | 19.7759 | -- | 40% | 49.4398 | 19.7759 | H2 | 2 | -- | TRUE | 2586 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 49.67% | 93.5036 | 46.4402 | Reduce | 30.42% | 65.224 | 19.8425 | H1 | 1 | Worsening | TRUE | 641.9583 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-059 | Project_008_Risk-059 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Project Resource Efficencies | Person_565 | 2015-08-22 01:00 | 2018-08-21 | 40% | 50.3777 | 20.1511 | -- | 40% | 50.3777 | 20.1511 | H2 | 2 | Stable | TRUE | 1094.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 71% | 35.885 | 25.4784 | Accept | 75% | 27.0826 | 20.3119 | H1 | 1 | Worsening | TRUE | 178.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2018-04-11 | 71% | 35.885 | 25.4784 | Accept | 75% | 27.0826 | 20.3119 | H1 | 1 | Worsening | TRUE | 658 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 71% | 35.885 | 25.4784 | Accept | 75% | 27.0826 | 20.3119 | H1 | 1 | Worsening | TRUE | 178.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2017-05-22 | 71% | 35.885 | 25.4784 | Accept | 75% | 27.0826 | 20.3119 | H1 | 1 | Worsening | TRUE | 334 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK012-Risk- | Project_065_RISK012-Risk- | Threat | Project Contingency | Open | H2 | 2 |  | Increased connector load causes crosstalk issues. | Person_594 | 2016-09-08 01:00 | 2019-11-20 01:00 | 45% | 10.4629 | 4.7083 | Reduce | 20% | 10.4629 | 2.0926 | H3 | 3 | -- | FALSE | 1168 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 |  | Open PR's | Person_319 | 2018-04-22 | 2018-11-20 01:00 | 50% | 7.6338 | 3.8169 | Reduce | 30% | 7.6338 | 2.2901 | H3 | 3 | Improving | TRUE | 212.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Lack of Spares Avaliability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 30% | 71.0212 | 21.3064 | Accept | 30% | 71.0212 | 21.3064 | H2 | 2 | -- | TRUE | 729.9583 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Lack of Spares Avaliability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 30% | 71.0212 | 21.3064 | Accept | 30% | 71.0212 | 21.3064 | H2 | 2 | -- | TRUE | 729.9583 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Lack of Spares Avaliability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 30% | 71.0212 | 21.3064 | Accept | 30% | 71.0212 | 21.3064 | H2 | 2 | -- | TRUE | 729.9583 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Lack of Spares Avaliability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 30% | 71.0212 | 21.3064 | Accept | 30% | 71.0212 | 21.3064 | H2 | 2 | -- | TRUE | 729.9583 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Lack of Spares Avaliability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 30% | 71.0212 | 21.3064 | Accept | 30% | 71.0212 | 21.3064 | H2 | 2 | -- | TRUE | 729.9583 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-078 | Project_008_Risk-078 | Threat | Project Contingency | Open | H2 | 2 | Acquisition and offsets | Lack of Spares Avaliability at end of contract | Person_639 | 2016-08-21 01:00 | 2018-08-21 | 30% | 71.0212 | 21.3064 | Accept | 30% | 71.0212 | 21.3064 | H2 | 2 | -- | TRUE | 729.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK153 | Project_024_RISK153 | Threat | Project Contingency | Open | H2 | 2 | Hardware/Software development | Processor memory/performance Issue | Person_331 | 2016-06-23 | 2017-03-22 | 30% | 112.3463 | 33.7039 | Reduce | 20% | 112.3463 | 22.4693 | H2 | 2 | Stable | TRUE | 272 |  | 1 | 0 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2016-04-22 | 2017-08-20 01:00 | 49.67% | 93.5036 | 46.4402 | Reduce | 29.08% | 78.3005 | 22.767 | H1 | 1 | -- | TRUE | 485.0417 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 49.67% | 93.5036 | 46.4402 | Reduce | 29.08% | 78.3005 | 22.767 | H1 | 1 | Worsening | TRUE | 641.9583 |  | 1 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2016-10-21 01:00 | 2018-07-25 | 49.67% | 93.5036 | 46.4402 | Reduce | 29.08% | 78.3005 | 22.767 | H1 | 1 | Worsening | TRUE | 641.9583 |  | 1 | 0 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 50% | 23.6737 | 11.8369 | Accept | 45% | 52.0822 | 23.437 | H2 | 2 | Stable | TRUE | 729 |  | 0 | 0 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 50% | 23.6737 | 11.8369 | Accept | 45% | 52.0822 | 23.437 | H2 | 2 | Stable | TRUE | 729 |  | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 50% | 23.6737 | 11.8369 | Accept | 45% | 52.0822 | 23.437 | H2 | 2 | Stable | TRUE | 729 |  | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 50% | 23.6737 | 11.8369 | Accept | 45% | 52.0822 | 23.437 | H2 | 2 | Stable | TRUE | 729 |  | 0 | 0 | 0
2016-11-20 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 50% | 23.6737 | 11.8369 | Accept | 45% | 52.0822 | 23.437 | H2 | 2 | Stable | TRUE | 729 |  | 0 | 0 | 0
2016-12-21 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 45% | 52.0822 | 23.437 | Accept | 45% | 52.0822 | 23.437 | H2 | 2 | Stable | TRUE | 729 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 |  | Open PR's | Person_319 | 2018-04-22 | 2018-11-20 01:00 | 50% | 7.6338 | 3.8169 | Reduce | 30% | 7.6338 | 2.2901 | H3 | 3 | Improving | TRUE | 212.0417 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 |  | Open PR's | Person_319 | 2018-04-22 | 2018-11-20 01:00 | 50% | 7.6338 | 3.8169 | Reduce | 30% | 7.6338 | 2.2901 | H3 | 3 | Improving | TRUE | 212.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 |  | Open PR's | Person_319 | 2018-04-22 | 2018-11-20 01:00 | 50% | 7.6338 | 3.8169 | Reduce | 30% | 7.6338 | 2.2901 | H3 | 3 | Improving | TRUE | 212.0417 |  | 1 | 0 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 |  | Open PR's | Person_294 | 2018-04-22 | 2018-11-20 01:00 | 50% | 7.6338 | 3.8169 | Reduce | 30% | 7.6338 | 2.2901 | H3 | 3 | Improving | TRUE | 212.0417 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 |  | Open PR's | Person_294 | 2018-04-22 | 2018-11-20 01:00 | 50% | 7.6338 | 3.8169 | Reduce | 30% | 7.6338 | 2.2901 | H3 | 3 | Improving | TRUE | 212.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK009 | Project_058_RISK009 | Threat | Project Contingency | Open | H3 | 3 |  | Open PR's | Person_294 | 2018-04-22 | 2018-11-20 01:00 | 50% | 7.6338 | 3.8169 | Reduce | 30% | 7.6338 | 2.2901 | H3 | 3 | Improving | TRUE | 212.0417 |  | 1 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK059 | Project_058_RISK059 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Manufacturing (Batching) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 50% | 4.6977 | 2.3489 | -- | 50% | 4.6977 | 2.3489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK068 | Project_049_RISK068 | Threat | Project Contingency | Open | H1 | 1 | Project Management | Concurrent Resource Requirements | Person_526 | 2017-08-23 01:00 | 2019-10-29 01:00 | 75% | 33.8935 | 25.4202 | Transfer | 75% | 33.8935 | 25.4202 | H1 | 1 | -- | TRUE | 797 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 40% | 35.885 | 14.354 | Accept | 71% | 35.885 | 25.4784 | H1 | 1 | Worsening | TRUE | 178.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 40% | 35.885 | 14.354 | Accept | 71% | 35.885 | 25.4784 | H1 | 1 | Worsening | TRUE | 178.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK187 | Project_024_RISK187 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Digital Video Chainredesign | Person_289 | 2016-06-22 | 2016-12-17 01:00 | 40% | 35.885 | 14.354 | Accept | 71% | 35.885 | 25.4784 | H1 | 1 | Worsening | TRUE | 178.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK240 | Project_024_RISK240 | Threat | Project Contingency | Open | H1 | 1 | Other Risks and Contingencies | Performance (collector risk) | Person_351 | 2016-04-22 | 2017-08-20 01:00 | 45.68% | 114.0947 | 52.1184 | Reduce | 31.27% | 82.1954 | 25.7066 | H1 | 1 | -- | TRUE | 485.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK059 | Project_058_RISK059 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Manufacturing (Batching) | Person_294 | 2016-05-23 | 2019-08-21 01:00 | 50% | 4.6977 | 2.3489 | -- | 50% | 4.6977 | 2.3489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK059 | Project_058_RISK059 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Manufacturing (Batching) | Person_537 | 2016-05-23 | 2019-08-21 01:00 | 50% | 4.6977 | 2.3489 | -- | 50% | 4.6977 | 2.3489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK059 | Project_058_RISK059 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Manufacturing (Batching) | Person_537 | 2016-05-23 | 2019-08-21 01:00 | 50% | 4.6977 | 2.3489 | -- | 50% | 4.6977 | 2.3489 | H3 | 3 | -- | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK059 | Project_058_RISK059 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Manufacturing (Batching) | Person_537 | 2018-07-06 | 2018-09-20 01:00 | 50% | 4.6977 | 2.3489 | -- | 50% | 4.6977 | 2.3489 | H3 | 3 | -- | TRUE | 76.0417 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK059 | Project_058_RISK059 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Manufacturing (Batching) | Person_537 | 2018-07-06 | 2018-09-20 01:00 | 50% | 4.6977 | 2.3489 | -- | 50% | 4.6977 | 2.3489 | H3 | 3 | -- | TRUE | 76.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK059 | Project_058_RISK059 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Manufacturing (Batching) | Person_537 | 2018-07-06 | 2018-11-20 01:00 | 50% | 4.6977 | 2.3489 | -- | 50% | 4.6977 | 2.3489 | H3 | 3 | -- | TRUE | 137.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 |  | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-11-19 01:00 | 60% | 11.6428 | 6.9857 | Reduce | 20% | 12.2515 | 2.4503 | H3 | 3 | Worsening | TRUE | 759 |  | 0 | 0 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 |  | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-11-19 01:00 | 60% | 11.6428 | 6.9857 | Reduce | 20% | 12.2515 | 2.4503 | H3 | 3 | Worsening | TRUE | 759 |  | 0 | 0 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 |  | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-11-19 01:00 | 60% | 11.6428 | 6.9857 | Reduce | 20% | 12.2515 | 2.4503 | H3 | 3 | Worsening | TRUE | 759 |  | 0 | 0 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 |  | sub-System Cleanliness | Person_324 | 2017-05-23 | 2018-09-20 01:00 | 75% | 13.3102 | 9.9826 | Reduce | 20% | 13.3102 | 2.662 | H3 | 3 | Stable | TRUE | 485.0417 |  | 1 | 0 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 |  | sub-System Cleanliness | Person_324 | 2017-05-23 | 2018-09-20 01:00 | 75% | 13.3102 | 9.9826 | Reduce | 20% | 13.3102 | 2.662 | H3 | 3 | Stable | TRUE | 485.0417 |  | 1 | 0 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_249 | 2017-05-23 | 2018-09-18 01:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 483.0417 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_249 | 2017-05-23 | 2018-09-18 01:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 483.0417 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_249 | 2017-05-23 | 2018-09-18 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 483 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_249 | 2017-05-23 | 2018-09-18 01:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 483.0417 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_249 | 2017-05-23 | 2018-09-17 23:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 482.9583 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_249 | 2017-05-23 | 2018-09-17 22:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 482.9167 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_249 | 2017-05-23 | 2018-09-17 23:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 482.9583 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_038 | 2017-05-23 | 2020-01-21 01:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 973.0417 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_249 | 2017-05-23 | 2018-09-17 22:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 482.9167 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_038 | 2017-05-23 | 2020-01-21 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 973 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_038 | 2017-05-23 | 2020-01-21 01:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 973.0417 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK463 | Project_065_RISK463 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between subsystems causes Rework and Delay to System Design Elements | Person_038 | 2017-05-23 | 2020-01-20 23:00 | 40% | 65.469 | 26.1876 | Accept | 40% | 65.469 | 26.1876 | H2 | 2 | -- | TRUE | 972.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_249 | 2017-09-20 01:00 | 2018-09-18 01:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_249 | 2017-09-20 01:00 | 2018-09-18 01:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_249 | 2017-09-20 | 2018-09-18 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_249 | 2017-09-20 01:00 | 2018-09-18 01:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_249 | 2017-09-19 23:00 | 2018-09-17 23:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_249 | 2017-09-19 22:00 | 2018-09-17 22:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_249 | 2017-09-19 23:00 | 2018-09-17 23:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_038 | 2017-09-20 01:00 | 2020-02-20 01:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 883 |  | 1 | 1 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_249 | 2017-09-19 22:00 | 2018-09-17 22:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 363 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_038 | 2017-09-20 | 2020-02-20 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 883 |  | 1 | 1 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_038 | 2017-09-20 01:00 | 2020-02-20 01:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 883 |  | 1 | 1 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK464 | Project_065_RISK464 | Threat | Project Contingency | Open | H2 | 2 | Business Strategy and Objectives | Misalignment of Lifecycle Between sub-systems - Unresolvable Constraints On System that cannot relax that cause additional work, delay and/or shortfall in performance | Person_038 | 2017-09-19 23:00 | 2020-02-19 23:00 | 40% | 67.8016 | 27.1206 | Accept | 40% | 67.8016 | 27.1206 | H2 | 2 | -- | TRUE | 883 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK218 | Project_024_RISK218 | Threat | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | System issues general | Person_289 | 2016-08-21 01:00 | 2016-10-04 01:00 | 40% | 90.8811 | 36.3524 | Reduce | 30% | 90.8811 | 27.2643 | H1 | 1 | Stable | TRUE | 44 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 50% | 32.3541 | 16.1771 | Accept | 85% | 33.1432 | 28.1718 | H2 | 2 | Stable | TRUE | 729 |  | 0 | 1 | 0
2016-06-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-067 | Project_008_Risk-067 | Threat | Project Contingency | Open | H2 | 2 | Supply chain | Repairs at Supplier | Person_565 | 2015-08-22 01:00 | 2017-08-20 01:00 | 50% | 32.3541 | 16.1771 | Accept | 85% | 33.1432 | 28.1718 | H2 | 2 | Stable | TRUE | 729 |  | 0 | 1 | 0
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK036 | Project_049_RISK036 | Threat | Project Contingency | Open | H1 | 1 | Contractual/Legal | Security Patching | Person_478 | 2018-09-15 01:00 | 2019-11-08 01:00 | 75% | 42.7783 | 32.0837 | Accept | 75% | 42.7783 | 32.0837 | H1 | 1 | -- | TRUE | 419 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 30% | 108.3186 | 32.4956 | Accept | 30% | 108.3186 | 32.4956 | H2 | 2 | Stable | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 30% | 108.3186 | 32.4956 | Accept | 30% | 108.3186 | 32.4956 | H2 | 2 | Stable | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 30% | 108.3186 | 32.4956 | Accept | 30% | 108.3186 | 32.4956 | H2 | 2 | Stable | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-08-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 30% | 108.3186 | 32.4956 | Accept | 30% | 108.3186 | 32.4956 | H2 | 2 | Stable | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-09-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 30% | 108.3186 | 32.4956 | Accept | 30% | 108.3186 | 32.4956 | H2 | 2 | Stable | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-10-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 | 30% | 108.3186 | 32.4956 | Accept | 30% | 108.3186 | 32.4956 | H2 | 2 | Stable | TRUE | 1185 |  | 1 | 1 | 0
2016-11-20 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 30% | 108.3186 | 32.4956 | Accept | 30% | 108.3186 | 32.4956 | H2 | 2 | Stable | TRUE | 1185.0417 |  | 1 | 1 | 0
2016-12-21 | ORG_001 | BA_002 | Portfolio_005 | Project_016 | Risk--R003 | Project_016_Risk--R003 | Threat | Project Contingency | Open | H2 | 2 | System Engineering | Engineering Risk | Person_667 | 2016-05-23 | 2019-08-21 01:00 | 30% | 108.3186 | 32.4956 | Accept | 30% | 108.3186 | 32.4956 | H2 | 2 | Stable | TRUE | 1185.0417 |  | 1 | 1 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 |  | sub-System Cleanliness | Person_294 | 2017-05-23 | 2018-09-20 01:00 | 75% | 13.3102 | 9.9826 | Reduce | 20% | 13.3102 | 2.662 | H3 | 3 | Stable | TRUE | 485.0417 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 |  | sub-System Cleanliness | Person_294 | 2017-05-23 | 2018-09-20 01:00 | 75% | 13.3102 | 9.9826 | Reduce | 20% | 13.3102 | 2.662 | H3 | 3 | Stable | TRUE | 485.0417 |  | 1 | 0 | 0
2018-08-22 | ORG_001 | BA_001 | Portfolio_001 | Project_066 | RISK107 | Project_066_RISK107 | Opportunitity | Project Contingency | Open | H2 | 2 |  | SW WP EAC reduction/Cost saving | Person_507 | 2018-08-23 01:00 | 2019-05-12 | 20% | 14.2229 | 2.8446 | -- | 20% | 14.2229 | 2.8446 | H3 | 3 | -- | FALSE | 261.9583 |  | 1 | 1 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK001 | Project_058_RISK001 | Threat | Project Contingency | Open | H3 | 3 |  | Items damaged in transit | Person_294 | 2017-04-22 | 2018-11-20 01:00 | 40% | 29.3607 | 11.7443 | Reduce | 10% | 29.3607 | 2.9361 | H3 | 3 | -- | TRUE | 577.0417 |  | 1 | 0 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_003 | Project_008 | Risk-066 | Project_008_Risk-066 | Opportunitity | Project Contingency | Open | H2 | 2 | Project Management | Efficiencies within the Forward Load | Person_565 | 2016-08-21 01:00 | 2018-08-21 | 50% | 71.8735 | 35.9367 | -- | 50% | 71.8735 | 35.9367 | H2 | 2 | -- | TRUE | 729.9583 |  | 1 | 1 | 0
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 |  | sub-System Cleanliness | Person_294 | 2017-05-23 | 2019-05-23 | 75% | 15.9918 | 11.9938 | Reduce | 20% | 15.9918 | 3.1984 | H3 | 3 | Stable | TRUE | 730 |  | 1 | 0 | 0
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 |  | sub-System Cleanliness | Person_294 | 2017-05-23 | 2019-05-23 | 75% | 15.9918 | 11.9938 | Reduce | 20% | 15.9918 | 3.1984 | H3 | 3 | Stable | TRUE | 730 |  | 1 | 0 | 0
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_058 | RISK052 | Project_058_RISK052 | Threat | Project Contingency | Open | H3 | 3 |  | sub-System Cleanliness | Person_294 | 2017-05-23 | 2019-05-23 | 75% | 15.9918 | 11.9938 | Reduce | 20% | 15.9918 | 3.1984 | H3 | 3 | Stable | TRUE | 730 |  | 1 | 0 | 0
2018-05-23 | ORG_002 | BA_005 | Portfolio_012 | Project_079 | RISK025 | Project_079_RISK025 | Opportunitity | Project Contingency | Open | H3 | 3 |  | Reclaim pellet delivery delays from Customer | Person_002 | 2018-02-02 01:00 | 2020-04-22 | 10% | 33.9266 | 3.3927 | -- | 10% | 33.9266 | 3.3927 | H3 | 3 | Worsening | TRUE | 809.9583 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_024 | RISK002 | Project_024_RISK002 | Threat | Project Contingency | Open | H1 | 1 | Hardware/Software development | S/W Productivity | Person_331 | 2016-05-22 | 2016-11-19 01:00 | 43% | 90.8811 | 39.0789 | Reduce | 43% | 90.8811 | 39.0789 | H1 | 1 | Stable | TRUE | 181.0417 |  | 1 | 1 | 0
2016-05-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK390 | Project_038_RISK390 | Threat | Project Contingency | Open | H2 | 2 |  | Component shock failure | Person_531 | 2016-01-17 01:00 | 2016-06-23 | 20% | 17.1093 | 3.4219 | -- | 20% | 17.1093 | 3.4219 | H3 | 3 | Stable | FALSE | 157.9583 |  | 1 | 1 | 1
2016-06-23 | ORG_001 | BA_001 | Portfolio_001 | Project_038 | RISK390 | Project_038_RISK390 | Threat | Project Contingency | Open | H2 | 2 |  | Component shock failure | Person_531 | 2016-01-17 01:00 | 2016-06-23 | 20% | 17.1093 | 3.4219 | -- | 20% | 17.1093 | 3.4219 | H3 | 3 | Stable | FALSE | 157.9583 |  | 1 | 1 | 1
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_081 | RISK009 | Project_081_RISK009 | Threat | Management Contingency | Open | H2 | 2 |  | Increase of Spares UPCs | Person_260 | 2017-09-27 01:00 | 2019-05-16 | 20% | 17.5011 | 3.5002 | Reduce | 20% | 17.5011 | 3.5002 | H3 | 3 | Stable | FALSE | 595.9583 |  | 1 | 1 | 1
2016-05-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 |  | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-09-19 01:00 | 60% | 11.6428 | 6.9857 | Reduce | 20% | 19.5167 | 3.9033 | H3 | 3 | Worsening | TRUE | 698 |  | 0 | 0 | 0
2016-06-23 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 |  | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-10-19 01:00 | 60% | 11.6428 | 6.9857 | Reduce | 20% | 19.5167 | 3.9033 | H3 | 3 | Worsening | TRUE | 728 |  | 0 | 0 | 0
2016-07-21 | ORG_001 | BA_002 | Portfolio_004 | Project_022 | RISK-22 | Project_022_RISK-22 | Threat | Project Contingency | Open | H3 | 3 |  | Setting to work Issues - monitor may require changing | Person_393 | 2014-10-22 01:00 | 2016-11-19 01:00 | 60% | 11.6428 | 6.9857 | Reduce | 20% | 19.5167 | 3.9033 | H3 | 3 | Worsening | TRUE | 759 |  | 0 | 0 | 0
2018-08-22 | ORG_002 | BA_004 | Portfolio_010 | Project_085 | R099 | Project_085_R099 | Threat | Project Contingency | Open | H2 | 2 |  | Uncertainty | Person_002 | 2018-11-21 | 2019-05-23 | 20% | 24.4638 | 4.8928 | -- | 20% | 24.4638 | 4.8928 | H3 | 3 | -- | FALSE | 183 |  | 1 | 1 | 1
2018-08-22 | ORG_001 | BA_003 | Portfolio_013 | Project_049 | RISK025 | Project_049_RISK025 | Threat | Management Contingency | Open | H2 | 2 | Project Management | Additional Cost variance | Person_218 | 2017-08-23 01:00 | 2020-05-23 | 50% | 94.501 | 47.2505 | Accept | 50% | 94.501 | 47.2505 | H2 | 2 | -- | TRUE | 1003.9583 |  | 1 | 1 | 0
2017-12-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2016-09-08 01:00 | 2019-11-22 01:00 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 1170 |  | 1 | 0 | 1
2018-01-21 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2016-09-08 01:00 | 2019-11-22 01:00 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 1170 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2016-09-08 | 2019-11-22 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 1170 |  | 1 | 0 | 1
2018-02-20 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2016-09-08 01:00 | 2019-11-22 01:00 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 1170 |  | 1 | 0 | 1
2018-03-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2016-09-07 23:00 | 2019-11-21 23:00 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 1170 |  | 1 | 0 | 1
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2016-09-07 22:00 | 2019-11-21 22:00 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 1170 |  | 1 | 0 | 1
2018-08-22 | ORG_001 | BA_002 | Portfolio_002 | Project_098 | Risk-001 | Project_098_Risk-001 | Threat | Project Contingency | Open | H1 | 1 | Supply chain | UNIT PRODUCTION COSTS | Person_660 | 2018-05-23 | 2033-05-22 | 80% | 276.8242 | 221.4594 | Reduce | 50% | 135.6137 | 67.8069 | H1 | 1 | Stable | TRUE | 5478 |  | 1 | 0 | 0
2018-04-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2016-09-07 23:00 | 2019-11-21 23:00 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 1170 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2021-10-21 01:00 | 2022-05-22 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 212.9583 |  | 1 | 0 | 1
2018-05-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2016-09-07 22:00 | 2019-11-21 22:00 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 1170 |  | 1 | 0 | 1
2018-06-23 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2021-10-21 | 2022-05-22 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 213 |  | 1 | 0 | 1
2018-07-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2021-10-21 01:00 | 2022-05-22 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 212.9583 |  | 1 | 0 | 1
2018-08-22 | ORG_002 | BA_005 | Portfolio_011 | Project_065 | RISK021 | Project_065_RISK021 | Threat | Project Contingency | Open | H2 | 2 |  | Customer complains of poor performance | Person_661 | 2021-10-20 23:00 | 2022-05-22 | 30% | 26.3684 | 7.9105 | Reduce | 20% | 26.3684 | 5.2737 | H3 | 3 | -- | FALSE | 213.0417 |  | 1 | 0 | 1
2018-08-22 | ORG_004 | BA_007 | Portfolio_019 | Project_077 | OPRisk-001 | Project_077_OPRisk-001 | Opportunitity | Project Contingency | Open | H1 | 1 | System Integration, Verification & Validation | Opportunity that fewer than expected customer problem reports are raised. | Person_544 | 2019-07-22 | 2020-02-21 01:00 | 50% | 3.3642 | 1.6821 | -- | 50% | 3364.2293 | 1682.1146 | H1 | 1 | Stable | TRUE | 214.0417 |  | 0 | 1 | 0